## Slide 1
COMMUNICATIONS
M&A DAY 1 READINESS
© 100-Day Advisors · MandAPlaybook.com

## Slide 2
WHAT THIS DECK COVERS
Communications Day 1 Integration — Readiness & Execution
01
Integration Timeline
Pre-Close milestones, Day 1 Readiness gate, and Week 1 priorities mapped to the March 2 close.
02
Day 1 Readiness Checklist
29 critical pre-close tasks confirmed complete — narrative, messaging, assets, dry runs, and readiness gate.
03
Day 1 / Week 1 Actions
Trigger Day 1 sequence, monitor reception, support exec comms, and assess Week 1 effectiveness.
04
Message Architecture
Master narrative, audience-specific frameworks, employee and customer guides, and executive talking points.
05
Media, Digital & Brand
Press release, CEO media briefing, website and social readiness, brand transition plan, and wire service.
06
Key Risks & Mitigations
Day 1 sequence execution, reception monitoring, exec message discipline, and active trademark conflict.
© 100-Day Advisors · MandAPlaybook.com
2

## Slide 3
DAY 1 READINESS
Day 1 Readiness — Critical Pre-Close Tasks, All Complete
✓
Develop master integration narrative and core messages
Comms Lead
✓
Build audience-specific messaging frameworks — employees, customers, media
Comms Lead
✓
Coordinate investor Day 1 communication with IR and Finance
Comms Lead
✓
Build media monitoring protocol — tracking, sentiment, and key narratives
Media Relations
✓
Develop Day 1 digital communications strategy — web, social, email, intranet
Digital Comms Mgr
✓
Develop reactive media holding statements for top 10 sensitive topics
Media Relations
✓
Plan and script Day 1 all-hands town hall — format, speakers, and run-of-show
Comms Lead
✓
Develop Day 1 announcement cascade plan with HR — who, what, to whom, in order
Comms Lead
✓
Prepare CEO, CFO, and division president talking points for Day 1
Comms Lead
✓
Develop all-employee announcement with HR — leadership letter and overview
Comms Lead
✓
Develop M&A Vendor Communication Guide — talking points, guidance, Q&A/FAQ
Comms Integration Mgr
✓
Develop M&A Employee Communication Guide with HR — talking points, Q&A/FAQ
Comms Lead
✓
Develop M&A Customer Communication Guide with Sales — talking points, Q&A/FAQ
Comms Lead
✓
Develop Day 1 brand transition plan — Day 1 vs. phased vs. Day 100 changes
Brand & Creative Dir
✓
Build internal communications calendar — cadence, channels, owners, themes
Comms Integration Mgr
✓
Develop government and community relations talking points and outreach
Comms Lead
✓
Prepare CEO media briefing and conduct mock interviews for Day 1 press
Media Relations
✓
Establish social media monitoring and community management protocol
Digital Comms Mgr
✓
Coordinate communications with Legal to regulatory bodies
Comms Lead
✓
Develop media strategy, spokesperson briefings, press kit, and interview prep
Media Relations
✓
Draft Day 1 press release — rationale, combined entity overview, quotes
Media Relations
✓
Stage and QA all Day 1 website content — homepage, about, leadership, newsroom
Digital Comms Mgr
✓
Prepare Day 1 social media posts — LinkedIn, X, Facebook, Instagram
Digital Comms Mgr
✓
Conduct Day 1 communications dry runs — publish workflows and timing sequence
Comms Lead
✓
Final legal and compliance review of all Day 1 assets
Comms Integration Mgr
✓
Confirm Day 1 publish sequencing: regulatory → investor → employee → press → social
Comms Lead
✓
Brief all communications team members on Day 1 roles and on-call contacts
Comms Lead
✓
Distribute M&A Employee Communication Guide to all managers
Comms Integration Mgr
✓
Confirm media wire service loaded, tested, and ready to publish on signal
Media Relations
✓
Comm Day 1 Readiness Gate — all tasks complete, no unresolved blockers
Comms Lead
© 100-Day Advisors · MandAPlaybook.com
3

## Slide 4
DAY 1 / WEEK 1 ACTIONS
What Happens in Week 1
Day 1
Execute Day 1 communications sequence — trigger all staged assets per approved run-of-show publish timeline
Monitor Day 1 communications reception — employee sentiment, media coverage, social reaction, and customer inquiries
Support executive team with real-time communications coaching and message discipline throughout Day 1
Coordinate with sales leadership to schedule personal outreach calls to top 20 strategic accounts
Days 2–7
Assess Day 1 / Week 1 communications effectiveness — media coverage quality, employee feedback, and customer reactions
© 100-Day Advisors · MandAPlaybook.com
4

## Slide 5
MESSAGE ARCHITECTURE
Day 1 State — Narrative, Messaging & Guides
Approved
Master Narrative
Master integration narrative and core messages developed and approved by CEO and CFO at T-34. All messaging anchored to deal rationale: combined entity value, continuity, and long-term growth. Every audience communication traces back to this approved narrative.
Complete
Audience Frameworks
Distinct messaging frameworks built and approved for employees, customers, media, investors, and regulators. Each framework includes approved messages, tone guidance, and off-limits topics. Frameworks distributed to all workstream leads before Day 1.
Approved
Employee Communication Guide
M&A Employee Communication Guide developed with HR — includes talking points, manager guidance for team conversations, and Q&A/FAQ covering all anticipated employee questions. Distributed to all managers before Day 1.
Approved
Customer Communication Guide
M&A Customer Communication Guide developed with Sales — talking points, guidance for account conversations, and Q&A/FAQ. Distributed to all sales managers and account owners before Day 1 customer outreach.
Complete
Executive Talking Points
Tailored talking points prepared for CEO, CFO, and all division presidents. Points aligned to master narrative. CEO media briefing materials ready. Mock interviews conducted. All executives briefed individually — not as a group.
Developed
Vendor & Community Comms
M&A Vendor Communication Guide ready with talking points, Q&A/FAQ. Government and community relations talking points developed. Cascade plan defines who communicates what, to whom, and in what order — from CEO to front-line managers.
© 100-Day Advisors · MandAPlaybook.com
5

## Slide 6
MEDIA, DIGITAL & BRAND
Day 1 Posture — Press, Web, Social & Brand Transition
Press & Media
Day 1 press release drafted, legally reviewed, and staged in wire service — ready to publish on close signal. CEO media briefing materials ready; mock interviews complete. Media list, press kit, and spokesperson protocols finalized. Reactive holding statements ready for top 10 sensitive topics.
Digital — Web & Social
All Day 1 website content updates staged and QA'd — homepage, about page, leadership team, and newsroom. Social posts prepared for LinkedIn, X/Twitter, Facebook, and Instagram. Media monitoring dashboard active. Social community management protocol live.
Brand Transition
Day 1 brand transition plan complete — defines what changes on Day 1, what follows a phased schedule, and what waits until Day 100. Trademark clearance complete in all operating jurisdictions. Brand strategy approved. One active trademark conflict in Germany and France — managed under interim protocol.
COMMS STATUS
Press Release
Staged in wire service. Legally reviewed. Ready to publish on Day 1 close signal.
Website
All content updates staged and QA'd. Ready to publish simultaneously with press release.
Social Media
Posts prepared across all platforms. Publishing queue loaded and scheduled for Day 1 trigger.
Employee Comms
All-employee letter and leadership cascade ready. Town hall scripted and production-ready.
Trademark ⚠ Active
Conflict in Germany and France — preferred combined brand name blocked. Interim protocol issued to EU teams for Day 1.
© 100-Day Advisors · MandAPlaybook.com
6

## Slide 7
KEY RISKS & MITIGATIONS
Top RAID Items — Part 1 of 2
Issue
Open
Trademark conflict — preferred combined brand name blocked in Germany and France
The preferred combined entity brand name cannot be used in Germany and France due to an existing trademark held by a third party. All Day 1 communications in those markets must use the interim approved name. Risk of customer confusion and brand inconsistency from Day 1.
→ Communications Lead to issue briefing to EU sales and account management teams by 9 AM on Day 1 covering interim naming protocol. All EU-facing Day 1 materials updated with interim name. Legal tracking resolution timeline. Expected resolution: 60–90 days.
Risk
Open
Day 1 communications sequence not fully executed per run-of-show timeline
If any staged asset fails to publish at its designated time — regulatory filing, investor comms, employee announcement, press release, social — the sequencing breaks down. Any out-of-order publication risks regulatory violation or stakeholder confusion.
→ Build a minute-by-minute Day 1 run-of-show from 6 AM with named owners for every action. Communications Lead on call at 5 AM. Backup publish method confirmed for every digital asset. Any missed milestone escalated to Communications Lead and IMO within 15 minutes.
Risk
Open
Day 1 communications reception not monitored in real time
Without real-time monitoring across employee sentiment, media coverage, social reaction, and customer inquiry channels, the team cannot identify and respond to emerging narratives before they escalate into Day 1 crises.
→ Day 1 monitoring dashboards established for employee sentiment, media tracking, and social listening. Alert thresholds set for volume and sentiment spikes. Named leads for each channel. Any negative spike escalated to Communications Lead within 30 minutes.
© 100-Day Advisors · MandAPlaybook.com
7

## Slide 8
KEY RISKS & MITIGATIONS
Top RAID Items — Part 2 of 2
Dependency
Open
Executive message discipline breaks down during Day 1 media or employee interactions
Any executive who goes off-message on Day 1 — whether in a media interview, town hall Q&A, or hallway conversation — can create a news cycle or employee relations issue that drowns out the planned narrative. The stakes are highest in the first 24 hours.
→ Brief every Day 1 executive individually — not as a group. Each executive gets a custom briefing card, their three approved messages, and two examples of how to bridge off-topic questions. Communications Lead on standby for real-time coaching throughout Day 1.
Risk
Open
Top 20 strategic accounts not reached with personal outreach on Day 1
Customers who learn of the transaction through press or social media before receiving a personal call from their account owner are significantly more likely to flag the deal as a disruption risk. Delayed personal outreach is the single most common source of customer churn in M&A.
→ Brief sales leadership on customer communication strategy and talking points before Day 1 customer calls. Coordinate scheduling so every top 20 account receives a personal call on Day 1 or Day 2. Communications Lead provides real-time support for escalated customer concerns.
© 100-Day Advisors · MandAPlaybook.com
8

## Slide 9
Communications is Day 1 Ready and Executing.
100-DAY ADVISORS
Accelerating M&A Integrations
mandaplaybook.com
inquiries@100dayadvisors.com
© 100-Day Advisors · MandAPlaybook.com
9