## Slide 1
FINANCE
M&A DAY 1 READINESS
© 100-Day Advisors · MandAPlaybook.com

## Slide 2
WHAT THIS DECK COVERS
Finance Day 1 Integration — Readiness & Execution
01
Integration Timeline
Pre-Close milestones, Day 1 Readiness gate, and Week 1 priorities mapped to the March 2 close.
02
Day 1 Readiness Checklist
14 critical tasks confirmed complete before close — controls, cash, compliance, and communications.
03
Day 1 / Week 1 Actions
Controls activation, payroll continuity, billing confirmation, tax notifications, and treasury unification.
04
Financial Systems
ERP landscape, intercompany settlement, AP/AR continuity, and synergy tracking infrastructure.
05
Compliance & Reporting
Financial controls, SOX compliance, regulatory filings, accounting policy alignment, and audit readiness.
06
Key Risks & Mitigations
Top RAID items: financial statement integrity, controls coverage, billing continuity, and Finance team retention.
© 100-Day Advisors · MandAPlaybook.com
2

## Slide 3
DAY 1 READINESS
Day 1 Readiness — Critical Pre-Close Tasks, All Complete
✓
Identify all regulatory and statutory filing requirements and deadlines
VP Finance / Controller
✓
Identify change of control triggers in key contracts and tax agreements
VP Finance / Controller
✓
Prepare investor FAQ and analyst briefing materials covering synergies, integration costs, and timeline
VP FP&A / Integration Manager
✓
Assess acquisition financing structure and ensure closing funds committed and available
CFO / Finance Workstream Lead
✓
Establish interim finance org chart and confirm reporting lines for combined team
VP Finance / Controller
✓
Set up integration cost tracking codes in the general ledger before Day 1
VP FP&A / Integration Manager
✓
Build pro forma combined P&L and balance sheet for Day 1 management review
VP FP&A / Integration Manager
✓
Establish combined entity delegation of authority and financial approval thresholds
VP Finance / Controller
✓
Confirm earnout and contingent consideration payment tracking mechanisms
VP Finance / Controller
✓
Set up interim intercompany settlement mechanism for Day 1
VP Finance / Controller
✓
Confirm purchasing and spend approval controls will be active on Day 1
VP FP&A / Integration Manager
✓
Confirm revenue recognition and billing processes will be operational on Day 1
VP Finance / Controller
✓
Validate combined entity bank account signatories and confirm wire transfer authorities
VP Finance / Controller
✓
Finance Day 1 Readiness Gate — all items green, no blockers
CFO / Finance Workstream Lead
© 100-Day Advisors · MandAPlaybook.com
3

## Slide 4
DAY 1 / WEEK 1 ACTIONS
What Happens in Week 1
Day 1
Distribute Day 1 finance communications to all staff in both companies
Confirm financial controls framework applies to acquired entity immediately
Confirm accounts payable payment run is executed on schedule — no vendor payment disruptions
Brief acquired finance team on acquirer's reporting tools, systems, templates, and T&E policy
Submit required tax notifications to relevant authorities post-close
Days 2–4
Confirm billing and invoicing continuity — no disruption to cash collection
Review and align travel and entertainment policies across both organizations
Confirm insurance policies are updated to reflect the combined entity
Confirm FP&A budget process and timeline for combined entity
Days 4–7
Align financial code of conduct and conflicts of interest policies
Finalize treasury centralization — all cash pooling, FX management, and banking unified
© 100-Day Advisors · MandAPlaybook.com
4

## Slide 5
SYSTEMS & INFRASTRUCTURE
Day 1 State — Financial Systems & Infrastructure
Confirmed
ERP & General Ledger
ERP-of-record decision made and documented. Integration cost tracking codes set up in GL before Day 1. Pro forma combined P&L and balance sheet built for management review. Chart of accounts mapping complete.
Active
AP / AR & Billing
Accounts payable payment run confirmed on schedule. Billing and invoicing cutover tested end-to-end. Customer master data, pricing tables, and invoice templates validated. AR lockbox and payment routing confirmed with treasury.
Established
Intercompany Settlement
Interim intercompany settlement mechanism in place for Day 1. Bank account signatories validated. Wire transfer authorities confirmed active. Delegation of authority and financial approval thresholds established for combined entity.
Active
Synergy Tracking
Integration cost tracking codes live in GL. Earnout and contingent consideration tracking mechanisms confirmed. Synergy realization reporting cadence set. Management reporting aligned to combined entity structure.
Ready
Treasury & Cash Management
Treasury centralization underway — cash pooling, FX management, and banking unification in progress. Purchasing and spend approval controls confirmed active. Insurance policies updated to reflect combined entity.
Aligned
Compliance & Controls
Acquirer financial controls framework applied to acquired entity on Day 1. SOX controls gap assessment assigned. Accounting policy comparison complete. External auditor briefed on combined entity structure.
© 100-Day Advisors · MandAPlaybook.com
5

## Slide 6
COMPLIANCE & REPORTING
Day 1 Posture — Compliance, Controls, and Reporting
Financial Controls
Acquirer financial controls framework applied to acquired entity on Day 1. Acquired Finance staff briefed on key controls in Week 1. Controller to complete gap assessment within 30 days and report to CFO. Compensating controls in place where remediation is pending.
SOX & Audit Readiness
Combined-environment controls test assigned — not attestation only. Access provisioning, change management, and audit logging all being validated. External auditor briefed on combined entity structure before Day 1 reporting window opens.
Accounting Policy Alignment
Accounting policy comparison complete across revenue recognition, depreciation, leases, and goodwill. Policy gap register approved by CFO. External auditor briefed on combined accounting policies. No unresolved policy conflicts permitted to carry into first combined close.
COMPLIANCE STATUS
Tax Notifications
Tax Notifications
Required post-close tax notifications submitted to relevant authorities. Tax elections and entity structure decisions filed within IRS deadlines.
Regulatory Filings
Statutory filing requirements and deadlines identified and calendared. All regulatory notifications on schedule. No open compliance blockers as of Day 1.
Regulatory Filings
Statutory filing requirements and deadlines calendared. All regulatory notifications on schedule. No open compliance blockers as of Day 1.
Contracts & CoC Clauses
Change-of-control contract review complete. Counterparty consent outreach completed 30+ days before close. No contract can terminate on Day 1.
Contracts & CoC Clauses
Change-of-control review complete. Counterparty consent outreach completed 30+ days before close. No contract can terminate on Day 1.
Debt Covenants
All debt obligations and covenants confirmed. Lender consent obtained or waived. Financing committed and closing funds confirmed available.
Debt Covenants
All debt obligations and covenants confirmed. Lender consent obtained or waived. Financing committed and closing funds confirmed available.
Opening Balance Sheet
Opening Balance Sheet
Pro forma combined P&L and balance sheet built. NWC peg and adjustment mechanism confirmed with Legal. External auditor briefed before first combined 10-Q window.
© 100-Day Advisors · MandAPlaybook.com
6

## Slide 7
KEY RISKS & MITIGATIONS
Top RAID Items — Part 1 of 2
Assumption
Active
Finance team personnel remain available through integration
If the Finance workstream lead or critical Finance staff depart at or near close, the combined entity loses institutional knowledge of legacy accounting policies, system configurations, and vendor relationships.
→ CFO to confirm availability and commitment of Finance workstream lead and top 5 critical Finance personnel before close. Initiate retention discussions for any at-risk team members identified during due diligence.
Assumption
Active
No material undisclosed accounting issues surface post-close
If material undisclosed accounting issues are discovered post-close, the purchase price allocation, opening balance sheet, and first combined financial statements will require revision — creating SEC restatement exposure and audit risk.
→ VP Finance to complete rapid financial statement validation in first 14 days. Any material differences escalated to CFO and General Counsel immediately. Auditors to assess materiality of any differences within 5 business days.
Issue
Open
Billing and invoicing continuity disrupted on Day 1
Acquired company's billing system did not successfully connect to acquirer's AR platform at open of business. Approximately 40 open invoices (~$200K) cannot be confirmed as transmitted. Three enterprise customers received duplicate invoice notifications.
→ Treasurer to convene war room with Finance IT and billing platform vendor immediately. All affected customers contacted within 2 hours. Manual billing confirmation for all 40 open invoices by end of Day 1. Status updates to CFO every hour until resolved.
© 100-Day Advisors · MandAPlaybook.com
7

## Slide 8
KEY RISKS & MITIGATIONS
Top RAID Items — Part 2 of 2
Risk
Open
Financial controls framework not yet validated in combined environment
If target's internal controls are materially weaker than acquirer's, a compensating control framework must be in place on Day 1. Absence of controls over the acquired entity in the first reporting period creates SOX exposure.
→ Implement acquirer's financial controls framework for acquired entity on Day 1. Brief acquired Finance staff on key controls in Week 1. Controller to complete gap assessment within 30 days and report findings to CFO.
Risk
Open
Billing and invoicing continuity — cash collection at risk
Any disruption to customer billing on Day 1 creates immediate AR aging risk. Billing system cutover must be tested end-to-end — no cutover without confirmed parallel-run success.
→ Complete billing system cutover testing before Day 1. Validate customer master data, pricing tables, and invoice templates. Confirm AR lockbox and payment routing with treasury. Monitor first 5 days of invoicing closely for errors.
© 100-Day Advisors · MandAPlaybook.com
8

## Slide 9
Finance is Day 1 Ready and Executing.
100-DAY ADVISORS
Accelerating M&A Integrations
MandAPlaybook.com
inquiries@100dayadvisors.com
© 100-Day Advisors · MandAPlaybook.com
9