## Slide 1
HUMAN RESOURCES M&A DAY 1 READINESS
© 100-Day Advisors · MandAPlaybook.com
PRE-CLOSE · DAY 1 READINESS · WEEK 1

## Slide 2
WHAT THIS DECK COVERS
HR Day 1 Integration — Roadmap & Priorities
01
Integration Timeline
Pre-Close milestones, Day 1 Readiness gate, and Week 1 priorities mapped to the March 2 close.
02
Day 1 Readiness Checklist
18 critical tasks confirmed complete before close — communications, payroll, systems, and org structure.
03
Day 1 / Week 1 Actions
Welcome messages, manager briefings, onboarding launch, 401(k) enrollment, and HR town hall.
04
Communications Strategy
Cascade plan, employee FAQ, CHRO message, HR intranet page, and hotline staffing.
05
People & Org
Interim org structure, key talent retention, separation communications, and culture alignment.
06
Key Risks & Mitigations
Top RAID items: HRIS compatibility, payroll funding, state registrations, and employee trust.
© 100-Day Advisors · MandAPlaybook.com
2

## Slide 3
DAY 1 READINESS
Critical Pre-Close Tasks — All Complete
✓
Employee issue process & HR hotline established and tested
Emp. Relations Mgr
✓
Day 1 announcement cascade plan finalized with Comms team
HR Workstream Lead
✓
Employee handbook prepared for acquired employees
HR Compliance Mgr
✓
Day 1 role eliminations identified; separation packages ready
HR Business Partner
✓
Day 1 FAQ document created, piloted, and approved
HR Workstream Lead
✓
Payroll tax IDs and state registrations complete
Payroll Manager
✓
Benefits summary card prepared and approved
HR Compliance Mgr
✓
Day 1 legal notices prepared (WARN, ERISA, benefit changes)
HR Compliance Mgr
✓
CHRO Day 1 welcome message drafted and approved
HR Workstream Lead
✓
Interim org structure determined and approved
HR Workstream Lead
✓
Combined entity employee directory built and verified
HRIS & Systems Mgr
✓
HR self-service portal set up and tested
HRIS & Systems Mgr
✓
Payroll funding accounts established; first cycle scheduled
Payroll Manager
✓
Email, collaboration tools & HR systems access confirmed
HRIS & Systems Mgr
✓
M&A Employee Communication Guide distributed to managers
HR Workstream Lead
✓
HR Day 1 Readiness Gate — all items green, no blockers
HR Workstream Lead
© 100-Day Advisors · MandAPlaybook.com
3

## Slide 4
DAY 1 / WEEK 1 ACTIONS
What Happens in Week 1
Day 1
Brief HR managers — talking points, Q&A guide, escalation protocols (before all-employee announcement)
Distribute CEO & CHRO welcome message to all employees
Communicate separation packages to any Day 1 affected employees
Launch HR integration intranet page — org chart, FAQs, key contacts, timeline
Confirm email, collaboration tools & HR systems access for all acquired staff
Days 2–3
Brief acquired HR team on combined entity processes, tools, timeline, and key contacts
Launch combined entity onboarding program — culture, values, and strategy
Confirm performance review cycle approach for acquired employees
Days 4–6
Communicate unified expense reimbursement policy to all acquired employees
Align code of conduct, ethics policies, and conflicts of interest policy
Complete 401(k) plan enrollment communications and blackout notices
Conduct HR town hall at end of Week 1 — real answers, not talking points
© 100-Day Advisors · MandAPlaybook.com
4

## Slide 5
COMMUNICATIONS STRATEGY
The Cascade: Right Message, Right Person, Right Order
1
Steering Committee
48 hrs before · Close confirmed; final cascade approved
2
HR Managers Brief
2 hrs before · Talking points, Q&A guide, escalation path
3
All-Employee Message
Day 1 open · CEO + CHRO welcome; no news before this
4
HR Intranet Live
Day 1 open · Org chart, FAQs, key contacts, timeline
5
HR Town Hall
End of Week 1 · Real answers — employees have had time to form questions
KEY DELIVERABLES
Day 1 FAQ Document
Covers benefits, payroll, reporting lines, key contacts. Piloted with managers; signed off by Legal & Benefits.
Benefits Summary Card
Coverage dates, carrier contacts, enrollment steps. Top driver of hotline volume if errors exist — requires CHRO sign-off.
HR Integration Hotline
Staffed with experienced HR generalists, not scripts. Tested 48 hrs before close. 5–10× normal call volume on Day 1.
Employee Communication Guide
Distributed to all managers before Day 1 announcement. Includes talking points and escalation contacts.
© 100-Day Advisors · MandAPlaybook.com
5

## Slide 6
PEOPLE & ORGANIZATION
Org Structure, Talent Retention & Separations
Interim Org Structure
› Effective Day 1 — every employee has one clear manager
› Published to all managers before all-employee announcement
› Approved by Steering Committee; no dual reporting lines
› Org chart live on HR intranet page at market open
Talent Retention
› Retention risk scored for all senior leadership pre-close
› Retention agreements ready on Day 1 for highest-risk individuals
› Compensation benchmarked; roles below 50th percentile flagged
› Day 30 pulse survey to detect early attrition signals
Day 1 Separations
› All eliminated roles identified; separation packages legally reviewed
› WARN Act compliance confirmed for any group separations
› Managers provided written script — no improvisation on severance
› Separation agreements signed before any communication occurs
Culture & Onboarding
› Culture assessment completed; findings shared with all workstream leads
› Onboarding designed for integration context, not just new hires
› Acquired HR team briefed on combined processes before Day 1
› Code of conduct acknowledgment documented with signature/confirmation
6

## Slide 7
COMPENSATION & BENEFITS
Key Actions and Compliance Requirements
Payroll — First Combined Cycle
Payroll funding accounts established. State tax registrations active in all jurisdictions. First pay cycle for acquired employees scheduled before Day 1. ACH authorization confirmed with bank.
401(k) Enrollment Communications
Enrollment communications issued Day 1 per ERISA notice requirements. Blackout period notices sent at least 30 days before any blackout. Investment change restrictions communicated to all participants.
Benefits Summary Card
Carrier names, coverage dates, enrollment steps, and contact info verified by Benefits, Legal, and CHRO. Distributed with Day 1 package. Rapid-correction process live on Day 1.
COMPLIANCE WATCH ITEMS
Section 409A
No deferred comp plan modifications post-close without tax counsel. Violations = 20% excise tax.
280G / Golden Parachute
280G calculations complete. Shareholder waiver or payment restructuring in place.
COBRA Administration
Compliance audit complete. Each violation = $100/day/beneficiary in IRS penalties.
ERISA / Plan Decisions
401(k) plan decision (terminate/merge/continue) made. IRS filings and employee notices issued.
I-9 Compliance
I-9 audit for all acquired employees complete. Remediation of substantive errors done.
© 100-Day Advisors · MandAPlaybook.com
7

## Slide 8
KEY RISKS & MITIGATIONS
Top RAID Items — Monitored Through Close
Risk
Closed
HRIS system incompatibility delays payroll integration 60–90 days
Full HRIS architecture assessment complete. Dedicated HRIS PM assigned. Day 1 contingency plan built for any system not integrated before close.
Dependency
Closed
Payroll funding account not active → failed pay cycle with no quick fix
Payroll funding accounts established T-10. ACH routing confirmed. Test payment run before first live cycle.
Risk
Closed
Inactive state payroll tax registration prevents payroll in that state
All state registrations submitted T-30+. Named owner per state. Confirmed active before processing.
Assumption
Active
Acquired employees accept combined entity terms — target: ≤5% voluntary departure in first 30 days
Compensation benchmarking complete. Retention packages ready. Day 30 pulse survey scheduled. >3% departure rate triggers CHRO/CEO escalation.
Risk
Closed
Unresolved Day 1 Readiness gaps = Day 1 execution failure
Day 1 Readiness Gate review with CHRO 48 hrs before close. All 18 checklist items confirmed complete. No open blockers.
Risk
Closed
No response to Day 1 employee concerns within 24 hrs = early voluntary attrition
Employee triage process live before Day 1. Named HR BP on call. 24-hr response SLA published.
8

## Slide 9
SYSTEMS & TECHNOLOGY
HRIS, Payroll & Access — Day 1 Readiness
Assessed
HRIS Platform
Full HRIS architecture assessment complete. Data quality assessment on 50-employee sample validated. Dedicated HRIS PM assigned. Migration timeline set; contingency plan for any system not integrated by Day 1.
Ready
Payroll System
Combined entity payroll configured. State tax registrations active in all jurisdictions. Funding accounts established. First combined payroll cycle scheduled. Test run completed successfully.
Tested
HR Self-Service Portal
Portal set up and tested for acquired employees. Access provisioning confirmed 48 hrs before Day 1. IT escalation path to Day 1 war room established. 4-hour SLA for access issues on Day 1.
Provisioned
Email & Collaboration Tools
Email and collaboration tool access confirmed for all acquired staff. Access validated on representative sample before all-employee announcement. IT on standby for Day 1 access issues.
Complete
Employee Directory
Combined entity directory built and verified. All acquired employees included. Directory reflects both legacy companies — signals to acquired employees that they are part of the team.
Live Day 1
HR Integration Intranet
HR intranet page launches with all-employee message. Contains: interim org chart, Day 1 FAQ, key contacts, benefits links, and integration timeline. 404 errors on Day 1 destroy employee confidence.
© 100-Day Advisors · MandAPlaybook.com
Human Resources is Day 1 Ready.
© 100-Day Advisors · MandAPlaybook.com
100-DAY ADVISORS
Accelerating M&A Integrations
mandaplaybook.com
inquiries@100dayadvisors.com
9