## Slide 1
INTEGRATION MANAGEMENT OFFICE
M&A DAY 1 READINESS
© 100-Day Advisors · MandAPlaybook.com

## Slide 2
WHAT THIS DECK COVERS
IMO Day 1 Integration — Readiness & Execution
01
Integration Timeline
Pre-Close milestones, Day 1 Readiness gate, and Week 1 priorities mapped to the March 2 close.
02
Day 1 Readiness Checklist
10 critical tasks confirmed complete before close — war room, communications, checklists, and dry runs.
03
Day 1 / Week 1 Actions
War room activation, all-workstream stand-up, hourly monitoring, end-of-day debrief, and Week 1 cadence.
04
Governance & Coordination
Steering Committee structure, workstream lead accountability, escalation paths, and synergy tracking.
05
Cross-Workstream Oversight
Dependency management, conflict resolution, RAID log maintenance, and milestone gate reviews.
06
Key Risks & Mitigations
Top RAID items: open items resolution, meeting attendance, dependency tracking, and synergy validation.
© 100-Day Advisors · MandAPlaybook.com
2

## Slide 3
DAY 1 READINESS
Day 1 Readiness — Critical Pre-Close Tasks, All Complete
✓
Consolidate Day 1 readiness checklists and ensure there are owners for each critical task
IMO Leader
✓
Oversee Sales team's development of M&A Customer Communication Guide — review drafts and ensure alignment with master narrative
IMO Leader
✓
Oversee Communications team's development of M&A Employee Communication Guide — review drafts and ensure narrative alignment
IMO Leader
✓
Oversee development of workstream risk mitigation plans pre-close
IMO Leader
✓
Circulate drafts of M&A Employee Communication Guide to workstreams for their input
Integration Coordinator
✓
Confirm all integration vendor contracts and external support resources are in place for Day 1
IMO Leader
✓
Stand up Day 1 IMO war room — staffing, communication channels, escalation contacts, and incident log
IMO Leader
✓
Conduct Day 1 communications dry runs — test all Day 1 announcement channels and verify distribution lists
IMO Leader
✓
Confirm M&A Customer Communication Guide distributed to all sales managers
Integration Coordinator
✓
Confirm M&A Employee Communication Guide distributed to all managers and people leaders before Day 1
Integration Coordinator
✓
IMO Day 1 Readiness Gate — all tasks complete, systems tested, communications ready, no unresolved blockers
IMO Leader
© 100-Day Advisors · MandAPlaybook.com
3

## Slide 4
DAY 1 / WEEK 1 ACTIONS
What Happens in Week 1
Day 1
Activate Day 1 IMO war room — run all-workstream morning stand-up at 7 AM and confirm go-status
Monitor Day 1 task completion across all workstreams hourly and escalate any blocked items
Conduct Day 1 end-of-day debrief with all workstream leads — capture immediate Day 1 issues
Days 2–4
Conduct Week 1 daily IMO stand-up (Mon–Fri) — 15 min, all workstream leads, RAG status and blockers only
Resolve all Day 1 open issues and confirm all Critical Day 1 checklist items are complete
Days 4–7
Update RAID log with all Day 1 issues, blockers, and new risks surfaced — close resolved items, assign owners and mitigations
Publish Week 1 IMO status report — task completion rates, milestone status, RAID summary
© 100-Day Advisors · MandAPlaybook.com
4

## Slide 5
GOVERNANCE & COORDINATION
Day 1 State — IMO Structure & Oversight
Active
Steering Committee
Steering Committee established at T-55 and actively engaged. Executive Sponsor confirmed available for all gate reviews and Steering Committee meetings. Monthly board reporting cadence set and confirmed.
Appointed
Workstream Leads
All workstream leads (HR, IT, Finance, Legal, Sales, Communications) identified, capacity-confirmed, and briefed before IMO kickoff. Backfill confirmed for BAU responsibilities where applicable.
Live
War Room
Day 1 IMO war room activated with full staffing, communication channels, escalation contacts, and incident log. War room activated 24 hours before close — not the morning of Day 1. All channels tested.
Confirmed
Communication Channels
Day 1 communications dry run completed. All announcement channels tested and distribution lists verified. Employee and Customer Communication Guides distributed to all managers and sales leaders before Day 1.
Established
Governance Cadence
Weekly all-workstream IMO meeting cadence established for Week 2 onwards. Daily stand-up confirmed for Week 1. All decisions and action items documented within 24 hours of each meeting.
Tracking
Synergy Tracking
Synergy tracking established at T-26. Each synergy owner has validated their estimate, cost-to-achieve, and realization timeline. Synergy validation status presented to Steering Committee at monthly board report.
© 100-Day Advisors · MandAPlaybook.com
5

## Slide 6
CROSS-WORKSTREAM OVERSIGHT
Day 1 Posture — Coordination, Dependencies & RAID
Dependency Management
Each workstream lead required to submit cross-workstream dependencies — identifying every input they need and every output they owe. Any dependency at risk of missing its delivery date escalated to IMO Leader within 48 hours.
Conflict Resolution
Formal escalation path in place: conflicts unresolved at workstream level within 48 hours escalate to IMO Leader; unresolved within 72 hours at IMO Leader level escalate to Executive Sponsor. No cross-workstream conflicts carried past Week 1.
RAID Log & Reporting
RAID log updated with all Day 1 issues within 24 hours of end-of-day debrief. Every open item has a named owner and 24-hour resolution deadline. Week 1 IMO status report published by Day 5 with task completion rates, milestone status, and RAID summary.
OVERSIGHT STATUS
Steering Committee
Established T-55. Executive Sponsor confirmed engaged. Monthly board report cadence confirmed.
All Workstream Leads
All leads appointed at T-51. Capacity confirmed. Backfill for BAU responsibilities in place where needed.
Integration Governance
IMO governance established at T-42. Charter approved at T-49. Clean room and data privacy protocols distributed.
Risk Assessment
Pre-close risk assessment complete at T-26. Named risk owner for every High-rated risk. All items reviewed by Steering Committee.
Day 1 Readiness Gate
All Day 1 Readiness tasks confirmed complete. War room active. Communications dry run passed. No unresolved blockers.
© 100-Day Advisors · MandAPlaybook.com
6

## Slide 7
KEY RISKS & MITIGATIONS
Top RAID Items — Part 1 of 2
Risk
Open
Day 1 open issues not resolved before Day 2 begins
Any Critical item unresolved past Day 1 without a formal executive waiver sets a precedent that deadlines are negotiable — eroding IMO authority and increasing slippage risk on future milestones.
→ Publish Day 1 open items log to all workstream leads within 2 hours of end-of-day debrief. Assign named owner and 24-hour resolution deadline to every open item. Any High-risk item not resolved within 24 hours escalates automatically to Executive Sponsor.
Dependency
Open
Weekly IMO all-workstream meeting attendance falls below required level
Low attendance or partial participation erodes cross-workstream visibility. Blocked dependencies get flagged too late and workstream leads lose shared context on priorities — compounding over successive weeks.
→ Require attendance from all workstream leads. A workstream lead who misses two consecutive meetings without a deputy must be escalated to IMO Leader immediately. Document all decisions and action items within 24 hours of each meeting.
Risk
Open
Cross-workstream dependencies undocumented or untracked
Undocumented cross-workstream dependencies are the leading cause of surprise delays. A dependency gap discovered in Week 3 often traces back to an input that was never formally captured in Week 1.
→ Require each workstream lead to submit a complete dependency register — every cross-workstream input they need and every output they owe. Any dependency at risk of missing its delivery date escalated to IMO Leader within 48 hours.
© 100-Day Advisors · MandAPlaybook.com
7

## Slide 8
KEY RISKS & MITIGATIONS
Top RAID Items — Part 2 of 2
Risk
Open
Cross-workstream conflicts escalate past IMO level to Steering Committee
Cross-workstream conflicts left unresolved at the IMO level consume executive bandwidth on issues that should have been resolved earlier. Repeated escalations erode Steering Committee confidence in IMO effectiveness.
→ Conflicts unresolved at workstream lead level within 48 hours escalate to IMO Leader. Conflicts unresolved at IMO Leader level within 72 hours escalate to Executive Sponsor. No conflict is allowed to carry into a second weekly IMO meeting unresolved.
Dependency
Open
Synergies lack confirmed owners or cost-to-achieve estimates
Synergies without confirmed owners will not be captured. Any synergy without a validated owner and CTA estimate at Day 30 becomes a gap in the board-facing integration summary — and a source of deal thesis risk.
→ Require each synergy owner to validate estimate, CTA, and realization timeline. Any synergy without a validated owner and CTA at Day 30 is removed from the baseline until re-validated. Present synergy validation status to Steering Committee at monthly board report.
© 100-Day Advisors · MandAPlaybook.com
8

## Slide 9
The IMO is Day 1 Ready and Executing.
100-DAY ADVISORS
Accelerating M&A Integrations
mandaplaybook.com
inquiries@100dayadvisors.com
© 100-Day Advisors · MandAPlaybook.com
9