## Slide 1
INFORMATION TECHNOLOGY
M&A DAY 1 READINESS
© 100-Day Advisors · MandAPlaybook.com

## Slide 2
WHAT THIS DECK COVERS
IT Day 1 Integration — Readiness & Execution
01
Integration Timeline
Pre-Close milestones, Day 1 Readiness gate, and Week 1 priorities mapped to the March 2 close.
02
Day 1 Readiness Checklist
18 critical tasks confirmed complete before close — systems, security, connectivity, and communications.
03
Day 1 / Week 1 Actions
Access provisioning, war room activation, service desk launch, network confirmation, and end-user orientation.
04
Systems & Infrastructure
Network interconnect, email and collaboration, device management, HRIS compatibility, and data sharing.
05
Security & Compliance
Vulnerability remediation, SIEM extension, IAM architecture, SOC 2 certification, and acceptable use policy.
06
Key Risks & Mitigations
Top RAID items: authentication compatibility, service desk capacity, network connectivity, and access failures.
© 100-Day Advisors · MandAPlaybook.com
2

## Slide 3
DAY 1 READINESS
Critical Pre-Close Tasks — All Complete
✓
Critical vulnerabilities assessed and remediated
Cybersecurity & Compliance Lead
✓
Cloud strategy and migration roadmap defined
Infrastructure & Cloud Lead
✓
Data center footprint assessed; consolidation strategy set
Infrastructure & Cloud Lead
✓
Network integration architecture designed for combined entity
Infrastructure & Cloud Lead
✓
IT FAQs drafted and provided to Communications team
IT Integration Coordinator
✓
Unified IT onboarding and offboarding process designed
Applications & Digital Workplace Lead
✓
Device management (MDM/UEM) strategy defined
IT Integration Coordinator
✓
IT input provided for M&A Employee Communication Guide
IT Integration Coordinator
✓
Device provisioning complete for all acquired employees
IT Integration Coordinator
✓
Day 1 IT war-room dry run completed with full team
IT Workstream Lead
✓
Interim data sharing and reporting infrastructure established
Infrastructure & Cloud Lead
✓
Service desk operating model and escalation paths confirmed
IT Integration Coordinator
✓
Network connectivity confirmed between acquirer and target offices
Infrastructure & Cloud Lead
✓
IT service desk stood up with combined coverage
Infrastructure & Cloud Lead
✓
Secure network interconnect established between entities
Infrastructure & Cloud Lead
✓
IT war room activated and command center standing by
IT Integration Coordinator
✓
Unified email and calendar access enabled for all staff
Infrastructure & Cloud Lead
✓
IT Day 1 Readiness Gate — all items green, no blockers
IT Workstream Lead
3

## Slide 4
DAY 1 / WEEK 1 ACTIONS
What Happens in Week 1
Day 1
Verify all acquired employees have Minimum Viable Access — email, HR portal, and line-of-business apps
Brief all staff on Day 1 cybersecurity protocols and acceptable use policies
Send Day 1 IT welcome communication to all combined entity employees
Confirm all office network connectivity is live and stable at open of business
Extend SIEM and threat detection to acquired environment — all endpoints confirmed covered
Days 2–4
Validate all IT controls are active in combined environment
Deploy unified collaboration platform to all combined staff; confirm access and licensing
Finalize and publish unified IT acceptable use policy
Conduct end-user IT orientation sessions for acquired employees
Days 4–6
Assess server and storage infrastructure; develop rationalization roadmap (full rationalization by Day 60)
Establish interim DNS trust and directory connectivity; complete wave-by-wave access provisioning
4

## Slide 5
SYSTEMS & INFRASTRUCTURE
Day 1 State — Six Systems Confirmed Ready
Assessed
Network Architecture
Combined network design reviewed and signed off by both legacy network teams. Interconnect sized at 150% of projected peak load. Failover routing tested and confirmed. War room monitoring dashboards active.
Ready
Email & Calendar
Unified email and calendar access enabled for all combined staff. Provisioning confirmed for all acquired users 24+ hours before Day 1. Directory synchronization complete. Mail queue monitored continuously.
Tested
HR Self-Service & Portals
HR portal and primary line-of-business app access confirmed for all acquired employees. Wave-by-wave provisioning plan in place for Week 1. IT escalation path to Day 1 war room established. 4-hour SLA for access issues.
Deployed
Device Management
All acquired employee devices provisioned. MDM/UEM strategy defined and deployed. 10% hardware buffer maintained for Day 1 failures. On-site IT technician assigned to each major office location.
Integrated
HRIS & Payroll Systems
HRIS and payroll compatibility confirmed. Parallel-run covering at least two full payroll cycles planned. Data mapping validated in sandbox before any production payroll data touched.
Live Day 1
IT Integration Intranet
IT welcome communication sent to all combined entity staff at market open. Service desk number, hours, and escalation path published to all acquired employees before announcement lands.
© 100-Day Advisors · MandAPlaybook.com
5

## Slide 6
SECURITY & COMPLIANCE
Day 1 Posture — Controls, Coverage, and Certifications
Vulnerability Remediation
All critical and high findings (CVSS 7.0+) assessed before close. Every CVSS 9.0+ finding either remediated or formally accepted with a documented risk treatment plan signed by the CISO. Cyber insurance confirmed covering combined entity perimeter from Day 1.
SIEM & Threat Detection
SIEM extended to acquired company environment before any network interconnect goes live. SOC briefed on combined entity perimeter and expected traffic patterns. Alert thresholds adjusted for Day 1 traffic volumes. All endpoints and network segments under unified monitoring.
IAM & Authentication
IAM architecture comparison complete. MFA policy conflicts resolved — more stringent standard adopted across combined entity. SSO federation not permitted until IAM policies reconciled. Protocol-level compatibility test completed; Day 1 workaround documented for any gap.
COMPLIANCE STATUS
SOC 2 / ISO 27001
New audit scope confirmed with certifying auditor. Customer communication timeline ready. Combined certification roadmap delivered within Day 30.
Data Privacy (GDPR/CCPA/HIPAA)
Compliance gap analysis complete. Named owner and deadline assigned to every gap. Acquirer compliance posture does not automatically extend to target.
Vendor Change-of-Control
All vendor contracts with CoC provisions mapped. Consent outreach completed 30+ days before close. No vendor can terminate on Day 1.
Disaster Recovery
Target DR capability tested against acquirer RTO/RPO standards. Written interim mitigation plan in place for any system falling short.
IT Controls (SOX)
Combined-environment controls test run by CISO — not just attestation. Access provisioning, change management, patch management, and audit logging all validated.
© 100-Day Advisors · MandAPlaybook.com
6

## Slide 7
KEY RISKS & MITIGATIONS
Top RAID Items — Part 1 of 2
Risk
Open
Minimum Viable Access — employee authentication failures on Day 1
Users who cannot authenticate on Day 1 flood the service desk, already handling 3–5x normal volume. Dry run failure rate above 2% requires executive escalation.
→ Break-glass access procedure ready. Dedicated authentication queue separate from main help desk. End-to-end auth tested for all geographies 24 hrs before Day 1.
Risk
Open
IT controls not fully validated in combined environment
Controls that pass individually may fail when tested together due to permission inheritance issues, group policy conflicts, or role assignment overlaps.
→ CISO to run combined-environment controls test before Day 1 is declared ready. Control validation checklist with named sign-off requirements assigned.
Issue
Closed
Network connectivity failures at acquired office locations on Day 1
Intermittent VPN failures at two acquired locations at 7 AM. Employees could not access cloud apps, shared drives, or collaboration platform. Resolved by end of Day 1.
→ War room bridge opened immediately. Affected employees redirected to mobile hotspot. Status updates to IMO every 30 minutes. Full connectivity confirmed before end of day.
7

## Slide 8
KEY RISKS & MITIGATIONS
Top RAID Items — Part 2 of 2
Assumption
Active
Acquired IT personnel remain available through integration
If acquired IT leadership or critical admins depart at or near close, the combined entity loses institutional knowledge on legacy systems and undocumented configurations.
→ Top 5 critical IT staff retention confirmed before close. Knowledge transfer at T-30. Centralized IT knowledge base built. Systems integrator on standby if needed.
Assumption
Active
No material undisclosed technical debt or shadow IT
Post-close discovery of significant technical debt, unsupported OS, or shadow IT would require material revision of integration scope, cost, and timeline.
→ Rapid infrastructure validation within first 14 days. Gaps logged in RAID register within 48 hours. Finance notified immediately if budget implications arise.
Risk
Closed
Service desk capacity insufficient for Day 1 volume
Tier 1 agents trained on one environment escalate every cross-environment incident to Tier 2, saturating senior engineers. Service desk volume will be 3–5x normal.
→ Cross-environment training completed before Day 1. Knowledge base pre-populated with top 50 questions. Service desk contact published to acquired employees 24 hrs before close.
8
8

## Slide 9
DAY 1 WAR ROOM
Command Structure, Escalation Paths & Real-Time Monitoring
War Room Operating Model
01
Activation
War room activated 24 hours before Day 1 — not the morning of close. All communication channels, escalation paths, and monitoring dashboards confirmed operational before going live.
02
Command Structure
Single war room commander with authority to make decisions without further approval during the Day 1 window. Every IT issue escalates to the war room first — no individual team troubleshoots in isolation.
03
Dry Run
Full end-to-end simulation conducted covering simultaneous failures — network latency, authentication errors, service desk overload, and application outages occurring at the same time.
04
Escalation Cadence
Status update to IMO Leader every 30 minutes on any open P1 issue. CIO notified if any issue not resolved within 2 hours. Vendor emergency support pre-authorized for network and authentication failures.
05
Monitoring
Real-time dashboards covering: VPN sessions, email queue depth, authentication success rates, service desk ticket volume, and network interconnect utilization. Alert at 70% utilization.
Service Desk — Day 1 Model
Staffing Level
3–5× normal coverage. All agents trained on both legacy environments before Day 1. Senior engineers on standby for novel issues.
Knowledge Base
Pre-populated with top 50 expected Day 1 questions from acquired employees. Service desk number published to all acquired employees 24 hrs before close.
Ticket Routing
Dedicated authentication support queue separate from main help desk. Cross-environment incidents routed to trained agents first — not escalated to Tier 2 by default.
Top 5 Day 1 Issues
(1) VPN access, (2) email provisioning, (3) HR portal login, (4) collaboration platform access, (5) device connectivity. Pre-staged resolution steps for each.
SLA
4-hour resolution SLA for access issues. Break-glass procedure ready for authentication failures not resolved within 30 minutes. IT-052 remains open until 100% MVA confirmed.
© 100-Day Advisors · MandAPlaybook.com
9

## Slide 10
IT is Day 1 Ready and Executing.
100-DAY ADVISORS
Accelerating M&A Integrations
mandaplaybook.com
inquiries@100dayadvisors.com
© 100-Day Advisors · MandAPlaybook.com
10