## Slide 1
LEGAL
M&A DAY 1 READINESS
© 100-Day Advisors · MandAPlaybook.com

## Slide 2
WHAT THIS DECK COVERS
Legal Day 1 Integration — Readiness & Execution
01
Integration Timeline
Pre-Close milestones, Day 1 Readiness gate, and Week 1 priorities mapped to the March 2 close.
02
Day 1 Readiness Checklist
10 critical pre-close tasks confirmed complete — closing docs, regulatory clearance, employment status, and Legal playbook.
03
Day 1 / Week 1 Actions
Close documents executed, entity structures confirmed, WARN notifications filed, contract novations, policy alignment.
04
Legal Entity & Compliance
Day 1 entity structures, regulatory clearances, privilege protocols, and compliance posture across the combined entity.
05
Contracts & IP
Contract novation and assignment, change-of-control consents, IP filings, and harmonization roadmap.
06
Key Risks & Mitigations
Top RAID items: closing documents, legal entity establishment, contract novation and assignment, and acquired GC retention.
© 100-Day Advisors · MandAPlaybook.com
2

## Slide 3
DAY 1 READINESS
Day 1 Readiness — Critical Pre-Close Tasks, All Complete
✓
Confirm Day 1 employment status for all acquired employees
Employment Counsel
✓
Review and finalize severance and CIC payment obligations
Employment Counsel
✓
Circulate pre-close legal integration RACI to all workstreams
Legal Integration Manager
✓
Review and legally clear the M&A Employee Communication Guide
Employment Counsel
✓
Confirm all operating licenses and permits are valid at close
Regulatory Counsel
✓
Confirm all non-compete and non-solicitation agreements are enforceable in relevant jurisdictions
Employment Counsel
✓
Confirm all regulatory pre-approval conditions have been satisfied
Regulatory Counsel
✓
Draft and distribute Day 1 Legal playbook — roles, escalation paths, and decision authority for all Day 1 legal activities
Legal Integration Manager
✓
Brief Legal team on Day 1 roles and protocols
General Counsel
✓
Legal Day 1 Readiness Gate — all tasks complete, systems tested, communications ready, no unresolved blockers
General Counsel
© 100-Day Advisors · MandAPlaybook.com
3

## Slide 4
DAY 1 / WEEK 1 ACTIONS
What Happens in Week 1
Day 1
Execute all Day 1 legal closing documents — confirm all authorized signatories and closing checklist complete
Confirm all legal entity structures are properly established — formations, mergers, and dissolutions legally effective
Send Day 1 integration status update to IMO
Days 2–6
Complete Day 1 WARN Act and equivalent statutory notifications within required timeframes
Establish unified legal hold and document retention policy for combined entity
Align employee handbooks and conduct policies across combined entity
Days 4–20
Execute contract novation and assignment for all required agreements — confirm counterparty consent obtained before execution
© 100-Day Advisors · MandAPlaybook.com
4

## Slide 5
LEGAL ENTITY & COMPLIANCE
Day 1 State — Entity, Regulatory & Employment
Executed
Closing Documents
All Day 1 legal closing documents executed by authorized signatories. Closing checklist complete. Deal counsel confirmed all board and shareholder resolutions authorizing the transaction are properly adopted and effective.
Confirmed
Regulatory Clearance
All required regulatory pre-approval conditions satisfied. Operating licenses and permits confirmed valid and transferable at close. State and local regulatory approvals calendared and obtained. Regulatory Counsel certified all conditions met 3+ days before close.
Confirmed
Employment Status
Day 1 employment status confirmed for all acquired employees — transfer mechanism (TUPE, asset purchase, or new agreement) confirmed per jurisdiction. CIC payment obligations modeled, confirmed, and scheduled. Non-compete enforceability confirmed in all relevant jurisdictions.
Active
Privilege Protocols
Attorney-client privilege protocols distributed to all integration team members before any pre-close data sharing. All legally sensitive communications routed through counsel. Privilege protocol memo acknowledged by all integration leads.
Established
Compliance Program
FCPA, UK Bribery Act, OFAC sanctions compliance certifications received. Data privacy gap assessment complete against GDPR, CCPA, and applicable local laws. Anti-corruption and export control compliance confirmed. Compliance Counsel owns Week 1 integration review.
In Progress
Entity Structure
All required entity formations, mergers, and dissolutions initiated. Corporate Counsel confirming legal effectiveness of each entity action. Entity structure chart updated to reflect combined entity at close. Confirmation expected by Day 6.
© 100-Day Advisors · MandAPlaybook.com
5

## Slide 6
CONTRACTS & IP
Day 1 Posture — Contracts, IP, and Document Retention
Contract Novation & Assignment
Contract novation and assignment underway for all required agreements. Counterparty consent confirmed before execution of each novation. Commercial Counsel tracking completion status. Change-of-control consents secured for all material customer and vendor contracts before Day 1.
Contract Harmonization
Contract harmonization roadmap complete — every material contract categorized as Keep As-Is, Amend, Novate, Renegotiate, or Terminate. Roadmap approved by General Counsel. Execution begins in Week 2 under Commercial Counsel ownership.
IP & Trademark
IP Counsel reviewed all registrations, ownership assignments, and joint development agreements. Trademark clearance complete in all operating jurisdictions. IP assignment filings to be executed post-close. No unresolved IP ownership disputes at Day 1.
LEGAL STATUS
Closing Documents
All Day 1 closing documents executed. Authorized signatories confirmed. Closing checklist complete.
Regulatory Approvals
All pre-approval conditions satisfied. Regulatory Counsel certified clearance 3+ days before close.
Document Retention
Unified legal hold and document retention policy being established by Compliance Counsel — target Day 6.
WARN Act Notifications
WARN Act and equivalent statutory notifications in progress. Employment Counsel owns. Target completion Day 6.
Employee Policy Alignment
Employee handbook and conduct policy alignment underway. Employment Counsel coordinating with HR. Target Day 31.
© 100-Day Advisors · MandAPlaybook.com
6

## Slide 7
KEY RISKS & MITIGATIONS
Top RAID Items — Part 1 of 2
Risk
Open
Day 1 closing documents not fully executed at open of business
If any closing document is missing a required signature or executed by an unauthorized signatory, the transaction may not be legally effective. Any defect in the closing document set creates title risk and potential deal failure.
→ Confirm all closing documents are pre-positioned with correct authorized signatories 48 hours before close. Build a closing document checklist with named custodian for each document. General Counsel to confirm closing package is complete before 9 AM on March 2.
Risk
Open
Legal entity structures not legally effective at Day 1 open
If required entity formations, mergers, or dissolutions are not legally effective at Day 1 open, the combined entity's legal structure is incomplete. Regulatory filings, tax elections, and counterparty notifications may be premature or invalid.
→ Corporate Counsel to confirm all required entity actions are legally effective and recorded by 8 AM on March 2. Any entity action not confirmed effective by close-of-business March 1 escalates to General Counsel and IMO Leader immediately.
Risk
Open
Contract novation and assignment delayed — counterparty consents outstanding
Any contract that cannot be novated or assigned without consent that has not yet been obtained cannot be transferred at close. Unauthorized assignment of a restricted contract may constitute a material breach, triggering counterparty termination rights.
→ Confirm counterparty consent is obtained before executing any novation or assignment. Commercial Counsel to flag any consent that is not confirmed at least 24 hours before close. Any outstanding consent escalated to General Counsel for decision on Day 1 sequencing.
© 100-Day Advisors · MandAPlaybook.com
7

## Slide 8
KEY RISKS & MITIGATIONS
Top RAID Items — Part 2 of 2
Assumption
Validated
Acquired company General Counsel and senior legal staff will remain available through integration
If the acquired company's GC or senior legal personnel depart at or near close, the combined entity loses institutional knowledge of target's contracts, litigation, regulatory relationships, and compliance posture — none of which can be quickly reconstructed.
→ General Counsel confirmed retention status of acquired company's top 3 legal personnel before close. Any at-risk departure escalated to Executive Sponsor before Day 1. Retention incentives in place where needed.
Assumption
Validated
All required regulatory pre-approvals will be obtained without conditions or consent orders
If regulatory approval is conditional — requiring divestitures, behavioral remedies, or consent orders — the integration scope, timeline, and synergy model must be revised. Any condition not anticipated in deal modeling creates significant post-close disruption.
→ Regulatory Counsel monitoring all pre-closing filings. No conditional approval accepted without Steering Committee review of revised integration scope. Any indication of conditional outcome escalated to General Counsel and Executive Sponsor within 24 hours of signal.
© 100-Day Advisors · MandAPlaybook.com
8

## Slide 9
Legal is Day 1 Ready and Executing.
100-DAY ADVISORS
Accelerating M&A Integrations
mandaplaybook.com
inquiries@100dayadvisors.com
© 100-Day Advisors · MandAPlaybook.com
9