## Slide 1
SALES
M&A DAY 1 READINESS
© 100-Day Advisors · MandAPlaybook.com

## Slide 2
WHAT THIS DECK COVERS
Sales Day 1 Integration — Readiness & Execution
01
Integration Timeline
Pre-Close milestones, Day 1 Readiness gate, and Week 1 priorities mapped to the March 2 close.
02
Day 1 Readiness Checklist
11 critical pre-close tasks confirmed complete — customer comms, enablement, dry run, and readiness gate.
03
Day 1 / Week 1 Actions
CEO outreach, all-hands kickoff, org announcement, enablement kit launch, and systems confirmation.
04
Customer & Channel Readiness
Top-50 account outreach, at-risk retention plan, channel partner notification, and contract inventory.
05
Sales Enablement
Combined enablement kit, battlecards, pricing sheets, objection handling guide, and onboarding program.
06
Key Risks & Mitigations
Top RAID item: sales systems not fully operational at Day 1 — CRM access, quoting tools, and telephony.
© 100-Day Advisors · MandAPlaybook.com
2

## Slide 3
DAY 1 READINESS
Day 1 Readiness — Critical Pre-Close Tasks, All Complete
✓
Develop customer communication strategy — segmentation, sequencing, channels, and key messages by segment
Marketing/Enablement Lead
✓
Develop M&A Customer Communication Guide — talking points, guidance for team conversations, Q&A/FAQ
Marketing/Enablement Lead
✓
Draft Day 1 customer announcement letter/email — CEO-signed; focus on continuity and value
Sales Operations Lead
✓
Develop objection handling guide for integration-related customer questions
Marketing/Enablement Lead
✓
Develop channel communication plan for transaction announcement
Channel Sales Lead
✓
Develop combined brand and messaging framework for sales outreach
Marketing/Enablement Lead
✓
Identify and prioritize top 20 at-risk customer accounts — develop account-specific Day 1 retention talking points
Sales Operations Lead
✓
Develop Day 1-ready sales enablement kit: decks, battlecards, pricing sheets
Marketing/Enablement Lead
✓
Distribute M&A Customer Communication Guide to all sales managers
Sales Operations Lead
✓
Conduct Day 1 readiness dry run with sales leadership team
VP Sales / Sales Workstream Lead
✓
Distribute M&A Employee Communication Guide (talking points, guidance, FAQs) to all sales managers
Sales Operations Lead
✓
Sales Day 1 Readiness Gate — all tasks complete, systems tested, comms ready, no unresolved blockers
VP Sales / Sales Workstream Lead
© 100-Day Advisors · MandAPlaybook.com
3

## Slide 4
DAY 1 / WEEK 1 ACTIONS
What Happens in Week 1
Day 1
Freeze sales territory assignments — no changes without formal approval
Execute Day 1 customer outreach — CEO letters to top 50 accounts
Communicate interim sales organization structure and reporting lines to all reps
Hold Day 1 all-hands with combined sales team — welcome, org structure, priorities
Distribute Day 1 sales enablement kit to full combined sales team
Send Day 1 integration status update to sales leadership, IMO, and steering committee
Confirm all Day 1 sales systems are operational — CRM, email, telephony, quoting ⚠ Delayed
Days 2–4
Notify channel partners of transaction close and combined entity structure
Conduct outreach check-in calls with top 20 accounts — capture concerns and sentiment
Communicate any pricing changes and contract approval process to sales team
Identify key sales talent to retain — create retention plan for top performers
Inventory all active customer contracts — flag non-standard terms
© 100-Day Advisors · MandAPlaybook.com
4

## Slide 5
CUSTOMER & CHANNEL READINESS
Day 1 State — Customer Coverage & Retention
Executed
Top-50 CEO Outreach
CEO-signed announcement letters delivered to top 50 customer accounts on Day 1. Focus on continuity of service, no disruption to contracts or support, and value from the combined entity.
Active
At-Risk Account Retention
Top 20 at-risk accounts identified and prioritized. Account-specific Day 1 retention talking points developed for each assigned account owner. VP Sales owns escalation for any accounts flagging churn intent.
In Progress
Channel Partner Notification
Channel partner notification underway — all partners notified of transaction close and combined entity structure by Day 2. Channel communication plan executed per pre-close playbook.
Underway
Check-In Call Cadence
Outreach check-in calls with top 20 accounts launched Day 2. All concerns and sentiment captured in CRM. Early flags escalated to VP Sales within 24 hours of the call.
Inventoried
Contract Review
Full inventory of active customer contracts underway. Non-standard terms flagged for Legal review. Any contract with a change-of-control clause confirmed with Legal before Day 1 customer outreach.
Confirmed
Pricing & Contract Process
Pricing changes and contract approval process communicated to sales team during Week 1. Interim combined pricing framework established. Sales reps briefed on approval thresholds for any exceptions.
© 100-Day Advisors · MandAPlaybook.com
5

## Slide 6
SALES ENABLEMENT
Day 1 Posture — Enablement, Org, and Systems
Enablement Kit — Day 1 Ready
Combined sales enablement kit distributed to full sales team on Day 1. Kit includes updated pitch decks, battlecards, pricing sheets, and objection handling guide for integration-related customer questions. Reps have materials needed to have confident conversations from Day 1.
Sales Org & Territory
Interim sales organization structure and reporting lines communicated to all reps on Day 1. Territory assignments frozen — no changes without formal VP Sales approval. Key sales talent identified; retention plan for top performers in progress.
Onboarding Program
Combined sales onboarding program for acquired-company reps launched in Week 1. Program covers acquirer products, pricing, CRM workflow, and combined value proposition. All-hands kickoff held Day 1 — welcome, org overview, and integration priorities communicated.
SYSTEMS STATUS
CRM Access ⚠ Delayed
CRM access not fully operational at Day 1 open. IT Lead actively resolving. VP Sales designated SAL-044 as P1. Estimated resolution: by end of Day 1.
Email & Collaboration
Unified email and collaboration access confirmed for all combined sales team members.
Quoting & Pricing Tools
Quoting tool license provisioning in progress. Temporary manual approval process in place for any quote requiring the tool before access is restored.
Sales Enablement Platform
Day 1 enablement kit distributed via email and shared drive as primary access method pending platform access confirmation.
Telephony
Telephony systems under IT review. Sales reps using mobile numbers as primary contact method for Day 1 customer calls where desk phone access is pending.
© 100-Day Advisors · MandAPlaybook.com
6

## Slide 7
KEY RISKS & MITIGATIONS
Top RAID Items — Active & Monitored
Issue
Open
Sales systems not fully operational at Day 1 — CRM, quoting, and telephony
Acquired-company reps who cannot access CRM cannot log customer interactions or update pipeline on Day 1. Without real-time pipeline visibility, VP Sales cannot assess combined entity forecast. Quoting delays slow response to Day 1 customer inquiries.
→ IT Lead resolving in real time. VP Sales designated SAL-044 a P1 issue. Manual workarounds in place — reps logging customer contacts via shared sheet. Status update to IMO every 2 hours until resolved. Full system access target: end of Day 1.
Assumption
Active
Key acquired-company sales talent will remain through Day 1 and the integration period
If top sales performers depart at or near close, the combined entity loses customer relationships, pipeline knowledge, and territory coverage that cannot be quickly replaced. Accounts managed by departing reps are at highest churn risk.
→ Retention plan for top performers in progress (SAL-034). VP Sales conducting 1:1s with priority reps this week. Compensation alignment confirmed before Day 1. Any voluntary departure in Week 1 escalated to Executive Sponsor immediately.
Assumption
Active
Target company will provide timely access to customer lists, pipeline data, and channel agreements
Sales planning, territory design, and channel conflict resolution all depend on timely access to target's customer and pipeline data. Delays in data access push back quota setting, territory decisions, and synergy modeling.
→ Data access confirmed under clean room protocols. Pipeline data received and loaded into IMO tracking model. Channel agreement inventory complete. Any new data access delays escalated to Legal and IMO Leader immediately.
Assumption
Active
Close occurred on March 2 as scheduled with no material delay
All Day 1 sales readiness work — customer communication distribution, territory freeze, systems preparation, and all-hands scheduling — was sequenced to the March 2 close date.
→ Close confirmed March 2. All Day 1 actions executing on schedule. No sequencing adjustments required. Any late-breaking close risk would have been escalated by Legal and IMO Leader with minimum 72-hour notice.
© 100-Day Advisors · MandAPlaybook.com
7

## Slide 8
Sales is Day 1 Ready and Executing.
100-DAY ADVISORS
Accelerating M&A Integrations
mandaplaybook.com
inquiries@100dayadvisors.com
© 100-Day Advisors · MandAPlaybook.com
8