## Comm Integration Plan
PRE-CLOSE COMMUNICATIONS MERGER INTEGRATION PLAN | [13 empty] | Click on + sign (above the top row on right) to see synergy columns
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
Risk Level | Status | % Complete |  |  | Links
High | Not Started | 0% |  |  | Milestones
Medium | Delayed | 25% |  |  | RAID Log (Includes Plan Assumptions)
Low | On Track | 50% |  |  | Tasks in Next 14 Days
| Complete | 75% |  |  | Executive Dashboard
100%
ID# | Category | Milestone | Phase | Assigned To | Task | Notes | Timing Anchor | Start | Finish | Status | Complete | Critical Path | Issues/Blockers | Risk Level | Team Dependency | Synergy Description | Synergy ($K) | Cost To Achieve ($K) | Synergy ($K) Realized | Actual Cost To Achieve ($K)
COM-001 | Governance & Planning | Comms Lead Appointed | Pre-Close | CEO / CMO | Identify and onboard Communications integration workstream lead and members of Communications integration team | Workstream lead must be in seat before IMO kickoff; Communications cannot function without a single accountable owner who has authority to approve messaging across both entities; prioritize candidates with cross-functional relationships in HR, Legal, and Sales — comms integration requires constant coordination across these teams | T-59 | 1/2 | 1/10 | Not Started | 0% | CP – Close | Every pre-close communications task — embargo protocols, agency alignment, master narrative, regulatory notifications — requires someone with authority to make decisions and approve content; without a named lead, each of those tasks either stalls or is decided by committee with no accountability, and committees do not move at the speed integration communications requires | High | Executive Sponsor, HR
COM-002 | Governance & Planning | Comms Integration Governance Established | Pre-Close | Communications Integration Manager | Review data privacy and confidentiality protocols for pre-close sharing | Clean room rules apply to all comms planning pre-close; any message drafted using non-public target information must be reviewed by Legal before distribution | T-53 | 1/8 | 1/12 | Not Started | 0% |  | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | High | Legal
COM-003 | Governance & Planning | Comms Integration Governance Established | Pre-Close | Communications Lead | Attend IMO Kickoff Meeting | Bring a written summary of Communications workstream scope and open questions; IMO kickoff is the single best opportunity to resolve cross-workstream dependencies in one session | T-50 | 1/11 | 1/11 | Not Started | 0% |  |  | Low | IMO
COM-004 | Governance & Planning | Comms Due Diligence Complete | Pre-Close | Communications Integration Manager | Receive access to integration data room and document repository | Request access on the day the NDA is signed; pre-close access is time-limited and every day of delay compresses the planning window | T-49 | 1/12 | 1/13 | Not Started | 0% |  |  | Low | Legal
COM-005 | Governance & Planning | Comms Integration Governance Established | Pre-Close | Communications Lead | Conduct Communications team kickoff | Set the agenda 48 hours in advance; first session should cover roles, Day 1 priorities, approval workflows, and the embargo protocol | T-49 | 1/12 | 1/12 | Not Started | 0% |  |  | Low | IMO
COM-006 | Governance & Planning | Comms Charter Approved | Pre-Close | Communications Lead | Develop the communications team integration charter | Charter must define scope boundary between Communications, HR, and Marketing; overlap in employee comms and brand is the most common source of workstream conflict | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Low | IMO
COM-007 | Governance & Planning | Comms Integration Governance Established | Pre-Close | Communications Lead | Define communication success metrics and KPIs | Establish metrics across four categories: reach (how many people received each communication), comprehension (do employees understand what is happening and what it means for them), sentiment (how are employees, media, and customers reacting), and timeliness (were communications delivered before employees heard from external sources) | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Low | IMO
COM-008 | Communications | Comms Due Diligence Complete | Pre-Close | Communications Lead | Audit both companies' communications functions — headcount, channels, agencies, budgets, and tech stack | Include headcount, agency rosters, owned media channels, editorial calendars, budgets, and tech stack (email platforms, DAM, social tools); output drives all agency and budget decisions | T-49 | 1/12 | 1/26 | Not Started | 0% |  |  | Medium | Legal, HR | Agency consolidation savings — auditing both companies PR, digital, and creative retainers identifies duplicate spend; rationalized to a single preferred roster post-close delivers vendor cost reduction; savings are identified through the communications audit process and realized through post-close agency transitions | 75 | 20
COM-009 | Communications | Comms Due Diligence Complete | Pre-Close | Communications Integration Manager | Map all active communications agency relationships, contracts, and change-of-control clauses | Flag any agency contracts with change-of-control clauses requiring counterparty consent; these must be reviewed by Legal before Day 1 agency strategy is finalized | T-49 | 1/12 | 1/26 | Not Started | 0% |  | An agency that holds exclusive rights to a brand campaign or crisis management relationship and discovers at close that their contract was transferred without consent can withdraw services on Day 1 — the day when Communications needs them most; the risk is not a legal fee, it is losing a specialized partner in the middle of the most demanding communications moment of the integration | High | Legal, Procurement
COM-010 | Communications | Comms Due Diligence Complete | Pre-Close | Communications Integration Manager | Inventory all active press releases, campaigns, and content commitments across both entities | Pause any campaigns or announcements that conflict with the deal narrative; maintain a hold list with Legal sign-off for each item paused | T-49 | 1/12 | 1/26 | Not Started | 0% |  |  | Medium | Legal, Marketing
COM-011 | Communications | Comms Infrastructure Ready | Pre-Close | Communications Lead | Establish communications approval workflow | Embargo protocol must be in writing and distributed to all agency partners and internal comms staff; any pre-close leak triggers legal and reputational risk — treat as a zero-tolerance control | T-49 | 1/12 | 1/19 | Not Started | 0% | CP – Close | A pre-close leak of deal information by a communications team member — internal or agency — triggers legal, regulatory, and reputational consequences; embargo protocol must be distributed in writing to all agency partners and internal staff, and compliance confirmed before any deal-related content is created | High | Legal, Executive Sponsor
COM-012 | Integration Management | Day 100 Comms Integration Complete | Pre-Close | Communications Integration Manager | Update Communications Executive Dashboard weekly | Dashboard rows owned by Communications Lead; RAG status must reflect the most current approval and publish timelines, not the original plan | T-49 | 1/12 | 6/10 | Not Started | 0% |  |  | Low | IMO
COM-013 | Communications | Master Narrative Approved | Pre-Close (Day 1 Readiness) | Communications Lead | Develop master integration narrative and core messages aligned with deal rationale and value drivers | Master narrative is the foundation for every downstream content piece; all audience-specific messaging must trace back to this document — do not write any external content before it is approved by the executive sponsor and Legal | T-49 | 1/12 | 1/27 | Not Started | 0% | CP – Day 1 Readiness | The master narrative is not just a document — it is the approval gate for every other content piece in the integration; a press release, employee letter, or customer guide that goes out before the narrative is approved will carry messaging that contradicts the CEO's talking points, and contradictions discovered by journalists, employees, or customers on Day 1 become the story instead of the story you intended to tell | High | Legal, HR, C-Level Executives
COM-014 | Governance & Planning | Comms Integration Governance Established | Pre-Close | Communications Lead | Define communications integration guiding principles, voice, and tone framework for combined entity | Tone framework must be approved by executive sponsor before any external-facing draft is written; establishes the voice that all content — internal and external — must reflect | T-47 | 1/14 | 1/25 | Not Started | 0% |  |  | Medium | Marketing, C-Level Executives
COM-015 | Governance & Planning | Comms Integration Governance Established | Pre-Close | Communications Integration Manager | Build communications RACI matrix — who approves, drafts, and reviews messages | RACI must cover all five audience types: employee, customer, media, investor, and regulatory; co-ownership is a common accountability gap — every content type needs a single approver | T-47 | 1/14 | 1/18 | Not Started | 0% |  |  | Low | IMO, HR, Legal
COM-016 | Communications | Comms Due Diligence Complete | Pre-Close | Communications Lead | Identify key government and community stakeholders requiring proactive outreach on deal announcement | Map includes local officials in headquarter cities, relevant trade associations, union contacts, and any government customers; proactive outreach prevents regulatory surprises and community backlash | T-46 | 1/15 | 1/20 | Not Started | 0% |  |  | Low | Legal, Government Affairs
COM-017 | Communications | Brand Strategy Determined | Pre-Close | Brand & Creative Director | Develop brand integration strategy — define combined entity naming, brand architecture, and transition timeline | Brand architecture decision (retain acquirer, retain target, co-brand, or new brand) must be made before any design work begins; all three options carry different legal, cost, and timeline implications — require CEO and board input | T-45 | 1/16 | 2/16 | Not Started | 0% |  | Every Day 1 creative asset — website, signage, social profiles, press materials — is built on an assumption about the brand architecture; if the decision changes after design work has begun, every asset must be rebuilt from scratch; the agencies and design teams that do this work have lead times measured in weeks, not days, and there is no fast-follow option on Day 1 brand execution | High | Legal, Marketing, C-Level Executives
COM-018 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Coordinate with IR and Finance team to develop investor Day 1 communication — deal rationale and financial impact | 8-K filing, investor letter, and earnings call script must all be cleared by Legal and the CFO before Day 1; any investor-facing communication that creates a material misstatement creates securities law exposure | T-45 | 1/16 | 2/16 | Not Started | 0% | CP – Day 1 Readiness | Investor communications must be sequenced correctly relative to regulatory filings; any investor-facing content that contains material non-public information before the 8-K is filed creates securities law exposure — IR and Legal must confirm the exact publish sequence and approve all language before Day 1 | High | IR, Finance, Legal
COM-019 | Communications | Messaging Frameworks Complete | Pre-Close (Day 1 Readiness) | Communications Lead | Build audience-specific messaging frameworks for: employees, customers, media, investors, and regulators | Employee messaging is the highest-stakes content stream — employees are the most trusted sources for customers and media; prioritize this framework first and get HR alignment before distributing to managers | T-45 | 1/16 | 2/2 | Not Started | 0% | CP – Day 1 Readiness | Audience-specific messaging that is developed in parallel with the master narrative — rather than derived from it — will produce inconsistent messages; the employee version of the story, the customer version, and the investor version will have different characterizations of the same facts, and those inconsistencies will be discovered by the employees, customers, and investors who talk to each other | High | All Workstreams
COM-020 | Integration Management | Day 100 Comms Integration Complete | Pre-Close | Communications Lead | Conduct weekly workstream status meeting |  | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
COM-021 | Governance & Planning | Day 100 Comms Integration Complete | Pre-Close | Communications Integration Manager | Develop communications integration plan (tasks, milestones, RAID log, Day 1 checklist) and update it weekly | Integration plan is the Communications workstream's operating document; update weekly and share with IMO coordinator by Thursday — delays in updating create cascading IMO reporting errors | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Medium | IMO
COM-022 | Communications | Comms Due Diligence Complete | Pre-Close | Brand & Creative Director | Coordinate with Legal to conduct trademark and legal review of combined entity brand name and logo options | IP counsel must clear the combined brand name in all operating jurisdictions before any external design work begins; domestic clearance alone is insufficient for companies with international operations | T-42 | 1/19 | 2/9 | Not Started | 0% |  | A brand name that reaches the design phase without IP clearance in a key jurisdiction — particularly in the EU, China, or markets with aggressive trademark enforcement — may need to be changed after months of design investment; the cost is not the legal filing fee but the creative write-off, the agency rework, and the delay to a Day 1 brand transition that was already on the critical path | High | Legal, IP Counsel
COM-023 | Communications | Comms Due Diligence Complete | Pre-Close | Digital Communications Manager | Audit both companies' social media accounts — define which handles to retain, merge, or retire | Document credentials for all accounts before any consolidation; archive legacy content before retiring accounts — deleted content cannot be recovered and may be referenced in media or legal contexts | T-42 | 1/19 | 2/6 | Not Started | 0% |  |  | Low | Marketing, Legal
COM-024 | Communications | Comms Infrastructure Ready | Pre-Close (Day 1 Readiness) | Media Relations Manager | Build media monitoring protocol — set up tracking for deal coverage, sentiment, and key narratives pre- and post-close | Daily briefing for Communications Lead; weekly summary distributed to executive sponsor — monitoring must be active from the day the deal is announced, not from Day 1 | T-42 | 1/19 | 1/30 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | IT, Marketing
COM-025 | Integration Management | Day 100 Comms Integration Complete | Pre-Close | Communications Integration Manager | Conduct weekly communications team status meetings | Same day and time every week — consistency builds team discipline; pre-read distributed 24 hours in advance with status update, blockers, and approvals needed | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
COM-026 | Integration Management | Day 100 Comms Integration Complete | Pre-Close | Communications Integration Manager | Update status of communications integration plan weekly | Status report due to IMO by Thursday 4 PM; include RAG by task, any new issues, and a list of decisions needed from the steering committee | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
COM-027 | Integration Management | Day 100 Comms Integration Complete | Pre-Close | Communications Lead | Attend weekly IMO Meeting to discuss issues and status | Bring a written Communications status summary; use this meeting to surface any cross-workstream dependencies that require IMO escalation | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
COM-028 | Governance & Planning | Day 1 Comms Readiness Confirmed | Pre-Close | Communications Lead | Establish communications budget for integration period — agency fees, media spend, events, and tools | Establish a separate integration comms budget line; track actuals monthly and report variance to IMO — agency overspend is the most common comms budget failure mode | T-41 | 1/20 | 2/15 | Not Started | 0% |  |  | Low | Finance
COM-029 | Communications | Comms Due Diligence Complete | Pre-Close | Brand & Creative Director | Inventory all branded touchpoints requiring update — signage, website, social, email, collateral, vehicles, uniforms | Categorize touchpoints by visibility and cost; digital assets (website, email, social) must change on Day 1 — physical signage and printed collateral can follow on a phased schedule | T-38 | 1/23 | 2/6 | Not Started | 0% |  |  | Low | Marketing, IT, Facilities, Procurement
COM-030 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Digital Communications Manager | Develop Day 1 digital communications strategy — website, social channels, email, and intranet update schedule | Minute-by-minute publish schedule must be dry-run tested with IT at least two weeks before Day 1; every asset must be staged and approved in advance — live-drafting on Day 1 is not acceptable | T-38 | 1/23 | 2/20 | Not Started | 0% | CP – Day 1 Readiness | Website and social channel updates must go live within minutes of the press release; any technical failure — broken links, missing content, staged assets not published — is immediately visible to customers, media, and investors; IT must confirm the publish workflow is tested end-to-end at least two weeks before Day 1 | High | Marketing, IT
COM-031 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Media Relations Manager | Develop reactive media holding statements for top 10 sensitive deal topics | Holding statements must be pre-approved by Legal and the executive sponsor; the Communications Lead must be able to deploy them within 30 minutes of a media inquiry without seeking further approval | T-38 | 1/23 | 2/20 | Not Started | 0% | CP – Day 1 Readiness | Media inquiries on deal-sensitive topics (layoffs, pricing, leadership, brand changes) will arrive on Day 1 without warning; holding statements must be pre-approved by Legal and the executive sponsor and deployable by the PR Manager within 30 minutes — waiting for approval on Day 1 under media pressure is not an acceptable protocol | High | Legal, Executive Sponsor
COM-032 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Plan and script Day 1 all-hands town hall — format, speakers, agenda, Q&A logistics, and run-of-show | Town hall within 48 hours of Day 1; record and post the replay within 24 hours for employees in other time zones — a well-run town hall is the single most powerful tool for reducing employee anxiety | T-35 | 1/26 | 2/25 | Not Started | 0% |  | Employees who do not hear directly from leadership within 48 hours of Day 1 will fill the silence with speculation; in a unionized environment or in jurisdictions with Works Councils, a town hall that is delayed can trigger a formal request for information from employee representatives — and a formal request means Legal is now involved in a communications timeline that should have been managed proactively | High | HR, IT, Executive Team
COM-033 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Develop with HR, all-employee announcement — leadership letter, and integration overview | CEO-signed letter must be in manager inboxes before the press release goes live; employees who learn about the deal from external sources before receiving a message from their own leadership lose trust immediately | T-31 | 1/30 | 2/25 | Not Started | 0% |  | An employee who reads about the acquisition on their phone before arriving at their desk is already processing the news through their personal filter rather than through the company's narrative; once that frame is set, the official communication that arrives later is received as a reaction, not a revelation — and an employee in reaction mode is harder to retain than an employee who felt informed | High | HR, Legal, C-Suite
COM-034 | Communications | Employee Comms Guide Approved | Pre-Close (Day 1 Readiness) | Communications Lead | Develop with HR the M&A Employee Communication Guide (includes talking points, guidance for team conversations, Q&A / FAQ covering anticipated questions) | Distribute to managers at least 24 hours before the all-employee announcement; managers are the most trusted source of information for employees and must be prepared to answer questions before they arrive | T-31 | 1/30 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | A manager who is handed the Employee Communication Guide the same morning as the all-employee announcement cannot prepare thoughtful responses to their team's questions — they are reading the guide in real time alongside the people they are supposed to lead; the first 30 minutes of employee reaction is the highest-stakes window in the integration, and it is the window where an unprepared manager does the most damage | High | HR
COM-035 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Prepare executive talking points for CEO, CFO, and division presidents for Day 1 announcements | Talking points must be rehearsed with each executive at least two weeks before Day 1; unrehearsed executives are the leading cause of off-message Day 1 interviews | T-31 | 1/30 | 2/20 | Not Started | 0% |  |  | Medium | Legal, C-Level Executives
COM-036 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Integration Manager | Develop M&A Vendor Communication Guide (includes talking points, guidance for team conversations, and Q&A / FAQ covering anticipated questions) | Vendor guide covers key talking points, FAQ, and timeline for supply chain and strategic vendor relationships; coordinate with Procurement on top 20 vendor accounts for personalized outreach | T-31 | 1/30 | 2/25 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Procurement, Legal
COM-037 | Communications | Customer Comms Guide Approved | Pre-Close (Day 1 Readiness) | Communications Lead | Develop with Sales team, the M&A Customer Communication Guide (includes talking points, guidance for team conversations, and Q&A / FAQ covering anticipated questions) | Customer-facing staff must be briefed before the press release goes out — customers who hear about the deal from media before their account manager is a serious relationship risk | T-31 | 1/30 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | A customer communication strategy developed without the master narrative in hand will produce messaging that contradicts what the CEO says publicly on Day 1; a customer who receives a communication from their account manager that tells a different story than the press release has received two versions of the same event from the same company, and the discrepancy becomes the story | High | Sales, Legal
COM-038 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Develop in concert with HR team Day 1 announcement cascade plan — who communicates what, to whom, and in what order | Cascade plan defines who hears what, in what order, and through which channel; managers must be briefed before the all-employee announcement goes out — employees who hear news from media before their manager is a preventable failure | T-31 | 1/30 | 2/16 | Not Started | 0% | CP – Day 1 Readiness | Cascade sequence failure — employees hearing deal news from media, social, or unofficial channels before their direct manager — is the most damaging and most preventable Day 1 communications failure; cascade plan must confirm manager briefing windows, distribution timing, and escalation contacts before Day 1 dry run | High | HR
COM-039 | Communications | Brand Strategy Determined | Pre-Close (Day 1 Readiness) | Brand & Creative Director | Develop Day 1 brand transition plan — what changes on Day 1 vs. phased transition vs. Day 100 | Day 1 brand changes must be limited to what can realistically be executed without error; over-ambitious Day 1 brand transitions are a common source of customer confusion — phase lower-visibility items | T-28 | 2/2 | 2/20 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Marketing, Legal, IT
COM-040 | Communications | Comms Infrastructure Ready | Pre-Close (Day 1 Readiness) | Communications Integration Manager | Build internal communications calendar for integration period — cadence, channels, owners, and content themes | Minimum weekly cadence for employees; bi-weekly for managers; monthly all-hands — consistency is more important than content volume; employees who stop hearing from leadership assume the worst | T-24 | 2/6 | 2/20 | Not Started | 0% |  |  | Medium | HR, IMO
COM-041 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close | Digital Communications Manager | Establish integration intranet site for resources, updates, and employee FAQ | Launch on Day 1 alongside the all-employee announcement; include integration timeline, org chart, FAQ, workstream updates, and a feedback mechanism — static sites without updates erode trust quickly | T-24 | 2/6 | 2/23 | Not Started | 0% |  |  | Medium | IT
COM-042 | Communications | Brand Strategy Determined | Pre-Close | Brand & Creative Director | Brief and align design agency on brand integration scope, timeline, and deliverables | Brief agency under NDA; design agency is subject to the same embargo rules as internal staff — any leak of brand direction pre-close is a material reputational risk | T-24 | 2/6 | 2/20 | Not Started | 0% |  |  | Medium | Marketing, Legal
COM-043 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Media Relations Manager | Prepare CEO media briefing materials and conduct mock interviews for Day 1 press activity | Minimum two full mock interview sessions required before Day 1; use the most aggressive questions from the media Q&A — an unprepared CEO interview on Day 1 can define the narrative for months | T-24 | 2/6 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | An unprepared CEO or CFO in a Day 1 media interview can define the integration narrative negatively for months; at least two full mock interview sessions using the most adversarial anticipated questions must be completed before Day 1 — if executive schedules prevent rehearsal time, escalate to the executive sponsor immediately | High | Legal, C-Level Executives
COM-044 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Develop government and community relations talking points and outreach materials | Focus on job retention, community investment, and economic impact; government and community stakeholders are most concerned about what changes — lead with continuity | T-24 | 2/6 | 2/20 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Legal, Government Affairs
COM-045 | Communications | Comms Infrastructure Ready | Pre-Close (Day 1 Readiness) | Digital Communications Manager | Establish social media monitoring and community management protocol for integration period | Protocol must include escalation paths for hostile or inaccurate social content; assign a social media responder for Day 1 who is empowered to post approved responses without waiting for approval cycles | T-18 | 2/12 | 2/20 | Not Started | 0% |  |  | Low | IT
COM-046 | Communications | Regulatory Approvals Obtained | Pre-Close (Day 1 Readiness) | Communications Lead | Coordinate communications with Legal to regulatory bodies | Legal leads all regulatory filings; Communications Lead supports with plain-language summaries and any required public notices — no communication to regulators without Legal review | T-16 | 2/14 | 2/27 | Not Started | 0% | CP – Close | A missed statutory notification deadline cannot be retroactively cured with a late filing — some jurisdictions impose automatic penalties for each day of non-compliance, and in regulated industries, a missed notification can trigger a temporary injunction on combined-entity operations; this is the one communications task where 'we'll catch up' is not available as a recovery option | High | Legal, Government Affairs
COM-047 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Media Relations Manager | Develop media strategy and spokesperson briefing materials — media list, press kit, and interview prep | Designate a single spokesperson for all media inquiries; all other executives and staff must be briefed to redirect press calls — rogue spokesperson incidents are difficult to contain and damage credibility | T-15 | 2/15 | 2/25 | Not Started | 0% | CP – Day 1 Readiness | In a contested media narrative — where reporters are asking about job cuts, pricing changes, or leadership uncertainty — the second executive who speaks on the record will be compared to the first by journalists who are specifically looking for inconsistency; two inconsistent statements from the same company on Day 1 become the headline, and no correction issued later will receive the same coverage as the original inconsistency | High | Legal, C-Level Executives
COM-048 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Media Relations Manager | Draft Day 1 press release — transaction rationale, combined entity overview, executive quotes, and deal terms | Press release must be cleared by Legal, IR, and the CEO before it is loaded into the wire service; embargo instructions must be sent to the wire service in writing — verbal embargoes are not enforceable | T-14 | 2/16 | 2/23 | Not Started | 0% | CP – Day 1 Readiness | A press release loaded to the wire service before it has final CFO sign-off — which happens when the review process has multiple parallel approvers rather than a sequential gate — cannot be recalled after distribution; wire services do not unpublish, and a retracted or corrected press release on Day 1 signals chaos to every journalist, investor, and employee who sees the correction | High | Legal, Finance, IR, C-Level Executives
COM-049 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Digital Communications Manager | Stage and QA all Day 1 website content updates — homepage, about page, leadership team, and newsroom | Content freeze 48 hours before Day 1; IT must confirm the publish workflow has been tested end-to-end — a failed website update on Day 1 is front-page news in the trade press | T-12 | 2/18 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | A broken or incomplete website on Day 1 — missing leadership pages, incorrect company description, broken newsroom links — is immediately visible to customers, investors, and media and signals operational dysfunction; all content must be staged and QA'd in a test environment, with IT confirming publish workflow at least 48 hours before the content freeze deadline | High | IT, Legal
COM-050 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Digital Communications Manager | Prepare Day 1 social media posts — LinkedIn, X/Twitter, Facebook, Instagram for combined entity | All posts must be pre-approved by Legal and the executive sponsor; social media is the fastest channel for misinformation to spread — no spontaneous posting on Day 1 by any company account | T-10 | 2/20 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Marketing, Legal
COM-051 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Conduct Day 1 communications dry runs — test all publish workflows, spokesperson readiness, and timing sequence | Full dress rehearsal including digital publish, press release wire, and internal blast; run at least two weeks before Day 1 — any technical failure discovered in the dry run must be resolved before the real sequence | T-10 | 2/20 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Every technical failure that is discovered during the dry run costs hours of advance preparation to fix; every technical failure discovered on Day 1 costs the same hours during the highest-stakes window of the integration, when the Communications Lead's attention cannot be on system troubleshooting — it must be on message management | High | IT, Legal
COM-052 | Compliance & Regulatory | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Integration Manager | Conduct final legal and compliance review of all Day 1 communications assets — press release, employee letter, website, social | No asset goes live without Legal sign-off; track version control carefully — Legal must review the final version of every asset, not an earlier draft | T-10 | 2/20 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Version control failures in Day 1 communications are more common than technical failures — someone makes a last-minute change to the employee letter after Legal has signed off, and the published version is different from the approved version; the risk is not the change itself but that the company published a legally unreviewed document at the moment of maximum scrutiny | High | Legal
COM-053 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Confirm Day 1 publish sequencing: regulatory filing → investor comms → employee announcement → press release → social | Sequence confirmed with Legal: regulatory filing first, then investor comms, then employee announcement, then press release, then social — any change to the sequence requires Legal and the CFO to sign off | T-7 | 2/23 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Publishing investor or employee communications before the regulatory filing is complete constitutes selective disclosure and creates securities law risk; the sequence is legally mandated, not a matter of preference — any proposed change to the publish sequence must be approved by Legal and IR before Day 1 | High | Legal, IR
COM-054 | Governance & Planning | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Brief all communications team members on Day 1 roles, responsibilities, and on-call contacts | Distribute the Day 1 war room contact list and hour-by-hour run-of-show to every team member; Communications Lead must be reachable from 6 AM on Day 1 | T-7 | 2/23 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | HR, IMO
COM-055 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Integration Manager | Distribute M&A Employee Communication Guide to Managers to prepare them for Day 1 | Distribute at least 24 hours before Day 1 all-employee announcement; managers who receive the guide on the same day they need to use it will not be prepared — inadequate manager preparation is the top employee comms failure mode | T-4 | 2/26 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | The Employee Communication Guide is only valuable if managers have time to read it, internalize it, and prepare for the questions their teams will ask; a guide that arrives in a manager's inbox the same morning as the all-employee announcement is not a preparation tool — it is a document that confirms the manager was not given more information than their reports, which is itself a message about how the company regards its managers | High | HR
COM-056 | Communications | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Media Relations Manager | Confirm media wire service is loaded, tested, and ready to distribute press release on Day 1 signal | Wire distribution must be confirmed in writing with the service provider; confirm the embargo lift timing matches the investor notification sequence to the minute | T-3 | 2/27 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | IT, Media Relations
COM-D1 | Integration Management | Day 1 Comms Readiness Confirmed | Pre-Close (Day 1 Readiness) | Communications Lead | Comm Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | Workstream lead formally certifies Day 1 readiness to the IMO; this gate must be green for every workstream before the IMO signs off on close; any open item at this gate is either resolved or escalated to the steering committee as a close-blocking risk | T-3 | 2/27 | 2/27 | Not Started | 0 | CP – Close | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | High | IMO, All Workstreams
THE DAY 1 AND DAY 100 COMMUNICATION PLANS ARE LOCATED IN THE DAY 1 AND DAY 100 SECTIONS OF MANDAPLAYBOOK.COM

## Milestones
COMMUNICATIONS M&A MILESTONES
TODAY'S DATE: T-60
Risk Level | Status | Links
High | Not Started | Communication Integration Plan
Medium | Delayed | RAID Log
Low | On Track | Tasks in Next 14 Days
| Complete | Executive Dashboard
Milestone ID | Category | Phase | Assigned To | Milestone | Timing Anchor | Finish | Status | Critical Path
MS-001 | Governance & Planning | Pre-Close | CEO / CMO | Comms Lead Appointed | T-51 | 1/10 | Not Started | CP – Close
MS-002 | Governance & Planning | Pre-Close | Communications Lead | Comms Charter Approved | T-42 | 1/19 | Not Started
MS-003 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Master Narrative Approved | T-34 | 1/27 | Not Started | CP – Day 1 Readiness
MS-004 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Messaging Frameworks Complete | T-28 | 2/2 | Not Started | CP – Day 1 Readiness
MS-005 | Communications | Pre-Close | Communications Integration Manager | Comms Due Diligence Complete | T-21 | 2/9 | Not Started
MS-006 | Governance & Planning | Pre-Close | Communications Lead | Comms Integration Governance Established | T-36 | 1/25 | Not Started
MS-007 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Comms Infrastructure Ready | T-10 | 2/20 | Not Started | CP – Close
MS-008 | Communications | Pre-Close | Brand & Creative Director | Brand Strategy Determined | T-10 | 2/20 | Not Started | CP – Day 1 Readiness
MS-009 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Day 1 Comms Readiness Confirmed | T-3 | 2/27 | Not Started | CP – Day 1 Readiness
MS-010 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Employee Comms Guide Approved | T-3 | 2/27 | Not Started | CP – Day 1 Readiness
MS-011 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Customer Comms Guide Approved | T-3 | 2/27 | Not Started | CP – Day 1 Readiness
MS-012 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Regulatory Approvals Obtained | T-3 | 2/27 | Not Started | CP – Close
MS-013 | Communications | Day 1 / Week 1 | Communications Lead | Day 1 / Week 1 Comms Integration Complete | T+7 | 3/9 | Not Started

## RAID Log
COMMUNICATIONS M&A RAID LOG (RAID = Risks, Assumptions, Issues, Dependencies)
TODAY'S DATE: T-60
RAID Type | Status | Links
Risk | Open | Communication Integration Plan
Issue | Closed | Milestones
Dependency | Active | Executive Dashboard
Assumption | Validated | Tasks in Next 14 Days
RAID Type | RAID ID | Related Task ID | Milestone | Owner | Task Description | Issues/Blockers | Status | Mitigation/Action | Timing Anchor | Finish
Assumption | RAID-001 | COM-002 | Comms Integration Governance Established | Communications Integration Manager | Integration planning begins 2 months prior to close | If the Communications workstream starts later than T-60, the master narrative, messaging frameworks, audience-specific guides, and Day 1 content calendar all compress into a shorter window — a Communications workstream that starts at T-30 will produce Day 1 materials that have not been sufficiently reviewed, tested, or rehearsed, significantly increasing the risk of a failed Day 1 announcement | Active | Communications Lead to confirm integration kickoff is no later than T-60 at the Steering Committee kickoff; if delayed beyond T-50, immediately re-prioritize the pre-close task list and brief the IMO Lead on which Day 1 communications deliverables are at risk | T-60 | 1/2
Assumption | RAID-002 | COM-001 | Comms Lead Appointed | Communications Lead | Communications Lead will be named, capacity-confirmed, and available by T-50 | A Communications workstream without a named lead by T-50 will miss the IMO kickoff, be unable to develop the master narrative and messaging frameworks on schedule, and arrive at Day 1 without pre-approved content — the Communications workstream has zero tolerance for leadership gaps because every Day 1 deliverable requires the Lead's approval before it can be published | Active | CEO/CMO to confirm Communications Lead appointment at the Steering Committee kickoff; if not filled by T-55, escalate to Executive Sponsor immediately; confirm backfill for BAU communications responsibilities before announcing the appointment | T-54 | 1/7
Dependency | RAID-003 | COM-001 | Comms Lead Appointed | CEO / CMO | Identify and onboard Communications integration workstream lead and members of Communications integration team | Every pre-close communications task — embargo protocols, agency alignment, master narrative, regulatory notifications — requires someone with authority to make decisions and approve content; without a named lead, each of those tasks either stalls or is decided by committee with no accountability, and committees do not move at the speed integration communications requires | Open | Escalate Comms Lead appointment to CEO and CMO immediately; role must be named and capacity confirmed before integration kickoff — a Comms Lead without dedicated capacity is the single biggest predictor of Day 1 communications failure; if filled internally, secure backfill for BAU responsibilities before the integration begins | T-51 | 1/10
Risk | RAID-004 | COM-002 | Comms Integration Governance Established | Communications Integration Manager | Review data privacy and confidentiality protocols for pre-close sharing | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | Open | Issue a written clean team and embargo protocol to all communications team members before any pre-close data sharing begins; Legal to specify exactly what information can be shared, with whom, and under what conditions; prohibit any pre-announcement communications activity — no agency briefings, no messaging development that requires sharing deal terms — until the clean team protocol is signed by each team member | T-49 | 1/12
Assumption | RAID-005 | COM-011 | Comms Infrastructure Ready | Communications Integration Manager | All Day 1 communications channels — website, intranet, social media accounts, email distribution lists, and wire service — will be accessible and operational for the combined entity on close day | A channel that is inaccessible or misconfigured on Day 1 can delay or prevent the publication of time-sensitive communications — if the wire service is not loaded and tested before close, the press release cannot go out on time; if the intranet site is not live, employees have no single source of truth on Day 1; each failed channel creates a gap that competitors and media will fill with speculation | Active | Communications Integration Manager to confirm access credentials, publishing rights, and operational status for every Day 1 channel at least 72 hours before close; conduct a full channel test as part of the Day 1 dry run at T-5; build a manual fallback plan for each channel in case of technical failure on Day 1 | T-49 | 1/13
Risk | RAID-006 | COM-011 | Comms Infrastructure Ready | Communications Lead | Establish communications approval workflow | A pre-close leak of deal information by a communications team member — internal or agency — triggers legal, regulatory, and reputational consequences; embargo protocol must be distributed in writing to all agency partners and internal staff, and compliance confirmed before any deal-related content is created | Open | Establish the approval workflow and embargo protocol before any integration communications are drafted; a single unauthorized disclosure through a wrong distribution list or an agency receiving pre-close messaging can break the embargo and trigger regulatory consequences | T-42 | 1/19
Risk | RAID-007 | COM-009 | Comms Due Diligence Complete | Communications Integration Manager | Map all active communications agency relationships, contracts, and change-of-control clauses | An agency that holds exclusive rights to a brand campaign or crisis management relationship and discovers at close that their contract was transferred without consent can withdraw services on Day 1 — the day when Communications needs them most; the risk is not a legal fee, it is losing a specialized partner in the middle of the most demanding communications moment of the integration | Open | Require target management to provide a complete agency roster with contract terms, notice periods, change-of-control provisions, and annual spend before close; map every active campaign and content commitment with a named owner and go-forward decision (keep, transition, or terminate); identify any exclusive agency relationship that could prevent the combined entity from using its preferred agency post-close | T-35 | 1/26
Risk | RAID-008 | COM-013 | Master Narrative Approved | Communications Lead | Develop master integration narrative and core messages aligned with deal rationale and value drivers | The master narrative is not just a document — it is the approval gate for every other content piece in the integration; a press release, employee letter, or customer guide that goes out before the narrative is approved will carry messaging that contradicts the CEO's talking points, and contradictions discovered by journalists, employees, or customers on Day 1 become the story instead of the story you intended to tell | Open | Route the master integration narrative through General Counsel, CHRO, and CEO for approval before any workstream communications are drafted from it; a narrative approved at the workstream level that contradicts CEO messaging will generate confusion and credibility loss when inconsistencies surface; conduct a narrative alignment session with all workstream leads before Day 1 | T-34 | 1/27
Assumption | RAID-009 | COM-013 | Master Narrative Approved | Communications Lead | The deal rationale, master narrative, and key messages will be approved by the CEO and General Counsel before any audience-specific communications are drafted from them | Communications built on an unapproved narrative will need to be rewritten when the CEO or Legal review the Day 1 content — rewriting approved customer letters, media statements, and employee announcements in the final week before close is the highest-risk scenario in the Communications workstream; any message that contradicts the CEO's approved narrative creates credibility loss that is difficult to recover from in the first 100 days | Active | Communications Lead to obtain written CEO and General Counsel sign-off on the master narrative before any audience-specific content is drafted; schedule the narrative approval as a fixed milestone at T-34 with no exceptions; brief all workstream leads who are developing communications on the approved narrative at the next IMO status meeting after approval | T-34 | 1/27
Risk | RAID-010 | COM-019 | Messaging Frameworks Complete | Communications Lead | Build audience-specific messaging frameworks for: employees, customers, media, investors, and regulators | Audience-specific messaging that is developed in parallel with the master narrative — rather than derived from it — will produce inconsistent messages; the employee version of the story, the customer version, and the investor version will have different characterizations of the same facts, and those inconsistencies will be discovered by the employees, customers, and investors who talk to each other | Open | Complete audience-specific messaging frameworks before any Day 1 communications are drafted — every employee, customer, investor, and media communication must be traceable to an approved message; conflicting messages to different audiences on Day 1 | T-28 | 2/2
Risk | RAID-011 | COM-022 | Comms Due Diligence Complete | Brand & Creative Director | Coordinate with Legal to conduct trademark and legal review of combined entity brand name and logo options | A brand name that reaches the design phase without IP clearance in a key jurisdiction — particularly in the EU, China, or markets with aggressive trademark enforcement — may need to be changed after months of design investment; the cost is not the legal filing fee but the creative write-off, the agency rework, and the delay to a Day 1 brand transition that was already on the critical path | Open | Have Legal complete trademark and brand name clearance in every jurisdiction where the combined entity operates before announcing any combined entity name or brand; a trademark conflict discovered after announcement forces an embarrassing reversal and can result in injunction, financial penalties, and rebranding costs that far exceed pre-close clearance costs | T-21 | 2/9
Risk | RAID-012 | COM-017 | Brand Strategy Determined | Brand & Creative Director | Develop brand integration strategy — define combined entity naming, brand architecture, and transition timeline | Every Day 1 creative asset — website, signage, social profiles, press materials — is built on an assumption about the brand architecture; if the decision changes after design work has begun, every asset must be rebuilt from scratch; the agencies and design teams that do this work have lead times measured in weeks, not days, and there is no fast-follow option on Day 1 brand execution | Open | Present the brand integration strategy to CEO and CMO at least 14 days before close for approval; brand decisions that are reversed post-announcement — rebranding from one name back to another, changing color palettes mid-rollout — create customer and employee confusion and signal organizational dysfunction; lock all brand decisions before any Day 1 materials are produced | T-14 | 2/16
Dependency | RAID-013 | COM-018 | Day 1 Comms Readiness Confirmed | Communications Lead | Coordinate with IR and Finance team to develop investor Day 1 communication — deal rationale and financial impact | Investor communications must be sequenced correctly relative to regulatory filings; any investor-facing content that contains material non-public information before the 8-K is filed creates securities law exposure — IR and Legal must confirm the exact publish sequence and approve all language before Day 1 | Open | Complete the investor Day 1 communications package in coordination with IR and Finance; confirm with IR that all regulatory filings and quiet period obligations are satisfied before any investor communication is released; a communication that pre-empts a required regulatory filing is a securities law violation | T-14 | 2/16
Dependency | RAID-014 | COM-038 | Day 1 Comms Readiness Confirmed | Communications Lead | Develop in concert with HR team Day 1 announcement cascade plan — who communicates what, to whom, and in what order | Cascade sequence failure — employees hearing deal news from media, social, or unofficial channels before their direct manager — is the most damaging and most preventable Day 1 communications failure; cascade plan must confirm manager briefing windows, distribution timing, and escalation contacts before Day 1 dry run | Open | Finalize the Day 1 announcement cascade plan — who communicates to whom, in what order, with what message — before any Day 1 communications assets are produced; the cascade must be triggered in the right sequence: regulatory filings → investor communications → manager briefings → all-employee announcement → customer communications → media; any out-of-sequence communication creates regulatory risk or credibility loss | T-14 | 2/16
Risk | RAID-015 | COM-030 | Day 1 Comms Readiness Confirmed | Digital Communications Manager | Develop Day 1 digital communications strategy — website, social channels, email, and intranet update schedule | Website and social channel updates must go live within minutes of the press release; any technical failure — broken links, missing content, staged assets not published — is immediately visible to customers, media, and investors; IT must confirm the publish workflow is tested end-to-end at least two weeks before Day 1 | Open | Complete all Day 1 digital communications assets — website updates, social media posts, email communications — and stage them in the publishing platforms before close; do not draft digital content at the last minute; conduct a full QA review of every asset at least 48 hours before close and confirm that platform access, credentials, and staging environments are operational | T-10 | 2/20
Risk | RAID-016 | COM-031 | Day 1 Comms Readiness Confirmed | Media Relations Manager | Develop reactive media holding statements for top 10 sensitive deal topics | Media inquiries on deal-sensitive topics (layoffs, pricing, leadership, brand changes) will arrive on Day 1 without warning; holding statements must be pre-approved by Legal and the executive sponsor and deployable by the PR Manager within 30 minutes — waiting for approval on Day 1 under media pressure is not an acceptable protocol | Open | Develop and pre-approve holding statements for the top 10 sensitive deal questions — leadership changes, headcount, customer commitments, product roadmap, financial performance — before close; a question that arrives on Day 1 without a pre-approved holding statement will either go unanswered (damaging credibility) or receive an improvised response (creating legal and reputational risk) | T-10 | 2/20
Risk | RAID-017 | COM-048 | Day 1 Comms Readiness Confirmed | Media Relations Manager | Draft Day 1 press release — transaction rationale, combined entity overview, executive quotes, and deal terms | A press release loaded to the wire service before it has final CFO sign-off — which happens when the review process has multiple parallel approvers rather than a sequential gate — cannot be recalled after distribution; wire services do not unpublish, and a retracted or corrected press release on Day 1 signals chaos to every journalist, investor, and employee who sees the correction | Open | Complete the Day 1 press release and obtain General Counsel, CEO, and IRO sign-off at least 5 days before close; the press release triggers the investor announcement sequence — any last-minute changes create a cascade of review cycles that can delay the entire Day 1 sequence; pre-position the final approved release with the wire service at least 24 hours before the scheduled release time | T-7 | 2/23
Risk | RAID-018 | COM-032 | Day 1 Comms Readiness Confirmed | Communications Lead | Plan and script Day 1 all-hands town hall — format, speakers, agenda, Q&A logistics, and run-of-show | Employees who do not hear directly from leadership within 48 hours of Day 1 will fill the silence with speculation; in a unionized environment or in jurisdictions with Works Councils, a town hall that is delayed can trigger a formal request for information from employee representatives — and a formal request means Legal is now involved in a communications timeline that should have been managed proactively | Open | Script and rehearse the Day 1 all-hands town hall with CEO and CHRO at least 5 days before close; record a backup video in case of technical failure or schedule conflict; prepare written Q&A responses for the 30 most likely questions; brief all town hall speakers individually before the session — an improvised answer to a sensitive question in a town hall setting is a significant communications risk | T-5 | 2/25
Dependency | RAID-019 | COM-033 | Day 1 Comms Readiness Confirmed | Communications Lead | Develop with HR, all-employee announcement — leadership letter, and integration overview | An employee who reads about the acquisition on their phone before arriving at their desk is already processing the news through their personal filter rather than through the company's narrative; once that frame is set, the official communication that arrives later is received as a reaction, not a revelation — and an employee in reaction mode is harder to retain than an employee who felt informed | Open | Route the all-employee announcement through HR, Legal, and CEO for approval at least 5 days before close; any implied promises about job security, compensation, or benefits must be explicitly reviewed by Legal and HR before the announcement is finalized; brief CHRO and HRBP leads on the announcement content before it is distributed so managers can anticipate employee questions | T-5 | 2/25
Risk | RAID-020 | COM-047 | Day 1 Comms Readiness Confirmed | Media Relations Manager | Develop media strategy and spokesperson briefing materials — media list, press kit, and interview prep | In a contested media narrative — where reporters are asking about job cuts, pricing changes, or leadership uncertainty — the second executive who speaks on the record will be compared to the first by journalists who are specifically looking for inconsistency; two inconsistent statements from the same company on Day 1 become the headline, and no correction issued later will receive the same coverage as the original inconsistency | Open | Complete media spokesperson identification, training, and briefing at least one week before close; designate a primary and backup spokesperson for each audience segment (financial media, trade media, local media); do not allow any spokesperson to give a media interview without a pre-approved talking points document; brief CEO and CFO on the media strategy before Day 1 | T-5 | 2/25
Dependency | RAID-021 | COM-034 | Employee Comms Guide Approved | Communications Lead | Develop with HR the M&A Employee Communication Guide (includes talking points, guidance for team conversations, Q&A / FAQ covering anticipated questions) | A manager who is handed the Employee Communication Guide the same morning as the all-employee announcement cannot prepare thoughtful responses to their team's questions — they are reading the guide in real time alongside the people they are supposed to lead; the first 30 minutes of employee reaction is the highest-stakes window in the integration, and it is the window where an unprepared manager does the most damage | Open | Route the M&A Employee Communication Guide through HR, Legal, and Communications Lead for approval at least 7 days before close; the guide must include talking points for the 20 most sensitive questions employees are likely to ask; conduct a manager briefing session to walk through the guide before it is distributed — managers who receive the guide without context will not use it effectively | T-3 | 2/27
Dependency | RAID-022 | COM-037 | Customer Comms Guide Approved | Communications Lead | Develop with Sales team, the M&A Customer Communication Guide (includes talking points, guidance for team conversations, and Q&A / FAQ covering anticipated questions) | A customer communication strategy developed without the master narrative in hand will produce messaging that contradicts what the CEO says publicly on Day 1; a customer who receives a communication from their account manager that tells a different story than the press release has received two versions of the same event from the same company, and the discrepancy becomes the story | Open | Route the M&A Customer Communication Guide through Sales leadership, Legal, and Communications Lead for approval at least 7 days before close; the guide must address the 10 questions customers are most likely to ask about product continuity, pricing, support, and account management; brief Sales leadership on the guide before customer communications go out | T-3 | 2/27
Risk | RAID-023 | COM-043 | Day 1 Comms Readiness Confirmed | Media Relations Manager | Prepare CEO media briefing materials and conduct mock interviews for Day 1 press activity | An unprepared CEO or CFO in a Day 1 media interview can define the integration narrative negatively for months; at least two full mock interview sessions using the most adversarial anticipated questions must be completed before Day 1 — if executive schedules prevent rehearsal time, escalate to the executive sponsor immediately | Open | Conduct at least two full mock interviews with the CEO at least 5 days before close — one for financial media and one for trade media; record the sessions and review responses for accuracy, consistency with approved messaging, and inadvertent disclosure risk; brief Legal on any question areas where the CEO's natural response could conflict with disclosure obligations | T-3 | 2/27
Risk | RAID-024 | COM-046 | Regulatory Approvals Obtained | Communications Lead | Coordinate communications with Legal to regulatory bodies | A missed statutory notification deadline cannot be retroactively cured with a late filing — some jurisdictions impose automatic penalties for each day of non-compliance, and in regulated industries, a missed notification can trigger a temporary injunction on combined-entity operations; this is the one communications task where 'we'll catch up' is not available as a recovery option | Open | Identify every regulatory body that requires proactive communication about the transaction and assign a named owner and deadline for each; coordinate with Legal on the required content and timing for each regulatory communication; do not send any regulatory communication without Legal review and sign-off | T-3 | 2/27
Risk | RAID-025 | COM-049 | Day 1 Comms Readiness Confirmed | Digital Communications Manager | Stage and QA all Day 1 website content updates — homepage, about page, leadership team, and newsroom | A broken or incomplete website on Day 1 — missing leadership pages, incorrect company description, broken newsroom links — is immediately visible to customers, investors, and media and signals operational dysfunction; all content must be staged and QA'd in a test environment, with IT confirming publish workflow at least 48 hours before the content freeze deadline | Open | Complete all Day 1 website content — homepage, about us, leadership page, product and solutions pages, investor relations page — and stage it for simultaneous publication at close; conduct a full QA review across all pages at least 48 hours before close; confirm that IT has the publishing access and credentials needed to push all updates simultaneously on Day 1 | T-3 | 2/27
Risk | RAID-026 | COM-051 | Day 1 Comms Readiness Confirmed | Communications Lead | Conduct Day 1 communications dry runs — test all publish workflows, spokesperson readiness, and timing sequence | Every technical failure that is discovered during the dry run costs hours of advance preparation to fix; every technical failure discovered on Day 1 costs the same hours during the highest-stakes window of the integration, when the Communications Lead's attention cannot be on system troubleshooting — it must be on message management | Open | Conduct the Day 1 dry run with the full communications team at least 5 days before close; test every asset, every platform, every publish workflow, and every escalation path under simulated Day 1 conditions; document every failure point discovered in the dry run and resolve it before close | T-3 | 2/27
Risk | RAID-027 | COM-052 | Day 1 Comms Readiness Confirmed | Communications Integration Manager | Conduct final legal and compliance review of all Day 1 communications assets — press release, employee letter, website, social | Version control failures in Day 1 communications are more common than technical failures — someone makes a last-minute change to the employee letter after Legal has signed off, and the published version is different from the approved version; the risk is not the change itself but that the company published a legally unreviewed document at the moment of maximum scrutiny | Open | Complete the final legal and compliance review of all Day 1 communications at least 3 days before close; provide Legal with the complete Day 1 communications package — press release, employee announcement, investor letter, social media posts, website content — as a single submission; a legal review that happens communication-by-communication will miss conflicts between messages | T-3 | 2/27
Dependency | RAID-028 | COM-053 | Day 1 Comms Readiness Confirmed | Communications Lead | Confirm Day 1 publish sequencing: regulatory filing → investor comms → employee announcement → press release → social | Publishing investor or employee communications before the regulatory filing is complete constitutes selective disclosure and creates securities law risk; the sequence is legally mandated, not a matter of preference — any proposed change to the publish sequence must be approved by Legal and IR before Day 1 | Open | Lock the Day 1 publish sequencing at least 5 days before close and distribute it to every team member involved in Day 1 execution; any deviation from the approved sequence on Day 1 must be escalated to the Communications Lead immediately | T-3 | 2/27
Dependency | RAID-029 | COM-055 | Day 1 Comms Readiness Confirmed | Communications Integration Manager | Distribute M&A Employee Communication Guide to Managers to prepare them for Day 1 | The Employee Communication Guide is only valuable if managers have time to read it, internalize it, and prepare for the questions their teams will ask; a guide that arrives in a manager's inbox the same morning as the all-employee announcement is not a preparation tool — it is a document that confirms the manager was not given more information than their reports, which is itself a message about how the company regards its managers | Open | Confirm that the M&A Employee Communication Guide has been distributed to every people manager at least 48 hours before the all-employee announcement; require managers to confirm receipt; brief managers on how to use the guide | T-3 | 2/27
Risk | RAID-030 | COM-D1 | Day 1 Comms Readiness Confirmed | Communications Lead | Comm Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | Open | Conduct the Day 1 Communications Readiness Gate with Communications Lead and IMO 48 hours before close; every staged asset must be confirmed operational — platform access, publish credentials, wire service connection, manager distribution lists; any gate item rated Red is a close blocker; document every gate decision with sign-offs and a named owner for every open item | T-3 | 2/27
Assumption | RAID-031 | COM-D1 | Day 1 Comms Readiness Confirmed | Communications Lead | Close will occur on 3/2/2026 as scheduled with no material delay | If close is delayed, all staged Day 1 communications assets — the all-employee announcement, press release, customer letter, website updates, and social media posts — must be rescheduled and re-approved; any delay beyond 2 weeks also risks embargo breach as staged content is held longer than intended and the deal news leaks before the combined entity is ready to communicate | Active | Communications Lead to confirm close timeline with IMO and Legal at T-15; any slip of more than 5 days triggers immediate replanning of all Day 1 comms assets, re-approval of staged content, and a briefing to the CEO within 24 hours on the updated sequencing plan | T-3 | 2/27
Risk | RAID-032 | COM-058 | Day 1 / Week 1 Comms Integration Complete | Communications Lead | Execute Day 1 communications sequence — trigger all staged assets per approved publish timeline | The Day 1 publish sequence is a timed operation with legal consequences for misordering; a command structure that relies on verbal confirmation rather than a written go/no-go protocol will fail when two people simultaneously believe they have authority to approve — and on Day 1, everyone believes they have authority, because everyone is under pressure | Open | Build a full Day 1 run-of-show timeline with named owners for every action, minute-by-minute from 6:00 AM to 6:00 PM on close day; confirm that every team member knows their role before Day 1; build a 15-minute buffer between each publication trigger to allow for real-time adjustments; designate a war room commander with authority to make real-time sequencing decisions | Day 1 (Close) | 3/2
Risk | RAID-033 | COM-059 | Day 1 / Week 1 Comms Integration Complete | Communications Integration Manager | Monitor Day 1 communications reception — employee sentiment, media coverage, social reaction, and customer inquiries | Negative employee sentiment, hostile media coverage, or viral social media criticism that is not identified and addressed within 2–4 hours of Day 1 announcement can entrench into the public narrative; the monitoring protocol must be active from 6 AM and the rapid response escalation path must be confirmed before Day 1 | Open | Establish Day 1 monitoring dashboards for employee sentiment (HR channels, anonymous feedback), media coverage (tone, reach, accuracy), and social media (volume, sentiment, viral risk) before close; brief the CEO and CHRO on real-time sentiment data within 2 hours of the all-employee announcement | Day 1 (Close) | 3/2
Dependency | RAID-034 | COM-060 | Day 1 / Week 1 Comms Integration Complete | Communications Lead | Support executive team with real-time communications coaching and message discipline on Day 1 | Executives who deviate from approved messaging under Day 1 media pressure — making unscripted commitments on headcount, pricing, or brand — create legal, investor relations, and employee relations problems that Communications cannot resolve in real time; Communications Lead must be physically or virtually present with the CEO throughout Day 1 media activity | Open | Brief every executive who will be speaking or giving interviews on Day 1 individually, not as a group, to allow for tailored coaching on their specific communication style and risk areas; conduct a final briefing the evening before close to ensure messaging is fresh; designate a communications coach to be physically present or on call for each executive during Day 1 | Day 1 (Close) | 3/2
Dependency | RAID-035 | COM-057 | Day 1 / Week 1 Comms Integration Complete | Communications Lead | Coordinate with sales leadership to schedule personal outreach calls to top 20 strategic accounts on Day 1 | Strategic customers who learn about the acquisition from media or public channels before receiving a direct call from their account executive are at elevated churn risk; outreach calls for top 20 accounts must be scheduled for Day 1 AM before the press release goes live — any customer not reached by noon on Day 1 requires same-day escalation to Sales leadership | Open | Brief Sales leadership on the customer communication strategy and talking points before any customer outreach is scheduled; coordinate with Sales operations to identify the top 20 at-risk accounts for priority executive outreach | T+4 | 3/6
Risk | RAID-036 | COM-D30 | 30-Day Integration Review Complete | Communications Lead | Comm Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | If the Day 30 check reveals open tasks, unresolved blockers, or synergy owners not yet active, the integration team has 70 days to correct course — but the Day 30 review must force honest status reporting; teams that report green when yellow or red create hidden risk that surfaces at Day 100 when it is too late to recover | Open | Conduct the Day 30 Communications Review as a formal meeting with Communications Lead, IMO lead, and HR; require written RAG status from each communications workstream; present media coverage quality, employee sentiment data, and brand transition progress; any Red item requires a named owner and resolution deadline; present synergy tracking at the Day 30 check | T+32 | 4/3
Risk | RAID-037 | COM-D100 | Day 100 Comms Integration Complete | Communications Lead | Comm Day 100 Integration Gate — confirm all integration tasks complete or formally deferred, synergy baseline locked, BAU transition signed off | A workstream that reaches Day 100 with open items must either formally complete them or accept them into BAU with a named owner and documented timeline — items that are neither closed nor formally accepted become permanent integration debt that resurfaces as operational problems without a clear owner or resolution path. | Open | Conduct the Day 100 Communications Gate as a formal milestone with Communications Lead, CEO, and IMO; require written close-out status covering brand transition completion, audience sentiment baseline, communications archives, and lessons learned documentation; any open item must be assigned to a named BAU owner with a resolution timeline before the integration team is stood down | T+100 | 6/10

## Next 14 Days
COMMUNICATIONS M&A NEXT 14 DAYS ACTIVITIES
TODAY'S DATE: T-60
Risk Level | Status | Links
High | Not Started | Communication Integration Plan
Medium | Delayed | Milestones
Low | On Track | RAID Log
| Complete | Executive Dashboard
Task ID | Category | Phase | Assigned To | Description | Risk Level | Timing Anchor | Start | Finish | Status | Critical Path
COM-001 | Governance & Planning | Pre-Close | CEO / CMO | Identify and onboard Communications integration workstream lead and members of Communications integration team | High | T-59 | 1/2 | 1/10 | Not Started | CP – Close
COM-002 | Governance & Planning | Pre-Close | Communications Integration Manager | Review data privacy and confidentiality protocols for pre-close sharing | High | T-53 | 1/8 | 1/12 | Not Started
COM-003 | Governance & Planning | Pre-Close | Communications Lead | Attend IMO Kickoff Meeting | Low | T-50 | 1/11 | 1/11 | Not Started
COM-004 | Governance & Planning | Pre-Close | Communications Integration Manager | Receive access to integration data room and document repository | Low | T-49 | 1/12 | 1/13 | Not Started
COM-005 | Governance & Planning | Pre-Close | Communications Lead | Conduct Communications team kickoff | Low | T-49 | 1/12 | 1/12 | Not Started
COM-006 | Governance & Planning | Pre-Close | Communications Lead | Develop the communications team integration charter | Low | T-49 | 1/12 | 1/19 | Not Started
COM-007 | Governance & Planning | Pre-Close | Communications Lead | Define communication success metrics and KPIs | Low | T-49 | 1/12 | 1/19 | Not Started
COM-008 | Communications | Pre-Close | Communications Lead | Audit both companies' communications functions — headcount, channels, agencies, budgets, and tech stack | Medium | T-49 | 1/12 | 1/26 | Not Started
COM-009 | Communications | Pre-Close | Communications Integration Manager | Map all active communications agency relationships, contracts, and change-of-control clauses | High | T-49 | 1/12 | 1/26 | Not Started
COM-010 | Communications | Pre-Close | Communications Integration Manager | Inventory all active press releases, campaigns, and content commitments across both entities | Medium | T-49 | 1/12 | 1/26 | Not Started
COM-011 | Communications | Pre-Close | Communications Lead | Establish communications approval workflow | High | T-49 | 1/12 | 1/19 | Not Started | CP – Close
COM-012 | Integration Management | Pre-Close | Communications Integration Manager | Update Communications Executive Dashboard weekly | Low | T-49 | 1/12 | 6/10 | Not Started
COM-013 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Develop master integration narrative and core messages aligned with deal rationale and value drivers | High | T-49 | 1/12 | 1/27 | Not Started | CP – Day 1 Readiness
COM-014 | Governance & Planning | Pre-Close | Communications Lead | Define communications integration guiding principles, voice, and tone framework for combined entity | Medium | T-47 | 1/14 | 1/25 | Not Started
COM-015 | Governance & Planning | Pre-Close | Communications Integration Manager | Build communications RACI matrix — who approves, drafts, and reviews messages | Low | T-47 | 1/14 | 1/18 | Not Started
COM-016 | Communications | Pre-Close | Communications Lead | Identify key government and community stakeholders requiring proactive outreach on deal announcement | Low | T-46 | 1/15 | 1/20 | Not Started
COM-017 | Communications | Pre-Close | Brand & Creative Director | Develop brand integration strategy — define combined entity naming, brand architecture, and transition timeline | High | T-45 | 1/16 | 2/16 | Not Started
COM-018 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Coordinate with IR and Finance team to develop investor Day 1 communication — deal rationale and financial impact | High | T-45 | 1/16 | 2/16 | Not Started | CP – Day 1 Readiness
COM-019 | Communications | Pre-Close (Day 1 Readiness) | Communications Lead | Build audience-specific messaging frameworks for: employees, customers, media, investors, and regulators | High | T-45 | 1/16 | 2/2 | Not Started | CP – Day 1 Readiness

## Executive Dashboard
HR M&A MILESTONES REPORT | COMMUNICATIONS M&A INTEGRATION EXECUTIVE DASHBOARD
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
TASKS
|  |  | TOTAL TASKS |  | NOT STARTED |  | DELAYED |  | ON TRACK | COMPLETE
|  |  | 73 |  | 73 |  | 0 |  | 0 | 0
| MILESTONE STATUS |  |  | PROGRESS BY PHASE TASKS DONE/TASKS |  |  |  | RAID LOG SUMMARY |  | SYNERGIES
| Not Started | 15 |  | Pre-Close |  | 0/73 |  | Open Risks | 32 | Targeted Synergies | $75K
| Delayed | 0 | [5 empty] | Open Items | 32 | Realized Synergies | $0K
| On Track | 0 | [5 empty] | Issues | 0 | Cost to Achieve Budget | $20K
| Complete | 0 | [5 empty] | Dependencies | 10 | Actual CTA | $0K
| CRITICAL PATH MILESTONES | [6 empty] | NEXT 14 DAYS |  | DAY 1 | TASKS DONE/TASKS
|  |  |  | Phase | Target Date | Status |  | Total Tasks | 19 | Day 1 Readiness | 0/30
| Comms Lead Appointed |  |  | Pre-Close | 1/10 | Not Started |  | On Critical Path | 8
| Comms Integration Governance Established |  |  | Pre-Close | 1/25 | Not Started
| Day 1 Comms Readiness Confirmed |  |  | Pre-Close | 2/27 | Not Started
LINKS
[8 empty] | Communication Integration Plan |  | Milestones
[8 empty] | RAID Log |  | Tasks in Next 14 Days