## Slide 1
COMMUNICATIONS
M&A INTEGRATION
KICKOFF MEETING
100-Day Advisors
100-DAY POST-MERGER INTEGRATION PLAYBOOK

## Slide 2
VALUE DRIVERS
Why Communications is a strategic workstream — not a support function
© Copyright 100-Day Advisors | Communications Integration Kickoff
1
Narrative Control
Every stakeholder — employees, customers, media, investors — forms an impression of this deal in the first 48 hours. A strong, coordinated narrative set on Day 1 is far easier to maintain than a fractured one to repair.
Employee Retention
Uncertainty drives attrition. Employees who receive clear, consistent, and timely communications from leadership stay engaged. Those who hear the deal narrative first from external sources lose trust — and trust is slow to rebuild.
Customer Confidence
Customers are retention risks the moment a deal is announced. Proactive outreach from their account contact — before the press release — signals continuity and preserves the relationship through the transition.
Regulatory & Investor Credibility
The sequencing and accuracy of investor and regulatory communications is a legal obligation. A misstatement in an investor letter or a gap in regulatory notice carries material securities law exposure.
Brand & Reputation Protection
The combined entity's market position is built on two brands that may carry different equity. A deliberate, legally cleared brand transition plan protects both while the combined narrative takes hold.

## Slide 3
SUCCESS METRICS
How we measure communications effectiveness — tracked weekly and reported to IMO
© Copyright 100-Day Advisors | Communications Integration Kickoff
2
Reach
100% of employees receive each integration communication through their primary channel
Top 20 strategic accounts personally contacted before press release goes live
All five audience types covered: employees, customers, media, investors, regulators
Comprehension
Day 30 pulse survey: employees can articulate the deal rationale in their own words
Manager briefings confirm guides received and team conversations completed
Integration intranet FAQ updated weekly; top questions addressed within 48 hours
Sentiment
Media sentiment tracked daily; no sustained negative narrative without rapid response
Employee Net Promoter Score at Day 30, 60, and 100 — no sustained decline
Customer inquiries resolved within 48 hours; no deal-related churn in first 30 days
Timeliness
Every communications asset published before employees hear from external sources
Day 1 publish sequence executes without error per rehearsed minute-by-minute plan
No inaccurate trade media coverage unaddressed more than 5 business days

## Slide 4
EXTENT OF INTEGRATION
What is being unified, what is being transitioned, and what stays separate until BAU
© Copyright 100-Day Advisors | Communications Integration Kickoff
3
FULLY INTEGRATE
Master integration narrative and core message platform
Communications approval workflow and embargo protocol
RACI matrix across all five audience types
Media monitoring and sentiment reporting
Internal communications calendar and cadence
Executive talking points and spokesperson protocols
PHASED / TRANSITIONAL
Brand architecture — decision Day 1; execution phased through Day 100
Agency consolidation — conflicts cleared by Day 45; rationalization by Day 60
Social media handle consolidation — Day 1 digital, physical assets phased
Integration intranet site — launched Day 1, built out through Day 60
Biweekly manager briefing cadence — live from Week 1 through Day 100
Journalist correction briefings — completed by Day 60
RETIRE / ARCHIVE
Legacy brand assets — retired per phased transition schedule
Duplicate agency relationships in same category
Separate social handles per approved consolidation plan
Legacy approval workflows — replaced by combined RACI
All integration communications archived at Day 100 per Legal hold schedule

## Slide 5
END STATES — WHAT 'INTEGRATION COMPLETE' LOOKS LIKE
Observable outcomes that signal the Communications workstream is done — by audience
© Copyright 100-Day Advisors | Communications Integration Kickoff
4
FOR SHAREHOLDERS
Combined entity narrative established in financial media; deal rationale understood
Day 100 integration success story issued; synergy and retention data anchors the coverage
All investor communications completed without securities disclosure gaps or corrections
FOR CUSTOMERS
Every customer account contacted before the press release; no deal news from external sources
Combined entity brand and service commitments communicated and confirmed
No deal-related customer churn attributable to communications failure
FOR MEDIA & REGULATORS
Inaccurate Day 1 trade coverage corrected via journalist briefings with on-record statements
Single designated spokesperson across all media inquiries through Day 100
All regulatory communications completed on Legal-approved timeline; no filing gaps
FOR EMPLOYEES
Every employee received leadership communication before hearing the news externally
Integration intranet site active with current FAQ, org chart, and workstream updates
Day 100 pulse survey shows comprehension and sentiment at or above Day 1 baseline

## Slide 6
NON-NEGOTIABLES
Communications commitments that cannot be deferred, delegated, or compromised
© Copyright 100-Day Advisors | Communications Integration Kickoff
5
Employees Hear It First
The CEO-signed employee letter reaches manager inboxes before the press release goes live — without exception. An employee who reads about the deal in the news before hearing from leadership loses trust that is slow and expensive to rebuild.
The Publish Sequence Is Locked
Regulatory filing → investor comms → employee announcement → press release → social. Any change to this order requires Legal and CFO sign-off. It cannot be modified on the fly during a live close sequence.
One Spokesperson. No Exceptions.
All media inquiries route to a single designated spokesperson. Every other executive and employee must be briefed to redirect press calls. A rogue spokesperson incident on Day 1 can define the combined entity's media narrative for months.
Master Narrative Before Any Content
No external-facing copy is written until the master integration narrative is approved by the executive sponsor and Legal. All audience-specific content must trace back to this document — without exception.
Legal Clears Every Asset
No communications asset — press release, employee letter, website update, social post — goes live without Legal sign-off on the final version. Version control must be tracked; Legal reviews the final draft, not an earlier one.
Day 1 Is Rehearsed, Not Improvised
A full-dress rehearsal — every publish workflow, every spokesperson, every timing sequence — must be completed at least two weeks before Day 1. Any technical failure found in the dry run must be resolved before the real sequence runs.

## Slide 7
GOVERNANCE MODEL
Who owns what — Communications sub-workstream leads and their responsibilities
© Copyright 100-Day Advisors | Communications Integration Kickoff
6
Communications Lead
Single accountable owner for the workstream. Commands the Day 1 publish sequence. Certifies readiness to IMO. Attends Steering Committee. Approves all audience-facing content.
Communications Integration Manager
Owns integration plan, RAID log, and weekly IMO status reporting. Manages internal communications calendar, executive dashboard, and Day 30/100 gate deliverables.
Media Relations Manager
Owns press release, media strategy, spokesperson briefing, mock interviews, holding statements, Day 30 press release, and Day 100 success story. Manages journalist correction briefings.
Brand & Creative Director
Owns brand architecture decision, trademark clearance coordination, design agency briefing, branded touchpoint inventory, and phased brand transition execution through Day 100.
Digital Communications Manager
Owns website, social channels, intranet, and email signature rollout. Manages Day 1 digital publish sequence, social monitoring protocol, and IT-pushed email signature adoption.
IMO (Integration Mgmt Office)
Cross-workstream coordination and steering committee reporting. Receives Communications status weekly. Facilitates Day 30 and Day 100 gate reviews. Escalates unresolved blockers.

## Slide 8
GUIDING PRINCIPLES
The criteria that guide every Communications integration decision
© Copyright 100-Day Advisors | Communications Integration Kickoff
7
01
Employees First, Always
Employees who understand the deal and hear it from leadership first are the best advocates to customers, media, and the market.
02
One Narrative, All Audiences
Every audience-specific message traces back to the master integration narrative. Consistency across channels prevents the contradictions that generate employee confusion.
03
Sequence Is Legal, Not Preference
The publish order — regulatory, investor, employee, press release, social — is a legal obligation, not a preference. Deviation requires Legal and CFO approval.
04
Rehearse Before You Execute
The Day 1 sequence is rehearsed end to end at least two weeks before close. Technical failures, spokesman gaps, and timing errors found in the dry run are fixed — not accepted as Day 1 risk.
05
Silence Is a Message
Every skipped newsletter, cancelled town hall, or unanswered employee question sends a signal. A consistent cadence — even when there is little new to say.
06
Correct Fast, Correct Once
Inaccurate media coverage is addressed proactively through journalist briefings with Legal-approved on-record statements — not ignored and not addressed through social media arguments.
07
Brand Changes Are Phased, Not Rushed
Day 1 brand changes are limited to what can be executed without error. Over-ambitious Day 1 transitions create customer confusion. Lower-visibility touchpoints follow a published phased schedule.
08
Archive Everything
All integration communications — press releases, employee letters, talking points, media coverage — are archived at Day 100

## Slide 9
CORE MESSAGES
What every employee and stakeholder needs to understand about this deal
© Copyright 100-Day Advisors | Communications Integration Kickoff
8
WHY THIS DEAL
This acquisition creates a combined entity with greater market reach, broader capabilities, and stronger competitive position than either company had independently.
WHAT CHANGES ON DAY 1
A CEO-signed letter is in your inbox. The combined entity's website, social channels, and intranet are live. One spokesperson handles all media inquiries. One narrative. One voice.
WHAT STAYS THE SAME
Customer relationships, service commitments, and existing contracts continue without interruption. No brand or process changes without advance communication and a clear transition plan.
HOW DECISIONS WILL BE MADE
The Communications Lead is the single accountable owner. All audience-facing content requires Communications Lead approval. Major brand or narrative decisions require CEO and executive sponsor sign-off.
WHAT WE ARE ASKING OF EMPLOYEES
Use the talking points. Do not improvise the deal narrative in customer conversations. If a journalist calls, redirect to the designated spokesperson immediately. Report customer concerns same day.
WHEN THIS WILL BE COMPLETE
The Communications integration closes at Day 100 with a formal gate review. By then, the brand transition is complete, all content is archived, and the combined entity is communicating as one organization.

## Slide 10
INTEGRATION TIMELINE
Communications milestones across three phases — Pre-Close through Day 100
© Copyright 100-Day Advisors | Communications Integration Kickoff
9
PRE-CLOSE
DAY 1 / WEEK 1
DAYS 8–100
PRE-CLOSE
Communications Lead appointed; team confirmed
Embargo protocol written and distributed to all staff and agencies
Both companies' comms functions fully audited
Master narrative and messaging frameworks approved
Brand architecture decision made; trademark clearance complete
All Day 1 assets drafted, Legal-cleared, and staged
Full Day 1 dress rehearsal completed
Day 1 Readiness Gate certified by Comms Lead to IMO
DAY 1 / WEEK 1
CEO letter in manager inboxes before press release
Top 20 accounts called before wire release
Publish sequence executed per approved plan
Website, social, and intranet go live simultaneously
Comms Lead shadows CEO for first 4 hours
Sentiment monitored hourly; escalation within 30 min
Week 1 effectiveness assessment; plan adjusted if needed
DAYS 8–100
Pulse survey data reviewed; gaps addressed
Milestone press release issued
Communications gate review with IMO
Agency consolidation complete
Brand transition on all digital assets complete
Journalist correction briefings complete
Email signature push confirmed by IT
All comms archived; lessons documented
Communications gate closed

## Slide 11
DUE DILIGENCE RULES OF ENGAGEMENT
Data sharing guidelines governing all pre-close Communications access and planning
© Copyright 100-Day Advisors | Communications Integration Kickoff
10
WHAT YOU MAY AND MAY NOT DO
All pre-close communications planning uses only information cleared through the data room — confirm scope with Legal before any draft uses non-public target information
No draft message, talking point, or press release may reference non-public target company data without Legal review and sign-off
Agency partners are subject to the same embargo rules as internal staff — brief them under NDA before any brand or creative work begins
Any message drafted pre-close that could constitute a material public statement must be reviewed by Legal and IR before it is shared internally
No proactive media or investor outreach before close without explicit Legal and CFO authorization
Social media accounts for the target company may be inventoried but not modified, merged, or retired before close
If you are unsure whether a pre-close communications action is permitted, stop and ask Legal or the Communications Lead before proceeding
CONSEQUENCES OF VIOLATIONS
Using non-public target information in a pre-close communication — even internally — can constitute gun-jumping under HSR antitrust rules. A leaked brand direction or draft press release can become a material public statement. The document trail is the liability.
WHEN IN DOUBT — STOP AND ASK
Before drafting any communications asset that uses target company information, contact the Communications Lead or Legal. The data room agreement defines what is in scope. If it is not explicitly cleared, it is not cleared.

## Slide 12
100-DAY ADVISORS
Accelerating M&A Integrations
MandAPlaybook.com
inquiries@MandAPlaybook.com