## Slide 1: HUMAN RESOURCES 10 KEY M&A RESPONSIBILITIES

## Slide 2
Develop workforce integration project plan.
1.
Assign accountabilities to individuals.
Assign deadline dates.
Obtain disclosure approvals, if necessary.
© 100-Day Advisors MandAPlaybook.com

## Slide 3
Conduct HR due diligence review.
2.
Complete due diligence checklist; collect and review data.
Evaluate potential liabilities.
Communicate concerns to those negotiating the deal.
Determine adjustments or actions necessary.
© 100-Day Advisors MandAPlaybook.com

## Slide 4
Compare benefits and analyze differences.
3.
Complete benefits comparison of Acquirer and Acquiree.
Compare and assess differences or concerns.
Summarize differences.
© 100-Day Advisors MandAPlaybook.com

## Slide 5
Compare compensation and analyze differences.
4.
Complete compensation comparison of Acquirer and Acquiree.
Compare and assess differences or concerns.
Summarize differences.
© 100-Day Advisors MandAPlaybook.com

## Slide 6
Develop compensation and benefits strategy for workforce integration.
5.
Complete Compensation and Benefits analysis
Review with appropriate parties.
Revise as necessary.
© 100-Day Advisors MandAPlaybook.com

## Slide 7
Determine leadership assignments.
6.
Review vision and business strategy.
Review the combined organizational structure.
Review the core competencies that support the business strategy.
Determine leadership needs by position.
Assess individual candidates.
Select leadership for new combined organization.
© 100-Day Advisors MandAPlaybook.com

## Slide 8
Address duplicate functions.
7.
Review functions and determine staffing requirements.
Identify the redundant jobs and individuals who will be separated.
Review for adverse impact.
Determine if the WARN Act applies.
Determine level of severance pay and outplacement, if any.
Create reduction in force communication documents.
Assign and prepare facilitators.
© 100-Day Advisors MandAPlaybook.com

## Slide 9
Prepare employee communication strategy.
8.
9
Determine methodologies and logistics for initial announcement.
Develop message content/presentation materials/Q&As/ Welcome Package.
Assign and prepare facilitators.
Hold announcement meetings.
Hold HR meetings.
Hold one-on-one management/employee meetings.
© 100-Day Advisors MandAPlaybook.com

## Slide 10
Define transition data requirements.
9.
Assess data requirements and availability.
Prepare test data and transfer.
Prepare to transfer final data.
© 100-Day Advisors MandAPlaybook.com

## Slide 11
Develop employee retention strategy.
10.
Set and keep focus on business goals.
Apply best practices and process changes.
Provide multiple training and learning opportunities.
Consider retention bonuses
Conduct employee surveys.
Hold employee roundtable discussions.
© 100-Day Advisors MandAPlaybook.com

## Slide 12
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com