## Integration Plan
PRE-CLOSE HUMAN RESOURCES MERGER INTEGRATION PLAN | [13 empty] | Click on + sign (above the top row on right) to see synergy columns
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
Risk Level | Status | % Complete |  |  | Links
High | Not Started | 0% |  |  | Milestones
Medium | Delayed | 25% |  |  | RAID Log (Includes Plan Assumptions)
Low | On Track | 50% |  |  | Next 14 Days
| Complete | 75% |  |  | Executive Dashboard
100%
ID# | Category | Milestone | Phase | Assigned To | Task | Notes | Timing Anchor | Start | Finish | Status | Complete | Critical Path | Issues/Blockers | Risk Level | Team Dependency | Synergy Description | Synergy ($K) | Cost To Achieve ($K) | Synergy ($K) Realized | Actual Cost To Achieve ($K)
HR-001 | Governance & Planning | HR Lead Appointed | Pre-Close | CHRO / HR Workstream Lead | Identify HR integration workstream lead and determine members of the HR integration team | HR Lead must be selected before integration kickoff; without a single accountable HR owner, every downstream task from benefits harmonization to org design lacks an approver; select HR staff with experience in M&A; functional HR expertise alone is insufficient — integration requires comfort with ambiguity, rapid decision-making, and cross-functional coordination | T-59 | 1/2 | 1/10 | Not Started | 0% | CP – Close | HR Lead appointment requires executive decision and HR functional backing; if the role is filled from within an HR team with heavy BAU responsibilities, capacity conflict is the leading cause of delayed HR integration milestones | High | Executive Sponsor, Board
HR-002 | Governance & Planning | HR Integration Governance Established | Pre-Close | HR Workstream Lead | Review data privacy and confidentiality protocols for pre-close sharing | Pre-close data sharing is subject to HSR clean room rules; any HR staff with access to target company systems or data must be briefed on what they can and cannot do — violations carry regulatory and legal consequences | T-53 | 1/8 | 1/12 | Not Started | 0% |  | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | High | Legal, Compliance
HR-003 | Integration Management | HR Integration Governance Established | Pre-Close | HR Workstream Lead | Attend IMO Kickoff Meeting | Use kickoff to align team leads on goals, value drivers, expectations, timeline, data sharing, and guiding principles | T-50 | 1/11 | 1/11 | Not Started | 0% |  |  | Low | IMO
HR-004 | Governance & Planning | HR Integration Governance Established | Pre-Close | HR Workstream Lead | Receive access to integration data room and document repository | Request data room access on the day the NDA is signed; pre-close access is time-limited and every day of delay compresses the planning window for benefits, comp, and legal review | T-49 | 1/12 | 1/13 | Not Started | 0% |  |  | Low | Legal
HR-005 | Governance & Planning | HR Integration Governance Established | Pre-Close | HR Workstream Lead | Conduct HR Integration Kickoff Meeting | Agenda should cover: guiding principles, clean room protocols, Day 1, priorities | T-49 | 1/12 | 1/12 | Not Started | 0% |  |  | Low | IMO
HR-006 | Governance & Planning | HR Charter Approved | Pre-Close | HR Workstream Lead | Develop the HR workstream integration charter and attend an IMO meeting to share charters with other teams; steering committee will approve charters | Charter should define the boundary between HR workstream and Finance (compensation budgets), Legal (employment law and litigation), and IT (HRIS integration); overlapping ownership of comp and benefits decisions is the most common HR integration conflict | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Low | IMO
HR-007 | Due Diligence | HR Due Diligence Complete | Pre-Close | HRIS & Systems Manager | Review organizational charts for all business units, functions, and geographies | Review org charts at the functional, not just the top level— compensation band, layer count, and span of control data embedded in the org chart reveal org design decisions that will need to be made before Day 1 | T-49 | 1/12 | 1/30 | Not Started | 0% |  | Org charts provided in due diligence are frequently out of date by the time the deal closes; confirm the reporting structure reflected in the chart matches actual headcount and title data in the roster — discrepancies reveal recent org changes that were not disclosed | High | Finance
HR-008 | Governance & Planning | HR Integration Governance Established | Pre-Close | HR Workstream Lead | Define HR integration success metrics and KPIs | KPIs should include: payroll success rate, benefits enrollment completion rate, retention rate for key talent at 30/60/90 days, and employee engagement | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Low | IMO
HR-009 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Business Partner | Assess retention risk of all senior leadership and key management positions | Retention risk assessment output drives the retention bonus program design; complete this before close so retention agreements can be ready on Day 1 for the highest-risk individuals | T-49 | 1/12 | 2/25 | Not Started | 0% |  | Retention risk assessment requires compensation data that is often restricted in the clean room; if full compensation data is unavailable pre-close, the assessment will be based on incomplete information — flag any missing comp data to Legal and request a carve-out for key individual compensation review | High | IMO
HR-010 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Identify all contract workers, consultants, and temporary staff — terms, costs, and renewal dates | Misclassified contractors are the most common employment law finding in HR due diligence; flag any independent contractor who works exclusively for the target company or who has worked there for more than 12 months | T-49 | 1/12 | 1/31 | Not Started | 0% |  | Misclassification that is not identified and remediated before close transfers back taxes, penalties, and benefits obligations to the acquirer | High | Legal
HR-011 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Business Partner | Obtain employee engagement survey results for last 2 years and assess culture and morale indicators | Prior engagement surveys reveal cultural flashpoints — low scores on leadership trust, fairness, or recognition are early warning indicators of post-close attrition; share findings with the CHRO before close | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Medium | IMO
HR-012 | Due Diligence | HR Due Diligence Complete | Pre-Close | Compensation Analyst | Obtain complete headcount roster — names, titles, departments, locations, employment type, and start dates | Headcount roster is the foundation for HR due diligence; request it on the first day of data room access | T-47 | 1/14 | 1/16 | Not Started | 0% |  |  | Medium | Legal, Executive Sponsor
HR-013 | Due Diligence | HR Due Diligence Complete | Pre-Close | Employee Relations Manager | Assess voluntary and involuntary turnover rates by level, function, and location | High voluntary turnover in a specific function or level is a leading indicator of post-close flight risk; compare target's turnover rates to industry benchmarks and to the acquirer's own rates | T-46 | 1/15 | 1/22 | Not Started | 0% |  |  | Medium | IMO
HR-014 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | Compensation Analyst | Assess compensation philosophy alignment | Compensation philosophy misalignment is the most common source of employee relations tension post-close | T-46 | 1/15 | 2/15 | Not Started | 0% |  |  | Medium | Finance
HR-015 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Assess OSHA compliance and safety record — review any citations, investigations, or penalties | OSHA violations that are open or recently settled become the acquirer's liability on Day 1; flag any repeat citations or willful violations to Legal immediately | T-45 | 1/16 | 1/23 | Not Started | 0% |  |  | Medium | Legal, IMO
HR-016 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | Compensation Analyst | Review annual incentive plan design — eligibility, targets, metrics, funding mechanics | Annual incentive plan triggers (change-of-control, pro-ration, double-trigger) must be understood before signing; unbudgeted bonus payouts post-close are a common financial surprise | T-45 | 1/16 | 2/16 | Not Started | 0% |  | Annual incentive plan change-of-control provisions — particularly those with single-trigger acceleration or guaranteed bonus payments — create unbudgeted cash obligations at close | High | Legal, Finance
HR-017 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | Compensation Analyst | Inventory all equity plans — stock options, RSUs, PSUs, SARs — with vesting schedules and underwater grants | Equity plan change-of-control provisions vary widely — some accelerate vesting, some require substitution, some expire; incorrect treatment results in employee complaints, legal claims, and tax issues | T-45 | 1/16 | 2/6 | Not Started | 0% |  | Equity plan acceleration clauses that trigger on change-of-control can create significant unplanned dilution or cash settlement obligations | High | Legal, Finance
HR-018 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | Compensation Analyst | Inventory all health and welfare benefit plans — medical, dental, vision, life, disability, and EAP | Benefit plan costs that exceed the acquirer's benchmarks must be factored into the cost-to-achieve model; mid-year benefit changes require regulatory compliance steps and employee notice periods | T-45 | 1/16 | 2/6 | Not Started | 0% |  | Benefit plan costs above market can only be reduced through plan design changes that require advance employee notice, ERISA compliance review, and potentially WARN Act compliance if the reduction is material; the cost-to-achieve for benefit harmonization must account for the compliance lead time before savings can be realized | High | Finance
HR-019 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Review all 401(k) and retirement plan documents — contribution rates, employer match, vesting, and investment options | 401(k) plan termination, merger, or continuation must be decided before close; each option has different IRS compliance requirements and employee communication obligations | T-45 | 1/16 | 2/6 | Not Started | 0% |  | 401(k) plan termination, merger, or continuation must be decided before close; each path has different IRS notice requirements and timelines — a plan merger requires IRS approval and employee notice at least 30 days in advance; a termination triggers full vesting and distribution rights that must be administered correctly to avoid excise taxes | High | Legal, Finance
HR-020 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | Benefits & Compensation Manager | Identify any defined benefit pension plans and obtain actuarial valuation and funded status | Defined benefit pension plans are frequently underfunded; the funding gap transfers to the acquirer — obtain an actuarial valuation and confirm the funding status before signing | T-45 | 1/16 | 2/6 | Not Started | 0% |  | The PBGC may impose variable-rate premiums on underfunded plans and, in extreme cases, can assert lien rights against the acquirer | High | Legal, Finance
HR-021 | Governance & Planning |  | Pre-Close | HR Workstream Lead | Develop HR integration plan (tasks, milestones, RAID log, Day 1 checklist) and update it weekly | HR integration plan is the operating document for the workstream; update weekly, share with IMO coordinator by Thursday. HR rows on the dashboard are owned by the HR Lead; RAG status must reflect current reality — optimistic reporting delays executive awareness of issues that require intervention | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Medium | IMO
HR-022 | Integration Management |  | Pre-Close | HR Workstream Lead | Conduct HR workstream status meeting weekly | Same day and time every week without exception; pre-read with status update and issues log circulated 24 hours before the meeting | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
HR-023 | Integration Management |  | Pre-Close | HR Workstream Lead | Attend IMO Meeting weekly to discuss issues and status | Bring the HR RAID log to every IMO meeting | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
HR-024 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Review all employment agreements for senior executives and identify change-of-control provisions | CIC provisions in executive agreements — single-trigger vs. double-trigger, golden parachute calculations, notice periods — must be modeled by Finance and reviewed by Legal before signing | T-42 | 1/19 | 1/31 | Not Started | 0% |  | Double-trigger CIC provisions require both a change of control and a qualifying termination to trigger payments; single-trigger agreements pay out at close regardless of whether the executive is retained | High | Legal
HR-025 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Business Partner | Identify all non-compete, non-solicitation, and confidentiality agreements — assess enforceability by jurisdiction | Non-competes are unenforceable in California and increasingly restricted in other states; map each agreement to the employee's work location before assuming enforceability post-close | T-42 | 1/19 | 1/31 | Not Started | 0% |  | Non-compete enforceability varies significantly by state | High | Legal
HR-026 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Review all severance agreements and separation policies | Severance agreements with broad release language can limit the acquirer's ability to pursue claims against departing employees; Legal must review before any separations are executed | T-42 | 1/19 | 1/31 | Not Started | 0% |  | Broad release language in existing severance agreements may prevent the acquirer from pursuing indemnity claims against employees who are separated | High | Legal
HR-027 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Assess all independent contractor agreements — flag misclassification risk under IRS and DOL standards | Misclassified independent contractors who are reclassified post-close trigger back taxes, penalties, and benefits obligations that were not in the deal model; flag any contractor who could be deemed a common-law employee | T-42 | 1/19 | 1/31 | Not Started | 0% |  | Misclassified independent contractors who are reclassified post-close trigger retroactive payroll tax liability, penalties, and benefits obligations that were not included in the deal model; the cost of remediation — including back benefits contributions — can be material for large contingent workforces | High | Legal
HR-028 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Review workers compensation claims history and assess reserve adequacy and carrier relationships | Workers' comp claims history reveals safety culture and hidden financial liabilities; experience modification rate (EMR) above 1.0 indicates above-average risk that will affect insurance costs | T-42 | 1/19 | 1/31 | Not Started | 0% |  |  | Medium | Legal, Finance
HR-029 | Systems & Technology | HR Due Diligence Complete | Pre-Close | HRIS & Systems Manager | Inventory all HR technology systems — HRIS, payroll, ATS, LMS, performance management, and learning and development platforms — across both entities | HRIS system compatibility determines the timeline and cost of people data migration; an incompatible HRIS can delay payroll integration by 3–6 months if not identified pre-close | T-41 | 1/20 | 2/14 | Not Started | 0% |  | HRIS system incompatibility is the most common technical delay in HR integration; if the target's HRIS cannot be migrated into the acquirer's platform before Day 1, HR will be operating from two separate systems with manual reconciliation — the resulting payroll and reporting errors typically persist for 60–90 days | High | IT
HR-030 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | Compensation Analyst | Assess golden parachute obligations and calculate 280G exposure for all covered employees | 280G gross-up obligations can represent significant unbudgeted cost; confirm whether the target's CIC agreements include gross-up provisions and model the full tax exposure before signing | T-38 | 1/23 | 2/6 | Not Started | 0% |  | The acquirer and target must conduct a joint 280G calculation before close and either restructure payments or obtain shareholder approval for a 280G waiver — failure to plan results in a 20% excise tax on excess payments | High | Legal, Finance
HR-031 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | Benefits & Compensation Manager | Assess benefit plan costs per employee and compare to acquirer benefit cost structure | High benefit costs are often a cost synergy opportunity but require benefit reductions that must be carefully managed | T-38 | 1/23 | 2/6 | Not Started | 0% |  |  | Medium | Finance
HR-032 | Due Diligence | HR Due Diligence Complete | Pre-Close | Benefits & Compensation Manager | Assess COBRA administration obligations and identify any outstanding COBRA compliance issues | COBRA administration gaps create regulatory exposure; confirm the target has been issuing qualifying event notices correctly — retrospective COBRA compliance failures can result in significant penalties | T-38 | 1/23 | 2/8 | Not Started | 0% |  | COBRA administration failures are one of the most common compliance findings in HR due diligence; each uncorrected COBRA violation can result in IRS penalties of $100 per day per qualified beneficiary, compounding from the date of the violation | High | Legal, Finance
HR-033 | Due Diligence | HR Due Diligence Complete | Pre-Close | Benefits & Compensation Manager | Review flexible spending accounts, HSA arrangements, and commuter benefit programs | FSA and HSA arrangements have IRS compliance requirements that transfer to the acquirer; confirm contribution limits, nondiscrimination testing, and plan year alignment before close | T-38 | 1/23 | 2/6 | Not Started | 0% |  |  | Low | Legal, Finance
HR-034 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | Benefits & Compensation Manager | Review insurance coverage alignment | Insurance coverage mismatches — particularly D&O, EPL, and key man policies — must be reconciled before Day 1; gaps in coverage during the transition period can leave the combined entity exposed | T-36 | 1/25 | 2/8 | Not Started | 0% |  |  | Medium | Legal, Finance
HR-035 | Communications | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HR Workstream Lead | Develop with Communications team the Day 1 announcement cascade plan — who communicates what, to whom, and in what order | All-employee announcement must be in manager inboxes before the press release goes live; employees who learn about the deal from media before hearing from their manager lose trust immediately | T-31 | 1/30 | 2/24 | Not Started | 0% | CP – Day 1 Readiness | All-employee announcement must be sequenced after regulatory clearance and before the press release; the timing of this task is a legal and communications dependency that cannot slip | High | Communications, Legal
HR-036 | Communications | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HR Workstream Lead | Create employee-facing Day 1 FAQ document covering benefits, payroll, reporting lines, and key contacts for inclusion in M&A Employee Communication Guide | FAQ document should address the top questions employees actually ask, not the questions HR thinks they will ask; pilot the FAQ with a small group of managers before Day 1 distribution | T-31 | 1/30 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Day 1 FAQ document errors — incorrect plan names, wrong enrollment dates, inaccurate coverage amounts — generate a disproportionate volume of employee complaints and HR hotline calls; pilot the FAQ with five managers before Day 1 and require Legal and Benefits sign-off on every claim made in the document | High | Legal, Finance
HR-037 | Due Diligence | HR Due Diligence Complete | Pre-Close | Employee Relations Manager | Obtain and review all pending and threatened employment litigation — claims, charges, and settlements | Pending employment litigation becomes the acquirer's liability on Day 1; confirm whether any cases involve class action risk, systemic pay equity claims, or patterns of discrimination that could expand post-close | T-31 | 1/30 | 2/20 | Not Started | 0% |  | Pending employment litigation that is not disclosed in due diligence is one of the most common post-close indemnity claims; confirm that the target's legal representation on litigation disclosure is accurate and that all matters — including threatened but unfiled claims — have been produced | High | Legal
HR-038 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Review all EEOC charges, DOL investigations, and state labor agency actions — open and closed last 5 years | Active EEOC charges require a response from the employer of record; confirm whether the acquirer becomes the respondent on Day 1 and brief Legal on open matters before close | T-31 | 1/30 | 2/20 | Not Started | 0% |  | Legal must be briefed on all open EEOC matters before close and a response strategy must be in place — charges that reveal systemic pay equity or discrimination patterns can expand into class actions post-close | High | Legal
HR-039 | Organization & Talent | HR Due Diligence Complete | Pre-Close | HR Business Partner | Perform culture assessment and identify differences in operating styles with acquired company | Culture assessment results should be shared with all workstream leads, not just HR; cultural friction points frequently surface in IT adoption rates, cross-team collaboration, and management style conflicts | T-29 | 2/1 | 2/25 | Not Started | 0% |  |  | Medium | Communications
HR-040 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Operations Manager | Identify and document all HR vendors and service providers that will be inherited from the acquired entity | HR vendor relationships with payroll processors, benefit administrators, and ATS providers may have change-of-control clauses | T-28 | 2/2 | 2/9 | Not Started | 0% |  |  | Low | Legal, Finance
HR-041 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Review HR vendor contracts — payroll processor, benefits broker, background check provider, and renewal dates | HR vendor contract terms — particularly payroll and benefits administration — often contain exclusivity provisions or termination fees that affect the timeline for consolidating to a single vendor | T-28 | 2/2 | 2/18 | Not Started | 0% |  |  | Low | Legal, Finance
HR-042 | Compliance & Regulatory | Combined Payroll Live for All Employees | Pre-Close (Day 1 Readiness) | Payroll Manager | Prepare payroll tax IDs and state registration changes | State payroll tax registrations can take 2–4 weeks to activate; initiate in every new state where acquired employees work no later than T-30 — a missing state registration prevents payroll from being processed | T-28 | 2/2 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | An inactive state registration prevents payroll from being processed in that state and creates tax compliance violations | High | Finance
HR-043 | Compliance & Regulatory | Employee Handbook Prepared | Pre-Close (Day 1 Readiness) | HR Compliance Manager | Prepare employee handbook for future distribution to all acquired employees | Employee handbook must reflect the combined entity's policies | T-28 | 2/2 | 2/25 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Legal
HR-044 | Due Diligence | HR Due Diligence Complete | Pre-Close | HR Compliance Manager | Review I-9 and work authorization compliance — assess audit exposure and identify remediation needs | I-9 audit findings become the acquirer's liability; if the target has employees whose I-9s are invalid or expired, the acquirer must remediate — fines for I-9 violations can be significant per violation | T-25 | 2/5 | 2/19 | Not Started | 0% |  | USCIS fines range from $272 to $27,000 per violation for substantive errors, and undocumented employees who cannot be reverified must be separated | High | Legal
HR-045 | Organization & Talent | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | Employee Relations Manager | Establish process for addressing employee issues and concerns during integration | HR integration inbox must be monitored by a senior HR staff member, not routed to a general inbox; employees who ask sensitive questions and receive automated responses disengage immediately | T-21 | 2/9 | 2/22 | Not Started | 0% | CP – Day 1 Readiness | An employee who raises a concern about pay, benefits, or treatment on Day 1 and receives no response within 24 hours will assume the worst — unresponsive HR during the first week is the single greatest driver of early voluntary attrition | High | Legal
HR-046 | Communications | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | Employee Relations Manager | Set up dedicated HR integration inbox and hotline — tested and staffed before Day 1 | HR hotline volume on Day 1 will be 5–10x normal; staff with experienced HR generalists who can provide live answers — automated responses to sensitive questions about job security and benefits erode trust | T-21 | 2/9 | 2/22 | Not Started | 0% | CP – Day 1 Readiness | HR hotline must be tested with actual call volume simulation before Day 1; a hotline that connects to voicemail or routes to an unmonitored inbox on the highest-call-volume day of the integration destroys employee trust — staff with experienced HR generalists who have authority to give real answers, not read from scripts | High | IT
HR-047 | Compensation & Benefits | HR Due Diligence Complete | Pre-Close | Compensation Analyst | Review deferred compensation plans and assess Section 409A compliance | Section 409A deferred compensation plans that are not properly maintained create significant excise tax exposure for employees and employer; engage outside tax counsel before making any changes to deferred comp plan terms | T-21 | 2/9 | 2/23 | Not Started | 0% |  | Section 409A violations result in immediate income inclusion, a 20% excise tax, and interest penalties on all deferred compensation in the same plan; any modification to a deferred compensation plan after the acquisition — including extending payment dates or changing investment options — must be reviewed by outside tax counsel before implementation | High | Legal, Finance
HR-048 | Compensation & Benefits | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HR Compliance Manager | Prepare benefits summary card for acquired employees — coverage effective dates, carrier contacts, enrollment steps | Benefits summary card must be accurate down to the plan name and enrollment deadline; errors in benefits communications are the top driver of acquired employee complaints in the first 30 days | T-20 | 2/10 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Benefits summary card errors are the top driver of Day 1 HR hotline volume; employees make healthcare decisions based on this document — require Benefits, Legal, and CHRO sign-off before distribution | High | Legal, Finance
HR-049 | Compliance & Regulatory | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HR Compliance Manager | Prepare all required Day 1 legal notices — WARN compliance, ERISA, benefit plan change notifications | WARN notice requirements depend on facility size, number of affected employees, and state law; some states require 90 days notice vs. the federal 60 days — engage employment counsel in every state where separations are occurring | T-19 | 2/11 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Legal
HR-050 | Organization & Talent | Day 1 Separations Communicated | Pre-Close (Day 1 Readiness) | HR Business Partner | Identify any acquired roles being eliminated on Day 1 and ensure separation packages are prepared and compliant | Roles being eliminated on Day 1 require written separation agreements, final pay calculations, and WARN compliance — all of which must be completed before Day 1; any role elimination without legal clearance is a significant employment law risk | T-17 | 2/13 | 2/25 | Not Started | 0% | CP – Day 1 Readiness | Any separation executed without Legal review creates wrongful termination exposure | High | Legal, Finance
HR-051 | Communications | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HR Workstream Lead | Draft CHRO Day 1 welcome message | CHRO message sets the tone for the HR function's role in the integration; it should address three questions every acquired HR employee is asking: what happens to my job, who do I report to, and what changes for the employees I support | T-15 | 2/15 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Communications
HR-052 | Organization & Talent | HR Due Diligence Complete | Pre-Close | Learning & Development Manager | Assess training needs of acquired company | Training needs assessment should distinguish between role-specific training (how to use the acquirer's systems) and cultural integration training (how decisions are made and how to work across teams) | T-15 | 2/15 | 2/27 | Not Started | 0% |  |  | Medium | All Workstreams
HR-053 | Organization & Talent | Interim Org Structure Announced | Pre-Close (Day 1 Readiness) | HR Workstream Lead | Determine interim org structure — combined entity reporting lines effective Day 1 | Interim org structure should be as simple as possible — avoid dual reporting lines and temporary matrices that persist beyond 30 days; every employee should have one clear manager from Day 1 | T-11 | 2/19 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Any delay in confirming reporting lines creates a management vacuum that is filled by rumors — the interim structure should be documented and approved by the Steering Committee or Executive Sponsor before Day 1 | High | Executive Sponsor
HR-054 | Systems & Technology | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HRIS & Systems Manager | Build combined entity employee directory and confirm all acquired employees are included | Employee directory must include both legacy companies; an employee directory that only reflects the acquirer signals to acquired employees that they are not yet part of the team | T-11 | 2/19 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | IT
HR-055 | Systems & Technology | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HRIS & Systems Manager | Set up and test HR self-service portal for acquired company | HR self-service portal must be tested by before Day 1 | T-10 | 2/20 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | IT
HR-057 | Systems & Technology | Combined Payroll Live for All Employees | Pre-Close (Day 1 Readiness) | Payroll Manager | Confirm payroll funding accounts are established and first pay cycle for acquired employees is scheduled | Payroll funding account setup requires bank authorization lead times of 7–10 business days; initiate no later than T-15 to avoid payroll processing failure on the first combined payroll run | T-6 | 2/24 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Payroll funding account setup requires bank processing times of 7–10 business days; ACH authorization and payroll account registration must be initiated at least T-15 before the first payroll run — a funding account that is not active on payroll processing day results in a failed pay cycle with no quick fix | High | Finance
HR-058 | Systems & Technology | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HRIS & Systems Manager | Confirm access to company email, collaboration tools, and key HR systems for all acquired staff | System access failures on Day 1 are the most common source of employee frustration; confirm access provisioning with IT at least 48 hours before Day 1 and have a help desk escalation path ready | T-5 | 2/25 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Email and HR self-service portal access — are the most common source of employee frustration; IT must confirm provisioning for acquired employees at least 48 hours before Day 1 and HR must have a direct escalation path to IT's Day 1 war room | High | IT
HR-059 | Communications | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HR Workstream Lead | Confirm M&A Employee Communication Guide has been distributed to managers | M&A Employee Communication Guide is a critical deliverable that must be distributed pre-close | T-4 | 2/26 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Communications
HR-D1 | Integration Management | Day 1 HR Readiness Confirmed | Pre-Close (Day 1 Readiness) | HR Workstream Lead | HR Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | Workstream lead formally certifies Day 1 readiness to the IMO; this gate must be green for every workstream before the IMO signs off on close; any open item at this gate is either resolved or escalated to the steering committee as a close-blocking risk | T-3 | 2/27 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | High | IMO, All Workstreams
THE POST-CLOSE PLANS ARE LOCATED IN THE DAY 1 AND DAY 100 SECTIONS OF MANDAPLAYBOOK.COM

## Milestones
HUMAN RESOURCES M&A MILESTONES
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
Status | Links
Not Started | Integration Plan
Delayed | RAID Log
On Track | Next 14 Days
Complete | Executive Dashboard
Milestone ID | Category | Phase | Assigned To | Milestone | Timing Anchor | Finish | Status | Critical Path
MS-001 | Governance & Planning | Pre-Close | CHRO / HR Workstream Lead | HR Lead Appointed | T-59 | 1/10 | Complete | CP – Close
MS-002 | Governance & Planning | Pre-Close | HR Workstream Lead | HR Integration Governance Established | T-49 | 1/19 | Complete | CP – Close
MS-003 | Governance & Planning | Pre-Close | HR Workstream Lead | HR Charter Approved | T-49 | 1/19 | Complete | CP – Close
MS-004 | Compliance & Regulatory | Pre-Close (Day 1 Readiness) | HR Compliance Manager | Employee Handbook Prepared | T-28 | 2/25 | Complete | CP – Day 1 Readiness
MS-005 | Due Diligence | Pre-Close | HRIS & Systems Manager | HR Due Diligence Complete | T-15 | 2/27 | Complete | CP – Close
MS-006 | Communications | Pre-Close (Day 1 Readiness) | HR Workstream Lead | Day 1 HR Readiness Confirmed | T-3 | 2/27 | Complete | CP – Day 1 Readiness
MS-007 | Organization & Talent | Pre-Close (Day 1 Readiness) | HR Workstream Lead | Interim Org Structure Announced | T-11 | 2/27 | Complete | CP – Day 1 Readiness

## RAID Log
HR M&A RAID LOG (RAID = Risks, Assumptions, Issues, Dependencies)
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
RAID Type | Status | Links
Risk | Open | Integration Plan
Issue | Closed | Milestones
Dependency | Active | Next 14 Days
Assumption | Validated | Executive Dashboard
RAID Type | RAID ID | Related Task ID | Milestone | Owner | Task Description | Issues/Blockers | Status | Mitigation/Action | Timing Anchor | Finish
Assumption | RAID-001 | HR-001 | HR Lead Appointed | CHRO | Key HR personnel in the acquired company will remain available and cooperative throughout the integration — it is assumed that the acquired company's HR lead, benefits administrator, and HRIS administrator will not depart before or immediately after close, maintaining institutional knowledge of legacy HR systems, benefits programs, and employee relations history | If the acquired company's HR team departs at or near close, the combined entity loses the primary source of knowledge on legacy benefits plan terms, open employee relations cases, HRIS configurations, and compensation structures that are not fully documented; every downstream integration task from benefits harmonization through HRIS migration depends on this assumption | Active | CHRO to confirm retention commitment of acquired company HR lead and top 3 HR staff before close; initiate knowledge transfer sessions beginning at T-30 for all critical HR processes, systems, and open employee relations matters; document all undocumented HR configurations and benefit plan terms in a shared knowledge base before close | T-51 | 1/10
Dependency | RAID-002 | HR-001 | HR Lead Appointed | CHRO / HR Workstream Lead | Identify HR integration workstream lead and determine members of the HR integration team | HR Lead appointment requires executive decision and HR functional backing; if the role is filled from within an HR team with heavy BAU responsibilities, capacity conflict is the leading cause of delayed HR integration milestones | Open | Escalate appointment to CHRO immediately; HR workstream lead must be named and capacity confirmed before integration kickoff; if filled internally, secure backfill for BAU responsibilities to prevent the integration from becoming the secondary priority | T-51 | 1/10
Risk | RAID-003 | HR-001 | HR Lead Appointed | CHRO / HR Workstream Lead | Identify HR integration workstream lead and determine members of the HR integration team | HR Lead appointment requires executive decision and HR functional backing; if the role is filled from within an HR team with heavy BAU responsibilities, capacity conflict is the leading cause of delayed HR integration milestones | Open | Conduct the Day 100 gate review as a formal board-level milestone; require each HR workstream lead to provide written close-out status; any item not formally closed must be assigned to a named BAU owner with a resolution timeline before the gate is approved | T-51 | 1/10
Risk | RAID-004 | HR-002 | HR Integration Governance Established | HR Workstream Lead | Review data privacy and confidentiality protocols for pre-close sharing | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | Open | Issue a written clean team protocol to all HR integration team members before any pre-close data sharing begins; Legal to specify exactly what data can be reviewed, by whom, and under what conditions; document all pre-close data access with dates and approvers | T-49 | 1/12
Assumption | RAID-005 | HR-010 | HR Due Diligence Complete | CHRO | Acquired company employees will accept the combined entity's employment terms and benefits structure without material attrition — it is assumed that the compensation and benefits offered post-close are sufficiently competitive that no more than 5% of acquired company employees voluntarily depart within the first 30 days of close | Involuntary attrition above 5% in the first 30 days would signal a breakdown in employee confidence that is very difficult to reverse; it would also trigger immediate knowledge loss in critical roles, increase recruiting and onboarding costs, and potentially disrupt customer relationships managed by departing employees; the integration plan's Day 1 communications program is the primary mitigation, but if compensation benchmarking reveals gaps, the CHRO must be prepared to act within the first week | Active | CHRO to complete compensation benchmarking for all acquired company roles before close and flag any roles where total compensation falls below the 50th percentile of the combined entity's structure; prepare retention packages for high-risk individuals before Day 1; conduct Day 30 pulse survey (HR-098) to detect early attrition signals and escalate any voluntary departure rate above 3% to the CHRO and CEO immediately | T-30 | 1/31
Risk | RAID-006 | HR-007 | HR Due Diligence Complete | HRIS & Systems Manager | Review organizational charts for all business units, functions, and geographies | Org charts provided in due diligence are frequently out of date by the time the deal closes; confirm the reporting structure reflected in the chart matches actual headcount and title data in the roster — discrepancies reveal recent org changes that were not disclosed | Open | Require target management to certify that org charts are current as of the submission date; cross-reference against payroll headcount to identify discrepancies; flag any roles that appear on the org chart but not in the payroll file for immediate reconciliation | T-31 | 1/30
Risk | RAID-007 | HR-010 | HR Due Diligence Complete | HR Compliance Manager | Identify all contract workers, consultants, and temporary staff — terms, costs, and renewal dates | Misclassification that is not identified and remediated before close transfers back taxes, penalties, and benefits obligations to the acquirer | Open | Require target management to provide a complete contractor roster including legal name, entity, contract start and end dates, and annual spend; engage employment counsel to assess misclassification exposure before close; include indemnification coverage in the SPA for pre-close misclassification | T-30 | 1/31
Risk | RAID-008 | HR-024 | HR Due Diligence Complete | HR Compliance Manager | Review all employment agreements for senior executives and identify change-of-control provisions | Double-trigger CIC provisions require both a change of control and a qualifying termination to trigger payments; single-trigger agreements pay out at close regardless of whether the executive is retained | Open | Obtain executed copies of all executive employment agreements and map all CIC provisions before close; engage employment counsel to calculate maximum single and double-trigger payout scenarios; confirm SPA price adjustment mechanisms can absorb the maximum exposure | T-30 | 1/31
Risk | RAID-009 | HR-025 | HR Due Diligence Complete | HR Business Partner | Identify all non-compete, non-solicitation, and confidentiality agreements — assess enforceability by jurisdiction | Non-compete enforceability varies significantly by state | Open | Engage employment counsel in every jurisdiction where acquired employees are located to assess enforceability; do not assume non-competes are enforceable — California, Minnesota, North Dakota, and Oklahoma ban them entirely; identify key employees in no-NCA states and develop alternative retention strategies | T-30 | 1/31
Risk | RAID-010 | HR-026 | HR Due Diligence Complete | HR Compliance Manager | Review all severance agreements and separation policies | Broad release language in existing severance agreements may prevent the acquirer from pursuing indemnity claims against employees who are separated | Open | Require target management to disclose all severance commitments in the SPA; include a rep that no undisclosed severance or separation agreements exist; obtain employment counsel review of any broad release provisions before approving separation transactions post-close | T-30 | 1/31
Risk | RAID-011 | HR-027 | HR Due Diligence Complete | HR Compliance Manager | Assess all independent contractor agreements — flag misclassification risk under IRS and DOL standards | Misclassified independent contractors who are reclassified post-close trigger retroactive payroll tax liability, penalties, and benefits obligations that were not included in the deal model; the cost of remediation — including back benefits contributions — can be material for large contingent workforces | Open | Complete contractor classification review before close; for any misclassified contractor, quantify the tax, benefits, and penalties exposure; obtain rep and warranty insurance coverage for pre-close misclassification; do not reclassify any contractor post-close without employment counsel guidance | T-30 | 1/31
Risk | RAID-012 | HR-017 | HR Due Diligence Complete | Compensation Analyst | Inventory all equity plans — stock options, RSUs, PSUs, SARs — with vesting schedules and underwater grants | Equity plan acceleration clauses that trigger on change-of-control can create significant unplanned dilution or cash settlement obligations | Open | Model all equity acceleration scenarios — single-trigger, double-trigger, and modified single-trigger — before signing the SPA; confirm price adjustment mechanism can absorb maximum acceleration cost; engage compensation counsel to review plan documents and calculate aggregate payout exposure | T-24 | 2/6
Risk | RAID-013 | HR-018 | HR Due Diligence Complete | Compensation Analyst | Inventory all health and welfare benefit plans — medical, dental, vision, life, disability, and EAP | Benefit plan costs above market can only be reduced through plan design changes that require advance employee notice, ERISA compliance review, and potentially WARN Act compliance if the reduction is material; the cost-to-achieve for benefit harmonization must account for the compliance lead time before savings can be realized | Open | Obtain the full benefits cost-per-employee analysis before close; model the cost of harmonizing benefits upward versus offering a transition period; confirm regulatory notice requirements with ERISA counsel before making any benefit plan changes post-close | T-24 | 2/6
Dependency | RAID-014 | HR-019 | HR Due Diligence Complete | HR Compliance Manager | Review all 401(k) and retirement plan documents — contribution rates, employer match, vesting, and investment options | 401(k) plan termination, merger, or continuation must be decided before close; each path has different IRS notice requirements and timelines — a plan merger requires IRS approval and employee notice at least 30 days in advance; a termination triggers full vesting and distribution rights that must be administered correctly to avoid excise taxes | Open | Engage ERISA counsel to determine whether the acquired 401(k) plan will be terminated, merged, or maintained separately; submit required IRS filings for any plan termination at least 30 days before the termination date; communicate the decision to acquired employees before close | T-24 | 2/6
Risk | RAID-015 | HR-020 | HR Due Diligence Complete | Benefits & Compensation Manager | Identify any defined benefit pension plans and obtain actuarial valuation and funded status | The PBGC may impose variable-rate premiums on underfunded plans and, in extreme cases, can assert lien rights against the acquirer | Open | Obtain a current actuarial valuation before close; confirm PBGC premium liability and unfunded status with the plan actuary; include pension liability indemnification in the SPA; notify PBGC of the acquisition within 30 days of close as required under ERISA Section 4062 | T-24 | 2/6
Risk | RAID-016 | HR-030 | HR Due Diligence Complete | Compensation Analyst | Assess golden parachute obligations and calculate 280G exposure for all covered employees | The acquirer and target must conduct a joint 280G calculation before close and either restructure payments or obtain shareholder approval for a 280G waiver — failure to plan results in a 20% excise tax on excess payments | Open | Complete the 280G calculation before signing and obtain a shareholder vote to waive the excise tax if feasible; engage executive compensation counsel to structure CIC payments to minimize 280G exposure; confirm the SPA has appropriate representations regarding 280G obligations | T-24 | 2/6
Risk | RAID-017 | HR-032 | HR Due Diligence Complete | Benefits & Compensation Manager | Assess COBRA administration obligations and identify any outstanding COBRA compliance issues | COBRA administration failures are one of the most common compliance findings in HR due diligence; each uncorrected COBRA violation can result in IRS penalties of $100 per day per qualified beneficiary, compounding from the date of the violation | Open | Establish a formal employee concerns process — a named HR Business Partner on call, a published triage decision tree (pay issue → Payroll, benefits question → Benefits, workplace concern → ER Manager), and a 24-hour response SLA; launch and test the process before the all-employee announcement so it is live when employees receive it | T-22 | 2/8
Risk | RAID-018 | HR-029 | HR Due Diligence Complete | HRIS & Systems Manager | Inventory all HR technology systems — HRIS, payroll, ATS, LMS, performance management, and learning and development platforms — across both entities | HRIS system incompatibility is the most common technical delay in HR integration; if the target's HRIS cannot be migrated into the acquirer's platform before Day 1, HR will be operating from two separate systems with manual reconciliation — the resulting payroll and reporting errors typically persist for 60–90 days | Open | Complete a full HRIS architecture assessment before close; identify all system integration points that must be operational on Day 1; assign a dedicated HRIS project manager to own the integration timeline; build a Day 1 contingency plan for any system that cannot be integrated before close | T-16 | 2/14
Risk | RAID-019 | HR-016 | HR Due Diligence Complete | Compensation Analyst | Review annual incentive plan design — eligibility, targets, metrics, funding mechanics | Annual incentive plan change-of-control provisions — particularly those with single-trigger acceleration or guaranteed bonus payments — create unbudgeted cash obligations at close | Open | Obtain all plan documents and model maximum CIC payout; engage compensation counsel to structure payouts to minimize 280G exposure; confirm the SPA has adequate representations and indemnification for undisclosed incentive plan obligations | T-14 | 2/16
Assumption | RAID-020 | HR-035 | Day 1 HR Readiness Confirmed | HR Technology Lead | The acquired company's HRIS data is clean, complete, and sufficiently structured to migrate to the combined entity's HRIS without a major data remediation project — it is assumed that employee records, compensation data, job codes, org structure, and benefits elections are accurate and will map cleanly to the acquirer's HRIS data model without requiring more than 20 hours of manual remediation per 100 employees | If the acquired company's HRIS data is materially incomplete or structured in a way that is incompatible with the acquirer's HRIS, the migration timeline extends significantly; this delays payroll integration, benefits enrollment confirmation, and the Day 1 employee portal launch — all of which are visible to employees and create negative Day 1 experiences if they fail | Active | HR Technology Lead to complete an HRIS data quality assessment at T-30 using a sample of 50 employee records; if data quality issues are found, immediately quantify the remediation scope and adjust the HRIS migration timeline accordingly; engage the HRIS vendor to assess whether automated field mapping tools can reduce manual remediation effort | T-6 | 2/24
Risk | RAID-021 | HR-044 | HR Due Diligence Complete | HR Compliance Manager | Review I-9 and work authorization compliance — assess audit exposure and identify remediation needs | USCIS fines range from $272 to $27,000 per violation for substantive errors, and undocumented employees who cannot be reverified must be separated | Open | Complete an I-9 audit for all acquired employees before close; remediate all substantive errors immediately; engage immigration counsel to assess work authorization exposure for any visa-sponsored employees; confirm HR is designated to handle any post-close USCIS audit | T-11 | 2/19
Risk | RAID-022 | HR-037 | HR Due Diligence Complete | Employee Relations Manager | Obtain and review all pending and threatened employment litigation — claims, charges, and settlements | Pending employment litigation that is not disclosed in due diligence is one of the most common post-close indemnity claims; confirm that the target's legal representation on litigation disclosure is accurate and that all matters — including threatened but unfiled claims — have been produced | Open | Require target management to provide a complete litigation schedule with counsel contact and estimated exposure for each matter; confirm legal reserve adequacy with target's outside counsel; include undisclosed litigation in rep and warranty insurance scope | T-10 | 2/20
Risk | RAID-023 | HR-038 | HR Due Diligence Complete | HR Compliance Manager | Review all EEOC charges, DOL investigations, and state labor agency actions — open and closed last 5 years | Legal must be briefed on all open EEOC matters before close and a response strategy must be in place — charges that reveal systemic pay equity or discrimination patterns can expand into class actions post-close | Open | Brief employment counsel on all open EEOC matters before close; ensure all investigation response deadlines are calendared and assigned to a named owner; include EEOC and DOL contingent liabilities in the rep and warranty insurance scope | T-10 | 2/20
Risk | RAID-024 | HR-045 | Day 1 HR Readiness Confirmed | Employee Relations Manager | Establish process for addressing employee issues and concerns during integration | An employee who raises a concern about pay, benefits, or treatment on Day 1 and receives no response within 24 hours will assume the worst — unresponsive HR during the first week is the single greatest driver of early voluntary attrition | Open | Establish a formal employee relations triage process before Day 1 — define who owns each category of concern (pay disputes → Payroll Manager, benefits questions → Benefits team, manager conduct → HR Business Partner), set response SLAs, and publish the process to all HR managers before the all-employee announcement | T-8 | 2/22
Risk | RAID-025 | HR-046 | Day 1 HR Readiness Confirmed | Employee Relations Manager | Set up dedicated HR integration inbox and hotline — tested and staffed before Day 1 | HR hotline must be tested with actual call volume simulation before Day 1; a hotline that connects to voicemail or routes to an unmonitored inbox on the highest-call-volume day of the integration destroys employee trust — staff with experienced HR generalists who have authority to give real answers, not read from scripts | Open | Test the HR hotline with simulated call volume at least 48 hours before Day 1; confirm IVR routing, hold times, and escalation paths are functioning; assign a primary and backup hotline manager for the first week post-close | T-8 | 2/22
Risk | RAID-026 | HR-047 | HR Due Diligence Complete | Compensation Analyst | Review deferred compensation plans and assess Section 409A compliance | Section 409A violations result in immediate income inclusion, a 20% excise tax, and interest penalties on all deferred compensation in the same plan; any modification to a deferred compensation plan after the acquisition — including extending payment dates or changing investment options — must be reviewed by outside tax counsel before implementation | Open | Engage executive compensation counsel to complete a 409A compliance review for all deferred compensation plans before close; if a violation is identified, assess eligibility for correction under IRS Notice 2010-6 — corrections must be made by December 31 of the year the violation is discovered; do not accelerate, delay, or modify any deferred compensation payment post-close without 409A counsel sign-off | T-7 | 2/23
Risk | RAID-027 | HR-035 | Day 1 HR Readiness Confirmed | HR Workstream Lead | Develop with Communications team the Day 1 announcement cascade plan — who communicates what, to whom, and in what order | All-employee announcement must be sequenced after regulatory clearance and before the press release; the timing of this task is a legal and communications dependency that cannot slip | Open | Complete the cascade plan at least 5 business days before the all-employee announcement; route through Legal, CHRO, and IMO for approval; confirm that manager briefings are scheduled 2 hours before the all-employee announcement and that managers have written talking points and escalation contacts | T-6 | 2/24
Dependency | RAID-028 | HR-009 | HR Due Diligence Complete | HR Business Partner | Assess retention risk of all senior leadership and key management positions | Retention risk assessment requires compensation data that is often restricted in the clean room; if full compensation data is unavailable pre-close, the assessment will be based on incomplete information — flag any missing comp data to Legal and request a carve-out for key individual compensation review | Open | Negotiate a clean room data sharing protocol with target management; limit access to deal team members with a defined need; use aggregate data where possible before close; complete the retention risk scoring matrix as early as clean room data permits so retention packages can be negotiated before close rather than after | T-5 | 2/25
Risk | RAID-029 | HR-050 | Day 1 Separations Communicated | HR Business Partner | Identify any acquired roles being eliminated on Day 1 and ensure separation packages are prepared and compliant | Any separation executed without Legal review creates wrongful termination exposure | Open | Require Legal review and written approval of every separation executed on or near Day 1; confirm WARN Act compliance for any group separations; provide each separated employee with a written separation agreement reviewed by employment counsel before any release is signed | T-5 | 2/25
Risk | RAID-030 | HR-036 | Day 1 HR Readiness Confirmed | HR Workstream Lead | Create employee-facing Day 1 FAQ document covering benefits, payroll, reporting lines, and key contacts for inclusion in M&A Employee Communication Guide | Day 1 FAQ document errors — incorrect plan names, wrong enrollment dates, inaccurate coverage amounts — generate a disproportionate volume of employee complaints and HR hotline calls; pilot the FAQ with five managers before Day 1 and require Legal and Benefits sign-off on every claim made in the document | Open | Route the Day 1 FAQ document through Legal, Benefits, and Payroll for fact-checking before distribution; require sign-off from the HR Workstream Lead before the FAQ is distributed; build a rapid-correction process — if an error is identified post-distribution, issue a correction within 2 hours | T-3 | 2/27
Risk | RAID-031 | HR-042 | Combined Payroll Live for All Employees | Payroll Manager | Prepare payroll tax IDs and state registration changes | An inactive state registration prevents payroll from being processed in that state and creates tax compliance violations | Open | Submit all state payroll tax registration applications at least 30 days before the first payroll run in each state; assign a named owner for each state registration; confirm registrations are active before processing any payroll in that jurisdiction | T-3 | 2/27
Risk | RAID-032 | HR-048 | Day 1 HR Readiness Confirmed | HR Compliance Manager | Prepare benefits summary card for acquired employees — coverage effective dates, carrier contacts, enrollment steps | Benefits summary card errors are the top driver of Day 1 HR hotline volume; employees make healthcare decisions based on this document — require Benefits, Legal, and CHRO sign-off before distribution | Open | Have the benefits summary card reviewed by the benefits broker, Legal, and HR before printing or distribution; confirm all plan names, dates, and enrollment contact information are accurate; build a rapid-correction process for Day 1 errors | T-3 | 2/27
Risk | RAID-033 | HR-053 | Interim Org Structure Announced | HR Workstream Lead | Determine interim org structure — combined entity reporting lines effective Day 1 | Any delay in confirming reporting lines creates a management vacuum that is filled by rumors — the interim structure should be documented and approved by the Steering Committee or Executive Sponsor before Day 1 | Open | Publish the interim org chart to all managers before the all-employee announcement; confirm every employee has a named manager in the interim structure; hold a manager briefing to walk through the interim reporting lines before the announcement goes out | T-3 | 2/27
Dependency | RAID-034 | HR-057 | Combined Payroll Live for All Employees | Payroll Manager | Confirm payroll funding accounts are established and first pay cycle for acquired employees is scheduled | Payroll funding account setup requires bank processing times of 7–10 business days; ACH authorization and payroll account registration must be initiated at least T-15 before the first payroll run — a funding account that is not active on payroll processing day results in a failed pay cycle with no quick fix | Open | Initiate payroll funding account setup at least 10 business days before the first pay cycle; confirm ACH routing and account numbers with the bank before the payroll processing date; run a test payment before the first live payroll cycle | T-3 | 2/27
Risk | RAID-035 | HR-058 | Day 1 HR Readiness Confirmed | HRIS & Systems Manager | Confirm access to company email, collaboration tools, and key HR systems for all acquired staff | Email and HR self-service portal access — are the most common source of employee frustration; IT must confirm provisioning for acquired employees at least 48 hours before Day 1 and HR must have a direct escalation path to IT's Day 1 war room | Open | Complete email and self-service portal access provisioning in the 48 hours before Day 1; test access for a representative sample of acquired employees before the all-employee announcement; assign IT a 4-hour SLA for access issues reported on Day 1 | T-3 | 2/27
Risk | RAID-036 | HR-D1 | Day 1 HR Readiness Confirmed | HR Workstream Lead | HR Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | Open | Conduct the HR Day 1 Readiness Gate review with CHRO and all HR workstream leads 48 hours before close; any incomplete task requires an immediate escalation decision — proceed with compensating control, delay specific activity, or pause close; document the gate decision with sign-offs | T-3 | 2/27

## Next 14 Days
HUMAN RESOURCES M&A NEXT 14 DAYS ACTIVITIES
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Milestones
Low | On Track | RAID Log
| Complete | Executive Dashboard
Task ID | Category | Phase | Assigned To | Description | Risk Level | Timing Anchor | Start | Finish | Status | Critical Path
HR-001 | Governance & Planning | Pre-Close | CHRO / HR Workstream Lead | Identify HR integration workstream lead and determine members of the HR integration team | High | T-59 | 1/2 | 1/10 | Not Started | CP – Close
HR-002 | Governance & Planning | Pre-Close | HR Workstream Lead | Review data privacy and confidentiality protocols for pre-close sharing | High | T-53 | 1/8 | 1/12 | Not Started
HR-003 | Integration Management | Pre-Close | HR Workstream Lead | Attend IMO Kickoff Meeting | Low | T-50 | 1/11 | 1/11 | Not Started
HR-004 | Governance & Planning | Pre-Close | HR Workstream Lead | Receive access to integration data room and document repository | Low | T-49 | 1/12 | 1/13 | Not Started
HR-005 | Governance & Planning | Pre-Close | HR Workstream Lead | Conduct HR Integration Kickoff Meeting | Low | T-49 | 1/12 | 1/12 | Not Started
HR-006 | Governance & Planning | Pre-Close | HR Workstream Lead | Develop the HR workstream integration charter and attend an IMO meeting to share charters with other teams; steering committee will approve charters | Low | T-49 | 1/12 | 1/19 | Not Started
HR-007 | Due Diligence | Pre-Close | HRIS & Systems Manager | Review organizational charts for all business units, functions, and geographies | High | T-49 | 1/12 | 1/30 | Not Started
HR-008 | Governance & Planning | Pre-Close | HR Workstream Lead | Define HR integration success metrics and KPIs | Low | T-49 | 1/12 | 1/19 | Not Started
HR-009 | Due Diligence | Pre-Close | HR Business Partner | Assess retention risk of all senior leadership and key management positions | High | T-49 | 1/12 | 2/25 | Not Started
HR-010 | Due Diligence | Pre-Close | HR Compliance Manager | Identify all contract workers, consultants, and temporary staff — terms, costs, and renewal dates | High | T-49 | 1/12 | 1/31 | Not Started
HR-011 | Due Diligence | Pre-Close | HR Business Partner | Obtain employee engagement survey results for last 2 years and assess culture and morale indicators | Medium | T-49 | 1/12 | 1/19 | Not Started
HR-012 | Due Diligence | Pre-Close | Compensation Analyst | Obtain complete headcount roster — names, titles, departments, locations, employment type, and start dates | Medium | T-47 | 1/14 | 1/16 | Not Started
HR-013 | Due Diligence | Pre-Close | Employee Relations Manager | Assess voluntary and involuntary turnover rates by level, function, and location | Medium | T-46 | 1/15 | 1/22 | Not Started
HR-014 | Compensation & Benefits | Pre-Close | Compensation Analyst | Assess compensation philosophy alignment | Medium | T-46 | 1/15 | 2/15 | Not Started

## Executive Dashboard
HUMAN RESOURCES M&A EXECUTIVE DASHBOARD
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
TASKS
|  | TOTAL TASKS |  | NOT STARTED |  | DELAYED |  | ON TRACK | COMPLETE
|  | 59 |  | 59 |  | 0 |  | 0 | 0
MILESTONES |  |  | PROGRESS BY PHASE | TASKS DONE/TASKS |  |  | RAID LOG |  | ANNUAL SYNERGIES
Not Started | 7 |  | Pre-Close | 0/59 |  |  | Open Risks | 29 | Targeted Synergies | $0K
Delayed | 0 | [5 empty] | Open Items | 33 | Realized Synergies | $0K
On Track | 0 | [5 empty] | Open Issues | 0 | Cost to Achieve Budget | $0K
Complete | 0 | [5 empty] | Dependencies | 4 | Actual CTA | $0K
CRITICAL PATH MILESTONES | [6 empty] | NEXT 14 DAYS |  | DAY 1 | TASKS DONE/TASKS
|  |  | Phase | Target Date | Status |  | Total | 14 | Day 1 Readiness | 0/17
HR Lead Appointed |  |  | Pre-Close | T-59 | 1/10 |  | On Critical Path | 1
HR Integration Governance Established |  |  | Pre-Close | T-49 | 1/19
HR Charter Approved |  |  | Pre-Close | T-49 | 1/19 |  | LINKS
Employee Handbook Prepared |  |  | Pre-Close (Day 1 Readiness) | T-28 | 2/25 |  | Integration Plan |  | Milestones
HR Due Diligence Complete |  |  | Pre-Close | T-15 | 2/27 |  | Next 14 Days |  | RAID Log
Day 1 HR Readiness Confirmed |  |  | Pre-Close (Day 1 Readiness) | T-3 | 2/27
Interim Org Structure Announced |  |  | Pre-Close (Day 1 Readiness) | T-11 | 2/27