## Slide 1: Integration Management Office (IMO) Roles & Responsibilities

## Slide 2: IMO Roles
1
2
3
4
5
6
Leader
Business Leads
Finance/Synergy/Communications Leads
Technology Lead
Program Manager
Communications Lead
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 3: IMO Leader
Overall accountability for successful delivery of the integration program
Accountable for benefits/synergy plan & realization
Owns the Integration Strategy and approach on behalf of the Steering Committee and Decision Executive(s)
Directs IMO activities
Sets pace of integration
Represents the IMO and integration program to the Steering Committee
Serves as Integration Advisor to Steering Committee
REPORTS TO
Decision Executives
DIRECTION FROM
Decision Executive(s)/ Steering Committee
PARTNERED WITH
Decision Executive(s) Operating Partners Finance Lead IMO Business Leads
INPUT FROM
IMO Leads
1
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 4: IMO Business Leads
REPORTS TO (INTEGRATION)
Decision Executive(s)
DIRECTION FROM
IMO Leader/Steering Committee
PARTNERED WITH
IMO Leader
Decision Executives
Function Workstream Leads
IMO Finance Lead
Operating Partner(s)
INPUT FROM
IMO Leads
Workstream Leads
Accountable for managing/maintaining benefits synergy realization plan
Serve as integration Co-Architects
Execute the integration for their respective businesses
Ensure business and customer impacts are negated/ minimized
Responsible for providing/ensuring resource commitments
Resolve resource and delivery issues
Act as integration strategy/plan champions
Serve as decision representatives for respective businesses
2
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 5: IMO Finance & Communications Leads
REPORTS TO (INTEGRATION)
IMO Leader
DIRECTION FROM
IMO Leader CFO/Operating Partner(s)
IMO Business Leads
PARTNERED WITH
IMO Leader
CFO/Operating Partner(s)
IMO Business Leads
IMO Communications
INPUT FROM
IMO Leads
Workstream Leads
3
Accountable for Integration/IMO budget, financials and reporting
Develops/manages/maintains organizational change processes and activities
Develops/manages/maintains IMO communications processes and activities
Synergy & communication plan champions
Overall responsibility to ensure program quality and compliance
Ensures integration program strategy, approach, and outcomes are in congruence with overall organizational transformation strategy
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 6: IMO Technology Lead
REPORTS TO (INTEGRATION)
Decision Executive(s)
DIRECTION FROM
IMO Leader
IMO Business Leads
Steering Committee
PARTNERED WITH
IMO Leader
IMO Business Leads
INPUT FROM
Workstream Leads
Integration Program
4
Accountable for overall technology integration strategy, plan and recommendations
Accountable for/owns all IT/product tools and processes
Accountable for all integrated business process automation/tools
Serves as Head of Technology security and compliance
Ensures delivery of all technology related/enabled workstreams
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 7: IMO Program Manager
REPORTS TO (INTEGRATION)
IMO Leader
DIRECTION FROM
IMO Leader
IMO Finance Lead
PARTNERED WITH
IMO Leader
IMO Finance Lead
INPUT FROM
Accountable for creating and maintaining overall integrated plan
Accountable for/owns all IMO project/program supporting/ enabling processes (scope, schedule, risk, cost, etc.)
Accountable for program/project status reporting
Leads IMO regular team meetings, stand-ups, ensures IMO internal delivery to plan
Accountable for/owns risk/issues and decisions register(s)
Ensures adherence to IMO program methodology, standards, processes and schedule
Manages all project managers, functional workstream delivery leads
Ensures overall delivery to plan
5
IMO Leads
Workstream Leads
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 8: IMO Communications Lead
REPORTS TO (INTEGRATION)
IMO Leader/IMO Communications
DIRECTION FROM
IMO Leader
IMO Business Leads
IMO Communications
INPUT FROM
6
Responsible for creation of all messaging and communications (internal/external) focused on announcement, day 1, and ongoing
Ensures communications requirements are identified and addressed
Serves as communications workstream lead and project manager
Workstream Leads
Integration Program Manager, IMO
PARTNERED WITH
IMO Communications Leader
IMO Business Leads
Integration Program Manager
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 9: thank you
contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting