## IMO Integration Plan
DAY 1 INTEGRATION MANAGEMENT OFFICE M&A PLAN (Also includes tasks preceding Day 1) | [13 empty] | Click on + sign (above the top row on right) to see synergy columns
TODAY'S DATE: T-0 (CLOSE)
Risk Level | Status | % Complete |  |  | Links
High | Not Started | 0% |  |  | Day 1 Checklist
Medium | Delayed | 25% |  |  | Milestones
Low | On Track | 50% |  |  | RAID Log (Includes Plan Assumptions)
| Complete | 75% |  |  | Executive Dashboard
100%
ID# | Category | Milestone | Phase | Assigned To | Task | Notes | Timing Anchor | Start | Finish | Status | Complete | Critical Path | Issues/Blockers | Risk Level | Team Dependency | Synergy Description | Synergy ($K) | Cost To Achieve ($K) | Synergy ($K) Realized | Actual Cost To Achieve ($K)
IMO-001 | Governance & Planning | Steering Committee Established | Pre-Close | C-Level Executives | Hold Steering Committee Kickoff meeting with board and executive leadership — align on deal rationale, integration priorities, and governance structure | Output should be documented and shared with all workstream leads at IMO kickoff; the executive team should begin integration strategy discussions before Steering Committee kickoff occurs | T-59 | 1/2 | 1/6 | Complete | 100% | CP – Close | If Steering Committee delays foundational decisions, the integration will be delayed and teams may begin planning without proper direction and as a consequence, prioritize the wrong initiatives | High | Legal, Finance, HR
IMO-002 | Governance & Planning | All Workstream Leads Appointed | Pre-Close | C-Level Executives | Identify Integration Leader of IMO and other members of core IMO team (i.e. admin, lead from Acquired Co.) | Must be appointed before integration kickoff; IMO Lead should be identified at or before LOI signing to allow pre-close planning | T-59 | 1/2 | 1/10 | Complete | 100% | CP – Close | If the IMO Lead is not named before LOI signing, pre-close planning stalls and workstream leads will operate without a single point of accountability — increasing the risk of misaligned priorities at kickoff | High | Board, Executive Sponsor
IMO-003 | Governance & Planning | All Workstream Leads Appointed | Pre-Close | IMO Leader | Identify IMO workstream leads for each functional area (i.e. HR, Finance, IT, Sales) | Workstream leads must be identified before integration kickoff; every week without a named lead delays planning for that functional area. | T-59 | 1/2 | 1/10 | Complete | 100% | CP – Close | Functional leaders pulling double duty on integration and BAU operations are a flight risk; losing a workstream lead mid-integration causes immediate coverage gaps and delays milestone delivery | High | HR, All Workstreams
IMO-004 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Establish governance structure (i.e. teams' hierarchy, escalation process, and decision rights— what gets resolved at IMO vs. steering committee vs. board) | Governance structure defines who can make which decisions without escalation | T-59 | 1/2 | 1/10 | Complete | 100% |  |  | Medium | All Workstreams
IMO-005 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Distribute data privacy and confidentiality protocols for pre-close sharing to workstream teams | Pre-close data sharing is subject to HSR clean room rules; any acquirer staff with access to target company competitively sensitive data must operate under formal clean room protocols; distribute protocols in writing and obtain written acknowledgment | T-53 | 1/8 | 1/12 | Complete | 100% |  | Any integration team member who accesses target's data without a formal clean room briefing puts the deal at regulatory risk; Legal must deliver the briefing and obtain written acknowledgment from each integration team member before data room access is granted | High | Legal, Compliance
IMO-006 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Hold IMO kickoff meeting with all workstream leads — align on value delivery, integration timeline, governance structure, and workstream interdependencies | Must happen before detailed planning begins to ensure teams operate in alignment, use common planning tools, and do not pursue conflicting or different agendas and goals | T-50 | 1/11 | 1/11 | Complete | 100% | CP – Close |  | Low | All Workstreams
IMO-007 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Stand up data room with workstream folders, templates, and document controls | Naming convention and version control should be established on Day 1 of data room setup; documents without clear versioning create confusion during reviews | T-49 | 1/12 | 1/13 | Complete | 100% |  |  | Low | IT, Legal
IMO-008 | Governance & Planning | IMO Charter Approved | Pre-Close | IMO Leader | Develop the IMO workstream integration charter and confirm team roles and responsibilities | Charter should define scope boundaries with each functional workstream — particularly HR (comp and org decisions), Finance (budget authority), and Legal (regulatory filings). Ambiguous scope boundaries are the most common source of cross-workstream conflict | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | All Workstreams
IMO-009 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Define IMO success metrics and KPIs | Establish metrics across four categories: reach (how many people received each communication and workstream update), completion rate (percentage of integration tasks completed on schedule vs. plan), issue resolution rate (percentage of RAID log items resolved within SLA), and stakeholder confidence (steering committee satisfaction with integration progress). All metrics require a pre-close baseline to be meaningful. Report metrics weekly to the steering committee and flag any KPI that falls below threshold for two consecutive weeks as requiring a formal recovery plan. | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | All Workstreams
IMO-010 | Governance & Planning | IMO Integration Governance Established | Pre-Close | Integration Coordinator | Coordinate with Finance to establish integration budget framework and spend tracking process across all workstreams | Budget approvals routed through IMO and Finance Integration budget should be tracked separately from operating budget; establish a cost code before any integration spend is incurred so actuals can be reported against the approved budget from Week 1 | T-48 | 1/13 | 1/19 | Complete | 100% |  |  | Low | Finance
IMO-011 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Develop IMO integration plan (tasks, milestones, RAID log, Day 1 checklist) and update status of plan weekly. | Integration plan is the IMO's operating document; it must be updated every Thursday so the Friday Executive Dashboard reflects current status, not last week's data | T-42 | 1/19 | 6/10 | On Track | 50% | CP – Close |  | Medium | All Workstreams
IMO-012 | Integration Management | Initial Risk Assessment Complete | Pre-Close | IMO Leader | Oversee pre-close integration risk assessment across all workstreams | Risk identification requires input from all workstream leads; a risk register built only by the IMO will miss the operational risks that functional teams see first | T-42 | 1/19 | 2/4 | Complete | 100% | CP – Close | Clean room constraints mean the risk assessment will reflect only publicly available and shared data — undisclosed liabilities or operational risks in the target may not surface until post-close, when mitigation options are narrower | High | Legal, Finance, All Workstreams
IMO-013 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | IMO facilitates ongoing weekly IMO meetings with all workstream leads — review RAG status, escalate blockers, and confirm milestone progress | Two-hour all-hands meeting; a two-hour format is sustainable only if the agenda is disciplined — 30 minutes workstream RAG status, 30 minutes cross-workstream dependencies, 30 minutes blockers requiring escalation, 30 minutes decisions and actions; pre-read distributed 24 hours in advance | T-42 | 1/19 | 6/10 | On Track | 50% |  | Low attendance or partial participation in the weekly all-hands erodes cross-workstream visibility; blocked dependencies get flagged too late, and workstream leads lose shared context on priorities | High | All Workstreams
IMO-014 | Integration Management | Initial Risk Assessment Complete | Pre-Close | IMO Leader | Ensure all cross-workstream dependencies are identified and logged | Cross-workstream dependencies are the IMO's highest-leverage focus area; a dependency that is not logged is a blocker that arrives without warning. Require workstream leads to submit new dependencies weekly | T-42 | 1/19 | 6/10 | On Track | 50% |  | Undocumented cross-workstream dependencies are the leading cause of surprise delays | High | All Workstreams
IMO-015 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Facilitate IMO steering committee meeting every two weeks covering RAG status review, risks escalations, decisions needed | Steering committee meets every two weeks; agenda covers: integration plan status, RAID log review, synergy tracking update, and any decisions requiring executive authority; meeting notes distributed within 24 hours with owners and deadlines for all decisions | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | All Workstreams
IMO-016 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Review and consolidate all workstream plans into master plan and report status weekly | Master plan should have one row per workstream with status, owner, risks; workstream plans that are too granular at the IMO level slow review and miss the signal in the noise. The IMO owns the summary; workstream leads own the detail | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Medium | All Workstreams
IMO-017 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Facilitate resolution of cross-workstream integration conflicts and blocked dependencies | Cross-workstream conflicts escalated to the IMO must be resolved within 48 hours; unresolved conflicts that sit in the RAID log without a decision owner become organizational drag. The IMO Lead should be the tie-breaker for most workstream disputes | T-42 | 1/19 | 6/10 | On Track | 50% |  | Cross-workstream conflicts left unresolved at the IMO level tend to escalate to the steering committee, consuming executive bandwidth on issues that should have been resolved earlier in the process | High | All Workstreams
IMO-018 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Consolidate RAID log weekly — close resolved items, escalate emerging risks | Workstreams report new items by Thursday RAID log is the most important risk management tool in the integration; currency matters more than completeness. A risk log with stale items gives false assurance | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | All Workstreams
IMO-019 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Consolidate Day 1 readiness checklists and ensure there are owners for each critical task | Any workstream with uncompleted critical tasks on the Day 1 checklist must escalate to the IMO for a waiver decision. | T-38 | 1/23 | 2/20 | Complete | 100% | CP – Day 1 Readiness | A Day 1 readiness checklist with unassigned tasks is not a readiness — unowned critical items will not get completed, and gaps will surface on Day 1 when there is no time to recover | High | All Workstreams
IMO-020 | Synergy Tracking & Realization | Synergy Tracking Established | Pre-Close | IMO Leader | Ensure all synergies are validated with an owner and have cost-to-achieve estimates before close | Synergy validation requires owner sign-off on baseline, target, and cost-to-achieve; unvalidated synergies reported to investors create legal exposure. The IMO is accountable for ensuring the Finance team has received confirmation from every synergy owner before synergies are communicated externally | T-35 | 1/26 | 6/10 | On Track | 50% |  | Synergies without confirmed owners will likely not be captured | High | Finance, All Workstreams
IMO-021 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Publish weekly Executive Dashboard (RAG by workstream, milestones, RAID summary) | Updates due every Thursday | T-35 | 1/26 | 6/10 | On Track | 50% |  |  | Low | Finance, All Workstreams
IMO-022 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Oversee Communications team's development of M&A Employee Communication Guide — review drafts and ensure alignment with master narrative | IMO reviews drafts before distribution; approves tone and timing alignment with overall integration narrative | T-31 | 1/30 | 2/27 | Complete | 100% |  |  | Medium | Communications, HR, Legal
IMO-023 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Oversee Sales team's development of M&A Customer Communication Guide — review drafts and ensure alignment with master narrative | IMO reviews customer-facing content for consistency with deal messaging | T-31 | 1/30 | 2/25 | Complete | 100% |  |  | Medium | Sales, Communications, Legal
IMO-024 | Synergy Tracking & Realization | Synergy Tracking Established | Pre-Close | Integration Coordinator | Coordinate with Finance to establish synergy tracking model — baseline, milestones, and reporting cadence | Link to Finance P&L model; report realized vs. projected monthly | T-26 | 2/4 | 2/15 | Complete | 100% |  |  | Medium | Finance
IMO-025 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Oversee development of workstream risk mitigation plans pre-close | Mitigation plans should be specific: owner, action, timeline, and success criterion. A mitigation plan that says 'monitor closely' is not a mitigation plan. IMO Lead should reject any mitigation that does not specify who does what by when | T-25 | 2/5 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Risk mitigation plans developed without complete due diligence data will have material gaps; risks identified post-close that were foreseeable pre-close reflect poorly on IMO and advisory team credibility | High | Legal, Finance, All Workstreams
IMO-026 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | Integration Coordinator | Circulate drafts of M&A Employee Communication Guide to workstreams for their input | Workstream leads have 48 hours to review and provide comments; IMO consolidates feedback for Comm Lead | T-20 | 2/10 | 2/27 | Complete | 100% |  |  | Medium | All Workstreams
IMO-027 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Confirm all integration vendor contracts and external support resources are in place for Day 1 | Third-party integration support agreements signed and mobilized | T-17 | 2/13 | 2/27 | Complete | 100% |  |  | Medium | Legal, Finance, IT
IMO-028 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Stand up Day 1 IMO war room — staffing, communication channels, escalation contacts, and incident log | War room open from 6 AM Day 1; IMO Lead on-site or remote bridge | T-10 | 2/20 | 2/25 | Complete | 100% | CP – Day 1 Readiness | If IT infrastructure for the war room is not confirmed at least 5 days before Day 1, the risk of a communication failure during the highest-pressure day of the integration is unacceptable | High | IT, All Workstreams
IMO-029 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Conduct Day 1 communications dry runs — test all Day 1 announcement channels, and verify distribution lists for press release, employee announcement, and customer communications | Dry run must simulate the actual Day 1 sequence in real time — not a checklist review; each channel owner must confirm their content is staged, access credentials are active, and distribution lists are accurate; any channel that fails the dry run must be remediated before T-3 | T-9 | 2/21 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A communications channel that has not been tested before Day 1 will fail at the worst possible moment — the press release cannot go out late, the employee announcement cannot be delayed, and a failed intranet post on Day 1 leaves employees with no source of truth; every untested channel is a Day 1 execution risk | High | Communications, IT, Legal
IMO-030 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | Integration Coordinator | Confirm M&A Customer Communication Guide has been distributed to all sales managers to prepare them for customer conversations | Confirm distribution covered all customer-facing reps and account managers | T-4 | 2/26 | 2/26 | Complete | 100% |  |  | Medium | Sales, Marketing
IMO-031 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | Integration Coordinator | Confirm M&A Employee Communication Guide has been distributed to all managers and people leaders before Day 1 | Confirm distribution list covered all employee-facing managers | T-3 | 2/27 | 2/27 | Complete | 100% |  |  | Medium | HR, Communications
IMO-D1 | Integration Management | Day 1 Readiness Confirmed — All Workstreams | Pre-Close (Day 1 Readiness) | IMO Leader | IMO Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | Workstream lead formally certifies Day 1 readiness to the IMO; this gate must be green for every workstream before the IMO signs off on close; any open item at this gate is either resolved or escalated to the steering committee as a close-blocking risk | T-3 | 2/27 | 2/27 | Complete | 100% | CP – Close | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | High | All Workstreams
IMO-032 | Integration Management | Day 1 / Week 1 IMO Integration Complete | Day 1 / Week 1 | IMO Leader | Activate Day 1 IMO war room — run all-workstream morning stand-up at 7 AM and confirm go-status | IMO Lead chairs 30-minute war-room stand-up; red issues escalated immediately | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% | CP – Close | A delayed or poorly run morning stand-up removes the only structured opportunity to identify and escalate Day 1 blockers before business hours; issues that surface after 9 AM have already impacted employees and customers | High | All Workstreams
IMO-033 | Integration Management | Day 1 / Week 1 IMO Integration Complete | Day 1 / Week 1 | IMO Leader | Monitor Day 1 task completion across all workstreams hourly and escalate any blocked items | IMO maintains live issue log throughout Day 1 | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% | CP – Close | Without hourly monitoring, a workstream issue that could be resolved in 30 minutes can compound into a multi-hour outage or a missed Day 1 commitment; real-time visibility is the only way to contain Day 1 risk | High | All Workstreams
IMO-034 | Integration Management | Day 1 / Week 1 IMO Integration Complete | Day 1 / Week 1 | IMO Leader | Conduct Day 1 end-of-day debrief with all workstream leads — captures immediate Day 1 issues and is early input to the Day 30 gate assessment | 4 PM debrief; close war room only after all critical issues resolved | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  |  | Low | All Workstreams
IMO-035 | Integration Management | Day 1 / Week 1 IMO Integration Complete | Day 1 / Week 1 | IMO Leader | Conduct Week 1 daily IMO stand-up (Mon–Fri) — 15 min, all workstream leads, RAG status and blockers only | Transition back to weekly cadence after Week 1 unless issues require daily check-in | Day 1 (Close) | 3/2 | 3/6 | On Track | 50% |  |  | Low | All Workstreams
IMO-036 | Integration Management | Day 1 / Week 1 IMO Integration Complete | Day 1 / Week 1 | IMO Leader | Resolve all Day 1 open issues and confirm all Critical Day 1 checklist items are complete | No open Critical items permitted past Day 1 without executive waiver | Day 1 (Close) | 3/2 | 3/6 | On Track | 50% | CP – Close | Any Critical item unresolved past Day 1 without formal executive waiver sets a precedent that deadlines are negotiable — eroding IMO authority and increasing the risk of similar slippage on future milestones | High | All Workstreams
IMO-037 | Integration Management | 30-Day Integration Review Complete | Day 1 / Week 1 | IMO Leader | Update RAID log with all Day 1 issues, blockers, and new risks surfaced during Day 1 execution — close resolved items, add new entries, and confirm each open item has a named owner and mitigation before the Week 1 status report is published | A RAID log that is not updated within 48 hours of Day 1 becomes stale before the Week 1 report is published; unlogged Day 1 issues that re-emerge at the Day 30 gate are the most common cause of credibility loss for the IMO — if the IMO did not capture it, leadership assumes the IMO did not know about it | T+2 | 3/4 | 3/4 | Not Started | 0% |  | If Day 1 issues are not logged by T+2 they will be buried under Week 1 activity and will surface without owners or mitigations at the Day 30 gate review | Low | All Workstreams
IMO-038 | Integration Management | Day 1 / Week 1 IMO Integration Complete | Day 1 / Week 1 | IMO Leader | Publish Week 1 IMO status report — task completion rates, milestone status, RAID summary | Week 1 status report establishes the format and cadence for the integration; get it right because workstream leads will anchor on the format going forward. Include: task completion rate, milestone status, RAID summary, integration budget update, and top three open issues | T+4 | 3/6 | 3/6 | Not Started | 0% |  |  | Low | All Workstreams
THE 100-DAY IMO PLAN IS LOCATED IN THE 100-DAY SECTION OF MANDAPLAYBOOK.COM

## Day 1 Checklist
IMO M&A DAY 1 / WEEK 1 CHECKLIST - Both Pre-Close (Day 1 Readiness) and Day 1/Week 1 Phases
TODAY'S DATE: T-0 (CLOSE)
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Milestones
Low | On Track | RAID Log
| Complete | Executive Dashboard
☐ Done | Task ID | Phase | Task Description | Assigned To | Risk Level | Timing Anchor | Start | Finish | Status | Milestone
☑ | IMO-019 | Pre-Close (Day 1 Readiness) | Consolidate Day 1 readiness checklists and ensure there are owners for each critical task | IMO Leader | High | T-38 | 1/23 | 2/20 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-023 | Pre-Close (Day 1 Readiness) | Oversee Sales team's development of M&A Customer Communication Guide — review drafts and ensure alignment with master narrative | IMO Leader | Medium | T-31 | 1/30 | 2/25 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-022 | Pre-Close (Day 1 Readiness) | Oversee Communications team's development of M&A Employee Communication Guide — review drafts and ensure alignment with master narrative | IMO Leader | Medium | T-31 | 1/30 | 2/27 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-025 | Pre-Close (Day 1 Readiness) | Oversee development of workstream risk mitigation plans pre-close | IMO Leader | High | T-25 | 2/5 | 2/27 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-026 | Pre-Close (Day 1 Readiness) | Circulate drafts of M&A Employee Communication Guide to workstreams for their input | Integration Coordinator | Medium | T-20 | 2/10 | 2/27 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-027 | Pre-Close (Day 1 Readiness) | Confirm all integration vendor contracts and external support resources are in place for Day 1 | IMO Leader | Medium | T-17 | 2/13 | 2/27 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-028 | Pre-Close (Day 1 Readiness) | Stand up Day 1 IMO war room — staffing, communication channels, escalation contacts, and incident log | IMO Leader | High | T-10 | 2/20 | 2/25 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-029 | Pre-Close (Day 1 Readiness) | Conduct Day 1 communications dry runs — test all Day 1 announcement channels, and verify distribution lists for press release, employee announcement, and customer communications | IMO Leader | High | T-9 | 2/21 | 2/27 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-030 | Pre-Close (Day 1 Readiness) | Confirm M&A Customer Communication Guide has been distributed to all sales managers to prepare them for customer conversations | Integration Coordinator | Medium | T-4 | 2/26 | 2/26 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-031 | Pre-Close (Day 1 Readiness) | Confirm M&A Employee Communication Guide has been distributed to all managers and people leaders before Day 1 | Integration Coordinator | Medium | T-3 | 2/27 | 2/27 | Complete | Day 1 IMO Readiness Confirmed
☑ | IMO-D1 | Pre-Close (Day 1 Readiness) | IMO Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | IMO Leader | High | T-3 | 2/27 | 2/27 | Complete | Day 1 Readiness Confirmed — All Workstreams
☑ | IMO-032 | Day 1 / Week 1 | Activate Day 1 IMO war room — run all-workstream morning stand-up at 7 AM and confirm go-status | IMO Leader | High | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IMO Integration Complete
☑ | IMO-033 | Day 1 / Week 1 | Monitor Day 1 task completion across all workstreams hourly and escalate any blocked items | IMO Leader | High | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IMO Integration Complete
☑ | IMO-034 | Day 1 / Week 1 | Conduct Day 1 end-of-day debrief with all workstream leads — captures immediate Day 1 issues and is early input to the Day 30 gate assessment | IMO Leader | Low | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IMO Integration Complete
☐ | IMO-035 | Day 1 / Week 1 | Conduct Week 1 daily IMO stand-up (Mon–Fri) — 15 min, all workstream leads, RAG status and blockers only | IMO Leader | Low | Day 1 (Close) | 3/2 | 3/6 | On Track | Day 1 / Week 1 IMO Integration Complete
☐ | IMO-036 | Day 1 / Week 1 | Resolve all Day 1 open issues and confirm all Critical Day 1 checklist items are complete | IMO Leader | High | Day 1 (Close) | 3/2 | 3/6 | On Track | Day 1 / Week 1 IMO Integration Complete
☐ | IMO-037 | Day 1 / Week 1 | Update RAID log with all Day 1 issues, blockers, and new risks surfaced during Day 1 execution — close resolved items, add new entries, and confirm each open item has a named owner and mitigation before the Week 1 status report is published | IMO Leader | Low | T+2 | 3/4 | 3/4 | Not Started | 30-Day Integration Review Complete
☐ | IMO-038 | Day 1 / Week 1 | Publish Week 1 IMO status report — task completion rates, milestone status, RAID summary | IMO Leader | Low | T+4 | 3/6 | 3/6 | Not Started | Day 1 / Week 1 IMO Integration Complete
☐
Note on J28: Aberger, Will:

## Milestones
IMO M&A MILESTONES
TODAY'S DATE: T-0 (CLOSE)
Status | Links
Not Started | Integration Plan
Delayed | Day 1 Checklist
On Track | RAID Log
Complete | Executive Dashboard
Milestone ID | Category | Phase | Assigned To | Milestone | Timing Anchor | Finish | Status | Critical Path
MS-001 | Governance & Planning | Pre-Close | C-Level Executives | Steering Committee Established | T-55 | 1/6 | Complete | CP – Close
MS-002 | Governance & Planning | Pre-Close | C-Level Executives | All Workstream Leads Appointed | T-51 | 1/10 | Complete | CP – Close
MS-003 | Governance & Planning | Pre-Close | IMO Leader | IMO Integration Governance Established | T-42 | 1/19 | Complete | CP – Close
MS-004 | Governance & Planning | Pre-Close | IMO Leader | IMO Charter Approved | T-49 | 1/19 | Complete | CP – Close
MS-005 | Governance & Planning | Pre-Close | IMO Leader | Initial Risk Assessment Complete | T-26 | 2/4 | Complete | CP – Close
MS-006 | Synergy Tracking | Pre-Close | IMO Leader | Synergy Tracking Established | T-26 | 2/15 | Complete
MS-007 | Integration Management | Pre-Close (Day 1 Readiness) | IMO Leader | Day 1 IMO Readiness Confirmed | T-3 | 2/27 | Complete | CP – Day 1 Readiness
MS-008 | Integration Management | Pre-Close (Day 1 Readiness) | IMO Leader | Day 1 Readiness Confirmed — All Workstreams | T-3 | 2/27 | Complete | CP – Close
MS-009 | Integration Management | Day 1 / Week 1 | IMO Leader | Day 1 / Week 1 IMO Integration Complete | T+4 | 3/6 | Not Started | CP – Close

## RAID Log
IMO M&A RAID LOG (RAID = Risks, Assumptions, Issues, Dependencies)
TODAY'S DATE: T-0 (CLOSE)
RAID Type | Status | Links
Risk | Open | Integration Plan
Issue | Closed | Day 1 Checklist
Dependency | Active | Milestones
Assumption | Validated | Executive Dashboard
RAID Type | RAID ID | Related Task ID | Milestone | Owner | Task Description | Issues/Blockers | Status | Mitigation/Action | Timing Anchor | Finish
Dependency | RAID-001 | IMO-001 | Steering Committee Established | C-Level Executives | Hold Steering Committee Kickoff meeting with board and executive leadership — align on deal rationale, integration priorities, and governance structure | If Steering Committee delays foundational decisions, the integration will be delayed and teams may begin planning without proper direction and as a consequence, prioritize the wrong initiatives | Closed | Schedule the Steering Committee kickoff within the first 5 days of the integration period and confirm attendance from all C-Level participants before sending invites — a kickoff that is postponed or attended by deputies signals organizational ambivalence about the deal and undermines the integration team's authority from day one; brief the CEO on the agenda and desired outcomes before the session | T-55 | 1/6
Assumption | RAID-002 | IMO-001 | Steering Committee Established | C-Level Executives | Executive Sponsor and C-Level Executives will be available, committed, and engaged in integration governance from T-60 through Day 100 | If executive sponsors are pulled into BAU priorities or competing strategic initiatives, steering committee attendance drops, decisions are deferred, and the integration team loses the authority needed to drive workstream compliance — the single greatest predictor of integration failure is executive disengagement in the first 30 days | Validated | Executive Sponsor to confirm availability for all Steering Committee meetings and IMO gate reviews at the integration kickoff; if an executive must miss a scheduled governance meeting, a deputy with full decision-making authority must be designated in advance — not the morning of the meeting; IMO Leader to escalate any pattern of executive absenteeism to the CEO within 48 hours | T-55 | 1/6
Risk | RAID-003 | IMO-002 | All Workstream Leads Appointed | C-Level Executives | Identify Integration Leader of IMO and other members of core IMO team (i.e. admin, lead from Acquired Co.) | If the IMO Lead is not named before LOI signing, pre-close planning stalls and workstream leads will operate without a single point of accountability — increasing the risk of misaligned priorities at kickoff | Closed | Escalate the IMO Leader appointment to the CEO and Executive Sponsor; the IMO Leader must be named, capacity-confirmed, and briefed before any integration activity begins — every day without a named IMO Leader is a day of uncoordinated workstream activity; if filled internally, confirm backfill for BAU responsibilities before the appointment is announced | T-51 | 1/10
Dependency | RAID-004 | IMO-003 | All Workstream Leads Appointed | IMO Leader | Identify IMO workstream leads for each functional area (i.e. HR, Finance, IT, Sales) | Functional leaders pulling double duty on integration and BAU operations are a flight risk; losing a workstream lead mid-integration causes immediate coverage gaps and delays milestone delivery | Closed | Require each functional lead to be identified, capacity-confirmed, and briefed before the IMO kickoff meeting — a workstream lead who attends kickoff without having cleared time for integration work will not deliver; engage HR to confirm capacity before appointments are announced; brief each workstream lead individually on their integration responsibilities before the group kickoff | T-51 | 1/10
Assumption | RAID-005 | IMO-002 | All Workstream Leads Appointed | C-Level Executives | All workstream leads will be named and capacity-confirmed by T-50, with backfill for BAU responsibilities arranged before their integration appointments are announced | A workstream lead who is appointed without confirmed capacity relief will default to BAU priorities under pressure — integration tasks will slip, milestone dates will be missed, and the IMO will absorb the coordination burden that should sit with each functional lead; workstream leads who do not have backfill confirmed are flight risks | Validated | IMO Leader to require written capacity confirmation from each workstream lead's functional executive before the appointment is announced; confirm backfill arrangements are in place within 5 days of each appointment; any workstream lead operating without backfill at T-40 must be escalated to the Executive Sponsor immediately | T-51 | 1/10
Risk | RAID-006 | IMO-005 | IMO Integration Governance Established | IMO Leader | Distribute data privacy and confidentiality protocols for pre-close sharing to workstream teams | Any integration team member who accesses target's data without a formal clean room briefing puts the deal at regulatory risk; Legal must deliver the briefing and obtain written acknowledgment from each integration team member before data room access is granted | Closed | Issue the data privacy and clean team protocol to every integration team member before any cross-company data is shared — not after; require each team member to sign an acknowledgment before receiving any target company data; Legal must specify exactly what data each team member can access and under what conditions; brief all workstream leads on the protocol at the IMO kickoff | T-51 | 1/12
Assumption | RAID-007 | IMO-005 | IMO Integration Governance Established | IMO Leader | All integration team members will operate within the clean room and data privacy protocols established at kickoff, and Legal will have issued and obtained written acknowledgment of confidentiality requirements before any cross-company data is shared | An integration team member who accesses target company data without a formal clean team briefing creates regulatory exposure that can delay or unwind the deal; a single protocol breach discovered during regulatory review is sufficient to trigger a formal inquiry; the risk is asymmetric — the cost of a breach far exceeds the cost of rigorous protocol enforcement | Validated | Legal to issue the clean room and confidentiality protocol to all integration team members before any cross-company data is accessed; require written acknowledgment from every team member before data room access is granted; IMO Leader to confirm with Legal that all acknowledgments are received before the data room is opened to the integration team | T-49 | 1/12
Risk | RAID-008 | IMO-012 | Initial Risk Assessment Complete | IMO Leader | Oversee pre-close integration risk assessment across all workstreams | Clean room constraints mean the risk assessment will reflect only publicly available and shared data — undisclosed liabilities or operational risks in the target may not surface until post-close, when mitigation options are narrower | Closed | Assign a named risk owner for every High-rated risk identified in the pre-close assessment; present the consolidated risk register to the Steering Committee before close for executive visibility | T-26 | 2/4
Assumption | RAID-009 | IMO-012 | Initial Risk Assessment Complete | IMO Leader | The pre-close risk assessment will surface all material integration risks across workstreams, and each workstream lead will provide an honest RAG status rather than defaulting to green to avoid scrutiny | Risk assessments that understate workstream risk give the Steering Committee false confidence and deprive the IMO of the information needed to allocate resources to the highest-risk areas; a workstream that enters Day 1 with unacknowledged red risks is more likely to fail than one that has surfaced and mitigated its risks pre-close | Validated | IMO Leader to review all workstream risk assessments before submission to the Steering Committee and challenge any workstream rated fully green without supporting evidence; establish a norm in the first IMO meeting that honest red status is rewarded, not penalized; require each workstream lead to identify at least one High-rated risk in their pre-close assessment | T-26 | 2/4
Risk | RAID-010 | IMO-019 | Day 1 IMO Readiness Confirmed | IMO Leader | Consolidate Day 1 readiness checklists and ensure there are owners for each critical task | A Day 1 readiness checklist with unassigned tasks is not a readiness — unowned critical items will not get completed, and gaps will surface on Day 1 when there is no time to recover | Closed | Require each workstream lead to submit their Day 1 readiness checklist to the IMO at least 10 days before close — not 24 hours before; IMO to review, consolidate, and publish the master Day 1 readiness status 5 days before close so there is time to resolve open items; any workstream with more than 3 unresolved High-risk Day 1 items at T-5 must brief the IMO Leader on their remediation plan | T-10 | 2/20
Assumption | RAID-011 | IMO-019 | Day 1 IMO Readiness Confirmed | IMO Leader | Close will occur on 3/2 as scheduled with no material delay, and all Day 1 readiness tasks across workstreams will be completed before the IMO Day 1 Readiness Gate at T-3 | If close is delayed, all staged Day 1 assets, system cutovers, and communications must be rescheduled; any delay beyond 2 weeks also risks staged content leaking before the combined entity is ready to operate publicly; a delay that is not communicated to workstream leads within 24 hours will result in premature execution of Day 1 tasks that cannot be reversed | Validated | IMO Leader to confirm close timeline with Legal and Executive Sponsor at T-15; any slip of more than 5 days triggers an immediate replanning session with all workstream leads within 24 hours; IMO to issue a revised Day 1 readiness timeline to all workstreams within 48 hours of any close delay announcement | T-10 | 2/20
Risk | RAID-012 | IMO-028 | Day 1 IMO Readiness Confirmed | IMO Leader | Stand up Day 1 IMO war room — staffing, communication channels, escalation contacts, and incident log | If IT infrastructure for the war room is not confirmed at least 5 days before Day 1, the risk of a communication failure during the highest-pressure day of the integration is unacceptable | Closed | Activate the war room at least 24 hours before close — not the morning of Day 1; confirm all communication channels, monitoring dashboards, and escalation paths are operational before the war room goes live; assign a named war room commander with authority to make real-time decisions without further approval; conduct a war room dry run at least 5 days before close | T-5 | 2/25
Risk | RAID-013 | IMO-025 | Day 1 IMO Readiness Confirmed | IMO Leader | Oversee development of workstream risk mitigation plans pre-close | Risk mitigation plans developed without complete due diligence data will have material gaps; risks identified post-close that were foreseeable pre-close reflect poorly on IMO and advisory team credibility | Closed | Require each workstream lead to submit a written risk mitigation plan for every High-rated risk in their workstream by T-15; IMO to review all mitigation plans and identify any cross-workstream risks that require a joint mitigation response | T-3 | 2/27
Risk | RAID-014 | IMO-029 | Day 1 IMO Readiness Confirmed | IMO Leader | Conduct Day 1 communications dry runs — test all Day 1 announcement channels, and verify distribution lists for press release, employee announcement, and customer communications | A communications channel that has not been tested before Day 1 will fail at the worst possible moment — the press release cannot go out late, the employee announcement cannot be delayed, and a failed intranet post on Day 1 leaves employees with no source of truth; every untested channel is a Day 1 execution risk | Closed | Require each channel owner (Communications, IT) to confirm their content is staged, access credentials are active, and distribution lists are accurate before the dry run begins; any channel that cannot be confirmed operational by T-5 must be escalated to the IMO Leader as a Day 1 close-blocking risk; build a manual fallback plan for each channel before the dry run | T-3 | 2/27
Risk | RAID-015 | IMO-D1 | Day 1 Readiness Confirmed — All Workstreams | IMO Leader | IMO Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | Closed | Conduct the IMO Day 1 Readiness Gate with IMO Leader and Executive Sponsor 48 hours before close; any gate item rated Red is a close blocker unless a specific compensating control is agreed by the Executive Sponsor; document every gate decision with sign-offs; assign a named owner and resolution deadline to every open item before the gate is approved | T-3 | 2/27
Risk | RAID-016 | IMO-032 | Day 1 / Week 1 IMO Integration Complete | IMO Leader | Activate Day 1 IMO war room — run all-workstream morning stand-up at 7 AM and confirm go-status | A delayed or poorly run morning stand-up removes the only structured opportunity to identify and escalate Day 1 blockers before business hours; issues that surface after 9 AM have already impacted employees and customers | Closed | Activate the war room at least 30 minutes before close time; confirm all workstream leads are at their stations or on the bridge line before activation; run a 5-minute all-workstream check-in at the start of each hour on Day 1; designate a deputy war room commander to maintain continuity if the primary commander needs to step away | Day 1 (Close) | 3/2
Dependency | RAID-017 | IMO-033 | Day 1 / Week 1 IMO Integration Complete | IMO Leader | Monitor Day 1 task completion across all workstreams hourly and escalate any blocked items | Without hourly monitoring, a workstream issue that could be resolved in 30 minutes can compound into a multi-hour outage or a missed Day 1 commitment; real-time visibility is the only way to contain Day 1 risk | Closed | Build a real-time Day 1 task completion dashboard visible to all workstream leads in the war room; require each workstream lead to update their task status hourly; any task that is Red by 2pm on Day 1 triggers an automatic escalation to the war room commander; conduct a mid-day all-workstream sync at noon to surface and resolve emerging issues | Day 1 (Close) | 3/2
Risk | RAID-018 | IMO-036 | Day 1 / Week 1 IMO Integration Complete | IMO Leader | Resolve all Day 1 open issues and confirm all Critical Day 1 checklist items are complete | Any Critical item unresolved past Day 1 without formal executive waiver sets a precedent that deadlines are negotiable — eroding IMO authority and increasing the risk of similar slippage on future milestones | Open | Publish the Day 1 open items log to all workstream leads within 2 hours of the end-of-day debrief; assign a named owner and a 24-hour resolution deadline to every open item; any High-risk open item that is not resolved within 24 hours escalates automatically to the Executive Sponsor; confirm all Critical Day 1 checklist items are closed before Day 2 begins | T+4 | 3/6
Dependency | RAID-020 | IMO-013 | IMO Integration Governance Established | IMO Leader | IMO facilitates ongoing weekly IMO meetings with all workstream leads — review RAG status, escalate blockers, and confirm milestone progress | Low attendance or partial participation in the weekly all-hands erodes cross-workstream visibility; blocked dependencies get flagged too late, and workstream leads lose shared context on priorities | Open | Establish the weekly meeting cadence in the second week of the integration and require attendance from all workstream leads — a workstream lead who misses two consecutive meetings without a deputy must be escalated to the IMO Leader immediately; document all decisions and action items within 24 hours of each meeting | T+100 | 6/10
Risk | RAID-021 | IMO-014 | Initial Risk Assessment Complete | IMO Leader | Ensure all cross-workstream dependencies are identified and logged | Undocumented cross-workstream dependencies are the leading cause of surprise delays | Open | Require each workstream lead to submit dependencies — identifying every cross-workstream input they need and every output they owe to other workstreams; any dependency that is at risk of missing its delivery date must be escalated to the IMO Leader within 48 hours | T+100 | 6/10
Risk | RAID-022 | IMO-017 | IMO Integration Governance Established | IMO Leader | Facilitate resolution of cross-workstream integration conflicts and blocked dependencies | Cross-workstream conflicts left unresolved at the IMO level tend to escalate to the steering committee, consuming executive bandwidth on issues that should have been resolved earlier in the process | Open | Establish a formal escalation path for cross-workstream conflicts before the integration begins — conflicts that are not resolved within 48 hours at the workstream lead level escalate to the IMO Leader; conflicts not resolved within 72 hours at the IMO Leader level escalate to the Executive Sponsor | T+100 | 6/10
Dependency | RAID-023 | IMO-020 | Synergy Tracking Established | IMO Leader | Ensure all synergies are validated on an ongoing basis with an owner and have cost-to-achieve estimates | Synergies without confirmed owners will likely not be captured | Open | Require each synergy owner to validate their synergy estimate, cost-to-achieve, and realization timeline — any synergy without a validated owner and CTA estimate at Day 30 should be removed from the synergy baseline until re-validated; present the synergy validation status to the Steering Committee at the monthly board report | T+100 | 6/10

## Executive Dashboard
TODAY'S DATE: T+30 (DAY 30 POST-CLOSE — 4/1/2026)
IMO M&A INTEGRATION EXECUTIVE DASHBOARD
TODAY'S DATE: T-0 (CLOSE)
TASKS
|  |  | TOTAL |  | NOT STARTED |  | DELAYED |  | ON TRACK | COMPLETE
|  |  | 39 |  | 2 |  | 0 |  | 11 | 26
| MILESTONES |  |  | PROGRESS BY PHASE TASKS DONE/TASKS |  |  |  | RAID LOG SUMMARY |  | SYNERGIES
| Not Started | 1 |  | Pre-Close |  | 23/32 |  | Total Items | 22 | Targeted Synergies | $0K
| Delayed | 0 |  | Day 1/Week 1 |  | 3/7 |  | Open Risks | 4 | Realized Synergies | $0K
| On Track | 0 | [5 empty] | Issues | 0 | CTA Budget | $0K
| Complete | 8 | [5 empty] | Dependencies | 5 | Actual CTA | $0K
[8 empty] | Assumptions | 5
| CRITICAL PATH MILESTONES | [6 empty] | NEXT 7 DAYS |  | DAY 1 | TASKS DONE/TASKS
|  |  |  | Phase | Target Date | Status |  | Total Tasks | 7 | Day 1 Readiness | 11/11
| Steering Committee Established |  |  | Pre-Close | 1/6 | Complete |  |  |  | Day 1 / Week 1 | 3/7
| All Workstream Leads Appointed |  |  | Pre-Close | 1/10 | Complete
| IMO Integration Governance Established |  |  | Pre-Close | 1/19 | Complete |  | LINKS
| Day 1 IMO Readiness Confirmed |  |  | Pre-Close | 2/27 | Complete |  | Integration Plan |  | Milestones
| Day 1 / Week 1 IMO Integration Complete |  |  | Day 1 (Close) | 3/6 | Complete |  | Day 1 Checklist |  | RAID Log