## IMO Integration Plan
PRE-CLOSE INTEGRATION MANAGEMENT OFFICE MERGER INTEGRATION PLAN | [13 empty] | Click on + sign (above the top row on right) to see synergy columns
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
Risk Level | Status | % Complete |  |  | Links
High | Not Started | 0% |  |  | Milestones
Medium | Delayed | 25% |  |  | RAID Log (Includes Plan Assumptions)
Low | On Track | 50% |  |  | Next 14 Days
| Complete | 75% |  |  | Executive Dashboard
100%
ID# | Category | Milestone | Phase | Assigned To | Task | Notes | Timing Anchor | Start | Finish | Status | Complete | Critical Path | Issues/Blockers | Risk Level | Team Dependency | Synergy Description | Synergy ($K) | Cost To Achieve ($K) | Synergy ($K) Realized | Actual Cost To Achieve ($K)
IMO-001 | Governance & Planning | Steering Committee Established | Pre-Close | C-Level Executives | Hold Steering Committee Kickoff meeting with board and executive leadership — align on deal rationale, integration priorities, and governance structure | Output should be documented and shared with all workstream leads at IMO kickoff; the executive team should begin integration strategy discussions before Steering Committee kickoff occurs | T-59 | 1/2 | 1/6 | Not Started | 0% | CP – Close | If Steering Committee delays foundational decisions, the integration will be delayed and teams may begin planning without proper direction and as a consequence, prioritize the wrong initiatives | High | Legal, Finance, HR
IMO-002 | Governance & Planning | All Workstream Leads Appointed | Pre-Close | C-Level Executives | Identify Integration Leader of IMO and other members of core IMO team (i.e. admin, lead from Acquired Co.) | Must be appointed before integration kickoff; IMO Lead should be identified at or before LOI signing to allow pre-close planning | T-59 | 1/2 | 1/10 | Not Started | 0% | CP – Close | If the IMO Lead is not named before LOI signing, pre-close planning stalls and workstream leads will operate without a single point of accountability — increasing the risk of misaligned priorities at kickoff | High | Board, Executive Sponsor
IMO-003 | Governance & Planning | All Workstream Leads Appointed | Pre-Close | IMO Leader | Identify IMO workstream leads for each functional area (i.e. HR, Finance, IT, Sales) | Workstream leads must be identified before integration kickoff; every week without a named lead delays planning for that functional area. | T-59 | 1/2 | 1/10 | Not Started | 0% | CP – Close | Functional leaders pulling double duty on integration and BAU operations are a flight risk; losing a workstream lead mid-integration causes immediate coverage gaps and delays milestone delivery | High | HR, All Workstreams
IMO-004 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Establish governance structure (i.e. teams' hierarchy, escalation process, and decision rights— what gets resolved at IMO vs. steering committee vs. board) | Governance structure defines who can make which decisions without escalation | T-59 | 1/2 | 1/10 | Not Started | 0% |  |  | Medium | All Workstreams
IMO-005 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Distribute data privacy and confidentiality protocols for pre-close sharing to workstream teams | Pre-close data sharing is subject to HSR clean room rules; any acquirer staff with access to target company competitively sensitive data must operate under formal clean room protocols; distribute protocols in writing and obtain written acknowledgment | T-53 | 1/8 | 1/12 | Not Started | 0% |  | Any integration team member who accesses target's data without a formal clean room briefing puts the deal at regulatory risk; Legal must deliver the briefing and obtain written acknowledgment from each integration team member before data room access is granted | High | Legal, Compliance
IMO-006 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Hold IMO kickoff meeting with all workstream leads — align on value delivery, integration timeline, governance structure, and workstream interdependencies | Must happen before detailed planning begins to ensure teams operate in alignment, use common planning tools, and do not pursue conflicting or different agendas and goals | T-50 | 1/11 | 1/11 | Not Started | 0% | CP – Close |  | Low | All Workstreams
IMO-007 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Stand up data room with workstream folders, templates, and document controls | Naming convention and version control should be established on Day 1 of data room setup; documents without clear versioning create confusion during reviews | T-49 | 1/12 | 1/13 | Not Started | 0% |  |  | Low | IT, Legal
IMO-008 | Governance & Planning | IMO Charter Approved | Pre-Close | IMO Leader | Develop the IMO workstream integration charter and confirm team roles and responsibilities | Charter should define scope boundaries with each functional workstream — particularly HR (comp and org decisions), Finance (budget authority), and Legal (regulatory filings). Ambiguous scope boundaries are the most common source of cross-workstream conflict | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Low | All Workstreams
IMO-009 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Define IMO success metrics and KPIs | Establish metrics across four categories: reach (how many people received each communication and workstream update), completion rate (percentage of integration tasks completed on schedule vs. plan), issue resolution rate (percentage of RAID log items resolved within SLA), and stakeholder confidence (steering committee satisfaction with integration progress). All metrics require a pre-close baseline to be meaningful. Report metrics weekly to the steering committee and flag any KPI that falls below threshold for two consecutive weeks as requiring a formal recovery plan. | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Low | All Workstreams
IMO-010 | Governance & Planning | IMO Integration Governance Established | Pre-Close | Integration Coordinator | Coordinate with Finance to establish integration budget framework and spend tracking process across all workstreams | Budget approvals routed through IMO and Finance Integration budget should be tracked separately from operating budget; establish a cost code before any integration spend is incurred so actuals can be reported against the approved budget from Week 1 | T-48 | 1/13 | 1/19 | Not Started | 0% |  |  | Low | Finance
IMO-011 | Governance & Planning | IMO Integration Governance Established | Pre-Close | IMO Leader | Develop IMO integration plan (tasks, milestones, RAID log, Day 1 checklist) and update status of plan weekly. | Integration plan is the IMO's operating document; it must be updated every Thursday so the Friday Executive Dashboard reflects current status, not last week's data | T-42 | 1/19 | 6/10 | Not Started | 0% | CP – Close |  | Medium | All Workstreams
IMO-012 | Integration Management | Initial Risk Assessment Complete | Pre-Close | IMO Leader | Oversee pre-close integration risk assessment across all workstreams | Risk identification requires input from all workstream leads; a risk register built only by the IMO will miss the operational risks that functional teams see first | T-42 | 1/19 | 2/4 | Not Started | 0% | CP – Close | Clean room constraints mean the risk assessment will reflect only publicly available and shared data — undisclosed liabilities or operational risks in the target may not surface until post-close, when mitigation options are narrower | High | Legal, Finance, All Workstreams
IMO-013 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | IMO facilitates ongoing weekly IMO meetings with all workstream leads — review RAG status, escalate blockers, and confirm milestone progress | Two-hour all-hands meeting; a two-hour format is sustainable only if the agenda is disciplined — 30 minutes workstream RAG status, 30 minutes cross-workstream dependencies, 30 minutes blockers requiring escalation, 30 minutes decisions and actions; pre-read distributed 24 hours in advance | T-42 | 1/19 | 6/10 | Not Started | 0% |  | Low attendance or partial participation in the weekly all-hands erodes cross-workstream visibility; blocked dependencies get flagged too late, and workstream leads lose shared context on priorities | High | All Workstreams
IMO-014 | Integration Management | Initial Risk Assessment Complete | Pre-Close | IMO Leader | Ensure all cross-workstream dependencies are identified and logged | Cross-workstream dependencies are the IMO's highest-leverage focus area; a dependency that is not logged is a blocker that arrives without warning. Require workstream leads to submit new dependencies weekly | T-42 | 1/19 | 6/10 | Not Started | 0% |  | Undocumented cross-workstream dependencies are the leading cause of surprise delays | High | All Workstreams
IMO-015 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Facilitate IMO steering committee meeting every two weeks covering RAG status review, risks escalations, decisions needed | Steering committee meets every two weeks; agenda covers: integration plan status, RAID log review, synergy tracking update, and any decisions requiring executive authority; meeting notes distributed within 24 hours with owners and deadlines for all decisions | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | All Workstreams
IMO-016 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Review and consolidate all workstream plans into master plan and report status weekly | Master plan should have one row per workstream with status, owner, risks; workstream plans that are too granular at the IMO level slow review and miss the signal in the noise. The IMO owns the summary; workstream leads own the detail | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Medium | All Workstreams
IMO-017 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Facilitate resolution of cross-workstream integration conflicts and blocked dependencies | Cross-workstream conflicts escalated to the IMO must be resolved within 48 hours; unresolved conflicts that sit in the RAID log without a decision owner become organizational drag. The IMO Lead should be the tie-breaker for most workstream disputes | T-42 | 1/19 | 6/10 | Not Started | 0% |  | Cross-workstream conflicts left unresolved at the IMO level tend to escalate to the steering committee, consuming executive bandwidth on issues that should have been resolved earlier in the process | High | All Workstreams
IMO-018 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Consolidate RAID log weekly — close resolved items, escalate emerging risks | Workstreams report new items by Thursday RAID log is the most important risk management tool in the integration; currency matters more than completeness. A risk log with stale items gives false assurance | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | All Workstreams
IMO-019 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Consolidate Day 1 readiness checklists and ensure there are owners for each critical task | Any workstream with uncompleted critical tasks on the Day 1 checklist must escalate to the IMO for a waiver decision. | T-38 | 1/23 | 2/20 | Not Started | 0% | CP – Day 1 Readiness | A Day 1 readiness checklist with unassigned tasks is not a readiness — unowned critical items will not get completed, and gaps will surface on Day 1 when there is no time to recover | High | All Workstreams
IMO-020 | Synergy Tracking & Realization | Synergy Tracking Established | Pre-Close | IMO Leader | Ensure all synergies are validated with an owner and have cost-to-achieve estimates before close | Synergy validation requires owner sign-off on baseline, target, and cost-to-achieve; unvalidated synergies reported to investors create legal exposure. The IMO is accountable for ensuring the Finance team has received confirmation from every synergy owner before synergies are communicated externally | T-35 | 1/26 | 6/10 | Not Started | 0% |  | Synergies without confirmed owners will likely not be captured | High | Finance, All Workstreams
IMO-021 | Integration Management | IMO Integration Governance Established | Pre-Close | IMO Leader | Publish weekly Executive Dashboard (RAG by workstream, milestones, RAID summary) | Updates due every Thursday | T-35 | 1/26 | 6/10 | Not Started | 0% |  |  | Low | Finance, All Workstreams
IMO-022 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Oversee Communications team's development of M&A Employee Communication Guide — review drafts and ensure alignment with master narrative | IMO reviews drafts before distribution; approves tone and timing alignment with overall integration narrative | T-31 | 1/30 | 2/27 | Not Started | 0% |  |  | Medium | Communications, HR, Legal
IMO-023 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Oversee Sales team's development of M&A Customer Communication Guide — review drafts and ensure alignment with master narrative | IMO reviews customer-facing content for consistency with deal messaging | T-31 | 1/30 | 2/25 | Not Started | 0% |  |  | Medium | Sales, Communications, Legal
IMO-024 | Synergy Tracking & Realization | Synergy Tracking Established | Pre-Close | Integration Coordinator | Coordinate with Finance to establish synergy tracking model — baseline, milestones, and reporting cadence | Link to Finance P&L model; report realized vs. projected monthly | T-26 | 2/4 | 2/15 | Not Started | 0% |  |  | Medium | Finance
IMO-025 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Oversee development of workstream risk mitigation plans pre-close | Mitigation plans should be specific: owner, action, timeline, and success criterion. A mitigation plan that says 'monitor closely' is not a mitigation plan. IMO Lead should reject any mitigation that does not specify who does what by when | T-25 | 2/5 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Risk mitigation plans developed without complete due diligence data will have material gaps; risks identified post-close that were foreseeable pre-close reflect poorly on IMO and advisory team credibility | High | Legal, Finance, All Workstreams
IMO-026 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | Integration Coordinator | Circulate drafts of M&A Employee Communication Guide to workstreams for their input | Workstream leads have 48 hours to review and provide comments; IMO consolidates feedback for Comm Lead | T-20 | 2/10 | 2/27 | Not Started | 0% |  |  | Medium | All Workstreams
IMO-027 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Confirm all integration vendor contracts and external support resources are in place for Day 1 | Third-party integration support agreements signed and mobilized | T-17 | 2/13 | 2/27 | Not Started | 0% |  |  | Medium | Legal, Finance, IT
IMO-028 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Stand up Day 1 IMO war room — staffing, communication channels, escalation contacts, and incident log | War room open from 6 AM Day 1; IMO Lead on-site or remote bridge | T-10 | 2/20 | 2/25 | Not Started | 0% | CP – Day 1 Readiness | If IT infrastructure for the war room is not confirmed at least 5 days before Day 1, the risk of a communication failure during the highest-pressure day of the integration is unacceptable | High | IT, All Workstreams
IMO-029 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | IMO Leader | Conduct Day 1 communications dry runs — test all Day 1 announcement channels, and verify distribution lists for press release, employee announcement, and customer communications | Dry run must simulate the actual Day 1 sequence in real time — not a checklist review; each channel owner must confirm their content is staged, access credentials are active, and distribution lists are accurate; any channel that fails the dry run must be remediated before T-3 | T-9 | 2/21 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | A communications channel that has not been tested before Day 1 will fail at the worst possible moment — the press release cannot go out late, the employee announcement cannot be delayed, and a failed intranet post on Day 1 leaves employees with no source of truth; every untested channel is a Day 1 execution risk | High | Communications, IT, Legal
IMO-030 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | Integration Coordinator | Confirm M&A Customer Communication Guide has been distributed to all sales managers to prepare them for customer conversations | Confirm distribution covered all customer-facing reps and account managers | T-4 | 2/26 | 2/26 | Not Started | 0% |  |  | Medium | Sales, Marketing
IMO-031 | Integration Management | Day 1 IMO Readiness Confirmed | Pre-Close (Day 1 Readiness) | Integration Coordinator | Confirm M&A Employee Communication Guide has been distributed to all managers and people leaders before Day 1 | Confirm distribution list covered all employee-facing managers | T-3 | 2/27 | 2/27 | Not Started | 0% |  |  | Medium | HR, Communications
IMO-D1 | Integration Management | Day 1 Readiness Confirmed — All Workstreams | Pre-Close (Day 1 Readiness) | IMO Leader | IMO Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | Workstream lead formally certifies Day 1 readiness to the IMO; this gate must be green for every workstream before the IMO signs off on close; any open item at this gate is either resolved or escalated to the steering committee as a close-blocking risk | T-3 | 2/27 | 2/27 | Not Started | 0% | CP – Close | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | High | All Workstreams
THE DAY 1 AND DAY 100 IMO PLANS ARE LOCATED IN THE DAY 1 AND DAY 100 SECTIONS OF MANDAPLAYBOOK.COM

## Milestones
IMO M&A MILESTONES
TODAY'S DATE: T-60
Status | Links
Not Started | Integration Plan
Delayed | RAID Log
On Track | Next 14 Days
Complete | Executive Dashboard
Milestone ID | Category | Phase | Assigned To | Milestone | Timing Anchor | Finish | Status | Critical Path
MS-001 | Governance & Planning | Pre-Close | C-Level Executives | Steering Committee Established | T-55 | 1/6 | Not Started | CP – Close
MS-002 | Governance & Planning | Pre-Close | C-Level Executives | All Workstream Leads Appointed | T-51 | 1/10 | Not Started | CP – Close
MS-003 | Governance & Planning | Pre-Close | IMO Leader | IMO Integration Governance Established | T-42 | 1/19 | Not Started | CP – Close
MS-004 | Governance & Planning | Pre-Close | IMO Leader | IMO Charter Approved | T-49 | 1/19 | Not Started | CP – Close
MS-005 | Governance & Planning | Pre-Close | IMO Leader | Initial Risk Assessment Complete | T-26 | 2/4 | Not Started | CP – Close
MS-006 | Synergy Tracking | Pre-Close | IMO Leader | Synergy Tracking Established | T-26 | 2/15 | Not Started
MS-007 | Integration Management | Pre-Close (Day 1 Readiness) | IMO Leader | Day 1 IMO Readiness Confirmed | T-3 | 2/27 | Not Started | CP – Day 1 Readiness
MS-008 | Integration Management | Pre-Close (Day 1 Readiness) | IMO Leader | Day 1 Readiness Confirmed — All Workstreams | T-3 | 2/27 | Not Started | CP – Close

## RAID Log
IMO M&A RAID LOG (RAID = Risks, Assumptions, Issues, Dependencies)
TODAY'S DATE: T-60
RAID Type | Status | Links
Risk | Open | Integration Plan
Issue | Closed | Milestones
Dependency | Active | Next 14 Days
Assumption | Validated | Executive Dashboard
RAID Type | RAID ID | Related Task ID | Milestone | Owner | Task Description | Issues/Blockers | Status | Mitigation/Action | Timing Anchor | Finish
Dependency | RAID-001 | IMO-001 | Steering Committee Established | C-Level Executives | Hold Steering Committee Kickoff meeting with board and executive leadership — align on deal rationale, integration priorities, and governance structure | If Steering Committee delays foundational decisions, the integration will be delayed and teams may begin planning without proper direction and as a consequence, prioritize the wrong initiatives | Open | Schedule the Steering Committee kickoff within the first 5 days of the integration period and confirm attendance from all C-Level participants before sending invites — a kickoff that is postponed or attended by deputies signals organizational ambivalence about the deal and undermines the integration team's authority from day one; brief the CEO on the agenda and desired outcomes before the session | T-55 | 1/6
Assumption | RAID-002 | IMO-001 | Steering Committee Established | C-Level Executives | Executive Sponsor and C-Level Executives will be available, committed, and engaged in integration governance from T-60 through Day 100 | If executive sponsors are pulled into BAU priorities or competing strategic initiatives, steering committee attendance drops, decisions are deferred, and the integration team loses the authority needed to drive workstream compliance — the single greatest predictor of integration failure is executive disengagement in the first 30 days | Active | Executive Sponsor to confirm availability for all Steering Committee meetings and IMO gate reviews at the integration kickoff; if an executive must miss a scheduled governance meeting, a deputy with full decision-making authority must be designated in advance — not the morning of the meeting; IMO Leader to escalate any pattern of executive absenteeism to the CEO within 48 hours | T-55 | 1/6
Risk | RAID-003 | IMO-002 | All Workstream Leads Appointed | C-Level Executives | Identify Integration Leader of IMO and other members of core IMO team (i.e. admin, lead from Acquired Co.) | If the IMO Lead is not named before LOI signing, pre-close planning stalls and workstream leads will operate without a single point of accountability — increasing the risk of misaligned priorities at kickoff | Open | Escalate the IMO Leader appointment to the CEO and Executive Sponsor; the IMO Leader must be named, capacity-confirmed, and briefed before any integration activity begins — every day without a named IMO Leader is a day of uncoordinated workstream activity; if filled internally, confirm backfill for BAU responsibilities before the appointment is announced | T-51 | 1/10
Dependency | RAID-004 | IMO-003 | All Workstream Leads Appointed | IMO Leader | Identify IMO workstream leads for each functional area (i.e. HR, Finance, IT, Sales) | Functional leaders pulling double duty on integration and BAU operations are a flight risk; losing a workstream lead mid-integration causes immediate coverage gaps and delays milestone delivery | Open | Require each functional lead to be identified, capacity-confirmed, and briefed before the IMO kickoff meeting — a workstream lead who attends kickoff without having cleared time for integration work will not deliver; engage HR to confirm capacity before appointments are announced; brief each workstream lead individually on their integration responsibilities before the group kickoff | T-51 | 1/10
Assumption | RAID-005 | IMO-002 | All Workstream Leads Appointed | C-Level Executives | All workstream leads will be named and capacity-confirmed by T-50, with backfill for BAU responsibilities arranged before their integration appointments are announced | A workstream lead who is appointed without confirmed capacity relief will default to BAU priorities under pressure — integration tasks will slip, milestone dates will be missed, and the IMO will absorb the coordination burden that should sit with each functional lead; workstream leads who do not have backfill confirmed are flight risks | Active | IMO Leader to require written capacity confirmation from each workstream lead's functional executive before the appointment is announced; confirm backfill arrangements are in place within 5 days of each appointment; any workstream lead operating without backfill at T-40 must be escalated to the Executive Sponsor immediately | T-51 | 1/10
Risk | RAID-006 | IMO-005 | IMO Integration Governance Established | IMO Leader | Distribute data privacy and confidentiality protocols for pre-close sharing to workstream teams | Any integration team member who accesses target's data without a formal clean room briefing puts the deal at regulatory risk; Legal must deliver the briefing and obtain written acknowledgment from each integration team member before data room access is granted | Open | Issue the data privacy and clean team protocol to every integration team member before any cross-company data is shared — not after; require each team member to sign an acknowledgment before receiving any target company data; Legal must specify exactly what data each team member can access and under what conditions; brief all workstream leads on the protocol at the IMO kickoff | T-51 | 1/12
Assumption | RAID-007 | IMO-005 | IMO Integration Governance Established | IMO Leader | All integration team members will operate within the clean room and data privacy protocols established at kickoff, and Legal will have issued and obtained written acknowledgment of confidentiality requirements before any cross-company data is shared | An integration team member who accesses target company data without a formal clean team briefing creates regulatory exposure that can delay or unwind the deal; a single protocol breach discovered during regulatory review is sufficient to trigger a formal inquiry; the risk is asymmetric — the cost of a breach far exceeds the cost of rigorous protocol enforcement | Active | Legal to issue the clean room and confidentiality protocol to all integration team members before any cross-company data is accessed; require written acknowledgment from every team member before data room access is granted; IMO Leader to confirm with Legal that all acknowledgments are received before the data room is opened to the integration team | T-49 | 1/12
Risk | RAID-008 | IMO-012 | Initial Risk Assessment Complete | IMO Leader | Oversee pre-close integration risk assessment across all workstreams | Clean room constraints mean the risk assessment will reflect only publicly available and shared data — undisclosed liabilities or operational risks in the target may not surface until post-close, when mitigation options are narrower | Open | Assign a named risk owner for every High-rated risk identified in the pre-close assessment; present the consolidated risk register to the Steering Committee before close for executive visibility | T-26 | 2/4
Assumption | RAID-009 | IMO-012 | Initial Risk Assessment Complete | IMO Leader | The pre-close risk assessment will surface all material integration risks across workstreams, and each workstream lead will provide an honest RAG status rather than defaulting to green to avoid scrutiny | Risk assessments that understate workstream risk give the Steering Committee false confidence and deprive the IMO of the information needed to allocate resources to the highest-risk areas; a workstream that enters Day 1 with unacknowledged red risks is more likely to fail than one that has surfaced and mitigated its risks pre-close | Active | IMO Leader to review all workstream risk assessments before submission to the Steering Committee and challenge any workstream rated fully green without supporting evidence; establish a norm in the first IMO meeting that honest red status is rewarded, not penalized; require each workstream lead to identify at least one High-rated risk in their pre-close assessment | T-26 | 2/4
Risk | RAID-010 | IMO-019 | Day 1 IMO Readiness Confirmed | IMO Leader | Consolidate Day 1 readiness checklists and ensure there are owners for each critical task | A Day 1 readiness checklist with unassigned tasks is not a readiness — unowned critical items will not get completed, and gaps will surface on Day 1 when there is no time to recover | Open | Require each workstream lead to submit their Day 1 readiness checklist to the IMO at least 10 days before close — not 24 hours before; IMO to review, consolidate, and publish the master Day 1 readiness status 5 days before close so there is time to resolve open items; any workstream with more than 3 unresolved High-risk Day 1 items at T-5 must brief the IMO Leader on their remediation plan | T-10 | 2/20
Assumption | RAID-011 | IMO-019 | Day 1 IMO Readiness Confirmed | IMO Leader | Close will occur on 3/2 as scheduled with no material delay, and all Day 1 readiness tasks across workstreams will be completed before the IMO Day 1 Readiness Gate at T-3 | If close is delayed, all staged Day 1 assets, system cutovers, and communications must be rescheduled; any delay beyond 2 weeks also risks staged content leaking before the combined entity is ready to operate publicly; a delay that is not communicated to workstream leads within 24 hours will result in premature execution of Day 1 tasks that cannot be reversed | Active | IMO Leader to confirm close timeline with Legal and Executive Sponsor at T-15; any slip of more than 5 days triggers an immediate replanning session with all workstream leads within 24 hours; IMO to issue a revised Day 1 readiness timeline to all workstreams within 48 hours of any close delay announcement | T-10 | 2/20
Risk | RAID-012 | IMO-028 | Day 1 IMO Readiness Confirmed | IMO Leader | Stand up Day 1 IMO war room — staffing, communication channels, escalation contacts, and incident log | If IT infrastructure for the war room is not confirmed at least 5 days before Day 1, the risk of a communication failure during the highest-pressure day of the integration is unacceptable | Open | Activate the war room at least 24 hours before close — not the morning of Day 1; confirm all communication channels, monitoring dashboards, and escalation paths are operational before the war room goes live; assign a named war room commander with authority to make real-time decisions without further approval; conduct a war room dry run at least 5 days before close | T-5 | 2/25
Risk | RAID-013 | IMO-025 | Day 1 IMO Readiness Confirmed | IMO Leader | Oversee development of workstream risk mitigation plans pre-close | Risk mitigation plans developed without complete due diligence data will have material gaps; risks identified post-close that were foreseeable pre-close reflect poorly on IMO and advisory team credibility | Open | Require each workstream lead to submit a written risk mitigation plan for every High-rated risk in their workstream by T-15; IMO to review all mitigation plans and identify any cross-workstream risks that require a joint mitigation response | T-3 | 2/27
Risk | RAID-014 | IMO-029 | Day 1 IMO Readiness Confirmed | IMO Leader | Conduct Day 1 communications dry runs — test all Day 1 announcement channels, and verify distribution lists for press release, employee announcement, and customer communications | A communications channel that has not been tested before Day 1 will fail at the worst possible moment — the press release cannot go out late, the employee announcement cannot be delayed, and a failed intranet post on Day 1 leaves employees with no source of truth; every untested channel is a Day 1 execution risk | Open | Require each channel owner (Communications, IT) to confirm their content is staged, access credentials are active, and distribution lists are accurate before the dry run begins; any channel that cannot be confirmed operational by T-5 must be escalated to the IMO Leader as a Day 1 close-blocking risk; build a manual fallback plan for each channel before the dry run | T-3 | 2/27
Risk | RAID-015 | IMO-D1 | Day 1 Readiness Confirmed — All Workstreams | IMO Leader | IMO Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | Open | Conduct the IMO Day 1 Readiness Gate with IMO Leader and Executive Sponsor 48 hours before close; any gate item rated Red is a close blocker unless a specific compensating control is agreed by the Executive Sponsor; document every gate decision with sign-offs; assign a named owner and resolution deadline to every open item before the gate is approved | T-3 | 2/27

## Next 14 Days
IMO M&A NEXT 14 DAYS ACTIVITIES
TODAY'S DATE: T-60
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Milestones
Low | On Track | RAID Log
| Complete | Executive Dashboard
Task ID | Category | Phase | Assigned To | Description | Risk Level | Timing Anchor | Start | Finish | Status | Critical Path
IMO-001 | Governance & Planning | Pre-Close | C-Level Executives | Hold Steering Committee Kickoff meeting with board and executive leadership — align on deal rationale, integration priorities, and governance structure | High | T-59 | 1/2 | 1/6 | Not Started | CP – Close
IMO-002 | Governance & Planning | Pre-Close | C-Level Executives | Identify Integration Leader of IMO and other members of core IMO team (i.e. admin, lead from Acquired Co.) | High | T-59 | 1/2 | 1/10 | Not Started | CP – Close
IMO-003 | Governance & Planning | Pre-Close | IMO Leader | Identify IMO workstream leads for each functional area (i.e. HR, Finance, IT, Sales) | High | T-59 | 1/2 | 1/10 | Not Started | CP – Close
IMO-004 | Governance & Planning | Pre-Close | IMO Leader | Establish governance structure (i.e. teams' hierarchy, escalation process, and decision rights— what gets resolved at IMO vs. steering committee vs. board) | Medium | T-59 | 1/2 | 1/10 | Not Started
IMO-005 | Governance & Planning | Pre-Close | IMO Leader | Distribute data privacy and confidentiality protocols for pre-close sharing to workstream teams | High | T-53 | 1/8 | 1/12 | Not Started
IMO-006 | Governance & Planning | Pre-Close | IMO Leader | Hold IMO kickoff meeting with all workstream leads — align on value delivery, integration timeline, governance structure, and workstream interdependencies | Low | T-50 | 1/11 | 1/11 | Not Started | CP – Close
IMO-007 | Governance & Planning | Pre-Close | IMO Leader | Stand up data room with workstream folders, templates, and document controls | Low | T-49 | 1/12 | 1/13 | Not Started
IMO-008 | Governance & Planning | Pre-Close | IMO Leader | Develop the IMO workstream integration charter and confirm team roles and responsibilities | Low | T-49 | 1/12 | 1/19 | Not Started
IMO-009 | Governance & Planning | Pre-Close | IMO Leader | Define IMO success metrics and KPIs | Low | T-49 | 1/12 | 1/19 | Not Started
IMO-010 | Governance & Planning | Pre-Close | Integration Coordinator | Coordinate with Finance to establish integration budget framework and spend tracking process across all workstreams | Low | T-48 | 1/13 | 1/19 | Not Started

## Executive Dashboard
p
IMO M&A INTEGRATION EXECUTIVE DASHBOARD
TODAY'S DATE: T-60
TASKS
|  |  | TOTAL |  | NOT STARTED |  | DELAYED |  | ON TRACK | COMPLETE
|  |  | 32 |  | 32 |  | 0 |  | 0 | 0
| MILESTONES |  |  | PROGRESS BY PHASE TASKS DONE/TASKS |  |  |  | RAID LOG SUMMARY |  | SYNERGIES
| Not Started | 8 |  | Pre-Close |  | 0/32 |  | Total Items | 15 | Targeted Synergies | $0K
| Delayed | 0 | [5 empty] | Open Risks | 8 | Realized Synergies | $0K
| On Track | 0 | [5 empty] | Issues | 0 | CTA Budget | $0K
| Complete | 0 | [5 empty] | Dependencies | 2 | Actual CTA | $0K
[8 empty] | Assumptions | 5
| CRITICAL PATH MILESTONES | [6 empty] | NEXT 14 DAYS |  | DAY 1
|  |  |  | Phase | Target Date | Status |  | Total Tasks | 10 | Day 1 Readiness | 0/11
| Steering Committee Established |  |  | Pre-Close | 1/6 | Not Started |  | On Critical Path | 4
| All Workstream Leads Appointed |  |  | Pre-Close | 1/10 | Not Started
| IMO Integration Governance Established |  |  | Pre-Close | 1/19 | Not Started |  | LINKS
| Day 1 IMO Readiness Confirmed |  |  | Pre-Close | 2/27 | Not Started |  | Integration Plan |  | Milestones
[8 empty] | Next 14 Days |  | RAID Log