## IT Integration Plan
DAY 1 INFORMATION TECHNOLOGY M&A PLAN | [8 empty] | INFORMATION TECHNOLOGY DAY 1 POST-MERGER INTEGRATION PLAN | INFORMATION TECHNOLOGY DAY 1 POST-MERGER INTEGRATION PLAN | INFORMATION TECHNOLOGY DAY 1 POST-MERGER INTEGRATION PLAN | INFORMATION TECHNOLOGY DAY 1 POST-MERGER INTEGRATION PLAN | INFORMATION TECHNOLOGY DAY 1 POST-MERGER INTEGRATION PLAN | Click on + sign (above the top row on right) to see synergy columns
TODAY'S DATE: T-0 (DAY OF CLOSE)
Risk Level | Status | % Complete |  |  | Links
High | Not Started | 0% |  |  | Day 1 Checklist
Medium | Delayed | 25% |  |  | Milestones
Low | On Track | 50% |  |  | RAID Log (Includes Plan Assumptions)
| Complete | 75% |  |  | Executive Dashboard
100%
ID# | Category | Milestone | Phase | Assigned To | Task | Notes | Timing Anchor | Start | Finish | Status | Complete | Critical Path | Issues/Blockers | Risk Level | Team Dependency | Synergy Description | Synergy ($K) | Cost To Achieve ($K) | Synergy ($K) Realized | Actual Cost To Achieve ($K)
IT-001 | Governance & Planning | IT Lead Appointed | Pre-Close | IT Workstream Lead | Identify IT integration workstream lead and determine members of the IT integration team | Lead must be appointed before integration kickoff; IT Lead is the single accountable owner for all IT deliverables — without this role filled, every downstream task lacks an owner; prioritize people with relationships in both legacy IT orgs; integration requires trust across teams that may be unfamiliar with each other's environments and working styles | T-59 | 1/2 | 1/10 | Complete | 100% | CP – Close | IT workstream lead must be identified and available before integration kickoff; without a named IT Lead, there is no accountable owner for systems assessment, Day 1 readiness, or the ERP and HRIS integration workstreams — every IT integration dependency stalls without this role in seat | High | HR, IMO
IT-002 | Governance & Planning | IT Integration Governance Established | Pre-Close | Cybersecurity & Compliance Lead | Review data privacy and confidentiality protocols for pre-close sharing | Pre-close data sharing is subject to HSR clean room rules; any IT staff with access to target company systems or data must be briefed on what they can and cannot do — violations carry regulatory and legal consequences | T-53 | 1/8 | 1/12 | Complete | 100% |  | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | High | Legal, Compliance
IT-003 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Workstream Lead | Review IT organizational structure and headcount | Flag IT headcount with specialized skills that are not duplicated in the acquirer's team; losing these individuals before knowledge transfer is complete creates irreversible gaps | T-51 | 1/10 | 1/23 | Complete | 100% |  |  | Medium | HR | IT headcount rationalization — combining two IT organizations eliminates overlapping specialist roles | 200 | 60
IT-004 | Integration Management | IT Integration Governance Established | Pre-Close | IT Workstream Lead | Attend IMO Kickoff Meeting | Bring a written IT workstream summary; use kickoff to surface cross-workstream dependencies with Comms, HR, Finance, and Sales that will require IT support | T-50 | 1/11 | 1/11 | Complete | 100% |  |  | Low | IMO
IT-005 | Governance & Planning | IT Integration Governance Established | Pre-Close | Applications & Digital Workplace Lead | Receive access to integration data room and IT workstream templates and document repository | Establish version control and access permissions from day one; document naming conventions early — a disorganized data room becomes a bottleneck as artifact volume grows | T-49 | 1/12 | 1/13 | Complete | 100% |  |  | Low | Legal
IT-006 | Governance & Planning | IT Integration Governance Established | Pre-Close | IT Workstream Lead | Hold IT Integration Kickoff Meeting | Agenda should cover: RACI confirmation, Day 1 critical path, clean room constraints, and priorities for the first 30 days; distribute agenda 24 hours in advance | T-49 | 1/12 | 1/12 | Complete | 100% |  |  | Low | IMO
IT-007 | Governance & Planning | IT Integration Governance Established | Pre-Close | IT Workstream Lead | Define IT integration success metrics and KPIs | KPIs should include: Day 1 system uptime, employee login success rate, service desk ticket volume, application rationalization progress, and synergy realization vs. plan | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | IMO
IT-008 | Governance & Planning | IT Charter Approved | Pre-Close | IT Workstream Lead | Develop the IT workstream integration charter and confirm team roles and responsibilities | Charter must define the boundary between IT workstream and Finance (ERP ownership), HR (HRIS ownership), and Sales (CRM ownership) — overlapping ownership of enterprise systems is the most common IT integration conflict | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | IMO
IT-009 | Due Diligence | IT Due Diligence Complete | Pre-Close | Infrastructure & Cloud Lead | Assess network topology, connectivity, and bandwidth capacity | Network topology assessment determines latency, redundancy, and bandwidth constraints for all Day 1 connectivity tasks; gaps discovered post-close require expensive emergency procurement | T-49 | 1/12 | 1/23 | Complete | 100% |  | If the target restricts network topology data in the clean room, IT will be designing Day 1 connectivity based on assumptions rather than engineering data — require Legal to explicitly scope network architecture documentation into the data room access agreement before signing | High | Finance
IT-010 | Due Diligence | IT Due Diligence Complete | Pre-Close | Infrastructure & Cloud Lead | Inventory hardware assets, data centers, and hosting arrangements | Include end-of-life dates for all hardware; assets past end-of-support on Day 1 create security and compliance risk that must be remediated before the combined environment is certified | T-49 | 1/12 | 1/30 | Complete | 100% |  |  | Medium | Finance
IT-011 | Due Diligence | IT Due Diligence Complete | Pre-Close | Applications & Digital Workplace Lead | Inventory all enterprise applications and SaaS subscriptions | Capture contract expiry dates, per-seat pricing, and change-of-control clauses for every application; overlapping SaaS subscriptions are typically the fastest IT cost synergy to realize | T-49 | 1/12 | 1/30 | Complete | 100% |  | An incomplete SaaS inventory means the combined entity will continue paying for duplicate subscriptions it cannot see; require the target's procurement team to provide a complete software spend report with contract terms as a condition of data room access, not as a follow-up request | High | Legal, Procurement
IT-012 | Due Diligence | IT Due Diligence Complete | Pre-Close | Applications & Digital Workplace Lead | Assess core business systems compatibility | Focus on systems that must interoperate on Day 1: email, directory services, VPN, payroll, and finance; incompatible authentication protocols are the most common Day 1 blocker | T-49 | 1/12 | 2/26 | Complete | 100% |  | The highest-consequence incompatibility is authentication — if the two companies cannot federate identity on Day 1, every employee login fails; require IT to complete a protocol-level compatibility test (not just a platform inventory) and document a Day 1 workaround for any gap found before the go/no-go review | High | Finance
IT-013 | Governance & Planning | IT Integration Plan Locked | Pre-Close | IT Workstream Lead | Develop IT integration plan (tasks, milestones, RAID log, Day 1 checklist) | IT integration plan is the operating document for the entire workstream; update weekly, share with IMO coordinator by Thursday, and treat stale tasks as a red flag. Plan of record will be at 3/31. Significant plan changes subsequent to that date must go through formal change approval process. | T-49 | 1/12 | 3/31 | On Track | 50% |  |  | Medium | IMO
IT-014 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review data architecture, databases, and data governance maturity | Data architecture gaps — undocumented schemas, shadow databases, manual data feeds — are the leading cause of post-close data integration failures; document every data flow, not just primary systems | T-48 | 1/13 | 1/30 | Complete | 100% |  | Undocumented data flows become a data migration failure when the integration team discovers mid-migration that a critical downstream report relies on a manual feed no one knew existed; require target IT to attest in writing that the data architecture review is complete before DD sign-off | High | Legal
IT-015 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review cloud platform usage (AWS, Azure, GCP) and cloud cost structure | Cloud cost management maturity varies widely; target companies often have unoptimized reserved instance coverage, orphaned resources, and unused licenses that represent immediate savings | T-48 | 1/13 | 2/6 | Complete | 100% |  |  | Medium | Finance
IT-016 | Due Diligence | IT Due Diligence Complete | Pre-Close | Cybersecurity & Compliance Lead | Review data privacy program (GDPR, CCPA, HIPAA) and compliance gaps | If target operates under HIPAA, GDPR, or CCPA, the acquirer inherits compliance obligations on Day 1; gaps in target's privacy program must be remediated before close or the acquirer assumes undisclosed regulatory risk | T-48 | 1/13 | 2/13 | Complete | 100% |  | Compliance gaps inherited at close cannot be disclaimed after the fact; if the target has an active HIPAA or GDPR deficiency, the acquirer must either remediate before close, escrow funds for post-close remediation, or factor the penalty exposure into the purchase price — this is a deal-term issue, not just an IT task | High | Legal, Compliance
IT-017 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review IT vendor contracts, licenses, and software agreements | Change-of-control clauses in enterprise software agreements can trigger immediate price renegotiation or license termination; identify affected vendors at least 30 days before close to allow renegotiation | T-48 | 1/13 | 2/25 | Complete | 100% |  | Vendor change-of-control clauses are triggered at close, not when IT discovers them; if these agreements are not mapped before signing, the combined entity may face license suspension or emergency renegotiation from a position of weakness on Day 1 — Legal must complete the vendor contract review before the SPA is executed | High | Legal, Procurement
IT-018 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Estimate future IT spend and total cost of ownership | Build the TCO model on a per-system basis so rationalization decisions have a financial baseline; blended IT cost estimates obscure which investments are worth retaining | T-48 | 1/13 | 2/25 | Complete | 100% |  |  | Medium | Finance
IT-019 | Due Diligence | IT Due Diligence Complete | Pre-Close | Cybersecurity & Compliance Lead | Review IT compliance certifications (SOC 2, ISO 27001, PCI-DSS) | SOC 2 and ISO 27001 certifications have defined audit scopes; confirm whether the combined entity's certification will require re-scoping and what the timeline and cost implications are | T-47 | 1/14 | 2/13 | Complete | 100% |  | Customers with contractual requirements for SOC 2 compliance will ask whether the combined entity's certification covers them; if the answer is unknown at Day 1, those customers will escalate — confirm the new audit scope with the certifying auditor before close and communicate the timeline to affected customers before the press release goes out | High | Legal, Compliance
IT-020 | Systems & Technology | Systems Integration Complete | Pre-Close | Applications & Digital Workplace Lead | Develop application and SaaS rationalization strategy and portfolio roadmap | Rationalization strategy should produce a three-category output: keep (run on combined platform), migrate (move to surviving system), retire (decommission with data archive); all other decisions are downstream of this | T-47 | 1/14 | 2/27 | Complete | 100% |  | The rationalization strategy is only as good as the inventory it is built on; if application inventory is delayed or incomplete, every 'retire' decision in this strategy risks decommissioning a system that is still in active use — do not present this strategy to leadership until the full inventory has been independently verified | High | Finance, IMO
IT-021 | Systems & Technology | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Assess SDLC maturity and software delivery practices of target | SDLC maturity assessment output determines whether combined engineering teams can collaborate safely from Day 1 or need a transition period with separate release cycles | T-45 | 1/16 | 2/23 | Complete | 100% |  |  | Low | Engineering
IT-022 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | IT Integration Coordinator | Estimate initial IT cost synergies (licenses, infra, headcount) | Synergy estimates must distinguish between one-time savings (decommission costs avoided) and recurring run-rate savings (license reduction, headcount, infrastructure); investors care about run-rate | T-45 | 1/16 | 2/26 | Complete | 100% |  |  | Medium | Finance, Procurement
IT-023 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | Applications & Digital Workplace Lead | Develop IT integration cost-to-achieve (CTA) budget | CTA budget must include: migration tooling, parallel-run infrastructure, consulting fees, employee training, and severance for redundant IT roles — understating CTA is the most common IT integration budget failure | T-45 | 1/16 | 2/26 | Complete | 100% |  |  | Medium | Finance
IT-024 | IT Infrastructure | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Cybersecurity & Compliance Lead | Assess and remediate critical vulnerability findings | Remediation must be complete before Day 1; acquiring a company with unpatched critical vulnerabilities transfers full legal liability to the acquirer — prioritize by CVSS score and customer data exposure | T-44 | 1/17 | 2/27 | Complete | 100% | CP – Day 1 Readiness | The acquirer cannot assert it was unaware of inherited vulnerabilities after close; any CVSS 9.0+ finding identified in diligence that is not remediated before Day 1 must be formally accepted with a documented risk treatment plan signed by the CISO — undocumented acceptance is not acceptance | High | Cybersecurity
IT-025 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review disaster recovery and business continuity capabilities | If target's RTO and RPO commitments do not meet acquirer's standards, interim mitigation must be in place before Day 1; a DR gap discovered during an actual outage post-close is a board-level event | T-43 | 1/18 | 2/21 | Complete | 100% |  | An RTO gap is not a theoretical risk — it means the combined entity cannot recover within its contractual SLA if a critical system fails in the first 30 days; identify the specific systems where target's BCP falls short and require a written interim mitigation plan from IT leadership before Day 1, not after | High | Legal
IT-026 | Integration Management | Day 100 IT Integration Complete | Pre-Close | IT Integration Coordinator | Launch weekly IT workstream status meeting — same day, same time each week | Same day and time every week without exception; first missed meeting signals the cadence is optional | T-42 | 1/19 | 6/10 | On Track | 25% |  |  | Low | IMO
IT-027 | Integration Management | Day 100 IT Integration Complete | Pre-Close | IT Integration Coordinator | Update Executive Dashboard weekly | IT rows on the dashboard are owned by the IT Lead; RAG status must reflect current reality — optimistic reporting delays executive awareness of issues that require intervention | T-42 | 1/19 | 6/10 | On Track | 25% |  |  | Low | IMO
IT-028 | Integration Management | Day 100 IT Integration Complete | Pre-Close | IT Integration Coordinator | Update status of integration plan and RAID log weekly | RAID log is the most important risk management tool in the IT workstream; new risks added by Thursday so IMO can incorporate into steering committee reporting | T-42 | 1/19 | 6/10 | On Track | 25% |  |  | Low | IMO
IT-029 | Integration Management | Day 100 IT Integration Complete | Pre-Close | IT Workstream Lead | Attend IMO Meeting every week to discuss issues and status | Bring the IT issues log and any cross-workstream blockers requiring IMO escalation | T-42 | 1/19 | 6/10 | On Track | 25% |  |  | Low | IMO
IT-030 | Due Diligence | IT Due Diligence Complete | Pre-Close | Cybersecurity & Compliance Lead | Review identity and access management (IAM) architecture | IAM architecture incompatibilities — Active Directory vs. LDAP, different MFA standards, conflicting role hierarchies — are the root cause of most Day 1 login and access failures | T-42 | 1/19 | 2/1 | Complete | 100% |  | The IAM incompatibility that is hardest to fix is MFA policy — if the target uses SMS-based MFA and the acquirer requires hardware tokens or authenticator apps, there is no fast migration path; every day this is unresolved after Day 1 is a day the target's users operate at a lower security standard inside the combined perimeter | High | Legal, Compliance
IT-031 | Systems & Technology | IT Due Diligence Complete | Pre-Close | Applications & Digital Workplace Lead | Inventory source code repositories and version control systems | Undocumented private repositories are a common IP and security risk; ensure all repositories are accounted for before any engineering team access changes are made | T-41 | 1/20 | 2/6 | Complete | 100% |  |  | Low | Legal
IT-032 | Systems & Technology | Systems Integration Complete | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Define cloud strategy and migration roadmap for combined entity | Cloud strategy decision (multi-cloud, single-cloud, or hybrid) must be made before any infrastructure migration begins; changing strategy mid-migration is significantly more expensive than choosing correctly upfront | T-41 | 1/20 | 2/27 | Complete | 100% |  | The cloud architecture decision is one of the few IT decisions that cannot be reversed cheaply — committing to a cloud provider or multi-cloud model without a migration cost model means the combined entity will discover the true cost only after vendor contracts are signed; require Finance sign-off on the TCO model before any cloud architecture is committed | High | Finance, IMO
IT-033 | IT Infrastructure | IT Infrastructure Consolidated | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Assess data center footprint and define consolidation strategy | Data center consolidation is typically the largest single IT cost synergy; quantify the fully-loaded cost of each facility (lease, power, cooling, headcount) before committing to a consolidation sequence | T-40 | 1/21 | 2/25 | Complete | 100% |  | A synergy number built on incomplete facility cost data — missing lease exit penalties, decommission costs, or headcount transfer costs — will be revised downward when Finance runs due diligence on the consolidation plan; obtain fully-loaded facility cost data from both real estate and Finance teams before publishing any consolidation synergy estimate to leadership | High | Finance, IMO
IT-034 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | IT Workstream Lead | Assign owners for each IT synergy | Each synergy line item must have a single named owner — shared ownership creates accountability gaps; the owner is responsible for measurement, reporting, and delivery | T-35 | 1/26 | 2/27 | Complete | 100% |  |  | Low | Finance
IT-035 | IT Infrastructure | Systems Integration Complete | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Develop network integration architecture and design for combined entity | Network architecture is the foundation on which every other Day 1 IT task depends; design must account for failover, latency requirements, and bandwidth peaks on Day 1 when traffic patterns will be abnormal | T-30 | 1/31 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Network architecture that has not been reviewed by both legacy network teams will have blind spots; require the target's network architect to formally review and sign off on the combined design before it is presented to the steering committee — an unreviewed design that fails on Day 1 is a much larger problem than a delayed design | High | IMO
IT-036 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Assist Communications team in drafting answers to Day 1 IT FAQs | IT perspective on FAQ answers is critical for questions about system access, email migration, device policy, and data privacy; assist Communications team in drafting answers and review for technical accuracy before distribution | T-25 | 2/5 | 2/24 | Complete | 100% |  |  | Medium | Communications
IT-037 | Systems & Technology | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review HRIS and payroll systems compatibility | HRIS and payroll system incompatibilities must be resolved before Day 1; a payroll failure on the first pay cycle of the combined entity is an immediate employee relations crisis and potential legal violation | T-23 | 2/7 | 2/27 | Complete | 100% |  | A HRIS compatibility gap that is discovered post-close and cannot be bridged with a parallel-run means employees may be on two separate payroll systems indefinitely; the cost and timeline of HRIS integration must be confirmed before close, not after, because it directly affects the benefit harmonization timeline that HR is planning around | High | HR, Finance
IT-038 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Applications & Digital Workplace Lead | Design unified onboarding and offboarding IT process | Onboarding process must cover Day 1 access provisioning for new hires joining the combined entity; a broken onboarding process is the first IT experience for every employee who joins post-close | T-22 | 2/8 | 2/25 | Complete | 100% | CP – Day 1 Readiness |  | Medium | HR
IT-039 | Systems & Technology | Systems Integration Complete | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Define unified device management (MDM/UEM) strategy | MDM strategy determines how employee devices will be managed, secured, and remotely wiped; incompatible MDM platforms create a security gap where one population's devices are unmanaged | T-20 | 2/10 | 2/23 | Complete | 100% | CP – Day 1 Readiness |  | Medium | HR | Unified device management — consolidating to a single MDM/UEM platform eliminates duplicate per-device licensing and reduces IT administration overhead | 25 | 10
IT-040 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Provide input on drafts of M&A Employee Communication Guide (includes talking points, guidance for team conversations) in preparation for Day 1 | IT-specific questions to address: what email platform will I use, will my devices change, what systems will I have access to, and who do I call if something breaks | T-20 | 2/10 | 2/27 | Complete | 100% |  |  | Medium | Communications
IT-041 | Systems & Technology | Systems Integration Complete | Pre-Close | Infrastructure & Cloud Lead | Define combined entity data governance framework and policies | Data governance framework determines who owns, classifies, and controls access to data across the combined entity; gaps here create regulatory risk (GDPR, CCPA) and audit findings | T-15 | 2/15 | 3/31 | On Track | 25% |  | Data ownership disputes between Finance, Sales, HR, and IT are the most common reason data governance frameworks stall; schedule a cross-functional data ownership workshop within the first 30 days and escalate any unresolved ownership conflict to the CFO — frameworks without resolved ownership are shelf ware | High | All Workstreams
IT-042 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Complete device provisioning for all acquired employees | Device provisioning for large acquired workforces requires weeks of lead time; if devices cannot be provisioned before Day 1, establish a clear interim access plan so employees are not blocked from working | T-15 | 2/15 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Device provisioning that relies on shipping hardware to employee home addresses introduces customs, carrier, and address-accuracy risks that can delay delivery by 1–2 weeks beyond the expected date; build the provisioning schedule from confirmed ship dates, not order dates | High | HR
IT-043 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Workstream Lead | Conduct Day 1 IT war-room dry run with full team | Dry run must test every Day 1 task in sequence and under realistic conditions; issues discovered in the dry run have days to be resolved — issues discovered on Day 1 must be fixed under live pressure | T-14 | 2/16 | 2/26 | Complete | 100% | CP – Day 1 Readiness | A dry run that only tests individual components in sequence does not surface the failures that happen when all systems run simultaneously under combined-entity load; the single most valuable thing the dry run can do is generate a live ticket backlog — if the service desk cannot clear that backlog within two hours during the dry run, it cannot probably clear it on Day 1 either | High | All Workstreams
IT-044 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Set up interim data sharing and reporting infrastructure for Day 1 | Interim data sharing must be established within clean room constraints pre-close; design it to be replaced, not extended — interim infrastructure that becomes permanent is an integration debt | T-13 | 2/17 | 2/27 | Complete | 100% | CP – Day 1 Readiness |  | Medium | Legal, IMO
IT-045 | Systems & Technology | IT Due Diligence Complete | Pre-Close | Infrastructure & Cloud Lead | Assess CI/CD pipeline and DevOps toolchain compatibility | Toolchain incompatibilities that are not resolved before combined engineering teams begin working together result in broken builds, deployment conflicts, and lost productivity | T-12 | 2/18 | 2/27 | Complete | 100% |  |  | Medium | Engineering
IT-046 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Confirm first-day IT service desk operating model and escalation paths | Service desk must be staffed and tested before Day 1; acquired employees will flood the helpdesk with access and connectivity questions in the first hour — under-staffing on Day 1 creates a backlog that persists for weeks | T-10 | 2/20 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A service desk that is not staffed before the first employee's laptop fails on Day 1 cannot be stood up fast enough to prevent the backlog from compounding; confirm staffing levels, escalation contacts, and ticket routing at least one week before Day 1 — any gap found in that confirmation window still has time to be fixed | High | HR
IT-049 | IT Infrastructure | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Confirm Day 1 network connectivity between acquirer and target offices | Network connectivity test must be conducted under full traffic load; Day 1 bandwidth demand will be higher than any previous test due to the combined user population accessing systems simultaneously | T-6 | 2/24 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Testing connectivity at off-peak hours on the day before Day 1 does not validate performance under the peak load of both organizations authenticating simultaneously at 8 AM; run the full-load connectivity test at least one week before Day 1 so there is time to add bandwidth or adjust routing before the real deadline | High | Facilities
IT-050 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Stand up IT service desk on Day 1 with combined coverage | Service desk ticket volume on Day 1 will be 3–5x normal; pre-stage responses for the top 20 anticipated issues and staff with senior engineers who can resolve novel problems in real time | T-6 | 2/24 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Tier 1 help desk agents who have been trained on only one entity's environment will escalate every cross-environment incident to Tier 2, saturating senior engineers with tickets that should be resolvable at Tier 1; run cross-environment training sessions for all help desk staff in the week before Day 1 and validate coverage before the service desk goes live | High | HR
IT-051 | IT Infrastructure | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Establish secure network interconnect between acquirer and target Day 1 | Network interconnect must include failover routing; a single-path interconnect that fails on Day 1 takes down communication between both entities simultaneously | T-6 | 2/24 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A network interconnect designed for average daily traffic will degrade under the spike of two organizations communicating across a newly connected link for the first time; test the interconnect at 150% of projected peak load and confirm failover actually routes traffic before Day 1, not after the primary link saturates | High | Network Carriers
IT-053 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Activate IT integration war room and stand up command center for Day 1 | War room must be staffed from 6 AM on Day 1 with a clear command structure; every IT issue escalates to the war room first — do not allow individual teams to troubleshoot in isolation | T-5 | 2/25 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A war room that is stood up on the morning of Day 1 without prior rehearsal will lose 30–60 minutes to logistics (who has the bridge line, who can see the dashboard, who approves emergency changes) while live incidents queue up; the war room command structure must be rehearsed in the dry run, not improvised on Day 1 | High | IMO
IT-054 | Systems & Technology | Day 1 / Week 1 IT Integration Complete | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Enable unified email and calendar access for all staff Day 1 | Email and calendar access is the single most visible IT deliverable on Day 1; test with a sample of acquired-company users at least 48 hours before cutover — do not discover provisioning failures on Day 1 | T-4 | 2/26 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Email provisioning failures are not recoverable quickly because they involve directory services, MX records, and spam filtering — all of which have propagation delays measured in hours, not minutes; confirm that provisioning for all acquired users has completed at least 24 hours before Day 1 so that any failures have time to be resolved before employees arrive | High | HR
IT-D1 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Workstream Lead | IT Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | Workstream lead formally certifies Day 1 readiness to the IMO; this gate must be green for every workstream before the IMO signs off on close; any open item at this gate is either resolved or escalated to the steering committee as a close-blocking risk | T-3 | 2/27 | 2/27 | Complete | 100% | CP – Day 1 Readiness | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | High | IMO, All Workstreams
IT-052 | IT Infrastructure | Day 1 IT Readiness Confirmed | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Verify all acquired employees have Day 1 Minimum Viable Access — email, HR portal, and primary line-of-business apps; full access provisioning to roll out in waves through Week 1 | Credential verification must cover every authentication system: VPN, email, ERP, CRM, and any application with SSO; a rep who cannot access their sales tools on Day 1 cannot sell | Day 1 (Close) | 3/2 | 3/6 | On Track | 75% | CP – Day 1 Readiness | A user who cannot authenticate on Day 1 will call the help desk, which will already be handling 3–5x normal volume; the authentication failure rate from the dry run is the most reliable predictor of Day 1 service desk load — treat any dry run failure rate above 2% as a blocker requiring executive escalation | High | HR
IT-055 | IT Infrastructure | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Brief staff on Day 1 cybersecurity protocols and acceptable use policies | Focus on the most common Day 1 cybersecurity failures: phishing emails impersonating the acquirer, credential stuffing on newly provisioned accounts, and unauthorized data exfiltration by departing employees | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  |  | Medium | HR, Cybersecurity
IT-056 | Integration Management | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | IT Integration Coordinator | Send Day 1 all-staff IT welcome communication to combined entity employees | Welcome communication sets the tone for IT's relationship with the combined employee base; focus on what support is available and who to contact — not on the technical complexity of the integration | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  |  | Low | Communications
IT-057 | IT Infrastructure | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | Infrastructure & Cloud Lead | Confirm all office network connectivity is live and stable at open of business | Test connectivity from every office location, not just headquarters; remote offices frequently have connectivity issues that are not caught in central testing | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  | Remote offices are the gap in almost every Day 1 IT test plan because they are assumed to inherit the fix applied at headquarters; assign a named IT contact at every acquired office location with instructions to confirm connectivity at 7 AM on Day 1 and escalate immediately if anything is down | High | Facilities
IT-058 | IT Infrastructure | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Extend SIEM and threat detection to acquired company environment on Day 1 — confirm all endpoints and network segments are covered under unified monitoring | SIEM extension is non-negotiable on Day 1; a threat that originates in the target environment and propagates to the acquirer's network cannot be detected without unified visibility | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  | A threat actor who knows both companies are in an integration transition will target the newly connected link between environments specifically because monitoring is likely to have gaps in the first 24 hours; SIEM coverage of the target environment must be confirmed active, not just configured, before any network interconnect goes live | High | Cybersecurity
IT-059 | IT Infrastructure | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Validate all IT controls are active in combined environment | IT controls validation must cover: access provisioning, change management, patch management, and audit logging; gaps in any of these create SOX and audit exposure from the first reporting period | Day 1 (Close) | 3/2 | 3/6 | On Track | 75% |  | IT controls that pass individually may fail when tested in the combined environment due to permission inheritance issues, group policy conflicts, or role assignment overlaps; require the CISO to run a combined-environment controls test — not just an attestation. | High | Finance
IT-060 | Systems & Technology | Email & Collaboration Unified | Day 1 / Week 1 | Applications & Digital Workplace Lead | Deploy unified collaboration platform to all combined staff — confirm access, licensing, and data migration from legacy tools before decommissioning | If both companies use different collaboration platforms, decide on a single standard before Day 1 and communicate the migration plan to employees at the all-hands — running two platforms simultaneously degrades productivity and security | Day 1 (Close) | 3/2 | 3/6 | On Track | 50% |  |  | Medium | HR
IT-061 | IT Infrastructure | Compliance Program Integrated | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Finalize and publish unified IT acceptable use policy | Acceptable use policy must address the combined entity's specific risk profile; a generic policy that does not reflect the actual systems employees use will be ignored | Day 1 (Close) | 3/2 | 3/6 | On Track | 75% |  |  | Low | Legal, HR
IT-062 | Systems & Technology | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | IT Integration Coordinator | Conduct end-user IT orientation sessions for acquired employees | Orientation sessions must cover the top five things employees need to do on their first day: log in, access email, connect to VPN, submit a ticket if something breaks, and find the IT self-service portal | Day 1 (Close) | 3/2 | 3/6 | On Track | 50% |  |  | Low | HR
IT-047 | IT Infrastructure | Systems Integration Complete | Day 1 / Week 1 | Infrastructure & Cloud Lead | Assess server and storage infrastructure and develop rationalization roadmap — ensure Day 1 stability; full rationalization delivered in phases by Day 60 | Prioritize server rationalization by workload type: consolidate like-for-like workloads first, then address application dependencies before decommissioning hardware | Day 1 (Close) | 3/2 | 4/30 | On Track | 25% | CP – Day 1 |  | Medium | Finance | Server and storage rationalization assessment — cost identification only; savings realized through IT-091 data center migration | 0 | 20
IT-048 | IT Infrastructure | IT Service Management Framework Established | Day 1 / Week 1 | Applications & Digital Workplace Lead | Establish interim DNS trust relationships and directory connectivity for Day 1; full Active Directory and DNS unification to follow in controlled migration by Day 30 | DNS and directory services must be tested in a staging environment before Day 1 cutover; a DNS failure on Day 1 can prevent all authenticated access across the combined entity | Day 1 (Close) | 3/2 | 3/31 | On Track | 25% | CP – Day 1 | DNS is the dependency that everything else depends on; a DNS failure does not just break one application — it breaks authentication, email, internal name resolution, and any service discovery that relies on DNS; do not proceed with any production DNS cutover without a tested, documented rollback procedure that can be executed in under 15 minutes | High | Network Carriers
THE 100-DAY IT PLAN IS LOCATED IN THE DAY 100 SECTION OF MANDAPLAYBOOK.COM

## Day 1 Checklist
IT M&A DAY 1 / WEEK 1 CHECKLIST - Pre-Close (Day 1 Readiness) and Day 1/Week 1 Phases
TODAY'S DATE: T-0
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Milestones
Low | On Track | RAID Log
| Complete | Executive Dashboard
☐ Done | Task ID | Phase | Task Description | Assigned To | Risk Level | Timing Anchor | Start | Finish | Status | Milestone
☑ | IT-024 | Pre-Close (Day 1 Readiness) | Assess and remediate critical vulnerability findings | Cybersecurity & Compliance Lead | High | T-44 | 1/17 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-032 | Pre-Close (Day 1 Readiness) | Define cloud strategy and migration roadmap for combined entity | Infrastructure & Cloud Lead | High | T-41 | 1/20 | 2/27 | Complete | Systems Integration Complete
☑ | IT-033 | Pre-Close (Day 1 Readiness) | Assess data center footprint and define consolidation strategy | Infrastructure & Cloud Lead | High | T-40 | 1/21 | 2/25 | Complete | IT Infrastructure Consolidated
☑ | IT-035 | Pre-Close (Day 1 Readiness) | Develop network integration architecture and design for combined entity | Infrastructure & Cloud Lead | High | T-30 | 1/31 | 2/27 | Complete | Systems Integration Complete
☑ | IT-036 | Pre-Close (Day 1 Readiness) | Assist Communications team in drafting answers to Day 1 IT FAQs | IT Integration Coordinator | Medium | T-25 | 2/5 | 2/24 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-038 | Pre-Close (Day 1 Readiness) | Design unified onboarding and offboarding IT process | Applications & Digital Workplace Lead | Medium | T-22 | 2/8 | 2/25 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-039 | Pre-Close (Day 1 Readiness) | Define unified device management (MDM/UEM) strategy | IT Integration Coordinator | Medium | T-20 | 2/10 | 2/23 | Complete | Systems Integration Complete
☑ | IT-040 | Pre-Close (Day 1 Readiness) | Provide input on drafts of M&A Employee Communication Guide (includes talking points, guidance for team conversations) in preparation for Day 1 | IT Integration Coordinator | Medium | T-20 | 2/10 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-042 | Pre-Close (Day 1 Readiness) | Complete device provisioning for all acquired employees | IT Integration Coordinator | High | T-15 | 2/15 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-043 | Pre-Close (Day 1 Readiness) | Conduct Day 1 IT war-room dry run with full team | IT Workstream Lead | High | T-14 | 2/16 | 2/26 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-044 | Pre-Close (Day 1 Readiness) | Set up interim data sharing and reporting infrastructure for Day 1 | Infrastructure & Cloud Lead | Medium | T-13 | 2/17 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-046 | Pre-Close (Day 1 Readiness) | Confirm first-day IT service desk operating model and escalation paths | IT Integration Coordinator | High | T-10 | 2/20 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-049 | Pre-Close (Day 1 Readiness) | Confirm Day 1 network connectivity between acquirer and target offices | Infrastructure & Cloud Lead | High | T-6 | 2/24 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-050 | Pre-Close (Day 1 Readiness) | Stand up IT service desk on Day 1 with combined coverage | Infrastructure & Cloud Lead | High | T-6 | 2/24 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-051 | Pre-Close (Day 1 Readiness) | Establish secure network interconnect between acquirer and target Day 1 | Infrastructure & Cloud Lead | High | T-6 | 2/24 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-053 | Pre-Close (Day 1 Readiness) | Activate IT integration war room and stand up command center for Day 1 | IT Integration Coordinator | High | T-5 | 2/25 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-054 | Pre-Close (Day 1 Readiness) | Enable unified email and calendar access for all staff Day 1 | Infrastructure & Cloud Lead | High | T-4 | 2/26 | 2/27 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-D1 | Pre-Close (Day 1 Readiness) | IT Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | IT Workstream Lead | High | T-3 | 2/27 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☐ | IT-052 | Day 1 / Week 1 | Verify all acquired employees have Day 1 Minimum Viable Access — email, HR portal, and primary line-of-business apps; full access provisioning to roll out in waves through Week 1 | Cybersecurity & Compliance Lead | High | Day 1 (Close) | 3/2 | 3/6 | On Track | Day 1 IT Readiness Confirmed
☑ | IT-055 | Day 1 / Week 1 | Brief staff on Day 1 cybersecurity protocols and acceptable use policies | Cybersecurity & Compliance Lead | Medium | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-056 | Day 1 / Week 1 | Send Day 1 all-staff IT welcome communication to combined entity employees | IT Integration Coordinator | Low | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-057 | Day 1 / Week 1 | Confirm all office network connectivity is live and stable at open of business | Infrastructure & Cloud Lead | High | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-058 | Day 1 / Week 1 | Extend SIEM and threat detection to acquired company environment on Day 1 — confirm all endpoints and network segments are covered under unified monitoring | Cybersecurity & Compliance Lead | High | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IT Integration Complete
☐ | IT-059 | Day 1 / Week 1 | Validate all IT controls are active in combined environment | Cybersecurity & Compliance Lead | High | Day 1 (Close) | 3/2 | 3/6 | On Track | Day 1 / Week 1 IT Integration Complete
☐ | IT-060 | Day 1 / Week 1 | Deploy unified collaboration platform to all combined staff — confirm access, licensing, and data migration from legacy tools before decommissioning | Applications & Digital Workplace Lead | Medium | Day 1 (Close) | 3/2 | 3/6 | On Track | Email & Collaboration Unified
☐ | IT-061 | Day 1 / Week 1 | Finalize and publish unified IT acceptable use policy | Cybersecurity & Compliance Lead | Low | Day 1 (Close) | 3/2 | 3/6 | On Track | Compliance Program Integrated
☐ | IT-062 | Day 1 / Week 1 | Conduct end-user IT orientation sessions for acquired employees | IT Integration Coordinator | Low | Day 1 (Close) | 3/2 | 3/6 | On Track | Day 1 / Week 1 IT Integration Complete
☐ | IT-047 | Day 1 / Week 1 | Assess server and storage infrastructure and develop rationalization roadmap — ensure Day 1 stability; full rationalization delivered in phases by Day 60 | Infrastructure & Cloud Lead | Medium | Day 1 (Close) | 3/2 | 4/30 | On Track | Systems Integration Complete
☐ | IT-048 | Day 1 / Week 1 | Establish interim DNS trust relationships and directory connectivity for Day 1; full Active Directory and DNS unification to follow in controlled migration by Day 30 | Applications & Digital Workplace Lead | High | Day 1 (Close) | 3/2 | 3/31 | On Track | IT Service Management Framework Established

## Milestones
INFORMATION TECHNOLOGY M&A MILESTONES
TODAY'S DATE: T-0
Status | Links
Not Started | Integration Plan
Delayed | Day 1 Checklist
On Track | RAID Log
Complete | Executive Dashboard
Milestone ID | Category | Phase | Assigned To | Milestone | Timing Anchor | Finish | Status | Critical Path
MS-001 | Governance & Planning | Pre-Close | IT Workstream Lead | IT Lead Appointed | T-51 | 1/10 | Complete | CP – Close
MS-002 | Governance & Planning | Pre-Close | Cybersecurity & Compliance Lead | IT Integration Governance Established | T-42 | 1/19 | Complete
MS-003 | Governance & Planning | Pre-Close | IT Workstream Lead | IT Charter Approved | T-42 | 1/19 | Complete
MS-004 | Due Diligence | Pre-Close | IT Workstream Lead | IT Due Diligence Complete | T-3 | 2/27 | Complete
MS-005 | IT Infrastructure | Pre-Close (Day 1 Readiness) | Cybersecurity & Compliance Lead | Day 1 IT Readiness Confirmed | T-3 | 2/27 | Complete | CP – Day 1 Readiness
MS-006 | Synergy Tracking & Realization | Pre-Close | IT Integration Coordinator | Synergy Tracking Active | T-3 | 2/27 | Complete
MS-007 | IT Infrastructure | Day 1 / Week 1 | Infrastructure & Cloud Lead | Day 1 / Week 1 IT Integration Complete | T+4 | 3/6 | Not Started | CP – Day 1
MS-008 | Systems & Technology | Day 1 / Week 1 | Applications & Digital Workplace Lead | Email & Collaboration Unified | T+4 | 3/6 | Not Started

## RAID Log
IT M&A RAID LOG (RAID = Risks, Assumptions, Issues, Dependencies)
TODAY'S DATE: T-0
RAID Type | Status | Links
Risk | Open | Integration Plan
Issue | Closed | Day 1 Checklist
Dependency | Active | Milestones
Assumption | Validated | Executive Dashboard
RAID Type | RAID ID | Related Task ID | Milestone | Owner | Task Description | Issues/Blockers | Status | Mitigation/Action | Timing Anchor | Finish
Risk | RAID-001 | IT-001 | IT Lead Appointed | IT Workstream Lead | Identify IT integration workstream lead and determine members of the IT integration team | IT workstream lead must be identified and available before integration kickoff; without a named IT Lead, there is no accountable owner for systems assessment, Day 1 readiness, or the ERP and HRIS integration workstreams — every IT integration dependency stalls without this role in seat | Closed | Escalate workstream lead appointment to CIO immediately; role must be named and capacity confirmed before integration kickoff; if filled from within the IT organization, secure backfill for BAU responsibilities to prevent the integration becoming a secondary priority from day one | T-51 | 1/10
Assumption | RAID-002 | IT-001 | IT Lead Appointed | IT Workstream Lead | Key acquired company IT personnel — including IT leadership, systems administrators, and critical application owners — will remain available and cooperative through the integration period and will not depart before or immediately after close | If the acquired company's IT leadership or critical systems administrators depart at or near close, the combined entity loses the primary source of institutional knowledge on legacy systems, undocumented configurations, and vendor relationships that are not fully captured in documentation; every integration task that requires access to, migration of, or decommissioning of acquired company systems depends on this assumption; departure of key IT staff would significantly slow the Day 1 Readiness tasks and the To Day 100 systems integration workstreams | Active | IT Workstream Lead to identify the top 5 critical IT personnel at the acquired company and confirm retention status before close; initiate knowledge transfer sessions for each critical role beginning at T-30; document all undocumented configurations, access credentials, and vendor contacts in a centralized IT knowledge base before close; if key personnel cannot be retained, engage a systems integrator to provide bridging coverage for their functional areas | T-51 | 1/10
Risk | RAID-003 | IT-002 | IT Integration Governance Established | Cybersecurity & Compliance Lead | Review data privacy and confidentiality protocols for pre-close sharing | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | Closed | Issue a written clean team protocol to every IT team member before any pre-close data sharing begins; Legal to specify exactly what data can be reviewed, by whom, and under what conditions; prohibit any IT team member from using clean room data to contact customers, inform pricing decisions, or brief the sales team before close | T-49 | 1/12
Assumption | RAID-004 | IT-005 | IT Integration Governance Established | IT Workstream Lead | Acquired company IT infrastructure is stable, adequately documented, and free of material undisclosed technical debt — it is assumed that pre-close systems assessments have surfaced all end-of-life systems, unsupported software, and known infrastructure gaps, and that no material issues will emerge post-close that significantly expand the integration scope beyond what was planned | This assumption underpins the integration timeline and budget — if significant undisclosed technical debt, unsupported operating systems, or undocumented shadow IT environments are discovered post-close, the integration scope, cost, and timeline will require material revision; every downstream integration task that depends on the systems assessment (IT-005 through IT-020) is at risk if this assumption is violated | Active | IT Workstream Lead to conduct a rapid infrastructure validation within the first 14 days post-close to confirm all systems are as represented in due diligence; any gap between actual infrastructure and the assessed state to be logged in the RAID register and escalated to the IMO Leader within 48 hours of discovery; Finance to be notified immediately if the gap has budget implications | T-48 | 1/13
Risk | RAID-005 | IT-009 | IT Due Diligence Complete | Infrastructure & Cloud Lead | Assess network topology, connectivity, and bandwidth capacity | If the target restricts network topology data in the clean room, IT will be designing Day 1 connectivity based on assumptions rather than engineering data — require Legal to explicitly scope network architecture documentation into the data room access agreement before signing | Closed | Negotiate clean room access to network topology data as early as possible; if the target refuses, escalate to deal counsel to clarify what infrastructure data is permissible under the LOI; build Day 1 network architecture from the public-facing information available and plan a rapid validation exercise within the first 48 hours of close | T-38 | 1/23
Risk | RAID-006 | IT-011 | IT Due Diligence Complete | Applications & Digital Workplace Lead | Inventory all enterprise applications and SaaS subscriptions | An incomplete SaaS inventory means the combined entity will continue paying for duplicate subscriptions it cannot see; require the target's procurement team to provide a complete software spend report with contract terms as a condition of data room access, not as a follow-up request | Closed | Require the target to provide a complete SaaS inventory as a closing condition, certified by their CTO or IT lead; cross-reference against AP invoices and SSO audit logs after close to identify shadow IT; prioritize duplicate SaaS discovery in the first 30 days as it is the fastest synergy to realize | T-31 | 1/30
Risk | RAID-007 | IT-014 | IT Due Diligence Complete | IT Integration Coordinator | Review data architecture, databases, and data governance maturity | Undocumented data flows become a data migration failure when the integration team discovers mid-migration that a critical downstream report relies on a manual feed no one knew existed; require target IT to attest in writing that the data architecture review is complete before DD sign-off | Closed | Require target IT to provide an entity-relationship diagram and data dictionary for all production systems before close; escalate any refusal to deal counsel; use the data architecture assessment to build the migration sequencing plan — systems with undocumented dependencies must be migrated last | T-31 | 1/30
Assumption | RAID-008 | IT-010 | IT Due Diligence Complete | IT Workstream Lead | Neither entity will undertake material ERP upgrades, platform migrations, major infrastructure changes, or additional acquisitions during the 100-day integration window that would conflict with, delay, or require rework of the IT integration workstreams | The 100-day IT integration plan assumes a stable BAU technology environment in both entities; if either entity launches a major ERP upgrade, cloud migration, or new acquisition during the integration window, the IT integration team will be resource-constrained and the integration timeline will slip; this is a particularly high risk for the acquirer entity, where BAU IT project backlogs may have been deprioritized in anticipation of the deal closing and may now re-enter the queue simultaneously with integration work | Active | IT Workstream Lead to confirm with the CIO that all major IT projects in both entities are either paused, descoped, or resource-fenced for the 100-day integration window; any new project request with IT resource dependency to be reviewed by the IT Workstream Lead before approval during the integration period; if a business-critical BAU project cannot be deferred, IT Workstream Lead to formally assess the impact on integration capacity and escalate to IMO Leader and CIO | T-31 | 1/30
Dependency | RAID-009 | IT-030 | IT Due Diligence Complete | Cybersecurity & Compliance Lead | Review identity and access management (IAM) architecture | The IAM incompatibility that is hardest to fix is MFA policy — if the target uses SMS-based MFA and the acquirer requires hardware tokens or authenticator apps, there is no fast migration path; every day this is unresolved after Day 1 is a day the target's users operate at a lower security standard inside the combined perimeter | Closed | Map the IAM architecture comparison as the first technical output of the integration — complete before close even if it requires additional clean room access; resolve MFA policy conflicts by adopting the more stringent standard; do not permit any SSO federation before the IAM policies are reconciled | T-29 | 2/1
Risk | RAID-010 | IT-016 | IT Due Diligence Complete | Cybersecurity & Compliance Lead | Review data privacy program (GDPR, CCPA, HIPAA) and compliance gaps | Compliance gaps inherited at close cannot be disclaimed after the fact; if the target has an active HIPAA or GDPR deficiency, the acquirer must either remediate before close, escrow funds for post-close remediation, or factor the penalty exposure into the purchase price — this is a deal-term issue, not just an IT task | Closed | Complete a gap-to-remediation analysis for every compliance deficiency identified before close; assign a named owner and deadline for each gap; do not assume the acquirer's compliance posture covers the target — the combined entity's compliance profile is the union of both, not the acquirer's alone | T-17 | 2/13
Risk | RAID-011 | IT-019 | IT Due Diligence Complete | Cybersecurity & Compliance Lead | Review IT compliance certifications (SOC 2, ISO 27001, PCI-DSS) | Customers with contractual requirements for SOC 2 compliance will ask whether the combined entity's certification covers them; if the answer is unknown at Day 1, those customers will escalate — confirm the new audit scope with the certifying auditor before close and communicate the timeline to affected customers before the press release goes out | Closed | Obtain copies of all SOC 2 reports and penetration test results before close; assess the gap between the target's current certification scope and what customers contractually require; develop a combined certification roadmap within the first 30 days and communicate timeline to customer-facing teams | T-17 | 2/13
Risk | RAID-012 | IT-025 | IT Due Diligence Complete | IT Integration Coordinator | Review disaster recovery and business continuity capabilities | An RTO gap is not a theoretical risk — it means the combined entity cannot recover within its contractual SLA if a critical system fails in the first 30 days; identify the specific systems where target's BCP falls short and require a written interim mitigation plan from IT leadership before Day 1, not after | Closed | Test the target's DR capability against the acquirer's RTO/RPO standards before close, not after; if the target cannot meet the combined entity's recovery requirements, build a remediation plan with a hard deadline before the first mission-critical workload is run on target infrastructure | T-9 | 2/21
Risk | RAID-013 | IT-017 | IT Due Diligence Complete | IT Integration Coordinator | Review IT vendor contracts, licenses, and software agreements | Vendor change-of-control clauses are triggered at close, not when IT discovers them; if these agreements are not mapped before signing, the combined entity may face license suspension or emergency renegotiation from a position of weakness on Day 1 — Legal must complete the vendor contract review before the SPA is executed | Closed | Require the target to deliver a complete vendor contract schedule with change-of-control provisions highlighted before close; initiate consent outreach at least 30 days before close for any contract that requires counterparty approval; do not close without knowing which vendors can terminate on change-of-control | T-5 | 2/25
Risk | RAID-014 | IT-033 | IT Infrastructure Consolidated | Infrastructure & Cloud Lead | Assess data center footprint and define consolidation strategy | A synergy number built on incomplete facility cost data — missing lease exit penalties, decommission costs, or headcount transfer costs — will be revised downward when Finance runs due diligence on the consolidation plan; obtain fully-loaded facility cost data from both real estate and Finance teams before publishing any consolidation synergy estimate to leadership | Closed | Obtain actual facility cost data — lease rates, decommissioning penalties, power costs, exit terms — before finalizing the data center synergy number; build three scenarios: keep, migrate, co-locate; do not commit to a facility exit timeline until the migration sequence and application dependencies are fully mapped | T-5 | 2/25
Risk | RAID-015 | IT-012 | IT Due Diligence Complete | Applications & Digital Workplace Lead | Assess core business systems compatibility | The highest-consequence incompatibility is authentication — if the two companies cannot federate identity on Day 1, every employee login fails; require IT to complete a protocol-level compatibility test (not just a platform inventory) and document a Day 1 workaround for any gap found before the go/no-go review | Closed | Prioritize authentication compatibility as the first systems assessment — federated SSO or LDAP directory incompatibility is the longest lead-time item to resolve; escalate any authentication architecture conflict to the IT Workstream Lead immediately | T-4 | 2/26
Risk | RAID-016 | IT-043 | Day 1 IT Readiness Confirmed | IT Workstream Lead | Conduct Day 1 IT war-room dry run with full team | A dry run that only tests individual components in sequence does not surface the failures that happen when all systems run simultaneously under combined-entity load; the single most valuable thing the dry run can do is generate a live ticket backlog — if the service desk cannot clear that backlog within two hours during the dry run, it cannot probably clear it on Day 1 either | Closed | Conduct the dry run as a full end-to-end simulation covering simultaneous failures — network latency, authentication errors, service desk overload, and application outages occurring at the same time; record every decision and escalation path exercised; use the dry run output to update the war room runbook before Day 1 | T-4 | 2/26
Risk | RAID-017 | IT-020 | Systems Integration Complete | Applications & Digital Workplace Lead | Develop application and SaaS rationalization strategy and portfolio roadmap | The rationalization strategy is only as good as the inventory it is built on; if application inventory is delayed or incomplete, every 'retire' decision in this strategy risks decommissioning a system that is still in active use — do not present this strategy to leadership until the full inventory has been independently verified | Closed | Validate the application inventory against SSO logs, AP invoices, and engineering asset registers before finalizing the rationalization strategy; categorize every application as Keep, Replace, Retire, or Migrate before close; assign a named owner to every application in the portfolio before rationalization decisions are locked | T-3 | 2/27
Risk | RAID-018 | IT-024 | Day 1 IT Readiness Confirmed | Cybersecurity & Compliance Lead | Assess and remediate critical vulnerability findings | The acquirer cannot assert it was unaware of inherited vulnerabilities after close; any CVSS 9.0+ finding identified in diligence that is not remediated before Day 1 must be formally accepted with a documented risk treatment plan signed by the CISO — undocumented acceptance is not acceptance | Closed | Treat every critical or high vulnerability inherited at close as an immediate remediation requirement; assign a named owner and a 30-day deadline for every CVSS 7.0+ finding; brief the Board on inherited vulnerability exposure at the first post-close board meeting; confirm cyber insurance covers combined entity perimeter from Day 1 | T-3 | 2/27
Risk | RAID-019 | IT-032 | Systems Integration Complete | Infrastructure & Cloud Lead | Define cloud strategy and migration roadmap for combined entity | The cloud architecture decision is one of the few IT decisions that cannot be reversed cheaply — committing to a cloud provider or multi-cloud model without a migration cost model means the combined entity will discover the true cost only after vendor contracts are signed; require Finance sign-off on the TCO model before any cloud architecture is committed | Closed | Present the cloud architecture recommendation — including a 3-year TCO model covering migration costs, licensing, egress fees, and ongoing operational costs for each viable option — to the CIO and CFO before any cloud vendor is selected; require Finance sign-off on the TCO model before the architecture decision is locked; do not allow any workload migration to begin until the cloud strategy is approved; once committed, assign a named cloud architect to own the migration roadmap with a formal quarterly review cadence through Day 100 | T-3 | 2/27
Risk | RAID-020 | IT-035 | Systems Integration Complete | Infrastructure & Cloud Lead | Develop network integration architecture and design for combined entity | Network architecture that has not been reviewed by both legacy network teams will have blind spots; require the target's network architect to formally review and sign off on the combined design before it is presented to the steering committee — an unreviewed design that fails on Day 1 is a much larger problem than a delayed design | Closed | Require both legacy network teams to review the integration architecture design jointly before Day 1; schedule a joint technical review session with network leads from both companies at least 10 days before close; document all known blind spots and assign a monitoring plan for each | T-3 | 2/27
Risk | RAID-021 | IT-037 | IT Due Diligence Complete | IT Integration Coordinator | Review HRIS and payroll systems compatibility | A HRIS compatibility gap that is discovered post-close and cannot be bridged with a parallel-run means employees may be on two separate payroll systems indefinitely; the cost and timeline of HRIS integration must be confirmed before close, not after, because it directly affects the benefit harmonization timeline that HR is planning around | Closed | Test the HRIS integration in a sandbox environment before any production payroll data is touched; confirm the parallel-run period covers at least two full payroll cycles; escalate any data mapping gap to HR and Finance immediately | T-3 | 2/27
Risk | RAID-022 | IT-042 | Day 1 IT Readiness Confirmed | IT Integration Coordinator | Complete device provisioning for all acquired employees | Device provisioning that relies on shipping hardware to employee home addresses introduces customs, carrier, and address-accuracy risks that can delay delivery by 1–2 weeks beyond the expected date; build the provisioning schedule from confirmed ship dates, not order dates | Closed | Begin device provisioning at least 2 weeks before close for remote and international employees; confirm shipping addresses for every acquired employee before ordering hardware; assign an IT technician to each major office location for Day 1 on-site support; maintain a 10% hardware buffer for provisioning failures | T-3 | 2/27
Risk | RAID-023 | IT-046 | Day 1 IT Readiness Confirmed | IT Integration Coordinator | Confirm first-day IT service desk operating model and escalation paths | A service desk that is not staffed before the first employee's laptop fails on Day 1 cannot be stood up fast enough to prevent the backlog from compounding; confirm staffing levels, escalation contacts, and ticket routing at least one week before Day 1 — any gap found in that confirmation window still has time to be fixed | Closed | Confirm service desk staffing levels, shift coverage, and escalation paths at least 5 business days before Day 1; conduct a load test simulation using historical ticket volumes from both entities; publish the service desk number and hours to all acquired employees before the Day 1 all-staff communication goes out | T-3 | 2/27
Risk | RAID-024 | IT-049 | Day 1 IT Readiness Confirmed | Infrastructure & Cloud Lead | Confirm Day 1 network connectivity between acquirer and target offices | Testing connectivity at off-peak hours on the day before Day 1 does not validate performance under the peak load of both organizations authenticating simultaneously at 8 AM; run the full-load connectivity test at least one week before Day 1 so there is time to add bandwidth or adjust routing before the real deadline | Closed | Test network connectivity under realistic load — concurrent VPN sessions, video calls, file transfers — at least 48 hours before Day 1; identify the 5 applications most sensitive to latency and test each individually; build explicit failover paths for the top 3 connectivity failure scenarios | T-3 | 2/27
Risk | RAID-025 | IT-050 | Day 1 IT Readiness Confirmed | Infrastructure & Cloud Lead | Stand up IT service desk on Day 1 with combined coverage | Tier 1 help desk agents who have been trained on only one entity's environment will escalate every cross-environment incident to Tier 2, saturating senior engineers with tickets that should be resolvable at Tier 1; run cross-environment training sessions for all help desk staff in the week before Day 1 and validate coverage before the service desk goes live | Closed | Staff the combined service desk with agents trained on both environments before Day 1 — any agent who can only support one entity's environment will be a bottleneck; pre-populate the knowledge base with the top 50 expected Day 1 questions from acquired employees; publish the service desk contact to all acquired employees 24 hours before close | T-3 | 2/27
Risk | RAID-026 | IT-051 | Day 1 IT Readiness Confirmed | Infrastructure & Cloud Lead | Establish secure network interconnect between acquirer and target Day 1 | A network interconnect designed for average daily traffic will degrade under the spike of two organizations communicating across a newly connected link for the first time; test the interconnect at 150% of projected peak load and confirm failover actually routes traffic before Day 1, not after the primary link saturates | Closed | Size the network interconnect for peak load, not average load — Day 1 generates 3-5x normal cross-entity traffic as employees access each other's systems for the first time; build bandwidth monitoring alerts that fire at 70% utilization so IT can act before the link is saturated | T-3 | 2/27
Risk | RAID-027 | IT-053 | Day 1 IT Readiness Confirmed | IT Integration Coordinator | Activate IT integration war room and stand up command center for Day 1 | A war room that is stood up on the morning of Day 1 without prior rehearsal will lose 30–60 minutes to logistics (who has the bridge line, who can see the dashboard, who approves emergency changes) while live incidents queue up; the war room command structure must be rehearsed in the dry run, not improvised on Day 1 | Closed | Activate the war room 24 hours before Day 1, not the morning of; confirm all communication channels, escalation paths, and access to monitoring dashboards are operational before the war room goes live; assign a war room commander with authority to make decisions without further approval during the Day 1 window | T-3 | 2/27
Risk | RAID-028 | IT-054 | Day 1 / Week 1 IT Integration Complete | Infrastructure & Cloud Lead | Enable unified email and calendar access for all staff Day 1 | Email provisioning failures are not recoverable quickly because they involve directory services, MX records, and spam filtering — all of which have propagation delays measured in hours, not minutes; confirm that provisioning for all acquired users has completed at least 24 hours before Day 1 so that any failures have time to be resolved before employees arrive | Closed | Test email provisioning end-to-end for at least 10% of acquired employees 48 hours before Day 1; confirm directory synchronization is complete before any email provisioning is activated; have a manual provisioning procedure ready for any account that fails automated provisioning; monitor mail queue depth continuously on Day 1 | T-3 | 2/27
Risk | RAID-029 | IT-D1 | Day 1 IT Readiness Confirmed | IT Workstream Lead | IT Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | Closed | Conduct the IT Day 1 Readiness Gate with CIO and all IT workstream leads 48 hours before close; any incomplete task requires an immediate escalation decision — proceed with a compensating control, delay the specific activity, or pause close; document every gate decision with sign-offs and a named owner for any open item | T-3 | 2/27
Risk | RAID-030 | IT-057 | Day 1 / Week 1 IT Integration Complete | Infrastructure & Cloud Lead | Confirm all office network connectivity is live and stable at open of business | Remote offices are the gap in almost every Day 1 IT test plan because they are assumed to inherit the fix applied at headquarters; assign a named IT contact at every acquired office location with instructions to confirm connectivity at 7 AM on Day 1 and escalate immediately if anything is down | Closed | Test connectivity at every remote office, not just headquarters — remote office failures are the most common Day 1 surprise; confirm ISP circuit status and on-site IT contact at each location; have a 4G/LTE failover option ready and pre-tested for any location without redundant connectivity | Day 1 (Close) | 3/2
Risk | RAID-031 | IT-058 | Day 1 / Week 1 IT Integration Complete | Cybersecurity & Compliance Lead | Extend SIEM and threat detection to acquired company environment on Day 1 — confirm all endpoints and network segments are covered under unified monitoring | A threat actor who knows both companies are in an integration transition will target the newly connected link between environments specifically because monitoring is likely to have gaps in the first 24 hours; SIEM coverage of the target environment must be confirmed active, not just configured, before any network interconnect goes live | Closed | Extend SIEM coverage to the target environment to establish a threat baseline; brief the SOC on the combined entity perimeter and expected network traffic patterns; define alert thresholds appropriate for Day 1 traffic volumes — normal thresholds will generate false positives at scale | Day 1 (Close) | 3/2
Issue | RAID-032 | IT-057 | Day 1 / Week 1 IT Integration Complete | Infrastructure & Cloud Lead | Network connectivity not fully stable at open of business on Day 1 — acquired company office locations in two regions are reporting intermittent VPN failures and latency spikes; combined entity employees at those sites cannot reliably access cloud applications, shared drives, or the collaboration platform as of 7 AM on close day. Problem was solved by end of Day 1. | Employees who cannot connect to core systems on Day 1 cannot access email, HR portals, or the IT welcome communication that was scheduled to land at 8 AM; VPN instability in acquired locations means those employees are effectively dark on the most visible day of the integration — this is the exact scenario that creates lasting negative impressions about the acquiring company's IT capability; if the issue persists past the all-hands meeting, acquired employees will have no reliable access to the systems they are being told will make them more productive | Closed | IT Workstream Lead has been notified and network operations team is investigating in real time — a war room bridge has been opened with the network and infrastructure team and acquired company IT contacts; all acquired-company employees at affected sites have been redirected to mobile hotspot access as an interim measure until VPN is restored; IT Workstream Lead to provide status update to IMO Leader every 30 minutes until resolved; if not resolved within 2 hours, escalate to CIO for vendor emergency support engagement; IT-057 close-out will not be marked complete until written confirmation of full connectivity stability is received from all affected locations | Day 1 (Close) | 3/2
Risk | RAID-033 | IT-052 | Day 1 IT Readiness Confirmed | Cybersecurity & Compliance Lead | Verify all acquired employees have Day 1 Minimum Viable Access — email, HR portal, and primary line-of-business apps; full access provisioning to roll out in waves through Week 1 | A user who cannot authenticate on Day 1 will call the help desk, which will already be handling 3–5x normal volume; the authentication failure rate from the dry run is the most reliable predictor of Day 1 service desk load — treat any dry run failure rate above 2% as a blocker requiring executive escalation | Open | Test authentication end-to-end for a representative sample of acquired employees in every geography at least 24 hours before Day 1; assign a dedicated authentication support queue separate from the main help desk; have a break-glass access procedure ready for Day 1 authentication failures that cannot be resolved within 30 minutes | T+4 | 3/6
Risk | RAID-034 | IT-059 | Day 1 / Week 1 IT Integration Complete | Cybersecurity & Compliance Lead | Validate all IT controls are active in combined environment | IT controls that pass individually may fail when tested in the combined environment due to permission inheritance issues, group policy conflicts, or role assignment overlaps; require the CISO to run a combined-environment controls test — not just an attestation. | Open | Test controls in the combined environment, not individually — the most common control failure occurs at integration points between the two environments; assign a control validation checklist to the Cybersecurity Lead with a sign-off requirement before Day 1 is declared ready | T+4 | 3/6

## Executive Dashboard
HR M&A MILESTONES REPORT | INFORMATION TECHNOLOGY M&A EXECUTIVE DASHBOARD
TODAY'S DATE: T-0
TASKS
|  |  | TOTAL TASKS |  | NOT STARTED |  | DELAYED |  | ON TRACK | COMPLETE
|  |  | 63 |  | 0 |  | 0 |  | 13 | 50
| MILESTONES |  |  | PROGRESS BY PHASE TASKS DONE/TASKS |  |  |  | RAID LOG |  | ANNUAL SYNERGIES
| Not Started | 2 |  | Pre-Close |  | 46/52 |  | Open Risks | 2 | Targeted Synergies | $225K
| Delayed | 0 |  | Days 1 / Week 1 |  | 4/11 |  | Open Items | 2 | Realized Synergies | $0K
| On Track | 0 |  | Days 8 -100 |  | 0/0 |  | Open Issues | 0 | Cost to Achieve Budget | $90K
| Complete | 6 | [5 empty] | Dependencies | 1 | Actual CTA | $0K
[8 empty] | Assumptions | 3
| CRITICAL PATH MILESTONES | [6 empty] | NEXT 7 DAYS |  | DAY 1 | TASKS DONE/TASKS
| IT Lead Appointed |  |  | Pre-Close | 1/10 | Complete |  | Total Tasks | 11 | Day 1 Readiness | 18/18
| IT Integration Governance Established |  |  | Pre-Close | 1/19 | Complete |  |  |  | Day 1 | 4/11
| IT Charter Approved |  |  | Pre-Close | 1/19 | Complete
| IT Due Diligence Complete |  |  | Pre-Close | 2/27 | Complete |  | LINKS
| Day 1 IT Readiness Confirmed |  |  | Pre-Close (Day 1 Readiness) | 2/27 | Complete |  | Integration Plan |  | Milestones
| Synergy Tracking Active |  |  | Pre-Close | 2/27 | Complete |  | Day 1 Checklist |  | RAID Log
| Day 1 / Week 1 IT Integration Complete |  |  | Day 1 / Week 1 | 3/6 | Not Started
| Email & Collaboration Unified |  |  | Day 1 / Week 1 | 3/6 | Not Started
| Email & Collaboration Unified |  |  | Day 1 / Week 1 | 3/6 | Not Started