## Slide 1
From 100-Day Advisors
INFORMATION TECHNOLOGY
M&A INTEGRATION
KICKOFF MEETING
100-DAY POST-MERGER INTEGRATION PLAYBOOK

## Slide 2
VALUE DRIVERS
Why this integration matters — and what it must deliver
Cost Synergy Realization
Eliminating duplicate SaaS subscriptions, rationalizing overlapping infrastructure, and consolidating vendor contracts unlocks $675K in targeted annual IT savings.
Revenue Enablement
IT integration enables the revenue bridge — unified CRM, integrated product data, and combined sales tools allow cross-sell and upsell motions that neither company could execute independently.
Compliance & Risk Reduction
Remediating security vulnerabilities, unifying compliance certifications, and establishing unified data governance reduces exposure from Day 1.
Combined Technology Capability
Merging two IT estates creates a platform stronger than either alone: broader cloud coverage, deeper security posture, and a unified application portfolio built for the combined entity's scale.
Operational Continuity
Keeping the business running without disruption during the transition protects existing revenue, customer trust, and employee productivity — every day of IT instability has a measurable cost.
2
Notes: Emphasize that IT is the connective tissue for every other workstream synergy. Without IT integration, Finance can't close the books, HR can't pay employees, and Sales can't cross-sell.

## Slide 3
SUCCESS METRICS
© Copyright 100-Day Advisors | IT Integration Kickoff
How we will know the integration is working — tracked weekly by IT Lead and reported to IMO
Revenue Enablement
Revenue bridge data pipeline live and reconciled before first combined earnings call
CRM fully migrated; zero broken opportunity or contact records
Sales team access to combined product catalog and pricing on Day 1
Synergy Realization
$675K annual run-rate IT synergies targeted; Phase 1 scorecard published by Day 100
SaaS contract consolidation tracked contract-by-contract, not in aggregate
Vendor renegotiation savings confirmed vs. deal model; variances >10% escalated to CFO
Customer Retention
Zero service outages attributable to IT integration activities during transition
SOC 2 and ISO 27001 certifications re-scoped and confirmed for combined entity before customer inquiry
Customer-facing systems (CRM, support portal, billing) available Day 1 with 100% uptime SLA
Employee Continuity
100% of acquired employees have Minimum Viable Access (email, VPN, core apps) on Day 1
IT helpdesk ticket backlog returns to baseline within 5 business days of close
Employee satisfaction with IT support tracked via pulse survey at Day 30 and Day 60
3
Notes: These metrics should be in the IT workstream dashboard from Day 1. Every metric needs a named owner. If it doesn't have an owner, it won't get measured.

## Slide 4
EXTENT OF INTEGRATION
© Copyright 100-Day Advisors | IT Integration Kickoff
What is being integrated, what is being preserved, and what is being retired
FULLY INTEGRATE
Email and collaboration platforms — single standard, all staff
Identity and directory services (Active Directory / IAM)
Network connectivity and WAN
Security monitoring (SIEM) and threat detection
IT service management (ITSM) and helpdesk
Unified acceptable use and IT policies
PHASED / SELECTIVE
ERP — evaluate consolidate vs. migrate; decision by Day 14
CRM — migrate acquired accounts into combined system by Day 30
HRIS / payroll — unified employee data migration Day 1
Data center footprint — consolidation sequenced after application rationalization
DevOps toolchain — align standards within 30 days; full merge by Day 100
OPERATE SEPARATELY / RETIRE
Legacy ticketing tools — retire after ITSM migration confirmed complete
Redundant SaaS applications — decommission post data migration and validation
Legacy network connectivity — retired after network convergence at ~Day 78
Separate compliance programs — unified under combined program by Day 60
4
Notes: The rationalization strategy (keep / migrate / retire) was finalized pre-close. This slide operationalizes that decision. Every team lead should know which category their systems fall into on Day 1.

## Slide 5
END STATES — WHAT 'INTEGRATION COMPLETE' LOOKS LIKE
© Copyright 100-Day Advisors | IT Integration Kickoff
Specific, observable outcomes that signal the IT integration is done — by audience
FOR SHAREHOLDERS
$675K annual IT cost synergy run-rate confirmed and published in Day 100 scorecard
Cost-to-achieve spend within budget; CTA vs. plan variance accepted by CFO
Combined IT operating model sustainable within BAU budget — no integration carryover costs
FOR CUSTOMERS
Zero service disruption experienced during integration period
SOC 2 / ISO 27001 certifications confirmed covering combined entity — no lapse in coverage
Customer-facing systems and support channels fully operational and unified
FOR VENDORS
All change-of-control clauses resolved; no contracts in default or emergency renegotiation
Vendor consolidation roadmap executed; combined entity operating on rationalized contracts
IT vendor relationships transitioned from two contacts to one combined entity relationship
FOR EMPLOYEES
Single set of IT tools, policies, and support processes for all staff
IT onboarding / offboarding process unified and documented
Helpdesk volumes returned to pre-integration baseline; no open Day 1 access issues
5
Notes: End states are the definition of done. If the team can't point to a specific, observable outcome, the task isn't complete. Use this slide to align leadership on what 'done' means before the integration begins.

## Slide 6
NON-NEGOTIABLES
© Copyright 100-Day Advisors | IT Integration Kickoff
Clear boundaries that cannot be compromised regardless of timeline, cost, or complexity
Day 1 Employee Access
Every acquired employee must have Minimum Viable Access — email, VPN, and primary line-of-business apps — at open of business on Day 1. This is non-negotiable. Provisioning failures are escalated to the IT Lead immediately, not triaged through normal helpdesk.
Unified Security Monitoring
SIEM and threat detection must be extended to the acquired environment on Day 1. A threat originating in the target environment that propagates to the acquirer's network cannot be detected without unified visibility. No exceptions.
Clean Room Compliance Pre-Close
All pre-close data sharing must comply with HSR clean room rules. Any IT staff with access to target company systems must be briefed before access is granted. Violations carry regulatory and legal consequences that are not reversible.
No Payroll Disruption
HRIS and payroll system integration must be validated before go-live. A payroll failure on the first pay cycle of the combined entity is an immediate employee relations crisis and potential legal violation. Finance and IT must jointly sign off before any payroll cutover.
Zero Compliance Gaps Inherited
All critical security vulnerability findings must be remediated before close. Compliance certifications (SOC 2, ISO 27001) must remain in force for the combined entity. Gaps identified in diligence that are not remediated require a documented risk treatment plan signed by the CISO.
ERP Decision Before Execution
The ERP architecture decision — retain acquirer's system, migrate to target's, or implement a new platform — must be made and approved before any migration work begins. Changing the ERP strategy mid-migration is significantly more expensive than choosing correctly upfront.
6
Notes: Non-Negotiables are commitments made to leadership and the board. They are not subject to re-prioritization. If a resource constraint threatens a Non-Negotiable, it escalates to the Steering Committee immediately.

## Slide 7
GOVERNANCE MODEL
© Copyright 100-Day Advisors | IT Integration Kickoff
Who is accountable, who is responsible, and how decisions are made and escalated
IT Workstream Lead
Single accountable owner for all IT integration deliverables. Attends weekly IMO meeting. Formally certifies Day 1 readiness to IMO. Escalates blockers that cross workstream boundaries. Owns the IT integration charter.
IT Integration Coordinator
Maintains the integration plan, RAID log, and executive dashboard weekly. Tracks synergy realization against targets. Owns cross-workstream dependency mapping. Distributes status to IMO by Thursday each week.
Infrastructure & Cloud Lead
Owns all network, data center, cloud, and server infrastructure tasks. Leads Day 1 connectivity testing and war room infrastructure. Executes data center consolidation and network convergence through Day 100.
Applications & Digital Workplace Lead
Owns application and SaaS rationalization. Leads email, collaboration, CRM, and ERP migration tracks. Manages ITSM platform selection and HRIS integration. Coordinates device provisioning for acquired employees.
Cybersecurity & Compliance Lead
Owns all security, IAM, SIEM, and compliance workstreams. Leads vulnerability remediation, acceptable use policy, and compliance certification re-scoping. Extends security monitoring to combined environment on Day 1.
IMO (Integration Mgmt Office)
Cross-workstream coordination and steering committee reporting. Receives IT status weekly. Manages integration risk register. Facilitates Day 30 and Day 100 gate reviews. Escalates unresolved blockers to executive sponsors.
7
Notes: Emphasize RACI: every task in the integration plan has a single named Assigned To. Shared ownership is not ownership. Overlapping jurisdiction — especially between IT, Finance (ERP), and HR (HRIS) — is the most common governance failure in IT integrations.

## Slide 8
GUIDING PRINCIPLES
© Copyright 100-Day Advisors | IT Integration Kickoff
The criteria that guide every IT integration decision — from system selection to sequencing
01
Business Continuity First
No integration activity proceeds if it creates unacceptable risk to Day 1 operations. Stability of the combined business takes precedence over integration speed.
02
Single Owner Per Decision
Every integration decision — system selection, migration sequence, decommission date — has one named owner. If two people are accountable, no one is.
03
Decide Before You Execute
Architecture decisions (ERP, CRM, cloud strategy) must be made and approved before execution begins. Changing direction mid-migration is the costliest integration mistake.
04
Clean Data Before Migration
No data migration begins until a data quality assessment is complete. Moving dirty data creates compliance risk and customer-visible errors that are expensive to remediate.
05
Security Is Non-Negotiable
Unified security monitoring, access rationalization, and vulnerability remediation are not subject to timeline trade-offs. A security gap in the acquired environment is now our liability.
06
Retire Interim Solutions
Temporary infrastructure built for Day 1 must have a defined retirement date. Interim solutions that become permanent create technical debt that carries into BAU operations.
07
Report Reality, Not Optimism
RAID logs and executive dashboards must reflect current facts. Optimistic reporting delays leadership awareness of issues that require intervention — and delays cost more than honesty.
08
Speed and Completeness Together
Integration speed matters — delay has a cost. But completeness matters too. Closing the IT gate without resolving open issues passes debt to BAU operations. Both matter.
8
Notes: These principles are decision filters. When the team disagrees on a path forward, come back to this list. The principle that applies most directly to the disagreement points to the answer.

## Slide 9
CORE MESSAGES
The foundational communications that explain this deal — what every employee and stakeholder should understand
WHY THIS DEAL
This acquisition combines two complementary IT organizations into a platform with greater scale, broader capability, and stronger security than either company had independently. The deal was driven by technology synergy, not cost cutting alone.
WHAT CHANGES ON DAY 1
On Day 1, employees gain access to a unified email and collaboration platform. Network connectivity between both organizations is live. IT support is available through a combined helpdesk with expanded coverage hours.
WHAT STAYS THE SAME
Core business operations continue without interruption. Employees retain access to the tools they use today through a managed transition. No system will be decommissioned without advance notice and migration support.
HOW DECISIONS WILL BE MADE
The IT Workstream Lead is the single accountable owner for all IT integration decisions. Major decisions — ERP architecture, data center strategy, security platform selection — are made by the IT Lead with IMO and executive review before execution begins.
WHAT WE ARE ASKING OF EMPLOYEES
Report IT access issues to the helpdesk immediately — do not work around them. Follow updated acceptable use policies from Day 1. Attend IT orientation sessions in the first week. Expect some disruption and trust that issues will be resolved quickly.
WHEN THIS WILL BE COMPLETE
The formal IT integration concludes at Day 100. By that date, all systems will be unified or on a published migration path, compliance certifications will cover the combined entity, and the IT operating model will be running as a single organization.
Notes: These messages are the basis for all IT communications — the Day 1 all-staff email, the IT FAQ document, and talking points for team conversations. IT Lead and Communications should align on these before any external message goes out.

## Slide 10
INTEGRATION TIMELINE
© Copyright 100-Day Advisors | IT Integration Kickoff
IT integration milestones across three phases — Pre-Close through Day 100
PRE-CLOSE
T-60 Days
IT Lead appointed; integration team confirmed
IT Integration Governance established; charter approved
Full IT due diligence complete: network, infrastructure, applications, cloud, vendors, compliance
Application and SaaS rationalization strategy finalized
Day 1 IT readiness confirmed; war room dry run complete
All acquired employees device-provisioned
Day 1 Readiness Gate certified by IT Lead to IMO
DAY 1 / WEEK 1
IT war room activated at 6AM Day 1
Unified email and calendar access live for all staff
Combined helpdesk staffed and operational
SIEM and threat detection extended to acquired environment
Cybersecurity protocols briefed to all staff
Day 1 IT welcome communication sent to combined entity
End-user IT orientation sessions completed
DAYS 8–100
ERP architecture decision made and approved
CRM migration complete and validated
IT integration health check and risk reassessment
HRIS employee data unified
Telephony platform unified
Data center consolidation executed
Annual security risk assessment complete
Network convergence; legacy connectivity retired
Redundant applications decommissioned
IT integration gate closed; synergy scorecard published
10
Notes: The integration plan has 101 tasks total. The timeline on this slide shows the critical path milestones. Weekly status meetings on the same day and time each week are mandatory from Day 1 through Day 100.

## Slide 11
DUE DILIGENCE RULES OF ENGAGEMENT
© Copyright 100-Day Advisors | IT Integration Kickoff
Data sharing guidelines governing all pre-close IT access and information exchange
A
WHAT YOU MAY AND MAY NOT DO
All pre-close IT data access is governed by clean room protocols established with Legal
IT staff may review target company systems and data only within designated clean room boundaries
No IT staff member may contact a named target customer or access customer pricing data before close
Network topology and architecture data may be reviewed only after Legal has scoped it into the data room agreement in writing
Any IT finding that could affect deal terms must be escalated to Legal immediately — not documented informally
Vendor contracts with change-of-control clauses may be reviewed but not renegotiated until Legal authorizes outreach
IT headcount data is restricted to the IT Lead and named team members; it may not be shared with business unit leaders without IMO and Legal approval
CONSEQUENCES OF VIOLATIONS
Clean room violations constitute 'gun-jumping' under HSR antitrust rules. The risk is not the intent — it is the document trail. Regulators can cite the violation regardless of whether harm was intended. Penalties can affect deal closing.
IF YOU'RE UNSURE — STOP AND ASK
Before accessing any target company system, data, or personnel: contact the IT Lead or Legal. Do not proceed on the assumption that access is permitted. The clean room agreement defines what is in scope — if it is not explicitly in scope, it is out of scope.
11
Notes: Every IT team member with any pre-close access must be briefed on these rules before access is granted. The IT Lead is responsible for confirming that briefing has occurred. This is not optional and cannot be delegated.

## Slide 12
100-DAY ADVISORS
Accelerating M&A Integrations
MandAPlaybook.com
inquiries@MandAPlaybook.com