## Slide 1
100-DAY POST-MERGER INTEGRATION PLAYBOOK
TEAM ROLES AND GOVERNANCE
100-DAY INTEGRATION

## Slide 2
WHO'S ON THE TEAM
Integration Organization
BOARD OF DIRECTORS
STEERING COMMITTEE
CEO · CFO · COO · VP HR · Acquired Co. CEO
INTEGRATION MANAGEMENT OFFICE
IMO Leader · Integration Coordinator
HR
Talent & Benefits
IT
Systems & Infrastructure
Operations
Business Continuity
Finance
Tax & Treasury
Legal
Entities & Compliance
Sales
Revenue & Retention
Comms
Narrative & Trust
© 100-Day Advisors
2

## Slide 3
WHO DECIDES WHAT
Governance Structure
BOARD / STEERING COMMITTEE
Sets deal rationale and integration priorities at kickoff
Approves the governance structure and escalation process
Reviews RAG status, risks, and decisions every two weeks
Signs off the Day 30 and Day 100 gate deliverables
IMO LEADER
Designs governance structure, escalation path, and decision rights
Owns the weekly RAID log, Executive Dashboard, and plan of record
Runs the Day 1 war room and daily stand-ups through Week 1
Authors the Day 30 and Day 100 gate reports
WORKSTREAM LEADS
Plan and execute the integration for their function
Escalate yellow/red items and blocked dependencies to the IMO
Report task-level status into the weekly RAID and dashboard cycle
© 100-Day Advisors
3

## Slide 4
WHO OWNS THE WORK
Governance Roles
IMO Leader
OWNS DAY-TO-DAY GOVERNANCE
Builds the operating cadence and chairs IMO and Steering Committee meetings
Consolidates the RAID log and Executive Dashboard every week
Authors every gate report from Pre-Close through Day 100
Integration Coordinator
SUPPORTS EXECUTION
Circulates communication guides and confirms distribution to managers
Coordinates the integration budget framework with Finance
Confirms readiness materials reach sales and people leaders
Steering Committee
SETS DIRECTION
Holds the Steering Committee kickoff meeting to align on rationale and governance
Appoints the IMO Leader and core team prior to Day 1 planning
Approves the governance structure before pre-close sharing begins
© 100-Day Advisors
4

## Slide 5
THE GOVERNANCE RHYTHM
Meeting Cadence
Frequency
Forum
Purpose
Owner
Daily
(Day 1–Week 1)
IMO War Room Stand-Up
7 AM go-status call; RAG and blockers only, 15 minutes
IMO Leader
Weekly
IMO Team Meeting
Review RAG status, escalate blockers, confirm milestone progress
IMO Leader
Weekly
Executive Dashboard
RAG by workstream, milestones, RAID summary — published Friday
IMO Leader
Every Two Weeks
Steering Committee
RAG review, risks/escalations, decisions needed
IMO Leader
Day 30 Gate
Integration Check
Progress report to Steering Committee; synergy tracking confirmed live
IMO Leader
Day 100 Gate
Close-Out Review
Close-out report to the Board; BAU handoff signed off
IMO Leader
© 100-Day Advisors
5

## Slide 6
THE PAPER TRAIL
Governance Artifacts
C
Integration Charter
Defines scope boundaries by workstream — i.e., comp/org decisions for HR, budget authority for Finance, and similar guardrails for Legal
R
RAID Log
Consolidated weekly — resolved items closed, emerging risks escalated, every open item assigned a named owner
D
Executive Dashboard
Published every Friday — RAG status by workstream, milestone tracking, and RAID summary in one view
P
Plan of Record
Master integration plan under formal change control onward from the Day 30 lock-down point
L
Decision Log
Captures what was decided, by whom, and when — so decisions already made don't get re-litigated
G
Gate Reports
Day 30 progress report and Day 100 close-out report — the formal deliverables reviewed by Steering Committee and Board
© 100-Day Advisors
6

## Slide 7
FORMAL CHECKPOINTS
Decision Gates
1
PRE-CLOSE
DAY 1 READINESS GATE
Confirms all Day 1 tasks complete, systems tested, and communications ready — no unresolved blocker may pass through this gate
Reviewed by: IMO Leader
2
TO DAY 100
DAY 30 GATE
Reviews progress against plan and confirms synergy tracking is working across teams; the progress report is the gate deliverable
Reviewed by: Steering Committee
3
TO DAY 100
DAY 100 GATE
Confirms all integration tasks complete or formally deferred, synergy baseline locked, and BAU transition signed off
Reviewed by: Board of Directors
© 100-Day Advisors
7

## Slide 8
BEFORE CLOSE, RULES STILL APPLY
Pre-Close Data Governance
CLEAN ROOM PROTOCOLS
Data privacy and confidentiality protocols distributed to workstream teams before any sharing begins
Subject to HSR clean room rules — antitrust exposure is real, not theoretical
Acquirer staff with access to target's competitively sensitive data operate under documented restrictions
Governance structure itself must be established before pre-close sharing starts
DATA ROOM STRUCTURE
Organized by workstream folder, with shared templates and document controls
Naming convention and version control established on Day 1 of setup — undated files create confusion during review
IMO Leader owns setup and access; workstream leads populate their own folders
© 100-Day Advisors
8

## Slide 9
100-DAY ADVISORS
Accelerating M&A Integrations
MandAPlaybook.com
inquiries@MandAPlaybook.com