## Slide 1
LEGAL
M&A INTEGRATION
KICKOFF MEETING
From 100-Day Advisors
100-DAY POST-MERGER INTEGRATION PLAYBOOK

## Slide 2
VALUE DRIVERS
Why this integration matters — and what Legal must protect and deliver
© Copyright 100-Day Advisors | Legal Integration Kickoff
1
Deal Certainty
Legal clears the path to close — regulatory approvals, board authorizations, and contract consents. Without this work, there is no transaction.
Risk Containment
Inherited litigation, compliance gaps, and undisclosed liabilities become the acquirer's problem on Day 1. Legal quantifies and mitigates that exposure before close.
Contract Value Protection
Material customer, vendor, and partner contracts must survive the transaction. Change-of-control clauses, assignment restrictions, and consent requirements are identified and managed pre-close.
IP and Brand Security
The combined entity's competitive position depends on clean IP ownership, valid trademarks in every market, and enforceable licensing arrangements across both companies.
Compliance Foundation
A unified compliance program — covering anti-corruption, data privacy, export controls, and employee conduct — is the legal infrastructure the combined entity runs on from Day 1.

## Slide 3
SUCCESS METRICS
How we will measure Legal integration success — tracked weekly and reported to IMO
© Copyright 100-Day Advisors | Legal Integration Kickoff
2
Deal Execution
All regulatory filings submitted on schedule; approvals confirmed before close
Closing documents executed without defect; no post-close cure required
Board and shareholder authorizations obtained within required timeframes
Contract & IP
Material contracts consented or novated before close; zero revenue gaps
IP assignments filed in all relevant registries by Day 60
Contract harmonization roadmap published and in execution by Day 30
Compliance & Risk
No regulatory violations attributable to integration activities
Combined compliance program live and training completed by Day 60
All inherited litigation matters transferred to combined legal team by Day 30
Employee & Operational
WARN Act and equivalent notifications issued on time; no statutory violations
Works Council consultations completed before any employee announcement
Unified policies and employee handbooks live for all staff on Day 1

## Slide 4
EXTENT OF INTEGRATION
What is being unified, what is being transitioned, and what stays separate until BAU
© Copyright 100-Day Advisors | Legal Integration Kickoff
3
FULLY INTEGRATE
Legal workstream governance and RACI across combined entity
Compliance program — code of conduct, whistleblower hotline, training
Data privacy framework and cross-border transfer agreements
Legal hold and document retention policies
Employee handbooks and conduct policies
Anti-corruption, sanctions, and export control programs
PHASED / TRANSITIONAL
Contract templates and approval authority matrix — standard terms adopted by Day 30
IP assignments filed through Day 60 across all registries
Outside counsel consolidation — conflict checks and firm rationalization by Day 45
Government contract novations — agency-by-agency sequenced through Day 60
Legal matter management system — migration complete by Day 60
MANAGE SEPARATELY / RETIRE
Legacy legal entity structures — dissolved or merged per corporate restructuring plan
Separate compliance reporting lines — unified under combined GC by Day 30
Duplicate outside counsel relationships — rationalized by Day 45
Legacy legal billing and matter tracking systems — retired post-migration

## Slide 5
END STATES — WHAT 'INTEGRATION COMPLETE' LOOKS LIKE
Observable outcomes that signal the Legal workstream is done — by audience
© Copyright 100-Day Advisors | Legal Integration Kickoff
4
FOR SHAREHOLDERS
All regulatory approvals obtained; no post-close remedy or divestiture required
Legal synergies confirmed — outside counsel consolidation and litigation reserve reductions locked in deal model
No undisclosed liabilities surfaced post-close that materially affect deal economics
FOR CUSTOMERS
All customer contracts consented, novated, or assigned without interruption to service
Data privacy rights and processing agreements honored under the combined entity from Day 1
Combined entity's contract terms published and counterparties notified
FOR VENDORS & PARTNERS
All material vendor contracts transitioned; change-of-control clauses resolved
Government contracts novated with agency consent; no lapse in performance authority
Unified contract templates and approval authority in place for new agreements
FOR EMPLOYEES
Unified code of conduct, employment policies, and handbooks live for all staff
WARN Act and Works Council obligations met; no statutory violations
Single legal escalation path and RACI understood by all workstream leads

## Slide 6
NON-NEGOTIABLES
Legal requirements that cannot be deferred, delegated, or compromised
© Copyright 100-Day Advisors | Legal Integration Kickoff
5
Works Council First
No employee announcement, restructuring action, or integration activity affecting represented employees proceeds without completed Works Council consultation. Violations can result in injunctions that block or reverse the transaction.
Regulatory Clearance Before Close
HSR, CFIUS, and all required international competition filings must be approved before close. The deal does not close until every required regulatory condition is satisfied.
Privilege Protection from Day 1
All legally sensitive integration communications — regulatory strategy, litigation exposure, workforce planning — must be routed through counsel to maintain attorney-client privilege. Unprotected documents are discoverable.
WARN Act Timing Is Non-Negotiable
Statutory notice periods for workforce reductions cannot be shortened. If a WARN-triggering action is planned, the 60-day notice clock must start on time regardless of integration schedule pressure.
IP Must Be Assigned, Not Assumed
No IP can be treated as owned by the combined entity until assignments are formally executed and filed. Operating on unassigned IP creates ownership gaps that affect customer contracts, financing, and future transactions.
Contract Consents Before Close
Revenue-generating customer contracts with assignment restrictions must be consented or novated before close. A contract that lapses at close because consent was not obtained is a permanent revenue loss.

## Slide 7
GOVERNANCE MODEL
Who owns what — Legal sub-workstream leads and their responsibilities
© Copyright 100-Day Advisors | Legal Integration Kickoff
6
General Counsel
Single accountable owner for the Legal workstream. Certifies Day 1 readiness to IMO. Attends Steering Committee. Signs off on all major legal decisions and escalations.
Legal Integration Manager
Owns the integration plan, RAID log, and weekly status reporting to IMO. Manages cross-workstream legal dependencies. Coordinates sub-workstream leads.
Commercial Counsel
Owns contract review, consent-to-assignment outreach, novation execution, and contract harmonization roadmap. Manages vendor renegotiations post-close.
Employment Counsel
Owns employment agreements, CIC payments, WARN Act notices, Works Council consultations, and unified HR policies. Day 1 employment status confirmation.
IP Counsel
Owns IP diligence, trademark clearance, and formal assignment and registration filings in all relevant jurisdictions through Day 60.
Regulatory & Compliance Counsel
Owns all regulatory filings, license transfers, government contract novations, anti-corruption, data privacy, and combined compliance program.

## Slide 8
GUIDING PRINCIPLES
The criteria that guide every Legal integration decision
© Copyright 100-Day Advisors | Legal Integration Kickoff
7
01
Privilege Is a Discipline
Attorney-client privilege does not attach automatically. Every sensitive integration topic must be routed through counsel, documented correctly, and kept out of unprotected channels.
02
Consent Before Action
No integration step that requires legal consent — contract assignment, government contract novation, Works Council consultation — proceeds without that consent in hand.
03
One Owner Per Commitment
Every legal task, approval gate, and open item has a single named owner. Shared ownership of legal obligations creates gaps that become violations.
04
Statutory Deadlines Are Not Negotiable
WARN Act, Works Council, regulatory filing, and securities disclosure deadlines are fixed by law. Integration timelines are built around them, not the other way around.
05
Disclose Fully, Early
Material liabilities, compliance gaps, and open regulatory matters are disclosed to the Steering Committee when discovered — not managed quietly and escalated late.
06
Harmonize to the Higher Standard
When the two entities' policies, practices, or compliance programs differ, the combined entity adopts the more protective standard — not the more convenient one.
07
Inherited Risk Is Owned Risk
Litigation, regulatory exposure, and compliance gaps inherited at close are the acquirer's responsibility. Legal monitors and manages these from Day 1 without exception.
08
Lessons Feed the Playbook
At Day 100, Legal documents what was missed, what was over-engineered, and what should be done differently. That debrief updates the playbook for the next transaction.

## Slide 9
CORE MESSAGES
What every employee and stakeholder needs to understand about this deal
© Copyright 100-Day Advisors | Legal Integration Kickoff
8
WHY THIS DEAL
This acquisition creates a combined entity with greater commercial reach and stronger legal and compliance infrastructure than either company had independently.
WHAT CHANGES ON DAY 1
Employment transfers to the combined entity. New policies, codes of conduct, and escalation paths are live. Legal is available to support every workstream from open of business.
WHAT STAYS THE SAME
All existing contracts continue in force. Employees retain their current terms until a formal transition is communicated. No system or process changes without notice and transition support.
HOW DECISIONS WILL BE MADE
The General Counsel is the single accountable owner for Legal. Every sub-workstream has a named lead. Escalations follow a clear path — workstream lead to GC to Steering Committee.
WHAT WE ARE ASKING OF EMPLOYEES
Route legally sensitive questions to Legal before committing anything to writing. Follow updated policies from Day 1. If you are unsure whether something requires legal review — ask.
WHEN THIS WILL BE COMPLETE
The formal Legal integration closes at Day 100. By that date, all contracts are harmonized, IP assignments are filed, the compliance program is unified, and Legal is operating as one team.

## Slide 10
INTEGRATION TIMELINE
Legal milestones across three phases — Pre-Close through Day 100
© Copyright 100-Day Advisors | Legal Integration Kickoff
9
PRE-CLOSE
DAY 1 / WEEK 1
DAYS 8–100
PRE-CLOSE
Legal Lead appointed; sub-workstream leads assigned
Privilege protocols established across all workstreams
Due diligence complete: litigation, contracts, IP, employment, compliance, regulatory
HSR, CFIUS, and all regulatory filings submitted and approved
Works Council consultations initiated and completed
Material contract consent-to-assignment outreach executed
Day 1 Legal Readiness Gate certified by GC to IMO
DAY 1 / WEEK 1
All closing documents executed
WARN Act and statutory notifications issued
Legal entity structures confirmed
Contract novation and assignment executed
Unified employee policies and handbooks live
Legal hold policy published for all inherited matters
Day 1 status update sent to IMO
DAYS 8–100
All Day 1 legal tasks confirmed closed
Litigation transferred to combined legal team
Contract harmonization roadmap in execution
Outside counsel conflicts cleared; firms rationalized
IP assignments filed in all registries
Government contract novations complete
Combined compliance program live
Legal matter management system migrated
Legal gate closed; synergies confirmed

## Slide 11
100-DAY ADVISORS
Accelerating M&A Integrations
MandAPlaybook.com
inquiries@MandAPlaybook.com