## Slide 1: M&A Integration Team Roles

## Slide 2: Team Roles & Responsibilities
Steering Committee | SteerCo
Communicates the integration vision; defines any in/out of scope mandates
Guides, validates, and supports the IMO and Functional teams as they perform the integration work
Reviews Yellow/Red task items including escalations, risks/issues, resource constraints, funding, scope of work changes, etc.
Responsible for the overall success of the Integration Program
Integration Management Office | IMO
Designs the approach and methods for managing the integration work (due diligence, project plans, dashboards, etc.)
Measures and tracks the synergies and costs to integrate the two companies
Defines core messages and coordinates communications (both internal and external)
Communicates executive guidance on the pace, scope, cost of the Integration
Facilitates and schedules Functional team reporting to the Steering Committee
Functional Leads
Engage with cross-organizational teams to plan and complete the integration work
Perform diligence to evaluate the operating environments of both companies
Define the end-state operating environment for the eventual combined organizations
Create and maintain integration work product (project plans, process maps, status reports, meeting notes, etc.)
Escalate and make visible any Yellow/Red items in workplan (risks/issues, resource constraints, funding, required decisions, scope of work changes, etc.)
Participate in both IMO and SteerCo meetings
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 3: Meeting Cadence
 | Monday | Tuesday | Wednesday | Thursday | Friday
Team | Functional Teams | IMO | Functional Teams | SteerCo | Functional Team
Frequency | Weekly/Mondays | Weekly/Tuesdays | Every Other Wednesday | Every Other Thursday | As Needed
Description | Prepare for Tuesday IMO meeting | Discuss Red/Yellow task items Discuss cross-functional dependencies and constraints Define SteerCo Agenda | SteerCo Prep Working sessions with IMO and Team Leads to review materials | Meetings to discuss status, R/Y, risks and escalations Approve changes to scope, schedule, budget, organization Make decisions on proposed changes | Ad Hoc
Update | Smartsheet Project Plans Smartsheet Reports Dashboards |  | SteerCo Agenda Dashboard & Reports Decision Log SteerCo Meeting Notes & Actions |  | 
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 4: Integration Guiding Principles
Work together,
no “us and them”
1
Achieve integration objectives
5
Communicate candidly
2
Surface and fix mistakes quickly
6
Don’t kill the entrepreneurial spirit
3
Simplify, do not overengineer
7
Operate with urgency
4
Make the integration a top priority
8
© Copyright 100-Day Advisors MandAPlaybook.com

## Slide 5
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com