## Slide 1
POST-MERGER INTEGRATION
COMMUNICATION MATRIX
HEALTHCARE EXAMPLE
50
Total
Communications
19
One-Time
Events
27
Recurring
Communications
5
Completed
50+
Stakeholder
Audiences
1 / 7

## Slide 2
Leadership & Governance
1 of 5 · 8 items
Stakeholder Audience
Message Theme
Type
Channel
Freq.
Owner
Date
Status
#001
All Employees
Merger Announcement
Announcement
Live Town Hall + Video
One-time
Joint CEOs
15-Feb-25
#002
Board of Directors
Integration Progress
Update
Monthly Board Report
Monthly
Integration PMO
17-Mar-25
#003
Executive Leadership Team
Weekly Integration Sync
Meeting
In-person Leadership Meeting
Weekly
Chief Integration Officer
22-Feb-25
#004
Senior Leadership (Directors+)
Culture Integration
Workshop
Facilitated Workshop
Quarterly
Chief People Officer
01-Apr-25
#005
Integration Workstream Leads
Project Status & Coordination
Update
Weekly StandUp Call
Weekly
PMO Director
18-Feb-25
#006
C-Suite Executives
Strategic Investor Update
Briefing
Investor Relations Memo
Quarterly
CFO
16-May-25
#007
Board Audit Committee
Integration Risk Management
Report
Risk Dashboard
Monthly
Chief Risk Officer
12-Mar-25
#008
Executive Assistants Network
Administrative Coordination
Information
Bi-weekly Email Digest
Bi-weekly
Chief of Staff
01-Mar-25
Completed
Recurring
Scheduled
In Progress
Planning
© 100-Day Advisors · MandAPlaybook.com
2 / 7

## Slide 3
Clinical Staff
2 of 5 · 12 items
Stakeholder Audience
Message Theme
Type
Channel
Freq.
Owner
Date
Status
#009
Physicians - All Specialties
Clinical Integration Vision
Town Hall
Grand Rounds Format
One-time
Chief Medical Officer
25-Feb-25
#010
Nursing Staff (RNs, LPNs)
Staffing & Scheduling Changes
Update
Department Huddles
Weekly
Chief Nursing Officer
20-Feb-25
#011
Medical Residents & Fellows
Training Program Integration
Q&A Session
Virtual Town Hall
Monthly
GME Director
07-Mar-25
#012
Pharmacists & Pharmacy Techs
Formulary Standardization
Training
Online Training Module
One-time
Chief Pharmacy Officer
17-Mar-25
#013
Laboratory Staff
Lab Integration Timeline
Update
Email Newsletter
Bi-weekly
Lab Services Director
22-Feb-25
#014
Radiology & Imaging Teams
PACS Integration
Training
Hands-on Workshop
One-time
Radiology IT Lead
27-Mar-25
#015
Emergency Department Staff
ED Protocol Harmonization
Meeting
Department Meeting
Monthly
ED Medical Director
02-Mar-25
#016
Surgical Services Teams
OR Block Time Allocation
Negotiation
Surgeon Committee Meeting
One-time
VP Surgical Services
06-Apr-25
#017
Specialty Clinic Managers
Patient Scheduling Systems
Training
Webinar Series
Weekly for 4 weeks
Ambulatory Services Director
12-Mar-25
#018
Quality & Patient Safety Team
Incident Reporting Integration
Policy Announcement
Policy Memo + Training
One-time
Chief Quality Officer
22-Mar-25
#019
HR Business Partners
Employee Relations Support
Briefing
Weekly HR Sync
Weekly
CHRO
17-Feb-25
#020
All Employees
Benefits Enrollment Changes
Information Campaign
Multi-channel
One-time campaign
Benefits Director
16-Apr-25
Completed
Recurring
Scheduled
In Progress
Planning
© 100-Day Advisors · MandAPlaybook.com
3 / 7

## Slide 4
Administrative & Operations
3 of 5 · 10 items
Stakeholder Audience
Message Theme
Type
Channel
Freq.
Owner
Date
Status
#021
IT Department
Systems Integration Roadmap
Update
Department All-Hands
Monthly
CIO
27-Feb-25
#022
Finance & Accounting Teams
Month-End Close Process
Training
Process Workshop
One-time
Controller
05-Mar-25
#023
Facilities & Maintenance Staff
Work Order System Change
Training
In-person Training
One-time
Facilities Director
15-Mar-25
#024
Revenue Cycle Staff
Billing System Integration
Update
Weekly Email Update
Weekly
Revenue Cycle Director
19-Feb-25
#025
Patient Access Representatives
Registration Process Changes
Training
Computer-Based Training
One-time
Patient Access Manager
09-Mar-25
#026
Supply Chain & Purchasing
Vendor Consolidation
Meeting
Department Meeting
Monthly
Supply Chain VP
03-Mar-25
#027
Security & Public Safety
Unified Security Protocols
Training
In-person Training
One-time
Chief Security Officer
08-Mar-25
#028
Environmental Services
Cleaning Standards Alignment
Training
Team Huddles
One-time
EVS Director
01-Mar-25
#029
Food Services Staff
Menu & Dietary Integration
Information
Department Meeting
Monthly
Food Services Director
06-Mar-25
#030
Medical Records & HIM Staff
EHR Documentation Standards
Policy Announcement
Policy Memo + Q&A
One-time
HIM Director
13-Mar-25
Completed
Recurring
Scheduled
In Progress
Planning
© 100-Day Advisors · MandAPlaybook.com
4 / 7

## Slide 5
Patients, Community & External
4 of 5 · 10 items
Stakeholder Audience
Message Theme
Type
Channel
Freq.
Owner
Date
Status
#031
Current Patients
Merger Patient Notice
Announcement
Direct Mail + Patient Portal
One-time
Chief Marketing Officer
18-Feb-25
#032
Patient Advisory Council
Patient Experience Focus
Meeting
Quarterly Council Meeting
Quarterly
Patient Experience Officer
01-Apr-25
#033
Community Leaders & Officials
Community Health Commitment
Briefing
In-person Briefings
One-time
VP Community Relations
23-Feb-25
#034
Referring Physicians
Referral Process Continuity
Information
Email + Practice Visits
One-time
Physician Liaison Team
20-Feb-25
#035
Health Plan Partners
Contract Continuity
Negotiation
Contract Discussion Meetings
As needed
VP Payer Relations
17-Mar-25
#036
Patient Family Members
Visiting & Amenities Updates
Information
Website + Signage
One-time
Patient Experience Team
02-Mar-25
#037
Local Media
Merger Progress Updates
Media Relations
Press Releases + Interviews
Quarterly
Corporate Communications
16-May-25
#038
Social Media Followers
Integration Success Stories
Content Marketing
Social Media Posts
Weekly
Digital Marketing Manager
22-Feb-25
#039
Union Representatives
Labor Agreement Discussions
Negotiation
Bargaining Sessions
As needed
Labor Relations Director
07-Mar-25
#040
Research Faculty & Staff
Research Operations Continuity
Update
Research Town Hall
Monthly
VP Research
12-Mar-25
Completed
Recurring
Scheduled
In Progress
Planning
© 100-Day Advisors · MandAPlaybook.com
5 / 7

## Slide 6
Academic, Research & Compliance
5 of 5 · 10 items
Stakeholder Audience
Message Theme
Type
Channel
Freq.
Owner
Date
Status
#041
Medical Staff Office
Credentialing Integration
Training
Process Training
One-time
VP Medical Affairs
20-Mar-25
#042
Compliance & Privacy Officers
Regulatory Compliance Alignment
Workshop
Compliance Workshop
Quarterly
Chief Compliance Officer
25-Mar-25
#043
Graduate Medical Education Cmte
Residency Program Integration
Meeting
GMEC Meeting
Monthly
DIO
14-Mar-25
#044
Clinical Department Chairs
Academic Integration Strategy
Retreat
Leadership Retreat
Semi-annual
Chief Academic Officer
16-Apr-25
#045
Infection Prevention Teams
IP Program Harmonization
Meeting
Monthly IP Committee
Monthly
Hospital Epidemiologist
04-Mar-25
#046
Case Management & Social Work
Discharge Planning Coordination
Training
Process Training
One-time
Director Care Coordination
16-Mar-25
#047
Volunteer Services
Volunteer Program Integration
Information
Volunteer Newsletter
Monthly
Volunteer Coordinator
26-Feb-25
#048
Foundation Board & Donors
Philanthropic Vision
Briefing
Donor Briefing Event
Quarterly
Foundation President
29-Mar-25
#049
Ambulance & EMS Partners
Transport & Coordination
Meeting
EMS Liaison Meetings
Monthly
ED Medical Director
10-Mar-25
#050
Regulatory Agencies
Compliance Notifications
Regulatory Filing
Official Notifications
As required
Regulatory Affairs Director
16-Feb-25
Completed
Recurring
Scheduled
In Progress
Planning
© 100-Day Advisors · MandAPlaybook.com
6 / 7

## Slide 7
Communication Status Summary
50 Total Communications
Completed
5
10% of total
#001 All Employees
#028 Environmental Services
#031 Current Patients
#034 Referring Physicians
#050 Regulatory Agencies
In Progress
6
12% of total
#007 Risk Management
#012 Formulary Standardization
#018 Quality & Safety
#025 Patient Access
#033 Community Leaders
#036 Patient Families
Scheduled
13
26% of total
#002 Board of Directors
#006 C-Suite Executives
#009 Physicians
#011 Medical Residents
#016 Surgical Teams
#022 Finance & Accounting
#027 Security & Safety
#032 Patient Advisory
#035 Health Plan Partners
#037 Local Media
#039 Union Representatives
#042 Compliance Officers
#048 Foundation Board
Planning
8
16% of total
#004 Senior Leadership
#014 Radiology Teams
#017 Specialty Clinics
#020 All Employees – Benefits
#023 Facilities Staff
#030 Medical Records
#041 Medical Staff Office
#044 Dept Chairs
#046 Case Management
Recurring
18
36% of total
#003 Exec Leadership
#005 Workstream Leads
#008 Exec Assistants
#010 Nursing Staff
#013 Laboratory Staff
#015 ED Staff
#019 HR Business Partners
#021 IT Department
#024 Revenue Cycle
#026 Supply Chain
#029 Food Services
#038 Social Media
#040 Research Faculty
#043 GME Committee
#045 Infection Prevention
#047 Volunteer Services
#049 Ambulance / EMS
#... + ongoing comms
© 100-Day Advisors · MandAPlaybook.com
7 / 8

## Slide 8
contact us
EMAIL
inquiries@MandAPlaybook.com
WEBSITE
MandAPlaybook.com
100-DAY ADVISORS
8 / 8