## Slide 1
POST-MERGER INTEGRATION PLAYBOOK
POST-MERGER INTEGRATION
MEETING CADENCE
© 100-Day Advisors MandAPlaybook.com
1
100-DAY INTEGRATION

## Slide 2
CADENCE AT A GLANCE
ELEVEN RECURRING MEETINGS, FOUR FREQUENCIES
DAILY
1
IMO Meeting — daily sync to resolve issues and align on the day's work.
WEEKLY
7
Workstream leads and functional teams report status, risks, and decisions.
BI-WEEKLY
2
Steering Committee and Shareholder Updates on synergies, costs, and risk.
AS NEEDED
1
Board Meeting — milestone reviews ahead of major decision points.
All meeting owners report into the Integration Management Office (IMO), which synthesizes workstream input for Steering Committee and Board review.
© 100-Day Advisors MandAPlaybook.com
2

## Slide 3
DAILY & WEEKLY MEETINGS
WORKSTREAM OPERATING RHYTHM
Meeting | Day | Time | Freq. | Reports / Due
IMO Meeting | Mon–Thu | 10–11am | Daily | NA
Workstream Lead Weekly Update | Monday | 1–2pm | Weekly | NA
Sales Workstream Meeting | Monday | 2–3:30pm | Weekly | Workplan & report — Thu 5pm
HR Workstream Meeting | Tuesday | 11am–Noon | Weekly | Workplan & report — Thu 5pm
IT Workstream Meeting | Wednesday | 3–4pm | Weekly | Workplan & report — Thu 5pm
Finance Workstream Meeting | Wednesday | 4–5pm | Weekly | Workplan & report — Thu 5pm
Legal Workstream Meeting | Thursday | 3–4pm | Weekly | Workplan & report — Thu 5pm
Corporate Workstream Meeting | Thursday | 4–5pm | Weekly | Workplan & report — Thu 5pm
© 100-Day Advisors MandAPlaybook.com
3

## Slide 4
GOVERNANCE & LEADERSHIP REPORTING
STEERING, SHAREHOLDER, AND BOARD CADENCE
Meeting | Agenda Focus | Day / Time | Freq. | Reports / Due
Steering Committee Meeting | Project update, top initiatives, synergy/dis-synergy & one-off costs, risks & issues | Friday, 3–4pm | Bi-Weekly | Deck — 3 days prior
Shareholder Update Meeting | Project update, top initiatives, synergy/dis-synergy & one-off costs, risks & issues | Friday, 9–10am | Bi-Weekly | Deck — 3 days prior
Board Meeting | Milestone review and key decisions | 11am–Noon | As needed | Deck — 10 days for first review, 5 days for final
Why it matters: This cadence ensures issues surfaced in daily IMO meetings reach Steering Committee within two weeks and the Board ahead of every major decision point — keeping integration speed and governance visibility in lockstep.
© 100-Day Advisors MandAPlaybook.com
4

## Slide 5
Let's talk integration.
© 100-Day Advisors MandAPlaybook.com
5
100-DAY ADVISORS
MandAPlaybook.com
inquiries@MandAPlaybook.com