## Slide 1
100-DAY POST-MERGER INTEGRATION PLAYBOOK
STEERING COMMITTEE
KICKOFF
100-DAY INTEGRATION

## Slide 2
AGENDA
STEERING COMMITTEE KICKOFF — TOPICS
VALUE DRIVERS
SUCCESS METRICS
END STATE EXAMPLES
GUIDING PRINCIPLES
CORE MESSAGES
PHASES & MILESTONES
PRE-CLOSE DATA SHARING RULES
GOVERNANCE, RACI & DECISION RIGHTS
NEXT STEPS
© 100-Day Advisors
2

## Slide 3
VALUE DRIVERS
WHAT THIS INTEGRATION MUST DELIVER TO JUSTIFY THE DEAL
Cost Synergies
Eliminate duplicate headcount across all 7 workstreams
Consolidate IT infrastructure, SaaS, and data centers
Rationalize vendors, agencies, and professional services
Merge benefit plans and insurance programs at scale
Revenue Growth
Accelerate cross-sell and upsell to combined customer base
Expand into new geographies using combined footprint
Launch combined product and service bundles
Retain acquired customer relationships through Day 100
Operational Excellence
Unify ERP, HRIS, CRM, and financial reporting
Standardize processes across Finance, HR, Legal, and IT
Achieve single management reporting view by Day 60
Consolidate shared services and back-office functions
Strategic Capability
Access new technology, IP, and talent through acquisition
Strengthen competitive position in core markets
Accelerate product roadmap through combined R&D
Build scale that supports future M&A activity
© 100-Day Advisors
3

## Slide 4
SUCCESS METRICS
HOW WE WILL MEASURE INTEGRATION PERFORMANCE ACROSS ALL WORKSTREAMS
Financial
Synergy realization vs. deal model at Day 30 / 60 / 100
Cost-to-achieve budget vs. actuals by workstream
Combined entity EBITDA vs. pro forma at Day 100
First combined financial close: on time, clean audit
People & HR
Key talent retention rate at 30 / 60 / 90 days
Payroll success rate: 100% on first combined cycle
Benefits enrollment completion by Day 45
Employee engagement score: Day 30 and Day 60 pulse surveys
Technology
Day 1 system uptime: all critical systems online
Employee login success rate: >98% on Day 1
Service desk ticket volume vs. baseline
ERP and CRM integration: complete by Day 100
Communications
Employee comprehension score (Day 30 pulse survey)
Manager cascade completion: 100% before all-hands
Media sentiment: net positive coverage on Day 1
Customer retention: top 50 accounts retained at Day 100
Customer & Revenue
Top 20 at-risk accounts: retention confirmed by Day 30
Cross-sell pipeline generated by Day 100
NPS scores: combined entity baseline established
Sales cycle disruption: <10% change in close rate
Governance & IMO
Task completion rate vs. plan: >90% each reporting period
RAID log current: all items owned and resolution-dated
Steering Committee meeting adherence: 100%
Integration complete: all workstreams closed at Day 100
© 100-Day Advisors
4

## Slide 5
END STATE EXAMPLES
WHAT "INTEGRATION COMPLETE" LOOKS LIKE AT DAY 100
End states are the specific, tangible outcomes that signal integration is done — for shareholders, employees, customers, and partners. Integration teams design backward from these.
HR
All employees on a single HRIS, one payroll system, unified benefits, and a completed org design with confirmed reporting lines and compensation bands.
IT
All acquired employees on combined email, collaboration, and core applications. ERP integrated or migrated. Data centers consolidated. Duplicate SaaS licenses retired.
Finance
First combined financial close complete. Single chart of accounts, unified controls, treasury centralized, and synergy realization validated against deal model.
Legal
All contracts novated, entity structure rationalized, compliance programs integrated across GDPR, SOX, FCPA, and export controls. All regulatory filings current.
Sales
Unified sales organization with confirmed territory assignments, single CRM of record, cross-sell program launched, and top 50 customer relationships secured.
Comms
Brand transition complete across all digital and physical touchpoints. Employee sentiment positive. Combined entity narrative established in media and with investors.
IMO
All workstream milestones closed or formally deferred to BAU. Synergy baseline locked. Lessons learned documented. IMO disbanded and integration handed to operations.
© 100-Day Advisors
5

## Slide 6
GUIDING PRINCIPLES
THE RULES THAT GOVERN DECISIONS WHEN PRIORITIES CONFLICT
These principles apply to every workstream. When a tradeoff must be made, integration teams use these to decide — without escalating to the Steering Committee for every judgment call.
1
Speed wins — but not at the expense of compliance.
Move as fast as possible on synergy capture, systems integration, and org design — but never bypass a legal, regulatory, or audit control to do it. A compliance failure is more expensive than a delayed milestone.
2
Employees hear it from their manager first.
No employee should learn about a material change — org structure, benefits, reporting lines, role elimination — from a system, a press release, or a rumor. Manager cascade is non-negotiable.
3
One owner per task, per synergy, per risk.
Shared accountability is no accountability. Every task in the integration plan has a single named owner. Every synergy has a single named owner. Every RAID item has a single named owner.
4
The acquirer's standards apply on Day 1.
Controls, compliance programs, code of conduct, financial approval authorities, and data governance apply to the combined entity from the moment the deal closes — not after a transition period.
5
Undecided is a decision — the wrong one.
Ambiguity about org structure, system choices, or policy alignment breeds anxiety and voluntary attrition. Make decisions early, communicate them clearly, and change them only with good reason.
6
Customers and key talent are protected first.
When resources are constrained, prioritize actions that protect revenue relationships and retain key employees. Integration machinery can catch up — lost customers and departed talent cannot.
© 100-Day Advisors
6

## Slide 7
CORE MESSAGES
THE FOUNDATIONAL NARRATIVE THIS INTEGRATION MUST COMMUNICATE — CONSISTENTLY, ACROSS ALL AUDIENCES
Employees
This combination makes us stronger — and that strength protects your future.
Your manager will be your first point of contact. Talk to them.
Your pay, benefits, and job status will be communicated clearly and on time.
We will give you real answers, not corporate language.
Customers
Your service continues without interruption. Your account team remains yours.
This combination expands what we can deliver to you, not what we take away.
You will hear from your account executive directly — not from the press.
Our commitment to service quality is stronger, not weaker, after this deal.
Investors
This deal delivers specific, validated synergies with confirmed owners and timelines.
Integration is being managed with discipline — tracked, reported, and accountable.
We will hit our integration milestones and synergy targets.
The combined entity is better positioned to deliver long-term shareholder value.
Media & Public
This is a strategically sound combination with a clear rationale.
We are committed to the communities where both companies operate.
We will be transparent about what changes and what stays the same.
The combined company is a stronger partner for customers and communities.
© 100-Day Advisors
7

## Slide 8
THE 100-DAY FRAMEWORK
THREE PHASES, ONE OUTCOME: INTEGRATION COMPLETE
PHASE 1
Pre-Close Planning
Day −60 to Day 0
Steering Committee and IMO established (T-59)
Workstream leads appointed and chartered (T-50)
Due diligence and risk assessment complete
Day 1 readiness confirmed — all gates green (T-3)
Communications, systems, and war rooms staged
PHASE 2
Day 1 / Week 1 Execution
Day 1 – Day 6
IMO war room activated at 6 AM — all workstreams live
All-employee announcement and CEO welcome distributed
IT: every employee authenticated and operational
Finance: controls active, billing live, payroll funded
HR: managers briefed, hotline staffed, FAQs distributed
Comms: press release, social, intranet launched in sequence
PHASE 3
Integration Complete
Day 8 – Day 100
Systems, processes, and org design finalized
Synergies tracked, validated, and realized
Combined payroll, HRIS, ERP, and CRM live
Brand transition complete across all touchpoints
Day 30 and Day 60 gate reviews — course corrections made
Day 100: all workstreams closed or deferred to BAU
© 100-Day Advisors
8

## Slide 9
PRE-CLOSE DATA SHARING RULES
CLEAN ROOM PROTOCOLS — REQUIRED FOR ALL INTEGRATION TEAM MEMBERS BEFORE DATA ROOM ACCESS IS GRANTED
⚠ These rules apply to every member of the integration team. Violations carry regulatory and legal consequences. Written acknowledgment required before data room access is granted.
What You CAN Do
Review information shared in the formal data room under the NDA
Discuss integration planning based on publicly available information
Coordinate on integration logistics that do not require target company data
Receive data explicitly authorized by Legal for clean room review
Develop integration plans based on your own company's information
What You CANNOT Do
Contact named customers, suppliers, or employees of the target company
Access target company pricing, customer lists, or cost data outside the clean room
Make decisions affecting the target company's operations before close
Share deal information with anyone outside the integration team without Legal approval
Gun-Jumping Risk
Pre-close coordination that substitutes for post-close competition is an antitrust violation
Intent does not matter — the document trail is what regulators examine
A Sales team member contacting a named customer using data room info can expose the entire deal
When in doubt: ask Legal before acting
Data Room Protocol
All access requests go through the IMO Integration Coordinator
Data downloaded from the data room must be stored in the designated secure folder only
Verbal acknowledgment of clean room rules is insufficient — written sign-off required
Any suspected breach must be reported to Legal within 24 hours
© 100-Day Advisors
9

## Slide 10
GOVERNANCE, RACI & DECISION RIGHTS
WHO DECIDES WHAT — AND HOW CONFLICTS GET RESOLVED
Board of Directors
Scope: Strategic direction, deal rationale, major capital allocation
Decides: Material changes to deal structure; decisions beyond CFO authority
Executive Sponsor / CEO
Scope: Integration strategy, synergy targets, executive talent decisions
Decides: Org structure, cross-workstream conflicts unresolved at Steering Committee
Steering Committee
Scope: Integration milestones, budget, cross-workstream escalations, risk
Decides: Workstream priorities, resource trade-offs, exceptions to guiding principles
IMO Leader
Scope: Day-to-day integration management, RAID log, plan of record
Decides: Cross-workstream conflicts unresolved at workstream level within 48 hours
Workstream Leads
Scope: All tasks within their functional area, resource management
Decides: All decisions within their chartered scope; escalate cross-workstream blockers
Unresolved conflicts: Workstream → IMO (48 hrs) → Steering Committee (72 hrs) → Executive Sponsor. No conflict carries into a second weekly IMO meeting open.
© 100-Day Advisors
10

## Slide 11
NEXT STEPS
ACTIONS REQUIRED THIS WEEK TO ACTIVATE THE INTEGRATION
Steerco
T-59
Confirm all Steering Committee members and communication preferences; schedule biweekly SteerCo cadence through Day 100
IMO Leader
T-59
Distribute signed IMO charter, RACI matrix, and workstream charter package to all leads; confirm weekly IMO meeting cadence
All Workstream Leads
T-57
Submit updated integration plan with current status, RAID log, and synergy owner confirmations to IMO by Thursday 4 PM
Finance
T-56
Establish integration cost tracking codes; confirm synergy tracking model is live with owner sign-off on all line items
Legal
T-57
Distribute clean room acknowledgment forms to all integration team members; confirm data room access is provisioned and logged
HR
T-57
Confirm all acquired employees are in the employee directory; validate payroll for first combined cycle scheduled March 15
IMO + All Leads
Weekly (Thursdays)
Update integration plan, RAID log, and Executive Dashboard before Thursday 4 PM for Friday IMO meeting. No exceptions.
© 100-Day Advisors
11

## Slide 12
100-DAY ADVISORS
Accelerating M&A Integrations
mandaplaybook.com
inquiries@mandaplaybook.com