## Slide 1: M&A DAY 1 CROSS-BORDER PLAN

## Slide 2: Communications Plan 30 days Pre & Post D1
By June 14
By June 7
First 30 days
July 1
D30 onwards: Integration Portal Updates/Monthly Newsletter
Press Release
CEO Welcome Day Message
Welcome Video
Integration Portal
Employee Information Pack
Employees Communications Guide (for people managers)
Customer Communications Guide (for customer facing employees)
Supplier Communications Guide (for employees with supplier responsibilities)
Welcome Week slide pack
Leader Prep Meeting materials
GM + HR appointments communicated
Email distribution lists and addresses of all employees
Country-led events
Central-led events
D3-30: GM Townhall/SiteVisits (localized)
Welcome Video
Integration Portal
Employee Information Pack
D1-3: Country Functional Engagement
Sales, Marketing & Customer Service Team
Procurement Teams
D1: Press Release in all markets
D1-3: Notification Letter
D1-3: Notification Letter
D1-15: Key Customer engagement by sales teams
D1-15: Key Supplier engagement by procurement teams
D1-3: Website + Social Media announcement
>D1: Media enquiries handling by Comms
>D1: On-going news and social media monitoring and response
D1: CEO Welcome Message
D2: Global Townhall
By D30: Senior Leadership Meeting
D2-5: Group Functional Meetings
LOCK DOWN MATERIALS
OTHER PREREQUISITES
Prep Meeting (Overview)
GM, HR, Sales & Marketing Leaders, Manufacturing Leaders, Finance/Procurement Leaders
IMO and Coms Led
Prep Meeting (Employees)
GM, HR, Manufacturing Leaders
IMO and Op Leaders
Prep Meeting (Customers)
GM, Sales & Marketing Leaders
IMIO and Sales Led
Prep Meeting (Suppliers)
GM, Finance/Procurement Leaders
(IMO + CCC + Manufacturing WS led)
LEADERS PREP MEETINGS*
EMPLOYEES
MEDIA
CUSTOMERS
SUPPLIERS
D1

## Slide 3: Pre-closing Preparatory Meetings
MEETING | PARTICIPANTS | TOPICS | SPEAKERS
Prep Meeting (Overview) June 12 10-11 AM | GM, HR, Sales & Marketing Leaders, Manufacturing Leaders, Finance/ Procurement Leaders | New Combined Co. Overview (scale, footprint, benefits) Integration Principles and Overview Day 1 – What’s Changing/What’s Not | 
Prep Meeting (Employees) June 12 11-12 PM | GM, HR, Manufacturing Leaders | Employee Communications Objectives Employee Key Messages Employee Communications Plan Employee Communications Resources Q&A | 
Prep Meeting (Customers) June 13 10-11 AM | GM, Sales & Marketing Leaders | Customer Communications Objectives Customer Key Messages Customer Communications Plan Customer Communications Resources Q&A | 
Prep Meeting (Suppliers) June 13 11-12 PM | GM, Finance/Procurement Leaders | Supplier Communications Objectives Supplier Key Messages Supplier Communications Plan Supplier Communications Resources Q&A | 
© 100-Day Advisors MandAPlaybook.com

## Slide 4: Day 1
KEY EVENTS |  |  | 
By June 14 | Complete all Prep Meetings Finalise all communications materials Prepare Global Townhall plan and material | July 1 Day 1 | 5 AM: Press release crosses PR newswire 6 AM: CEO Message distributed 6 AM: Invite sent for Global Townhall Website/Social Media banner released Plan local customer, supplier, employee outreach
By June 21 | Complete Integration Portal Prepare Global Townhall logistics | July 5 Day 4 | 10-12 PM: Global Townhall event
July 1-5 By D1-5 | Get clearance on closing for D1 (Jan 3) Email all leaders on closing date and final communications materials Distribute press release | July 7 By Day 5 | Customer and Supplier Letters sent Country begins key customer and supplier outreach (engagement) Country begins employee local town halls/plant visits

## Slide 5: Employee Outreach by Site
SITE | OWNER | SITE | OWNER
Central KL/SG | Led by Dan Davis John Porcell | Indonesia | Led by Joe Smith
Bangkok office | Led by Chris Davis | Korea | Led by Jack Jones
China (includes Hongkong Taiwan) | Led by Chou Lee Supported by Billy Mart | Malaysia, Singapore | Led by Domingo Lee
Thailand | Led by Ming Koi | India | Led by Sunny Doyt
Vietnam | Led by Chan Chow | Philippines | Led by Bali Saliy
Travel plans for senior leaders to align with local employee outreach plans/townhalls
Country HR to support local event coordination
© 100-Day Advisors MandAPlaybook.com

## Slide 6: Week 1 Functional Engagement
FUNCTION | PARTICIPANTS | OWNER | POTENTIAL TOPICS
HR | Central and Country HR leaders | HR | Establish contact and get to know the new functional organization Integration Plans for HR Guidance for HR leaders
Manufacturing | Central and Country Manufacturing Leaders | Manufacturing | Establish contact and get to know the new functional organization Integration Plans for Manufacturing Safety, Operating Principles Guidance for Manufacturing leaders
Finance | Central and Country Finance leaders | Finance | Establish contact and get to know the new functional organization Integration Plans for Finance Guidance for Finance leaders
IT | Central and Country IT leaders | IT | Establish contact and get to know the new functional organization Integration Plans for IT Guidance for IT leaders
Sales & Marketing | Central Sales and Marketing | TBC | TBC
© 100-Day Advisors MandAPlaybook.com

## Slide 7: Senior Leadership Meeting
Mode:
1 to 2 day workshop
Participants:
IMO
Group Functional Leaders
Country
Proposed Timing:
Week July 20
Objectives
Align new leadership team on new combined company’s vision, mission, strategic plan
Align new culture – setting the tone for the new business
Team-building/networking
© 100-Day Advisors MandAPlaybook.com

## Slide 8: contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting