## Slide 1
M&A DAY 1 READINESS REVIEW ACROSS ORGANZATION

## Slide 2
Key Functions
IT & Finance
Infrastructure, SAP, and Reporting readiness.
HR, Comms, & Legal
Employee packets and contract assignments.
Operations
East/West structures and safety plans.
Corporate
External stakeholder outreach.
1
© 100-Day Advisors MandAPlaybook.com

## Slide 3
IT Overall Status
100%
No Show-Stoppers Identified
Infrastructure testing for SharePoint, Email, and Skype fully passed. Production migration and auto-attendant execution scheduled for final tests.
2
© 100-Day Advisors MandAPlaybook.com

## Slide 4
IT Initiatives (1/2)
Initiative
Status
Day 1 Operations & SAP Interface
D
Email, Calendaring & SharePoint
D
Active Directory & GAL Integration
D
File System Access & IM Setup
D
3
© 100-Day Advisors MandAPlaybook.com
D = To be executed Day 1

## Slide 5
IT Initiatives (2/2)
Access & Connectivity
Testing application access (SAP, Lawson) and wireless/network integration across both company sites are complete.
Strategy & Support
IT Integration Roadmap, vendor contract analysis, and onsite L1/L2 support plans are finalized for Day 1.
4
© 100-Day Advisors MandAPlaybook.com

## Slide 6
Finance Initiatives Status
Reporting & Tax Leaders named, accounting policies conformed, and legal entity structure finalized.
Treasury & Settlement Debt consolidation complete; lockbox changes and loan paydowns pending Day 1 execution.
5
© 100-Day Advisors MandAPlaybook.com

## Slide 7
Communications & Legal
Comms
Welcome packets, gifts, and signage shipped. CEO road trip planned.
Legal
DOAs ready, CIC notifications sent, and contract assignments complete.
Safety
Day 1 safety plan and approach for all employees finalized.
6
© 100-Day Advisors MandAPlaybook.com

## Slide 8
HR Initiatives Status
HR Initiative
Status
Benefits & Pension Plan Amendments
Complete
Retention Plan & Placement Process
Complete
Stock/Equity Conversion & Severance
D
Careers Web Page Linking
D
D = To be executed Day 1
7
© 100-Day Advisors MandAPlaybook.com

## Slide 9
Operations (East & West)
East Operations
Org structure, customer/vendor comms, and safety practices are 100% complete. DOA communicated to managers.
West Operations
Finalizing management staff and HR transition. Customer communication and signage plans ready for execution.
8
© 100-Day Advisors MandAPlaybook.com

## Slide 10
Day 1 Mandatories – East Operations (1/2)
Initiative
Status
Org Structure: Complete framework and key personnel
✓
Org Structure: Create job descriptions and grades
✓
Customer/Vendor: Communicate process post-merger
✓
Customer/Vendor: Interim contracting process
✓
Safety: Review and confirm regional best practices
✓
Safety: Communicate incident contact information
✓
Policies: Communicate DOA to Region Managers
✓
Policies: Distribute Key Contacts for each office
✓
9
© 100-Day Advisors MandAPlaybook.com

## Slide 11
Day 1 Mandatories – East Operations (2/2)
Initiative
Status
Overhead Cost Synergies: List headcount adjustments
✓
Overhead Cost Synergies: Identify headcount costs & G&A
✓
Operations: Obtain REIT process guidelines
✓
On-Boarding: Communicate messaging and background packets
✓
On-Boarding: Determine sequence of management meetings
✓
On-Boarding: Finalize schedule and venues for Day 1
✓
On-Boarding: Distribute Contact matrix and ERP
✓
10
© 100-Day Advisors MandAPlaybook.com

## Slide 12
Initiative
Status
Org Structure: Finalize proposed org structure
D
Org Structure: Staff Region Mgr. role
D
Org Structure: Finalize management staff
D
Org Structure: Finalize HR transition plan
D
Acquired Co. MFG Processes: Safety, Signage, Contracts
✓
Sales & Marketing Integration: Customer communication plan
✓
Employee On-Boarding: Meeting sequence and schedules
D
Employee On-Boarding: Content and vehicles of communication
D
Employee On-Boarding: HR processes, policies, onsite roles
D
11
D = To be executed Day 1
Day 1 Mandatories – West Operations
© 100-Day Advisors MandAPlaybook.com

## Slide 13
Day 1 Mandatories – Corporate Services (1/2)
Initiative
Status
Develop integration Plan and limit monitoring
✓
Outreach Plan for Key External Stakeholders
✓
Media relations plan
✓
Support to businesses for customer/contractor outreach
✓
External websites (new home page, update Acquirer)
D
Clarify roles, responsibilities, reporting structure
D
Identify and assess status of all certificates
✓
Notify respective Certification Bodies
✓
Request 90-day blanket coverage for certifications
✓
Notify regulatory agencies and permit assignments
✓
Ensure compliance systems function effectively
✓
Maintain existing permits
✓
Roll out Day 1 Safety Plan
✓
12

## Slide 14
Develop integration Plan
Outreach Plan for Key External Stakeholders
Media relations plan
External websites redirect
D
Clarify roles and reporting structure
Maintain existing permits
Roll out Day 1 Safety Plan
13
Day 1 Mandatories – Corporate Services (2/2)
© 100-Day Advisors MandAPlaybook.com
✓
✓
✓
✓
✓
D
Initiative
Status

## Slide 15
contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting
14