## Slide 1: PRE-MERGER INTEGRATION FINANCE KICKOFF MEETING

## Slide 2: Agenda
Integration Success Metrics
Integration Guiding Principles
Integration Governance And Structure
Communications Workstream
Finance Objectives
Integration Scope Definition Process For Finance
Finance Day 1
Finance Project Plan Development
Finance Milestones Through End Of Year
Employee-facing Systems
Other Systems
Milestones/Key Activities
Finance Next Steps
© 100-Day Advisors MandAPlaybook.com

## Slide 3: Integration Success Metrics
15%
growth
Achieve
20%
Protect
95%
of employees
Retain
operating margin of
© 100-Day Advisors MandAPlaybook.com

## Slide 4: Integration Guiding Principles
1
2
3
4
5
Produce better results than either company could produce on its own
Provide consistent, excellent level of service for customers arounds the globe
Share and consider new ideas and alternative viewpoints, but recognize that Acquirer will make final decisions
Identify the best courses of action quickly and pursue them expeditiously
Communicate openly and honestly, and act with integrity
© 100-Day Advisors MandAPlaybook.com

## Slide 5: Integration Governance and Structure
Set strategy
Single point of decision making
Funding
Drive the pace of integration
Conflict resolution
Advise on best practices
Manage risks
Plan to achieve End State
Set and prioritize work streams
Assigned & provide resources
Resolve issues
Cross-functional collaboration
Travel as needed
Main contact with Acquiree counterparts
Develop, track and report detail functional & cross-functional work plans
Coordinate and maintain documentation of activities (meeting minutes, update issues log)
Execute tasks in work plans
Attend various working sessions
Steering Committee
Integration Core Team (Operations, Operations, Purchasing, Facilities Finance, HR, IT, Legal, Marketing)
Integration Support
(Operations, Operations Support, Purchasing, Facilities Finance, HR, IT, Legal, Marketing, Communications)
Integration
Consultant
(External)
SMEs
Communications
Resource Augmentation
(Backfill plan/External SME)
Cross-Functional Work Streams
© 100-Day Advisors MandAPlaybook.com
Notes: Q: Dedicated Cost Center to track Integration costs?

## Slide 6: Finance Objectives
 | Valuation | Financial due diligence | Transition services agreement | Process/operations due diligence
Objective | To determine purchase price and opening balances | To provide analysis of working capital, net debt, commitments and contingencies | To control and prioritize change management | To develop the right integration plan
Lead | External consulting firm | External consulting firm | Internal (TBD) | Internal w/external support (TBD)
Current Status | TBD | E&Y | 3-4 months out to determine scope | High level walkthroughs done Initial questions prepared E&Y
Next Steps | Interview another firm Budget approval Negotiate & execute contract | Interview another firm Budget approval Negotiate & execute contract | Define business needs Budget approval Negotiate & execute contract | Define business needs Budget approval Negotiate & execute contract
© 100-Day Advisors MandAPlaybook.com

## Slide 7: Integration Scope Definition Process for Finance
Enterprise Level
Value Drivers
Key Business Success Metrics
Risks
Guiding Principles
Governance & Structure
Communication Plan
Enterprise
Level
Functional
Level
Scope &
Prioritization
Legal &
Contractual
Obligations
Resources
(People & $)
Functional Level
Key Business Success Metrics
Risks
Governance & Structure
Communication Reqmts.
Day 1 &
End States
Feasibility
& Impact
Analysis
Q3/4 2027
Milestones
Lead
Discussions
Cross Functional
Discussions
© 100-Day Advisors MandAPlaybook.com

## Slide 8: Finance Day 1
Accounting
Opening balance
Valuation
F/S reporting
Cost centers
Accounts Payable
Vendor setup
Payments
T&E
ePayables
Investor relations
Comms
Payroll
EE setup
Payroll
TSA
New hires
Planning
Budget
Analysis
Reporting
Risk
Insurance claims
Security
Tax
Entity structure
Corp tax
S&U Tax
PR Tax
Treasury
CC setup
Cash management (bank accounts)
© 100-Day Advisors MandAPlaybook.com
Notes: Feedback on 7/19 – add timeframe

## Slide 9: Finance Project Plan Development
Finance Charter
Finance Project Plan
Accounting
Tax
FP & A
Treasury Management
© 100-Day Advisors MandAPlaybook.com

## Slide 10: Finance Milestones Through End of Year
F&A
Kickoff
Draft F&A Integration Methodology
Core Team
Kickoff
Scope Confirmation w/ SteerCo
F&A Day 1 & End States Draft Check in
Valuation & FDD Contract Executed
Valuation & FDD Firm Selected & Approved
High Level Planning
Detailed Planning
TSA Requirements
Cross-functional Scope
Finalize
P/ODD Scope
Finalize F&A Integration Methodology
Feasibility & Impact Analysis
F&A
Cross Functional
2029
Aug
Sep
Oct
Nov
Dec
© 100-Day Advisors MandAPlaybook.com

## Slide 11: Employee-Facing Systems
Purpose | Acquirer | Acquiree
Job Posting and Application | iCims – Corporate | Taleo – Corporate
Talent Assessment | The Predicted Index (for managers only) | PeopleAnswers
I9/WOTC/Unemployment Claims/Employment Verification | Equifax, eVerify | Equifax, eVerify
New Hire Processing | PayCom | Lawson MSS/UltiPro
Payroll Processing | PayCom | UltiPro
Garnishments & Payroll Tax Filing | Paycom | Lawson/UltiPro
Learning Management System | World Manager on North Portal (Fox Central) | CornerStone (CheesecakeU)
Travel Reservations | Concur | Plaza Travel
Expense Reports | Concur | BAML GRAM
© 100-Day Advisors MandAPlaybook.com

## Slide 12: Other Systems
Purpose | Acquirer | Acquiree
Accounting | Great Plains | Lawson
Planning & Financial Reports | Adaptive Insights | Cognos, BOARD, Hyperion FM
Check Printing Software | None used | MHC
Fixed Assets | Sage | Lawson
Data Poll/ESB | Mirus | iWay
BI Dashboard/Operational Reporting | Mirus | Micro Strategy
Workers’ Comp Reporting | Manual | Corvel
Utilities Payments | None used | eCova
Systems Management | Manage Engine | LanDesk
Wi-Fi | Cisco | Cisco
© 100-Day Advisors MandAPlaybook.com

## Slide 13: Milestones/Key Activities
  6/01 – SteerCo: Structure
  6/19 – Consulting Proposal
  6/20 – SteerCo: Guiding Principles
  7/03 – SteerCo: Future State – Critical Paths
  8/09 – SteerCo: Review of Kickoff Deck
  8/28 – IMO Team Kickoff
  9/18 – SteerCo: Pre & Post Activities & Prioritization
  10/22 – SteerCo: Risk Mitigation Plan
  11/6 – Scope review of each Function
  11/29 – SteerCo: Staffing & Budget
17
Kickoff w/ Acquiree
Effective
Date
Roadshow
“Me Issues”
Executive Team
Core Team
2029
6/7
Oct
Dec
Jun
Aug
Dec
Feb
Apr
Jun
Aug
Oct
Functional Initial Due Diligence
Exec
Kickoff
10
Initial Qs/ Recommendations for Roadmap
Core Team
Kickoff
Core Team Discovery
30-day Option Notice
Pre-work
Post-work
#1 Business Opportunity
#2 Guiding Principles
#4 Communication Plan
#3 Future State
#5 Pre & Post Activities
#9 Refined Future State
#6 Prioritization
#7 Risk Mitigation
#8 Staffing Plan
Apr
May
2028
Meeting dates
© 100-Day Advisors MandAPlaybook.com

## Slide 14: Finance – Next Steps
Determine for Finance
Specific Business Risks
Specific Communication Plan
Integration Structure
1
2
3
© 100-Day Advisors MandAPlaybook.com

## Slide 15
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting
11
15