## Finance Integration Plan
PRE-CLOSE FINANCE MERGER INTEGRATION PLAN | [13 empty] | Click on + sign (above the top row on right) to see synergy columns
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
Risk Level | Status | % Complete |  |  | Links
High | Not Started | 0% |  |  | Milestones
Medium | Delayed | 25% |  |  | RAID Log (Includes Plan Assumptions)
Low | On Track | 50% |  |  | Next 14 Days
| Complete | 75% |  |  | Executive Dashboard
100%
ID# | Category | Milestone | Phase | Assigned To | Task | Notes | Timing Anchor | Start | Finish | Status | Complete | Critical Path | Issues/Blockers | Risk Level | Team Dependency | Synergy Description | Synergy ($K) | Cost To Achieve ($K) | Synergy ($K) Realized | Actual Cost To Achieve ($K)
FIN-001 | Governance & Planning | Finance Lead Appointed | Pre-Close | CFO / Finance Workstream Lead | Identify Finance integration workstream lead and determine members of the Finance integration team | Finance workstream lead is the single accountable owner for all Finance integration deliverables; select individuals with both Finance expertise and change management capacity | T-59 | 1/2 | 1/10 | Not Started | 0% | CP – Close | Finance workstream lead must be identified and available before integration kickoff; if the role is filled internally from a team with significant BAU responsibilities, capacity conflict is the most common cause of delayed Finance integration milestones | High | Executive Sponsor, HR
FIN-002 | Governance & Planning | Finance Integration Governance Established | Pre-Close | VP Finance / Controller | Review data privacy and confidentiality protocols for pre-close sharing | Clean room protocols apply pre-close; confirm what data can be shared without HSR or regulatory risk | T-53 | 1/8 | 1/12 | Not Started | 0% |  | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | High | Legal, Compliance
FIN-003 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Assess normalized working capital requirements for the combined entity | NWC peg drives post-close settlement; errors here result in dollar-for-dollar price adjustments | T-51 | 1/10 | 1/20 | Not Started | 0% |  |  | Medium | IMO, Legal
FIN-004 | Governance & Planning | Finance Integration Governance Established | Pre-Close | CFO / Finance Workstream Lead | Attend IMO Kickoff Meeting | Finance workstream lead attends to align on integration timeline, governance structure, and Finance workstream priorities; bring an initial list of Finance integration dependencies on HR (payroll, benefits), IT (ERP, systems), and Legal (regulatory filings, tax) | T-50 | 1/11 | 1/11 | Not Started | 0% |  |  | Low | IMO
FIN-005 | Governance & Planning | Finance Integration Governance Established | Pre-Close | VP FP&A / Integration Manager | Receive access to integration data room and document repository | Pre-close access restrictions apply; confirm with Legal which financial data can be reviewed in the clean room vs. restricted; focus initial review on publicly available financial information and audited financial statements already disclosed to the acquirer under the NDA | T-49 | 1/12 | 1/13 | Not Started | 0% |  |  | Low | IT, Legal
FIN-006 | Governance & Planning | Finance Integration Governance Established | Pre-Close | CFO / Finance Workstream Lead | Hold Finance Integration Kickoff Meeting | Kickoff agenda: Finance integration timeline, Day 1 close checklist and priorities, reporting deadlines, escalation process, and workstream RACI; distribute agenda 24 hours in advance and circulate meeting notes within 48 hours | T-49 | 1/12 | 1/12 | Not Started | 0% |  |  | Low | IMO
FIN-007 | Governance & Planning | Finance Charter Approved | Pre-Close | VP Finance / Controller | Develop the Finance workstream integration charter and confirm team roles and responsibilities | Charter defines scope boundary between Finance workstream and other workstreams (HR, IT, etc.) | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Low | IMO
FIN-008 | Integration Management | Finance Integration Plan Locked | Pre-Close | VP FP&A / Integration Manager | Develop Finance integration plan (tasks, milestones, RAID log, Day 1 checklist) . Plan of record will be at 3/31. Significant plan changes subsequent to that date must go through formal change approval process. | Finance integration plan is the workstream's operating document; update weekly and share with IMO coordinator | T-49 | 1/12 | 3/31 | Not Started | 0% |  |  | Medium | IMO
FIN-009 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Confirm all insurance policies — D&O, E&O, general liability, property — and coverage limits | Confirm tail coverage for D&O; verify property values reflect current replacement cost, not historical cost | T-49 | 1/12 | 1/21 | Not Started | 0% |  |  | Medium | Legal
FIN-010 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Identify any material weaknesses or significant deficiencies noted by auditors | Prior auditor management letters are early indicators of control risk; request all letters for last 3 years | T-49 | 1/12 | 1/21 | Not Started | 0% |  | Material weaknesses identified by target's prior auditors must be disclosed in the acquirer's next SEC filing if not remediated; escalate immediately to CFO and General Counsel — requires board audit committee awareness | High | External Auditor
FIN-011 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review external auditor relationship, audit fees, and most recent management letter | Auditor change post-acquisition is common and introduces timeline risk; engage combined entity auditor early | T-49 | 1/12 | 1/21 | Not Started | 0% |  |  | Low | External Auditor
FIN-012 | Accounting & Financial Reporting | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review chart of accounts structure and identify gaps or conflicts with acquirer | COA mapping errors cause misclassified expenses and restatement risk; require Finance lead sign-off on final mapping | T-49 | 1/12 | 1/21 | Not Started | 0% |  |  | Medium | IT
FIN-013 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Confirm sales tax, VAT, and indirect tax compliance across all jurisdictions | Multi-state and international indirect tax compliance is frequently a gap in smaller targets; obtain nexus study | T-49 | 1/12 | 1/23 | Not Started | 0% |  |  | Medium | Legal
FIN-014 | Governance & Planning | Finance Integration Governance Established | Pre-Close | VP FP&A / Integration Manager | Define Finance integration success metrics and KPIs | KPIs should include: close timeline, synergy realization, systems cutover, and staff retention | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Low | IMO
FIN-015 | Governance & Planning | Finance Integration Governance Established | Pre-Close | VP Finance / Controller | Circulate integration roles and responsibilities to all finance team members — confirm who owns each workstream task and who escalates to whom | RACI must include both legacy finance teams; shared ownership is a common accountability gap | T-49 | 1/12 | 1/19 | Not Started | 0% |  |  | Medium | HR, IMO
FIN-016 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Identify any unusual cash movements or related-party transactions | Related-party transactions at non-arm's-length rates must be restated; flag for tax and legal review | T-46 | 1/15 | 1/22 | Not Started | 0% |  | Unusual cash movements or related-party loans at non-arm's-length rates require restatement before any closing price adjustment; if undisclosed, they trigger SPA indemnity claims | High | Legal
FIN-017 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Assess quality of earnings — confirm reported EBITDA reflects true operating performance | QoE adjustments directly impact purchase price; engage specialist advisors for complex revenue or cost structures | T-46 | 1/15 | 2/22 | Not Started | 0% |  | Seller may resist reclassifying addbacks that inflate EBITDA; engage QoE advisor early — disputes over addbacks directly affect purchase price and often require SPA representations to resolve | High | Legal
FIN-018 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review and validate purchase price and deal economics vs. original investment thesis | Validate IRR, MOIC, and payback assumptions against due diligence findings; flag any variance above 10% to CFO | T-46 | 1/15 | 2/22 | Not Started | 0% |  | If due diligence findings produce EBITDA adjustments exceeding agreed thresholds, purchase price renegotiation or additional SPA representations may be required; Finance must present findings to CFO before final price is locked | High | Legal
FIN-019 | Treasury & Cash Management | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review and validate net working capital peg and adjustment mechanism | NWC peg typically negotiated as trailing 12-month average; confirm definition with Legal before signing SPA | T-46 | 1/15 | 2/27 | Not Started | 0% |  | NWC peg is typically negotiated as a trailing 12-month average but sellers often propose a higher peg using peak periods; if the definition is disputed at close, the SPA mechanism governs | High | Legal
FIN-020 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | VP FP&A / Integration Manager | Design the synergy tracking framework — template, cadence, and reporting process | Include a cost-to-achieve column for each synergy | T-44 | 1/17 | 1/24 | Not Started | 0% |  |  | Medium | IMO
FIN-021 | Governance & Planning |  | Pre-Close | VP FP&A / Integration Manager | Launch weekly Finance workstream status meeting — same day, same time each week | Consistent meeting cadence is critical for cross-workstream coordination; skip no meetings in the first 60 days | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
FIN-022 | Integration Management |  | Pre-Close | VP Finance / Controller | Update Executive Dashboard weekly | Dashboard is the primary reporting tool for IMO and steering committee; Finance lead owns the Finance rows | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
FIN-023 | Integration Management |  | Pre-Close | VP FP&A / Integration Manager | Update status of integration plan weekly | Weekly update includes task status, RAID log changes, and any budget variances; due Thursday by 4 PM | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
FIN-024 | Integration Management |  | Pre-Close | VP FP&A / Integration Manager | Attend weekly IMO Meeting and discuss issues and status | Finance lead reports on task completion, RAID log, and budget status; escalate blockers requiring IMO or Steering Committee decision | T-42 | 1/19 | 6/10 | Not Started | 0% |  |  | Low | IMO
FIN-025 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Identify any net operating loss carryforwards and confirm availability post-close | NOL carryforwards are often partially or fully limited by Section 382; quantify the annual limitation | T-42 | 1/19 | 1/27 | Not Started | 0% |  | Section 382 annual limitation on NOL utilization is calculated based on the stock value at close and the long-term tax-exempt rate; limitations can reduce the value of carried losses by 80–90% | High | Legal | NOL utilization — confirmed carryforwards offset future taxable income, reducing cash tax payments | 50 | 10
FIN-026 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review deferred tax assets and liabilities and confirm recoverability | DTAs may be limited under IRC Section 382 post-acquisition; engage tax counsel before signing | T-42 | 1/19 | 1/31 | Not Started | 0% |  | Deferred tax assets tied to losses may be significantly impaired by the ownership change under IRC Section 382; engage tax counsel to model the annual limitation before signing — overvalued DTAs are a common purchase price dispute | High | Legal
FIN-027 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review most recent interim (monthly/quarterly) financial statements | Compare interim results to budget and prior year to identify trend breaks not visible in annual statements | T-42 | 1/19 | 1/31 | Not Started | 0% |  |  | Medium | IMO
FIN-028 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Analyze revenue trends, gross margin, and EBITDA over the last 5 years | Disaggregate by product, geography, and customer concentration; | T-42 | 1/19 | 1/31 | Not Started | 0% |  | Margin compression is a common diligence surprise in acquisitions — revenue may be growing while gross margin is quietly declining due to product mix shift, pricing concessions, or rising COGS; a margin trend that is not identified before close will surface in the first combined earnings report and cannot be explained away as an integration artifact | High | IMO
FIN-029 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Identify and assess all non-recurring, one-time, or extraordinary items | Addbacks must be defensible to auditors and lenders; document each item with source evidence | T-42 | 1/19 | 1/31 | Not Started | 0% |  |  | Medium | Legal
FIN-030 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review management accounts and board reporting packages | Board packs often reveal business issues not visible in financial statements — review at least 8 quarters | T-42 | 1/19 | 1/31 | Not Started | 0% |  |  | Low | IMO
FIN-031 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review accounts receivable aging and identify overdue or disputed balances | Identify any receivables that have been factored or pledged as collateral; confirm DSO vs. industry benchmark | T-42 | 1/19 | 1/31 | Not Started | 0% |  |  | Medium | IMO
FIN-032 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review accounts payable aging and confirm payment terms with key vendors | Early payment discounts may offset costs | T-42 | 1/19 | 1/31 | Not Started | 0% |  |  | Low | IMO
FIN-033 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Obtain and review financial statements for the last 3–5 years | Request audited statements where available; flag any audit qualifications or restatements for immediate escalation | T-42 | 1/19 | 1/31 | Not Started | 0% |  | Target company may resist providing full audited financials outside of a formal data room — confirm access protocol with Legal before requesting; if target is private, audited statements may not exist and compilation financials require additional QoE procedures | High | Legal, IMO
FIN-034 | Compliance & Regulatory | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Identify all regulatory and statutory filing requirements and deadlines | Include SEC, state, local, and international filings; map deadlines into IMO master calendar | T-42 | 1/19 | 2/23 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Legal
FIN-035 | Accounting & Financial Reporting | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Document accounting policy differences across both entities — revenue recognition, inventory valuation, depreciation, lease accounting, goodwill impairment, and other material accounting methodology differences | Gap analysis output drives policy alignment decisions; document divergences in writing for auditor reference | T-41 | 1/20 | 2/3 | Not Started | 0% |  | Undocumented or unreconciled accounting policy differences (revenue recognition, depreciation, leases, goodwill) create restatement risk when the first combined financial statements are prepared; differences that are not documented before Day 1 are discovered during close and delay the first combined reporting cycle | High | Legal
FIN-036 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Analyze working capital trends and identify seasonal or structural fluctuations | Seasonal working capital swings affect the NWC peg calculation; model at least 12 months of monthly data | T-39 | 1/22 | 2/3 | Not Started | 0% |  |  | Medium | IT
FIN-037 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review all off-balance-sheet items, commitments, and contingencies | Off-balance-sheet items include operating leases pre-ASC 842, take-or-pay contracts, and pension obligations | T-39 | 1/22 | 2/6 | Not Started | 0% |  | Confirm with target's auditor that all off-balance-sheet items are disclosed. | High | Legal
FIN-038 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review all letters of credit, guarantees, and contingent financial obligations | Letters of credit and guarantees may require lender consent on change of control; flag immediately to Legal | T-39 | 1/22 | 2/6 | Not Started | 0% |  | Missing required consent from lenders can create high legal exposure | High | Legal
FIN-039 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Confirm all debt obligations and covenants | Covenant compliance must be confirmed at close; some covenants are automatically breached by a change of control | T-39 | 1/22 | 2/6 | Not Started | 0% |  | Change-of-control provisions in debt agreements can trigger automatic acceleration or require lender consent to waive; Legal and Finance must confirm covenant compliance before signing — failure to obtain waivers can block close | High | Legal
FIN-040 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Identify any change-of-control clauses that may be triggered by the transaction | Change-of-control provisions can trigger debt acceleration, contract termination, or consent requirements | T-39 | 1/22 | 2/6 | Not Started | 0% |  | Key customer contracts, software licenses, and government agreements often contain change-of-control clauses requiring notice or consent within 30–60 days of close; failure to notify counterparties in time can trigger termination rights | High | Legal
FIN-041 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review accrued liabilities, provisions, and contingent liabilities on the balance sheet | Environmental, warranty, and litigation reserves are common diligence surprises; require supporting schedules | T-39 | 1/22 | 2/6 | Not Started | 0% |  |  | Medium | Legal
FIN-042 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Identify all pending or threatened litigation and quantify potential financial exposure | Obtain litigation schedule from Legal; quantify range of outcomes and determine whether reserves are adequate | T-39 | 1/22 | 2/6 | Not Started | 0% |  | Undisclosed or under reserved litigation is a top source of post-close disputes; require a complete litigation schedule from target's General Counsel and compare against reserves on the balance sheet — material gaps require SPA indemnity coverage | High | Legal
FIN-043 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Identify any open tax audits, disputes, or outstanding tax liabilities | Open audits create closing risk; confirm whether indemnity coverage in the SPA covers pre-close tax periods | T-39 | 1/22 | 2/6 | Not Started | 0% |  | Open IRS or state tax audits may be closing conditions under the SPA; if audits are in progress, confirm whether escrow or indemnity is required — unresolved audits in excess of threshold amounts can delay or prevent close | High | Legal
FIN-044 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review federal, state, and local tax returns for the last 3–5 years | Focus on unusual deductions, elections, and positions that may not survive IRS scrutiny post-acquisition | T-39 | 1/22 | 2/13 | Not Started | 0% |  | IRS and state tax penalties for late or incorrect filings can be substantial and are assessed against the combined entity from the date of the filing error regardless of which predecessor entity created the problem; unidentified tax exposures in the target's returns become the combined entity's liability at close | High | Legal
FIN-045 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review internal controls framework and assess adequacy for combined entity | Material weaknesses require remediation before first combined audit; factor timeline into integration plan | T-36 | 1/25 | 2/13 | Not Started | 0% |  | If target's external auditors have issued a material weakness opinion, remediation must be underway before the first combined audit period; remediation timelines of 6–12 months are common — factor into integration planning | High | External Auditor
FIN-046 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Assess target company compliance with financial regulations (SEC, PCAOB, FINRA if applicable) | PCAOB inspections and SEC comment letters on prior filings are key risk signals; review before signing | T-36 | 1/25 | 2/13 | Not Started | 0% |  |  | Medium | Legal, Compliance
FIN-047 | Accounting & Financial Reporting | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Confirm compliance with all applicable financial reporting standards (GAAP/IFRS) | Confirm whether target reports under IFRS or local GAAP; conversion to US GAAP may be required | T-36 | 1/25 | 2/3 | Not Started | 0% |  |  | Low | Legal, Compliance
FIN-048 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review inventory valuation and obsolescence risk | Obsolete inventory write-downs affect purchase price; require physical count and third-party valuation if material | T-35 | 1/26 | 2/6 | Not Started | 0% |  |  | Medium | IMO
FIN-049 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | VP Finance / Controller | Ensure synergy owners are assigned to initiatives so there is accountability for each initiative | One owner per synergy line item; co-ownership creates accountability gaps and missed targets | T-35 | 1/26 | 2/27 | Not Started | 0% |  |  | Medium | IMO
FIN-050 | Compliance & Regulatory | Compliance Program Integrated | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Identify change of control triggers in key contracts and tax agreements | Change-of-control triggers must be identified before Day 1; some require third-party consent within a defined window | T-32 | 1/29 | 2/23 | Not Started | 0% | CP – Day 1 Readiness | Change-of-control trigger identification must be completed before Day 1 — some contract clauses require counterparty notice within 5–10 business days of close; missed notice windows can result in automatic contract termination or loss of tax agreements | High | Legal
FIN-051 | Integration Management | Employee Comms Guide Approved | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Review drafts of the M&A Employee Communication Guide (includes talking points, guidance for team conversations, and Q&A / FAQ covering anticipated questions) | Review for tone accuracy around finance-specific topics; provide written feedback to Comm Lead within 72 hours | T-29 | 2/1 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Communications
FIN-052 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Assess tax structure of the deal and confirm optimal post-close entity structure | Tax structure drives post-close cash taxes and integration complexity; alternatives include stock vs. asset election | T-29 | 2/1 | 2/20 | Not Started | 0% |  | Post-close entity structure (stock vs. asset treatment, check-the-box elections) must be decided before signing because some elections are irrevocable; tax counsel and M&A counsel must align before the SPA is executed | High | Legal | Tax structure optimization — post-close entity rationalization reduces effective tax rate and simplifies compliance | 75 | 20
FIN-053 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Assess financial systems landscape — platforms, versions, and integration complexity | A parallel-run period may be required with significant IT resource commitment | T-29 | 2/1 | 2/27 | Not Started | 0% |  | System incompatibility is the top financial integration risk; assess data migration complexity before Day 1 | High | IT
FIN-054 | Accounting & Financial Reporting | Accounting Policy Alignment Complete | Pre-Close | VP FP&A / Integration Manager | Map chart of accounts across both entities and agree on combined structure | Agree on a single target COA before Day 1 reporting; avoid dual-COA approaches beyond the first close | T-29 | 2/1 | 2/27 | Not Started | 0% |  |  | Medium | IT
FIN-055 | Systems & Technology | Day 1 Finance Readiness Confirmed | Pre-Close | VP Finance / Controller | Confirm payroll provider, processing schedule, and payroll continuity plan for all employees | Confirm cutover date, employee data file format, and payroll funding mechanism with HR and payroll provider | T-29 | 2/1 | 2/15 | Not Started | 0% |  | Payroll provider requires 30+ days to onboard a new client entity; if bank account changes are also required, ACH authorization lead times add further delay — initiate no later than 45 days before first payroll run | High | HR, Legal
FIN-056 | Accounting & Financial Reporting | Opening Balance Sheet Finalized | Pre-Close | VP FP&A / Integration Manager | Complete purchase accounting entries and preliminary opening balance sheet | Engage external auditor early; preliminary OBS requires fair value of all assets and liabilities | T-28 | 2/2 | 3/31 | Not Started | 0% |  | Preliminary opening balance sheet requires third-party fair value appraisals for intangibles and fixed assets; appraisal firm must be engaged at least 30 days before close or Day 1 OBS will be estimated only | High | Legal
FIN-057 | Synergy Tracking & Realization | Synergy Realization (Phase 1) Report Done | Pre-Close | VP Finance / Controller | Ensure cost synergies are validated on an ongoing basis by synergy owners | Validation requires owner sign-off on baseline, target, and cost-to-achieve; unvalidated synergies should not be reported to investors | T-26 | 2/4 | 6/10 | Not Started | 0% |  |  | Medium | IMO, All Workstreams
FIN-058 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Complete lease and real estate obligation review — identify consolidation or exit opportunities | Identify leases subject to ASC 842 and flag any with change-of-control or assignment restrictions | T-24 | 2/6 | 2/20 | Not Started | 0% |  |  | Medium | Legal, IMO | Office and corporate real estate consolidation — exiting overlapping office leases in markets where both entities have a presence; scope covers office and corporate facilities only; data center facility exit savings are captured separately under the IT workstream data center migration initiative | 50 | 15
FIN-059 | Governance & Planning | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Prepare investor FAQ and analyst briefing materials covering synergies, integration costs, and timeline | Investor FAQ must be aligned with the synergy model; discrepancies with public guidance are a legal risk | T-24 | 2/6 | 2/25 | Not Started | 0% | CP – Day 1 Readiness | Investor FAQ figures must be cross-checked against the deal model, public filings, and earnings guidance; any discrepancy between the FAQ and other investor-facing materials creates legal risk — General Counsel must approve final version | High | IR, Legal
FIN-060 | Governance & Planning | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | CFO / Finance Workstream Lead | Assess acquisition financing structure and ensure closing funds are committed and available | Confirm funding source, wire instructions, and backup funding mechanism at least 5 days before closing | T-23 | 2/7 | 2/22 | Not Started | 0% | CP – Day 1 Readiness | Acquisition financing must be fully committed at least 5 business days before closing; any lender condition not satisfied by closing date risks deal termination — Finance must manage lender relationships actively through signing to close | High | Legal
FIN-061 | Organization & Talent | Org Design Complete | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Establish interim finance org chart and confirm reporting lines for combined team | Interim org chart prevents reporting confusion on Day 1; distribute to HR and payroll before close | T-15 | 2/15 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Finance staff at the acquired company who do not know their reporting line on Day 1 will seek informal answers from their legacy manager — and the informal hierarchy that forms in the first week is significantly harder to undo than the formal one; a Finance team operating without clear authority lines on Day 1 will also make payment authorization and approval decisions in an ad hoc way, creating audit exposure from the first day of combined operations | High | HR
FIN-062 | Accounting & Financial Reporting | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Build a pro forma combined P&L and balance sheet for Day 1 management review | Pro forma P&L is the primary financial management tool on Day 1 | T-12 | 2/18 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | If delayed, management will be operating without combined financial visibility on Day 1 | High | IMO
FIN-063 | Accounting & Financial Reporting | Synergy Tracking Active | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Set up integration cost tracking codes in the general ledger before Day 1 | Reclassification of integration costs is an audit risk | T-12 | 2/18 | 2/23 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | IMO
FIN-064 | Compliance & Regulatory | Compliance Program Integrated | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Establish the combined company's delegation of authority and financial approval thresholds | Delegation of authority matrix governs who can bind the combined entity; must be active on Day 1 | T-11 | 2/19 | 2/26 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | Legal, Executive Sponsor
FIN-065 | Accounting & Financial Reporting | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Confirm earnout and contingent consideration payment tracking mechanisms | Earnout mechanics must be documented in the GL from Day 1; retroactive setup creates audit and legal risk | T-10 | 2/20 | 2/25 | Not Started | 0% | CP – Day 1 Readiness | Earnout measurement periods begin on Day 1 under most SPAs; failure to establish tracking mechanisms on Day 1 creates disputes about the measurement baseline — Finance must confirm the earnout definition, metrics, and reporting protocol with Legal before close | High | Legal
FIN-066 | Treasury & Cash Management | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Set up interim intercompany settlement mechanism for Day 1 | Document the intercompany settlement rate and approval process; this mechanism is temporary — sunset by Day 30 | T-8 | 2/22 | 2/27 | Not Started | 0% | CP – Day 1 Readiness |  | Medium | IT
FIN-067 | Compliance & Regulatory | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Confirm purchasing and spend approval controls will be active on Day 1 | Verify approval limits are loaded in acquirer's procurement system before any target-entity purchase orders are processed | T-8 | 2/22 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Acquirer's spend approval system (ERP or procurement tool) must be configured with target-entity cost centers and approval hierarchies before Day 1; IT must confirm provisioning no later than T-3 days | High | IT, Procurement
FIN-068 | Systems & Technology | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Confirm revenue recognition and billing processes will be operational on Day 1 | Test billing system end-to-end before Day 1; revenue leakage on Day 1 is a material risk | T-8 | 2/22 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Revenue collection cannot be interrupted on Day 1; billing system cutover must be tested in full before close — any failure to invoice on Day 1 creates immediate cash flow impact and customer escalation risk | High | Sales, IT
FIN-069 | Accounting & Financial Reporting | PPA Valuation Finalized | Pre-Close | CFO / Finance Workstream Lead | Finalize purchase price allocation (PPA) valuation and audit sign-off purchase | PPA drives goodwill, intangibles, and deferred tax entries; delays here cascade into every financial statement line | T-5 | 2/25 | 5/15 | Not Started | 0% |  | Final PPA requires completed intangible asset valuation (customer relationships, technology, trade names) from a qualified third-party appraiser; delays in engaging the appraiser are the most common PPA bottleneck — engage no later than signing | High | Legal
FIN-070 | Treasury & Cash Management | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Validate combined entity bank account signatories and confirm wire transfer authorities will be active on Day 1 | Wire transfer authority must be active before the combined entity can fund payroll, make vendor payments, or execute any treasury transaction on Day 1; confirm with the bank at least 48 hours before close and test with a small internal transfer | T-4 | 2/26 | 2/27 | Not Started | 0% | CP – Day 1 Readiness | Wire transfer authority must be active before the combined entity can fund payroll, make vendor payments, or execute any treasury transaction on Day 1; failure to confirm with the bank before close means the combined entity cannot make financial commitments on Day 1, creating immediate operational paralysis | High | IMO, All Workstreams
FIN-D1 | Integration Management | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | CFO / Finance Workstream Lead | Finance Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | Workstream lead formally certifies Day 1 readiness to the IMO; this gate must be green for every workstream before the IMO signs off on close; any open item at this gate is either resolved or escalated to the steering committee as a close-blocking risk | T-3 | 2/27 | 2/27 | Not Started | 0% | CP – Close | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | High | IMO, All Workstreams
THE DAY 1 AND DAY 100 FINANCE PLANS ARE LOCATED IN THE DAY 1 AND DAY 100 SECTIONS OF MANDAPLAYBOOK.COM

## Milestones
FINANCE M&A MILESTONES
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
Status | Links
Not Started | Integration Plan
Delayed | RAID Log
On Track | Next 14 Days
Complete | Executive Dashboard
Milestone ID | Category | Phase | Assigned To | Milestone | Timing Anchor | Finish | Status | Critical Path
MS-001 | Governance & Planning | Pre-Close | CFO / Finance Workstream Lead | Finance Lead Appointed | T-51 | 1/10 | Not Started | CP – Close
MS-002 | Governance & Planning | Pre-Close | VP Finance / Controller | Finance Integration Governance Established | T-42 | 1/19 | Not Started
MS-003 | Governance & Planning | Pre-Close | VP Finance / Controller | Finance Charter Approved | T-42 | 1/19 | Not Started
MS-004 | Due Diligence | Pre-Close | VP FP&A / Integration Manager | Finance Due Diligence Complete | T-3 | 2/27 | Not Started
MS-005 | Compliance & Regulatory | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Day 1 Finance Readiness Confirmed | T-3 | 2/27 | Not Started | CP – Day 1 Readiness
MS-006 | Synergy Tracking & Realization | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Synergy Tracking Active | T-3 | 2/27 | Not Started
MS-007 | Communications | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Employee Comms Guide Approved | T-3 | 2/27 | Not Started | CP – Day 1 Readiness

## RAID Log
FINANCE M&A RAID LOG (RAID = Risks, Assumptions, Issues, Dependencies)
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
RAID Type | Status | Links
Risk | Open | Integration Plan
Issue | Closed | Milestones
Dependency | Active | Next 14 Days
Assumption | Validated | Executive Dashboard
RAID Type | RAID ID | Related Task ID | Milestone | Owner | Task Description | Issues/Blockers | Status | Mitigation/Action | Timing Anchor | Finish
Assumption | RAID-001 | FIN-001 | Finance Lead Appointed | CFO | The Finance workstream lead and core integration team members will remain available and engaged throughout the full 100-day integration window — it is assumed that key Finance personnel in both entities have been identified, are willing to participate, and will not depart before or immediately after close | If the Finance workstream lead or critical Finance staff depart at or near close, the combined entity loses institutional knowledge of legacy accounting policies, system configurations, vendor relationships, and financial processes that cannot be fully captured in documentation; every downstream integration task from charter development through the final 10-K preparation depends on stable Finance team leadership | Active | CFO to confirm availability and commitment of Finance workstream lead and top 5 critical Finance personnel before close; initiate retention discussions for any at-risk team members identified during due diligence | T-51 | 1/10
Risk | RAID-002 | FIN-001 | Finance Lead Appointed | CFO / Finance Workstream Lead | Identify Finance integration workstream lead and determine members of the Finance integration team | Finance workstream lead must be identified and available before integration kickoff; if the role is filled internally from a team with significant BAU responsibilities, capacity conflict is the most common cause of delayed Finance integration milestones | Open | Name the Finance workstream lead before integration kickoff and confirm capacity allocation; if filled internally, secure backfill for BAU responsibilities to prevent capacity conflict from becoming the primary integration bottleneck | T-51 | 1/10
Risk | RAID-003 | FIN-002 | Finance Integration Governance Established | VP Finance / Controller | Review data privacy and confidentiality protocols for pre-close sharing | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | Open | Conduct a formal clean room briefing for all Finance team members before any data sharing begins; Legal to issue written protocols specifying what data can be reviewed, by whom, and under what conditions; document all pre-close data access | T-49 | 1/12
Dependency | RAID-004 | FIN-010 | Finance Due Diligence Complete | VP Finance / Controller | Identify any material weaknesses or significant deficiencies noted by auditors | Material weaknesses identified by target's prior auditors must be disclosed in the acquirer's next SEC filing if not remediated; escalate immediately to CFO and General Counsel — requires board audit committee awareness | Open | Obtain the target's audit reports including any management letters before close; if a material weakness exists, assess scope with the combined entity's external auditor and develop a remediation roadmap before first combined 10-Q filing | T-40 | 1/21
Risk | RAID-005 | FIN-016 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Identify any unusual cash movements or related-party transactions | Unusual cash movements or related-party loans at non-arm's-length rates require restatement before any closing price adjustment; if undisclosed, they trigger SPA indemnity claims | Open | Require target management to provide a written representation that all related-party transactions are fully disclosed and at arm's-length; escalate any exceptions to CFO and Legal before SPA signing; add to rep and warranty scope | T-39 | 1/22
Risk | RAID-006 | FIN-025 | Finance Due Diligence Complete | VP Finance / Controller | Identify any net operating loss carryforwards and confirm availability post-close | Section 382 annual limitation on NOL utilization is calculated based on the stock value at close and the long-term tax-exempt rate; limitations can reduce the value of carried losses by 80–90% | Open | Engage external tax counsel to model Section 382 annual NOL limitation immediately; calculate the limitation based on stock value at close; quantify the NPV impact of restricted NOL utilization and incorporate into the deal model | T-34 | 1/27
Risk | RAID-007 | FIN-026 | Finance Due Diligence Complete | VP Finance / Controller | Review deferred tax assets and liabilities and confirm recoverability | Deferred tax assets tied to losses may be significantly impaired by the ownership change under IRC Section 382; engage tax counsel to model the annual limitation before signing — overvalued DTAs are a common purchase price dispute | Open | Engage external tax counsel to assess DTA recoverability under the post-close ownership structure; model the valuation allowance impact on the opening balance sheet; confirm treatment with external auditor before preliminary PPA is released | T-30 | 1/31
Risk | RAID-008 | FIN-028 | Finance Due Diligence Complete | VP Finance / Controller | Analyze revenue trends, gross margin, and EBITDA over the last 5 years | Margin compression is a common diligence surprise in acquisitions — revenue may be growing while gross margin is quietly declining due to product mix shift, pricing concessions, or rising COGS; a margin trend that is not identified before close will surface in the first combined earnings report and cannot be explained away as an integration artifact | Open | Require target management to provide gross margin by product line and customer segment; engage QoE advisor to validate margin trajectory; model the combined entity P&L using adjusted gross margin and flag any trends requiring price or cost action | T-30 | 1/31
Risk | RAID-009 | FIN-033 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Obtain and review financial statements for the last 3–5 years | Target company may resist providing full audited financials outside of a formal data room — confirm access protocol with Legal before requesting; if target is private, audited statements may not exist and compilation financials require additional QoE procedures | Open | Require full audited financials for the prior 3 fiscal years as a closing condition in the SPA; if target resists, escalate to deal counsel; do not proceed to close without audited statements — unaudited financials create material restatement risk | T-30 | 1/31
Assumption | RAID-010 | FIN-056 | Opening Balance Sheet Finalized | VP Finance / Controller | The acquired company's financial statements are accurate, complete, and free of material misstatements — it is assumed that the quality of earnings assessment and pre-close due diligence have identified all material adjustments, and that no significant undisclosed liabilities, revenue recognition issues, or accounting policy differences will surface post-close that require material restatement | If material undisclosed accounting issues are discovered post-close, the purchase price allocation, opening balance sheet, and first combined financial statements will require revision; this creates regulatory exposure (SEC restatement), auditor relationship risk, and potential representations and warranties insurance claims; it also delays the first combined 10-Q and disrupts the integration timeline for all Finance workstream tasks that depend on clean financial data | Active | VP Finance / Controller to complete a rapid financial statement validation in the first 14 days post-close; any material differences between due diligence findings and actual financial position to be escalated to the CFO and General Counsel immediately; engage auditors to assess materiality of any differences within 5 business days of discovery | T+29 | 3/31
Risk | RAID-011 | FIN-035 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Document accounting policy differences across both entities — revenue recognition, inventory valuation, depreciation, lease accounting, goodwill impairment, and other material accounting methodology differences | Undocumented or unreconciled accounting policy differences (revenue recognition, depreciation, leases, goodwill) create restatement risk when the first combined financial statements are prepared; differences that are not documented before Day 1 are discovered during close and delay the first combined reporting cycle | Open | Complete an accounting policy comparison across all material policies before close; document differences in a policy gap register; CFO to approve resolution approach for each gap; brief external auditor on combined entity accounting policies before Day 1 | T-27 | 2/3
Risk | RAID-012 | FIN-037 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Review all off-balance-sheet items, commitments, and contingencies | Confirm with target's auditor that all off-balance-sheet items are disclosed. | Open | Require target management to provide a complete schedule of off-balance-sheet commitments with quantified financial exposure; confirm scope with external auditor; add unquantified contingencies to the rep and warranty insurance scope | T-24 | 2/6
Risk | RAID-013 | FIN-038 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Review all letters of credit, guarantees, and contingent financial obligations | Missing required consent from lenders can create high legal exposure | Open | Obtain written confirmation from each lender that consent is not required or has been obtained before close; where consent is required, initiate outreach at least 60 days before close; do not proceed to close with unresolved lender consent requirements | T-24 | 2/6
Risk | RAID-014 | FIN-039 | Finance Due Diligence Complete | VP Finance / Controller | Confirm all debt obligations and covenants | Change-of-control provisions in debt agreements can trigger automatic acceleration or require lender consent to waive; Legal and Finance must confirm covenant compliance before signing — failure to obtain waivers can block close | Open | Map all debt instruments to their change-of-control provisions immediately; engage deal counsel to assess acceleration risk; initiate lender consent process at least 60 days before close; confirm covenant compliance calculations for the combined entity | T-24 | 2/6
Risk | RAID-015 | FIN-040 | Finance Due Diligence Complete | VP Finance / Controller | Identify any change-of-control clauses that may be triggered by the transaction | Key customer contracts, software licenses, and government agreements often contain change-of-control clauses requiring notice or consent within 30–60 days of close; failure to notify counterparties in time can trigger termination rights | Open | Complete a full contract-by-contract review of change-of-control clauses in all material customer, supplier, and license agreements; assign Legal to lead consent outreach for any agreement requiring counterparty approval before close | T-24 | 2/6
Risk | RAID-016 | FIN-042 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Identify all pending or threatened litigation and quantify potential financial exposure | Undisclosed or under reserved litigation is a top source of post-close disputes; require a complete litigation schedule from target's General Counsel and compare against reserves on the balance sheet — material gaps require SPA indemnity coverage | Open | Require a complete litigation schedule from target management and outside counsel as a closing condition; quantify financial exposure for each matter; confirm reserve adequacy with external auditor; add undisclosed litigation to rep and warranty insurance scope | T-24 | 2/6
Risk | RAID-017 | FIN-043 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Identify any open tax audits, disputes, or outstanding tax liabilities | Open IRS or state tax audits may be closing conditions under the SPA; if audits are in progress, confirm whether escrow or indemnity is required — unresolved audits in excess of threshold amounts can delay or prevent close | Open | Confirm the status of all open tax audits with target's tax counsel before close; negotiate SPA indemnity provisions that protect acquirer from pre-close tax liabilities; confirm that all open audit periods are included in the indemnity schedule | T-24 | 2/6
Risk | RAID-018 | FIN-044 | Finance Due Diligence Complete | VP Finance / Controller | Review federal, state, and local tax returns for the last 3–5 years | IRS and state tax penalties for late or incorrect filings can be substantial and are assessed against the combined entity from the date of the filing error regardless of which predecessor entity created the problem; unidentified tax exposures in the target's returns become the combined entity's liability at close | Open | Obtain and review federal, state, and local tax returns for the last 5 years; flag any positions that appear aggressive or inconsistent with current law; engage external tax counsel to assess exposure; confirm all returns were timely filed and no extensions are open | T-17 | 2/13
Risk | RAID-019 | FIN-045 | Finance Due Diligence Complete | VP Finance / Controller | Review internal controls framework and assess adequacy for combined entity | If target's external auditors have issued a material weakness opinion, remediation must be underway before the first combined audit period; remediation timelines of 6–12 months are common — factor into integration planning | Open | Obtain copy of internal controls assessment and any auditor communications regarding deficiencies; develop a remediation plan with Controller and external auditor; implement compensating controls on Day 1 where material weaknesses cannot be remediated before close | T-17 | 2/13
Dependency | RAID-020 | FIN-055 | Day 1 Finance Readiness Confirmed | VP Finance / Controller | Confirm payroll provider, processing schedule, and payroll continuity plan for all employees | Payroll provider requires 30+ days to onboard a new client entity; if bank account changes are also required, ACH authorization lead times add further delay — initiate no later than 45 days before first payroll run | Open | Initiate payroll provider onboarding immediately — minimum 30-day lead time required; confirm bank account setup, tax ID registrations, and payroll funding mechanisms before the first pay cycle; run a parallel payroll cycle at least two weeks before cutover | T-15 | 2/15
Risk | RAID-021 | FIN-052 | Finance Due Diligence Complete | VP Finance / Controller | Assess tax structure of the deal and confirm optimal post-close entity structure | Post-close entity structure (stock vs. asset treatment, check-the-box elections) must be decided before signing because some elections are irrevocable; tax counsel and M&A counsel must align before the SPA is executed | Open | Engage external tax counsel to determine optimal post-close entity structure before close; confirm check-the-box elections and IRC 338 decisions with tax counsel; document elections in board resolutions and file within required IRS deadlines | T-10 | 2/20
Risk | RAID-022 | FIN-017 | Finance Due Diligence Complete | VP Finance / Controller | Assess quality of earnings — confirm reported EBITDA reflects true operating performance | Seller may resist reclassifying addbacks that inflate EBITDA; engage QoE advisor early — disputes over addbacks directly affect purchase price and often require SPA representations to resolve | Open | Engage a quality of earnings advisor early in the process; require target management to formally respond to all addback reclassifications in writing; model both adjusted and unadjusted EBITDA scenarios for purchase price sensitivity analysis | T-8 | 2/22
Risk | RAID-023 | FIN-018 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Review and validate purchase price and deal economics vs. original investment thesis | If due diligence findings produce EBITDA adjustments exceeding agreed thresholds, purchase price renegotiation or additional SPA representations may be required; Finance must present findings to CFO before final price is locked | Open | Model purchase price impact of any EBITDA adjustments exceeding 10% of deal thesis; escalate material findings to CFO and deal counsel immediately; confirm SPA price adjustment mechanism can accommodate material changes before close | T-8 | 2/22
Risk | RAID-024 | FIN-060 | Day 1 Finance Readiness Confirmed | CFO / Finance Workstream Lead | Assess acquisition financing structure and ensure closing funds are committed and available | Acquisition financing must be fully committed at least 5 business days before closing; any lender condition not satisfied by closing date risks deal termination — Finance must manage lender relationships actively through signing to close | Open | Confirm financing commitments with lenders at least 10 business days before close; obtain executed commitment letters; confirm closing funds availability and wire instructions with treasury; have a contingency financing plan approved by CFO if primary funding falls through | T-8 | 2/22
Risk | RAID-025 | FIN-050 | Compliance Program Integrated | VP Finance / Controller | Identify change of control triggers in key contracts and tax agreements | Change-of-control trigger identification must be completed before Day 1 — some contract clauses require counterparty notice within 5–10 business days of close; missed notice windows can result in automatic contract termination or loss of tax agreements | Open | Complete the change-of-control contract review before close; for any contract requiring counterparty consent, send written consent requests at least 30 days before close; track responses weekly and escalate unresolved consents to CFO and deal counsel | T-7 | 2/23
Risk | RAID-026 | FIN-059 | Day 1 Finance Readiness Confirmed | VP FP&A / Integration Manager | Prepare investor FAQ and analyst briefing materials covering synergies, integration costs, and timeline | Investor FAQ figures must be cross-checked against the deal model, public filings, and earnings guidance; any discrepancy between the FAQ and other investor-facing materials creates legal risk — General Counsel must approve final version | Open | Complete investor FAQ and analyst briefing materials at least 5 business days before close; route through IR, Legal, and CFO for approval; cross-check all synergy figures against the deal model and confirm consistency with any public guidance already issued | T-5 | 2/25
Risk | RAID-027 | FIN-065 | Day 1 Finance Readiness Confirmed | VP Finance / Controller | Confirm earnout and contingent consideration payment tracking mechanisms | Earnout measurement periods begin on Day 1 under most SPAs; failure to establish tracking mechanisms on Day 1 creates disputes about the measurement baseline — Finance must confirm the earnout definition, metrics, and reporting protocol with Legal before close | Open | Establish earnout tracking mechanisms in the GL and management reporting before close; assign the Controller as primary owner of earnout compliance; confirm measurement methodology with Legal and target management before Day 1 | T-5 | 2/25
Risk | RAID-028 | FIN-019 | Finance Due Diligence Complete | VP Finance / Controller | Review and validate net working capital peg and adjustment mechanism | NWC peg is typically negotiated as a trailing 12-month average but sellers often propose a higher peg using peak periods; if the definition is disputed at close, the SPA mechanism governs | Open | Engage legal counsel to review NWC peg methodology and SPA adjustment mechanism before close; model high, base, and low NWC scenarios; assign Controller to lead true-up calculation with a target completion of Day 60 post-close | T-3 | 2/27
Risk | RAID-029 | FIN-053 | Finance Due Diligence Complete | VP Finance / Controller | Assess financial systems landscape — platforms, versions, and integration complexity | System incompatibility is the top financial integration risk; assess data migration complexity before Day 1 | Open | Complete a full financial systems inventory documenting all platforms, versions, and integration touchpoints before close; prioritize systems on the Day 1 critical path; assign IT workstream lead to own the systems integration plan with Finance | T-3 | 2/27
Risk | RAID-030 | FIN-061 | Org Design Complete | VP Finance / Controller | Establish interim finance org chart and confirm reporting lines for combined team | Finance staff at the acquired company who do not know their reporting line on Day 1 will seek informal answers from their legacy manager — and the informal hierarchy that forms in the first week is significantly harder to undo than the formal one; a Finance team operating without clear authority lines on Day 1 will also make payment authorization and approval decisions in an ad hoc way, creating audit exposure from the first day of combined operations | Open | Issue the interim org chart to all Finance managers on Day 1 before 9am local time; conduct a brief all-Finance team call on Day 1 to confirm reporting lines; assign an HR business partner to handle any employee concerns about the new structure in Week 1 | T-3 | 2/27
Risk | RAID-031 | FIN-062 | Day 1 Finance Readiness Confirmed | VP FP&A / Integration Manager | Build a pro forma combined P&L and balance sheet for Day 1 management review | If delayed, management will be operating without combined financial visibility on Day 1 | Open | Complete the combined pro forma P&L and balance sheet with VP FP&A no later than 48 hours before Day 1; have CFO review and approve before distribution; distribute to all Finance managers and the executive team on Day 1 morning | T-3 | 2/27
Risk | RAID-032 | FIN-067 | Day 1 Finance Readiness Confirmed | VP FP&A / Integration Manager | Confirm purchasing and spend approval controls will be active on Day 1 | Acquirer's spend approval system (ERP or procurement tool) must be configured with target-entity cost centers and approval hierarchies before Day 1; IT must confirm provisioning no later than T-3 days | Open | Configure the combined entity's spend approval workflow in the ERP before Day 1; test approval routing for all cost centers that will be active on Day 1; communicate the new approval thresholds and workflow to all Finance managers before close | T-3 | 2/27
Risk | RAID-033 | FIN-068 | Day 1 Finance Readiness Confirmed | VP Finance / Controller | Confirm revenue recognition and billing processes will be operational on Day 1 | Revenue collection cannot be interrupted on Day 1; billing system cutover must be tested in full before close — any failure to invoice on Day 1 creates immediate cash flow impact and customer escalation risk | Open | Test billing and invoicing system end-to-end before Day 1 cutover; validate the customer master data migration with the Controller; confirm AR collection continuity with the combined entity's bank; have a manual invoicing backup process ready if the system fails on Day 1 | T-3 | 2/27
Dependency | RAID-034 | FIN-070 | Day 1 Finance Readiness Confirmed | VP Finance / Controller | Validate combined entity bank account signatories and confirm wire transfer authorities will be active on Day 1 | Wire transfer authority must be active before the combined entity can fund payroll, make vendor payments, or execute any treasury transaction on Day 1; failure to confirm with the bank before close means the combined entity cannot make financial commitments on Day 1, creating immediate operational paralysis | Open | Hold the Day 1 Readiness review with all Finance workstream leads at least 48 hours before close; any item not green requires CFO decision to proceed or delay; document the readiness decision with a signed sign-off record | T-3 | 2/27
Risk | RAID-035 | FIN-D1 | Day 1 Finance Readiness Confirmed | CFO / Finance Workstream Lead | Finance Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | Open | Hold the Day 1 Readiness Gate review with CFO and all Finance leads 48 hours before close; any critical gap identified at this gate requires an immediate escalation decision — proceed with compensating control, delay specific activity, or pause close | T-3 | 2/27

## Next 14 Days
FINANCE M&A NEXT 14 DAYS ACTIVITIES
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Milestones
Low | On Track | RAID Log
| Complete | Executive Dashboard
Task ID | Category | Phase | Assigned To | Description | Risk Level | Timing Anchor | Start | Finish | Status | Critical Path
FIN-001 | Governance & Planning | Pre-Close | CFO / Finance Workstream Lead | Identify Finance integration workstream lead and determine members of the Finance integration team | High | T-59 | 1/2 | 1/10 | Not Started | CP – Close
FIN-002 | Governance & Planning | Pre-Close | VP Finance / Controller | Review data privacy and confidentiality protocols for pre-close sharing | High | T-53 | 1/8 | 1/12 | Not Started
FIN-003 | Due Diligence | Pre-Close | VP FP&A / Integration Manager | Assess normalized working capital requirements for the combined entity | Medium | T-51 | 1/10 | 1/20 | Not Started
FIN-004 | Governance & Planning | Pre-Close | CFO / Finance Workstream Lead | Attend IMO Kickoff Meeting | Low | T-50 | 1/11 | 1/11 | Not Started
FIN-005 | Governance & Planning | Pre-Close | VP FP&A / Integration Manager | Receive access to integration data room and document repository | Low | T-49 | 1/12 | 1/13 | Not Started
FIN-006 | Governance & Planning | Pre-Close | CFO / Finance Workstream Lead | Hold Finance Integration Kickoff Meeting | Low | T-49 | 1/12 | 1/12 | Not Started
FIN-007 | Governance & Planning | Pre-Close | VP Finance / Controller | Develop the Finance workstream integration charter and confirm team roles and responsibilities | Low | T-49 | 1/12 | 1/19 | Not Started
FIN-008 | Integration Management | Pre-Close | VP FP&A / Integration Manager | Develop Finance integration plan (tasks, milestones, RAID log, Day 1 checklist) . Plan of record will be at 3/31. Significant plan changes subsequent to that date must go through formal change approval process. | Medium | T-49 | 1/12 | 3/31 | Not Started
FIN-009 | Due Diligence | Pre-Close | VP Finance / Controller | Confirm all insurance policies — D&O, E&O, general liability, property — and coverage limits | Medium | T-49 | 1/12 | 1/21 | Not Started
FIN-010 | Due Diligence | Pre-Close | VP Finance / Controller | Identify any material weaknesses or significant deficiencies noted by auditors | High | T-49 | 1/12 | 1/21 | Not Started
FIN-011 | Due Diligence | Pre-Close | VP Finance / Controller | Review external auditor relationship, audit fees, and most recent management letter | Low | T-49 | 1/12 | 1/21 | Not Started
FIN-012 | Accounting & Financial Reporting | Pre-Close | VP Finance / Controller | Review chart of accounts structure and identify gaps or conflicts with acquirer | Medium | T-49 | 1/12 | 1/21 | Not Started
FIN-013 | Due Diligence | Pre-Close | VP FP&A / Integration Manager | Confirm sales tax, VAT, and indirect tax compliance across all jurisdictions | Medium | T-49 | 1/12 | 1/23 | Not Started
FIN-014 | Governance & Planning | Pre-Close | VP FP&A / Integration Manager | Define Finance integration success metrics and KPIs | Low | T-49 | 1/12 | 1/19 | Not Started
FIN-015 | Governance & Planning | Pre-Close | VP Finance / Controller | Circulate integration roles and responsibilities to all finance team members — confirm who owns each workstream task and who escalates to whom | Medium | T-49 | 1/12 | 1/19 | Not Started
FIN-016 | Due Diligence | Pre-Close | VP FP&A / Integration Manager | Identify any unusual cash movements or related-party transactions | High | T-46 | 1/15 | 1/22 | Not Started
FIN-017 | Due Diligence | Pre-Close | VP Finance / Controller | Assess quality of earnings — confirm reported EBITDA reflects true operating performance | High | T-46 | 1/15 | 2/22 | Not Started
FIN-018 | Due Diligence | Pre-Close | VP FP&A / Integration Manager | Review and validate purchase price and deal economics vs. original investment thesis | High | T-46 | 1/15 | 2/22 | Not Started
FIN-019 | Treasury & Cash Management | Pre-Close | VP Finance / Controller | Review and validate net working capital peg and adjustment mechanism | High | T-46 | 1/15 | 2/27 | Not Started

## Executive Dashboard
HR M&A MILESTONES REPORT | FINANCE M&A EXECUTIVE DASHBOARD
TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE — 1/1/2026) | TODAY'S DATE: T-60 (60 DAYS BEFORE CLOSE)
TASKS
|  |  | TOTAL TASKS |  | NOT STARTED |  | DELAYED |  | ON TRACK | COMPLETE
|  |  | 71 |  | 71 |  | 0 |  | 0 | 0
| MILESTONES |  |  | PROGRESS BY PHASE TASKS DONE/TASKS |  |  |  | RAID LOG |  | ANNUAL SYNERGIES
| Not Started | 7 |  | Pre-Close | 0/71 |  |  | Open Risks | 30 | Targeted Synergies | $175K
| Delayed | 0 | [5 empty] | Open Items | 35 | Realized Synergies | $0K
| On Track | 0 | [5 empty] | Open Issues | 0 | Cost to Achieve Budget | $45K
| Complete | 0 | [5 empty] | Dependencies | 3 | Actual CTA | $0K
| CRITICAL PATH MILESTONES | [6 empty] | NEXT 14 DAYS |  | DAY 1 | TASKS DONE/TASKS
|  |  |  | Phase | Target Date | Status |  | Total | 19 | Day 1 Readiness | 0/15
| Finance Lead Appointed |  |  | Pre-Close | 1/10 | Not Started |  | On Critical Path | 1
| Finance Integration Governance Established |  |  | Pre-Close | 1/19 | Not Started
| Finance Charter Approved |  |  | Pre-Close | 1/19 | Not Started |  | LINKS
| Finance Due Diligence Complete |  |  | Pre-Close | 2/27 | Not Started |  | Integration Plan |  | Milestones
| Day 1 Finance Readiness Confirmed |  |  | Pre-Close (Day 1 Readiness) | 2/27 | Not Started |  | Next 14 Days |  | RAID Log
| Synergy Tracking Active |  |  | Pre-Close (Day 1 Readiness) | 2/27 | Not Started