## Slide 1
HUMAN RESOURCES
M&A INTEGRATION
KICKOFF MEETING
Bringing Every HR Team Member Up to Speed Before Detailed Planning Begins
100-Day Advisors
100-DAY POST-MERGER INTEGRATION PLAYBOOK

## Slide 2
VALUE DRIVERS
Why HR is the most people-critical workstream in any integration
© Copyright 100-Day Advisors | HR Integration Kickoff
1
Talent Retention
The acquirer's biggest risk isn't legal or financial — it's losing the people the deal was built on. HR's first job is identifying who can't be lost and building a retention strategy before Day 1.
Payroll & Benefits Continuity
Every acquired employee is watching their first paycheck. A payroll error on the first pay cycle is an employee relations crisis. Flawless execution here is the baseline, not the goal.
Compliance Risk Elimination
The combined entity inherits every HR liability from the target — WARN Act exposure, EEOC charges, OSHA violations, I-9 gaps, contractor misclassification. HR's diligence work surfaces and remediates this before close.
Cultural Integration
Culture clash is the silent deal killer. HR owns the culture assessment, the onboarding program, and the pulse surveys that tell leadership whether two organizations are actually becoming one.
Org Design & Synergy Delivery
Headcount synergies are a value driver. HR owns the org design process, validates actuals against the deal model, and ensures every elimination is handled compliantly and humanely.

## Slide 3
SUCCESS METRICS
How we measure HR integration success — tracked weekly and reported to IMO
© Copyright 100-Day Advisors | HR Integration Kickoff
2
Retention
Zero unplanned departures of identified key talent through Day 100
Day 30 and Day 60 pulse surveys completed; attrition by team and manager tracked weekly
Retention bonus payments issued to identified key talent on schedule
Payroll & Benefits
Zero payroll errors on the first combined pay cycle
Benefits enrollment completed for 100% of acquired employees within 30 days
401(k), FSA, HSA, and all benefit elections loaded in carrier systems by Day 30
Compliance
All Day 1 legal notices issued on time — WARN, ERISA, benefit change notifications
No new EEOC charges, DOL actions, or I-9 violations attributable to integration
All contractor misclassification risks documented and remediation plans in place
Org Design & Synergies
Formal org structure finalized and communicated by Day 91
Headcount actuals validated against synergy model — variances >5% escalated
HRIS migration complete; all acquired records in system of record by Day 60

## Slide 4
EXTENT OF INTEGRATION
What HR unifies immediately, what is phased, and what transitions to BAU
© Copyright 100-Day Advisors | HR Integration Kickoff
3
DAY 1 — UNIFIED
Reporting lines and interim org structure
Code of conduct, ethics policies, conflicts of interest
Expense reimbursement policy
HR integration inbox and hotline
Employee handbook distributed
CHRO welcome message and Day 1 FAQ
Day 1 separations handled compliantly
PHASED — DAYS 1 TO 100
Payroll: acquired employees on combined payroll by Day 30
Benefits enrollment: open and confirmed by Day 30
Compensation alignment: total comp comparison to CHRO by Day 60
HRIS migration: all records migrated by Day 60
Org design: final structure announced by Day 91
Retention bonuses: issued to key talent by Day 60
Combined bonus plan: designed and communicated by Day 60
TRANSITION TO BAU
Succession planning for critical roles
Combined HR reporting dashboard (headcount, attrition, cost)
Unified hiring, promotion, and mobility policies
Harmonized remote/hybrid work policies
Backfill of roles created by departures or restructuring
HR retrospective and lessons learned at Day 100

## Slide 5
END STATES — WHAT 'INTEGRATION COMPLETE' LOOKS LIKE
Observable outcomes that signal HR is done — by audience
© Copyright 100-Day Advisors | HR Integration Kickoff
4
FOR THE BOARD
Headcount synergies confirmed against deal model at Day 100 gate
Benefit cost savings locked and reported to CFO
HR integration summary delivered: workforce metrics, open items, BAU handoff
FOR MANAGERS
Clear reporting lines effective from Day 1 — no ambiguity about who reports to whom
Talking points, Q&A guides, and escalation paths in hand before first employee conversation
HR hotline and integration intranet live with answers to common questions
FOR ACQUIRED EMPLOYEES
First paycheck correct, on time, and from the right entity
Benefits enrolled, coverage active, and carrier contacts known
One handbook, one set of policies, one HR team to call
FOR HR TEAM
HRIS fully migrated; all employee records in combined system of record
Combined HR dashboard live: headcount, attrition, open roles, cost metrics
Retrospective complete; lessons documented in M&A playbook before team disperses

## Slide 6
NON-NEGOTIABLES
HR requirements that cannot be deferred, delegated, or compromised
© Copyright 100-Day Advisors | HR Integration Kickoff
5
Zero Payroll Errors on Cycle 1
Every acquired employee's pay rate, pay cycle, and payroll entity must be validated before the first cycle runs. A payroll failure on the first combined paycheck is an immediate employee relations crisis and a legal exposure.
WARN Act Timing Is Fixed By Law
If Day 1 includes workforce reductions, the 60-day WARN notice clock is non-negotiable. Separation packages must be prepared and compliant before any communication happens. HR owns this — not Legal alone.
Key Talent Identified Before Close
Retention risk assessment for every senior leader and key manager is complete before the deal closes. Retention bonuses are structured and approved before those employees have a reason to start looking.
Managers Briefed Before Employees
Every people manager receives talking points, a Q&A guide, and a clear escalation path before any employee-facing communication goes out.
Day 1 Separations Are Handled First
If any roles are eliminated on Day 1, those conversations happen before anything else. In-person, prepared, compliant packages ready to hand over. This is not a task that gets scheduled for Day 2.
Benefits Enrollment Has a Hard Deadline
Acquired employees must complete benefits enrollment within the legally required window. Missed elections mean coverage gaps. HR owns the communication, the system setup, and the confirmation that every election is loaded in carrier systems.

## Slide 7
GOVERNANCE MODEL
Who owns what — HR sub-workstream leads and their responsibilities
© Copyright 100-Day Advisors | HR Integration Kickoff
6
CHRO / HR Workstream Lead
Single accountable owner. Certifies Day 1 readiness to IMO. Attends Steering Committee. Approves org design, comp plan, and all employee-facing communications.
HR Integration Manager
Owns the integration plan, RAID log, and weekly IMO status. Manages the master HR milestone tracker and coordinates all sub-workstream leads.
Compensation Analyst
Owns total comp comparison, bonus plan design, equity inventory, 280G assessment, 409A review, and retention bonus program design.
Benefits & Compensation Manager
Owns benefits enrollment, carrier alignment, 401(k) plan harmonization, FSA/HSA, PTO, life and disability alignment, and COBRA compliance.
HR Compliance Manager
Owns WARN Act, ERISA notices, I-9 compliance, EEOC/DOL history, OSHA review, severance policy, contractor misclassification, and employee handbook.
HRIS & Systems Manager
Owns HR technology inventory, HRIS migration, payroll system setup, combined employee directory, self-service portal, and HR reporting dashboard.

## Slide 8
GUIDING PRINCIPLES
The criteria that guide every HR integration decision
© Copyright 100-Day Advisors | HR Integration Kickoff
7
01
People First, Process Second
Integration efficiency matters. However, unnecessary employee friction is a cost that shows up in attrition and poor morale.
02
Retention Is the First Metric
Every HR decision is evaluated against its impact on key talent. The org design, the comp plan, the communication strategy — all of it runs through the lens of who we cannot afford to lose.
03
Compliance Is Non-Negotiable
WARN Act timing, ERISA notices, benefits enrollment windows, and I-9 requirements are set by law. Integration timelines are built around them — they don't bend for integration convenience.
04
Managers Are the Message
The manager is the most trusted source of information for most employees. Brief them first. Give them tools. If a manager is surprised by integration news, we've already failed that employee.
05
Diagnose Before You Prescribe
Total comp comparisons, culture assessments, and engagement survey data must be in hand before org design or comp decisions are finalized.
06
Surface Attrition Signals Early
Weekly attrition monitoring by team, manager, function, and location is not optional. A pattern spotted at Week 3 can be addressed. The same pattern spotted at Day 60 is a retention crisis.
07
Day 1 Separations Are Done Right
No cost-cutting decision justifies handling a separation carelessly. Every impacted employee gets an in-person conversation, a compliant package, and a clear answer to what happens next.
08
The Playbook Gets Better
At Day 100, HR documents what worked and what didn't across diligence, onboarding, benefits, HRIS, and org design. Those lessons go into the M&A playbook before the team disperses.

## Slide 9
CORE MESSAGES
What every HR team member must be able to communicate from Day 1
© Copyright 100-Day Advisors | HR Integration Kickoff
8
WHY THIS DEAL
This acquisition creates a combined organization with greater scale, capability, and talent. HR's role is to make sure the people side of the deal delivers what the financial model assumed.
WHAT CHANGES ON DAY 1
New reporting lines are live. The employee handbook, expense policy, and code of conduct apply to all staff. The HR hotline and intranet are open for questions.
WHAT STAYS THE SAME
Existing employment terms continue until employees are formally notified of any change. No comp or benefits change without advance notice and a clear transition plan.
HOW DECISIONS GET MADE
The CHRO owns all HR integration decisions. Comp, org design, and employee-facing communications require CHRO approval. Escalate through your sub-workstream lead to the HR Integration Manager.
WHAT WE ASK OF THE HR TEAM
Update your section of the plan weekly. Escalate issues within 24 hours — never absorb a problem quietly. Every task has a named owner. If it doesn't have your name on it, it still gets escalated if you see it slipping.
WHEN THIS IS COMPLETE
HR integration closes at Day 100. Payroll unified, benefits enrolled, HRIS migrated, org design final, synergies confirmed. Every open item has a named BAU owner.

## Slide 10
INTEGRATION TIMELINE
HR milestones across three phases — Pre-Close through Day 100
© Copyright 100-Day Advisors | HR Integration Kickoff
9
PRE-CLOSE
T-60 Days to Close
HR Lead and team appointed
Full diligence: comp, benefits, equity, employment agreements, compliance, HRIS
Culture assessment completed
Retention risk assessment: all senior leaders and key managers
Interim org structure determined
Day 1 separations identified; packages prepared
Payroll funding accounts and payroll tax IDs ready
Employee handbook, benefits card, Day 1 FAQ ready
HR hotline and intranet tested and staffed
Day 1 Readiness Gate certified by CHRO
DAY 1 / WEEK 1
CEO and CHRO welcome message distributed
Managers briefed with talking points before employee comms
Day 1 separations handled in person
HR intranet live with org chart, FAQ, contacts
Acquired HR team briefed on combined processes
Code of conduct and expense policy communicated
401(k) enrollment comms distributed
Week 1 HR town hall completed
DAYS 8–100
Day 30: Acquired employees on combined payroll
Day 30: Benefits enrollment complete; carriers loaded
Day 30: Pulse survey and Day 30 gate review
Day 60: Total comp comparison to CHRO
Day 60: Retention bonuses issued to key talent
Day 60: HRIS migration complete
Day 60: Combined bonus plan communicated
Day 60: Pulse survey and cultural assessment
Day 91: Formal org structure announced
Day 100: Synergies confirmed; HR gate closed

## Slide 11
DUE DILIGENCE RULES OF ENGAGEMENT
Pre-close data sharing guidelines every HR team member must follow
© Copyright 100-Day Advisors | HR Integration Kickoff
10
WHAT YOU MAY AND MAY NOT DO
All HR data access is governed by clean room protocols — confirm scope with Legal before reviewing any non-public target employee or compensation data
No HR team member may contact a named target employee about their role, comp, or future before Legal authorizes outreach
Headcount, compensation, and benefits data from the target may only be reviewed within the Legal-approved data room scope
Any diligence finding that affects deal terms or integration assumptions is escalated to the HR Lead and Legal immediately
Clean room protocols apply to every HR team member — not just the HR Lead; brief your team before they receive data room access
No HR team member may communicate org design decisions, role eliminations, or headcount plans to target employees or managers before close
If unsure whether a pre-close HR action is permitted — stop and ask the HR Integration Manager or Legal before proceeding
CONSEQUENCES OF VIOLATIONS
Sharing headcount, compensation, or benefits data before close constitutes gun-jumping under HSR antitrust rules. The document trail is the violation — intent doesn't matter. Penalties can delay or block deal closing.
WHEN IN DOUBT — STOP AND ASK
Before accessing any target employee data or taking any pre-close HR action: contact the HR Integration Manager or Legal. The data room agreement defines what is in scope. If it is not explicitly permitted, it is not permitted.

## Slide 12
100-DAY ADVISORS
Accelerating M&A Integrations
MandAPlaybook.com
inquiries@MandAPlaybook.com