## Slide 1
INTEGRATION MANAGEMENT OFFICE (IMO)
M&A INTEGRATION
KICKOFF MEETING
Aligning Every Integration Lead Before Planning Begins
100-Day Advisors
100-DAY POST-MERGER INTEGRATION PLAYBOOK

## Slide 2
VALUE DRIVERS
Why the IMO exists — and what it must protect from the first day of planning
© Copyright 100-Day Advisors | IMO Integration Kickoff
1
Deal Value Delivery
The deal thesis is a set of commitments — synergies, growth, capability — that erode fast without coordinated execution. The IMO's job is to make sure those commitments are tracked, owned, and delivered.
Cross-Workstream Coordination
No workstream operates independently. Dependencies, conflicts, and timing gaps between HR, Finance, IT, Sales, Legal, and Communications are managed at the IMO level.
Decision Velocity
Blocked decisions are the leading cause of integration delay. The IMO provides a clear escalation path so that decisions that can't be resolved at the workstream level reach the right authority fast, not weeks later.
Risk Visibility
Every integration carries risks that individual workstream leads can't see in full. The consolidated RAID log, weekly status, and steering committee reporting give leadership a real-time view of what threatens the plan.
Accountability Infrastructure
Every task has a named owner. Every synergy has a named owner. Every open risk has a named owner. The IMO builds and enforces the accountability structure that keeps the integration from drifting.

## Slide 3
SUCCESS METRICS
How we measure IMO effectiveness — reported weekly to the Steering Committee
© Copyright 100-Day Advisors | IMO Integration Kickoff
2
Plan Execution
All workstream plans updated weekly; master plan current at all times
No milestone slips more than 5 days without a documented recovery plan
Day 1 Readiness Gate certified green by all workstreams before close
Risk Management
RAID log consolidated weekly; every open item has a named owner
No high-severity risk sits unmitigated for more than 5 business days
Cross-workstream dependencies logged before they become blockers
Synergy Realization
Every synergy validated with a named owner before close
Day 30 synergy review completed; forecasts updated and accepted by Finance
Synergy variance >10% vs. deal model escalated to CFO within 48 hours
Stakeholder Confidence
Executive Dashboard published every week without exception
Steering Committee meets biweekly; board receives monthly progress report
Day 100 close-out report delivered on time with locked synergy baseline

## Slide 4
EXTENT OF INTEGRATION
What the IMO owns, what it coordinates, and what it hands off
© Copyright 100-Day Advisors | IMO Integration Kickoff
3
IMO OWNS
Master integration plan and milestone tracking
Consolidated RAID log across all workstreams
Weekly Executive Dashboard
Day 1, Day 30, and Day 100 gate reviews
Cross-workstream dependency management
Integration budget tracking and spend reporting
Synergy validation, tracking, and reporting
Board and steering committee reporting cadence
IMO COORDINATES
Workstream planning kickoffs and alignment sessions
Cross-workstream conflict resolution
Employee and customer communication guide review
Day 1 war room activation and hourly monitoring
Integration vendor and external support management
Change control after plans are locked at Day 30
Workstream retrospectives at Day 100
IMO HANDS OFF
All workstream execution — owned by named workstream leads
All workstream content — Legal, HR, IT, Sales own their deliverables
BAU operations — all open items formally transferred at Day 100
Lessons learned — documented in playbook before team disperses
Synergy ownership post-Day 100 — transfers to Finance and BAU owners

## Slide 5
END STATES — WHAT 'INTEGRATION COMPLETE' LOOKS LIKE
Observable outcomes that signal the IMO's work is done by audience
© Copyright 100-Day Advisors | IMO Integration Kickoff
4
FOR THE BOARD
Day 100 close-out report delivered with locked synergy baseline
All open integration items formally transferred to BAU owners
Integration lessons documented and incorporated into M&A playbook
FOR THE STEERING COMMITTEE
All workstreams certified complete or formally deferred at Day 100 gate
No unresolved close-blocking risks carried into BAU
Integration budget closed; actuals vs. plan variance accepted by CFO
FOR WORKSTREAM LEADS
Every workstream plan formally closed or handed off with named BAU owner
All cross-workstream dependencies resolved; no open blockers
RAID log closed; all items resolved, accepted, or formally transferred
FOR EMPLOYEES
Integration is visibly finished, no lingering uncertainty about org, roles, or tools
Communication cadence transitions from integration to BAU rhythm

## Slide 6
NON-NEGOTIABLES
IMO operating rules that apply to every workstream lead from this meeting forward
© Copyright 100-Day Advisors | IMO Integration Kickoff
5
Your Plan Is Due Weekly
Every workstream plan is updated and submitted to the IMO by Thursday. Late plans block the Executive Dashboard and the steering committee report.
One Owner Per Task
Every task, synergy, and open risk has a single named owner. Co-ownership is not ownership. If two people are accountable, no one is — and the IMO will push back until there is one name on the line.
Blockers Are Escalated, Not Absorbed
If a dependency is blocked or a milestone is at risk, it is escalated to the IMO immediately, not managed quietly until it becomes a crisis. Surface issues early; the IMO exists to resolve them.
The RAID Log Is Always Current
Every risk, assumption, issue, and dependency is logged. The RAID log is not a reporting artifact — it is a live operating document. An unlogged risk is an unmanaged risk.
Gate Reviews Are Non-Negotiable
The Day 1 Readiness Gate, Day 30 Integration Check, and Day 100 Gate are fixed events. They are not moved for schedule convenience. Every workstream must be prepared to certify status at each gate.
Synergies Have Named Owners Before Close
No synergy enters the deal model without a named workstream owner and a cost-to-achieve estimate. A synergy without an owner is a forecast assumption, not a commitment.

## Slide 7
GOVERNANCE MODEL
Who owns what — decision rights, escalation paths, and reporting structure
© Copyright 100-Day Advisors | IMO Integration Kickoff
6
Board of Directors
Receives monthly integration progress report. Reviews and accepts Day 100 close-out report. Approves major integration decisions that affect deal terms or significant capital allocation.
Steering Committee
Meets biweekly. Reviews RAG status, open risks, and decisions needed. Resolves escalations that exceed IMO authority. Chaired by executive sponsor.
IMO Leader
Single accountable owner for integration execution. Runs weekly IMO meeting. Certifies all gate reviews. Owns master plan, RAID log, Executive Dashboard, and synergy tracking.
Integration Coordinator
Supports IMO Leader. Manages document controls, communication guide circulation, synergy tracking model, budget reporting, and weekly administrative cadence.
Workstream Leads
Each functional lead (HR, Finance, IT, Sales, Legal, Communications) owns their plan, tasks, and RAID items. Reports RAG status weekly. Escalates blockers to IMO within 24 hours.
Acquired Company Lead
Core IMO team member representing the acquired entity. Provides insider context on target company systems, culture, and relationships. Flags integration friction early.

## Slide 8
GUIDING PRINCIPLES
The decision-making criteria every integration lead must internalize before planning begins
© Copyright 100-Day Advisors | IMO Integration Kickoff
7
01
One Owner Per Commitment
Every task, synergy, and risk has a single named owner. Shared ownership is no ownership. If it doesn't have one name, it doesn't get done.
02
Surface Issues Early
A problem raised on Day 5 is a problem. The same problem raised on Day 45 is a crisis. The IMO exists to resolve issues fast — but only if they're surfaced fast.
03
Plans Are Living Documents
Integration plans are updated weekly — not when convenient. A stale plan is a liability. The master plan reflects reality, not what we hoped would happen.
04
Separate Synergy from Noise
Synergy revenue and cost savings are tracked separately from organic performance. Blending them hides whether the deal thesis is being delivered.
05
Gates Are Checkpoints, Not Celebrations
Day 30 and Day 100 gate reviews assess reality against plan. Open items are escalated or formally accepted — not glossed over in the interest of declaring success.
06
Decisions Escalate, They Don't Stall
A decision that can't be made at the workstream level comes to the IMO. A decision the IMO can't make goes to the Steering Committee.
07
Inherited Risk Is Managed Risk
Every risk surfaced in diligence is owned and tracked from Day 1. Risks that were known and not logged are not surprises. They are failures of governance.
08
The Playbook Gets Better Every Deal
At Day 100, every workstream documents what worked and what didn't. The IMO synthesizes those lessons into the M&A playbook before the team disperses.

## Slide 9
CORE MESSAGES
What every integration lead must be able to communicate about this integration
© Copyright 100-Day Advisors | IMO Integration Kickoff
8
WHY THIS DEAL
This acquisition creates a combined entity with greater scale, capability, and market reach. Integration must deliver the synergies and capabilities the deal was built on.
WHAT THE IMO DOES
The IMO coordinates — it does not execute. Workstream leads own their plans. The IMO owns the master plan, the RAID log, the gate reviews, and the escalation path.
WHAT CHANGES ON DAY 1
The war room is active. Status reporting on execution begins. Every workstream lead has confirmed tasks, owners, and an escalation path before close of business.
HOW DECISIONS GET MADE
Workstream issues resolve at the workstream level. Cross-workstream blockers escalate to the IMO. Material risks and decisions that exceed IMO authority go to the Steering Committee.
WHAT WE ASK OF LEADS
Update your plan weekly. Log every risk the moment it appears. Escalate blockers within 24 hours. Never let a problem age. The IMO cannot resolve what it cannot see.
WHEN THIS IS COMPLETE
The integration closes at Day 100. Every workstream is certified complete or formally deferred. Every open item has a named BAU owner. Lessons are recorded in the playbook.

## Slide 10
INTEGRATION TIMELINE
IMO milestones across three phases — Pre-Close through Day 100
© Copyright 100-Day Advisors | IMO Integration Kickoff
9
PRE-CLOSE
T-60 to Close
Steering Committee kickoff; deal rationale aligned
IMO Leader and all workstream leads appointed
Governance structure and decision rights established
Data room standing, document controls in place
IMO charter approved; success metrics defined
Integration budget framework established
All synergies validated with owners pre-close
Day 1 war room planned; all comms guides ready
Day 1 Readiness Gate certified — all workstreams green
DAY 1 / WEEK 1
War room activated; 7 AM all-workstream stand-up
Hourly task monitoring across all workstreams
End-of-day debrief with all workstream leads
Daily 15-min stand-ups Mon–Fri, Week 1
All Day 1 open issues resolved
RAID log updated with all Day 1 risks
Week 1 IMO status report published
DAYS 8–100
Day 30: Plans locked under formal change control
Day 30: Synergy review; forecasts updated
Day 30: Gate review with Steering Committee
Day 30: Board progress report delivered
Monthly board reporting cadence through Day 100
Ongoing weekly IMO meetings and RAID updates
Day 100: Close-out report to board
Day 100: All open items to named BAU owners
Day 100: Lessons documented in M&A playbook

## Slide 11
DUE DILIGENCE RULES OF ENGAGEMENT
Pre-close data sharing guidelines every workstream lead must follow
© Copyright 100-Day Advisors | IMO Integration Kickoff
10
WHAT YOU MAY AND MAY NOT DO
All pre-close planning uses only information cleared through the data room — confirm scope with Legal before using any non-public target information
No workstream lead may contact a named target company employee, customer, or vendor without Legal authorization
Financial, pricing, headcount, and contract data from the target may only be reviewed within the Legal-approved data room scope
Any finding that could affect deal terms or integration assumptions is escalated to the IMO Leader and Legal immediately
Clean room protocols apply to all workstream leads — not just the IMO team; brief your team before they receive data room access
No workstream lead communicates integration plans, org changes, or operational decisions to external parties before close
If unsure whether a pre-close action is permitted — stop, and ask the IMO Leader or Legal before proceeding
CONSEQUENCES OF VIOLATIONS
Pre-close sharing of non-public information — customer lists, pricing, headcount plans — constitutes gun-jumping under HSR antitrust rules. The document trail is the violation. Penalties can delay or block deal closing.
WHEN IN DOUBT — STOP AND ASK
Before accessing any target company data or taking any pre-close action: contact the IMO Leader or Legal. The data room agreement defines what is in scope. If it is not explicitly permitted, it is not permitted.

## Slide 12
100-DAY ADVISORS
Accelerating M&A Integrations
mandaplaybook.com
inquiries@mandaplaybook.com