## Slide 1: M&A DAY 1 READINESS UPDATE BY WORKSTREAM

## Slide 2: Content
Communications
Sales & Marketing
Finance
Information
Technology
Facilities
Legal
Region 1
Region 2
Region 3
Early Win Opportunities
© 100 Day Advisors
© 100-Day Advisors MandAPlaybook.com

## Slide 3: Communications
Leadership changes will be subsumed within the wider Sales & Marketing plan
No expected changes in First 30 days
Dashboard Review
No signiﬁcant risks anticipated
12 pre-close activities relate to ﬁnal sign-off and distribution of the Playbook
Day 1 activity is the execution of the comms plan
Business Processes for Day 1
Day One = the same processes that have been in place these past 10 months.
All Day One timings and plans have been reviewed and communicated with Comms workstream and leadership for both Acquirer and Acquiree Group.
Day One comms responsibilities assigned
Coming Together SharePoint site - will be available on Day One and will host a wealth of information including: welcome video from CEO, information about our Values, Operating model, and new Leadership Team, close to 100 FAQs, a resource section for new sales/marketing collateral, Acquiree interim brand, and technical resources for both organizations in terms of shared access
Clients (Internal and/or External)
Playbook and Day One Townhall deck are complete and have been circulated to senior leadership for review and approval.
Press release
FAQs
'How To' guides
Client/ business partner/prospect emails
Key Messages
Social media and PR guidelines
Day One brieﬁng call for senior leaders scheduled for November 2; that deck has also been created and is currently in review.
Functional Alignment

## Slide 4: Sales & Marketing
Business as usual, let's keep generating leads, making calls, building pipeline, selling, marketing, and introducing our new services to the market.
Global Sales & Marketing call scheduled for next week
Day One collateral created for sales managers including lead capture page on Acquirer Global, sales sheet, and Outreach templates.
Pipeline reports will be available week one.
We have documented and evaluated sales and marketing vendors (data, tech, ops, creative, comms) and will begin planning transitions after Day One with the initial focus on moving Acquiree Group data into Acquirer's Salesforce instance.
Clients (Internal and/or External)
Highest level org structure identiﬁed and will be communicated in week one. Meaning, EVP's direct reports.
Will take time to work on level 2 and beyond.
Few changes in the ﬁrst 30 days
Townhalls/Meetings
Weekly leadership meetings
Monthly global sales meetings
Weekly pipeline meetings
Monthly marketing meetings
Dashboard Review
No outstanding pre-close tasks
No risks / issues related to Day 1
Business Processes for Day 1
Enterprise-wide client, prospects, and partner communications are captured in Communications Playbook.
List of Acquiree Group clients segmented by their three tiers and matched to Acquirer's client and prospect database available to Chief Sales & Marketing Ofﬁcer on Day One as well as Acquiree Group entities by service line.
War room contacts established
Functional Alignment

## Slide 5: Dashboard Review
“All Hands” meetings will be scheduled:
Finance Leader Meeting - Date TBD
Finance All Meeting – Date TBD
Leaders will also be traveling across the geographical regions for Meet & Greets.
Finance will be publishing weekly content on integration
Possible topics: Culture examples, discussing the future of Finance, changes/enhancements, etc. .
Centralized “war room” has been reserved for Day 1. Finance contacts and war room support resources identiﬁed to assist in reconciling any P1 / P2 escalations.
Operational Governance Guidelines have been revised and will be in place by Day 1
Finance OGG deliverables have been completed and OGG transitioned to Legal.
Finance
11 tasks due before close
No signiﬁcant risks / issues
Business Processes for Day 1
Clients (Internal and/or External)
Functional Alignment

## Slide 6: Dashboard Review
Information Technology
No expected changes within ﬁrst 30 days
No open pre-close tasks, key deliverable at close are the collab tools
No risks / issues related to Day 1
Business Processes for Day 1
Clients (Internal and/or External)
We will send out a short welcome video from CIO to the new Technology organization after Day 1.
We will have a virtual Technology War Room which will contain members of both the Acquirer and Acquiree Help Desks and other key technology leaders. Users will continue to report any technology issues via the existing channels for each organization.
Functional Alignment
Both Acquirer and Acquiree users will be able to chat/call each other via Teams
Outlook Calendar and Address Book - Both Acquirer and Acquiree users will have access to each other's calendars and address books
Intranet - All Acquiree users will have access to Acquirer’s intranet
Enable employees of Acquiree and Acquirer to access applications

## Slide 7: Facilities
Dashboard Review
No open pre-close tasks
No risks / issues related to Day 1
Business Processes for Day 1
Day 1 guide for selected Acquirer and Acquiree locations created, reviewed by Marketing and pages created for local ofﬁce fact sheets
Day 1 guides include visitor processes and building access including badges for buildings with focus on selected Acquirer and Acquiree locations
Clients (Internal and/or External)
Facilities Q&A created and reviewed by Marketing
War room support - Facilities is BAU for Day 1. People should continue to follow the processes to contact Facilities that are in place for Acquiree and Acquirer. If other workstreams war rooms receive a facilities related question or issue they contact our workstream via email). We will then collectively work together to answer or handle any issues.
Functional Alignment
All Acquirer and Acquiree leases were collected and uploaded into a shared system and identiﬁed all lease related activities (moves, expansions, remodels, lease amendments) for the next 15 months and are actively working together on those initiatives
First Facilities forum was held beginning of October to introduce team members to each other
Beyond Day 1, deﬁning facilities services, processes and systems and developing a plan to combine where applicable will continue through the end of 2028 and be executed in 2029
Implementation of the plan for a centralized Facilities Management team will take place in 2029

## Slide 8
Legal
Dashboard Review
Only two tasks related to deal close / settlement
No risks / issues related to Day 1
Business Processes for Day 1
OGG – under review, with limited changes mostly related to ﬁnance controls.
Hotline – no need to change. Both systems remain in place until further notice.
Other – no further updates.
Clients (Internal and/or External)
Are your client communications captured in the Comms playbook or do you have workstream speciﬁc comms ready to augment? - work stream comms ready to augment. Holding a town hall on 11/8
Do you know who they are? Do you have overlap you need to coordinate with BUs or across Acquiree and Acquirer? - Yes and no.
Describe your war room support / escalation process for your workstream. - Ian McConnel is on standby to support legal issues relating to the integration war room.
Functional Alignment
Ready to communicate and work together as a single business entity, inclusive of any org changes through First 30
Town hall / team meetings scheduled to share functional updates (vision plan and role within the combined organization)
Global Legal virtual town hall scheduled next week

## Slide 9: Region 1
Dashboard Review
8 pre-close tasks to ﬁnish, key deliverables include:
  Know access requests
  Tech change management review
  Intra-ofﬁce charter agreements
No open issues / risks related to Day 1
Business Processes for Day 1
Newly combined agreements and contractual model are mostly in place and have been socialized with Leaders, Legal Teams and local ofﬁce leads.
Onboarding team is in place in headquarters hub and London.
Local onboarding experts and Local Customer Service leads (points of contact) assigned and trained within all local ofﬁces (one team approach).
Speciﬁc user and application access will be enabled for Day 1 by the IT Workstream.
Local ofﬁce billing needs, including internal setup and system demos, are on track.
Messaging content shall follow the issued “Playbook,” "Talking Points," and "FAQs".
War Room established and escalation process communicated to Regional Leaders for client and operational concerns. (pre-war room ahead of IMO escalation established).
Vendor / Trusted Service Provider lists aligned.
Customer list and pipeline alignment will be a combined effort with Sales starting Day 1.
Functional Alignment
Business Services model documented and overview sessions held with Service Line Leads.
Town halls to be planned by Leaders in line with the Playbook.
Operating Model and Change Priorities to be further mapped out in Offsite scheduled December with Regional Managing directors.
Services Alignment and Pricing alignment (now legal approval given to share data) is work in progress but on track for alignment ahead of day 1.
Clients (Internal and/or External)

## Slide 10: Region 2
Dashboard Review
18 pre-close tasks on-track, key deliverables include:
  Procedure training for onboarding
  Day 1 readiness brieﬁng
  Staff comms planning
No known risks / issue
Business Processes for Day 1
Day 1 sales process – decision ﬂow, procedure and training for new clients – on track
Prospects pipeline – view of joint pipeline to be done manually between sales teams
There are no new tools required for these processes Post Day1:
Day 1 Pricing Committee – will be put in place in line with prospects
Business review will be kicked off by leadership team
We will depend on the standard client letters
‘Bottom up' client lists in place – and ready for Day1 sharing for client calls
  Account managers will align calls for shared clients
Sales teams will review prospects in ﬂight for Risk and Pricing alignment
  Teams will align pitch for shared prospects
Post Day1
  Partner calls will be made post day1
Org Alignment
All ORG alignment is subject to approvals
On Day 1, we will depend on the standard comms and announcements to staff
This will be followed by management call, to be scheduled
A series of jurisdictional and functional calls and visits to be setup for Day1-Day30
Clients (Internal and/or External)

## Slide 11: Region 3
Dashboard Review
No outstanding pre-close tasks
No risks / issues for Day 1
Business Processes for Day 1
Quote management process in place.
  Quote management process in place
Pipeline process
  Manual review of shared pipeline in interim
Updated collateral will be available to Acquiree ofﬁces
No changes to existing critical business processes
Clients (Internal and/or External)
Day 1 alignment for shared clients
  As soon as clearance received from Legal
Acquiree Quotes in ﬂight to be sourced next month
  Overlay on Acquirer quotes.
Oversight process in place for day 1 - Command & Control
  Link into IMO Incident management via PM.
  Tracking Client and staff feedback
Org Alignment
Day 1 country comms
  to existing org structures within entity
Post Day 1 comms
  During week 1 – revised BU comms
Regional visits Day 1 – Day 30.
Interim Leadership team to work on deﬁning Target Operating Model
  Next phase of discovery to commence immediately

## Slide 12: Early Win Opportunities
Early Wins
Comments
Establish early collaboration tools (e.g., employee speciﬁc platforms)
Closing and announcing to all employees & customers – the detail and nature of the transition – celebrate together
To have an internal plan for the sales teams with a good story about
the transaction – a game plan
Make smaller locations, ofﬁces or teams to be included as part of the communications process. Sometimes they may feel isolated
Get to know each other in detail – clients, processes, services in order to understand early sales closure
Day 1 communications plan with a ‘game plan’ for employees
IT security for key people on day 1 to prevent unwanted attacks on the ‘new’ organization (e.g., DOS, phishing etc.)
Public domain strategy that is consistent across the companies
Educate employees on compliance policies
‘Clean data’, establish a valid and reliable master ﬁle – key to many things.
Not easy given the nature of the transaction & the need for
regulatory approval
A clear go-to-market model with talking points
More focused, perhaps personal visits, a central site for project status and updates, wins etc.
Deep dive sessions for the sales teams
Over to the comms team
Cohesive threat assessment, communication to raise awareness
Critical for day 1
Harmonized approach

## Slide 13
Consulting Inquiries:
Email: inquiries@100DayAdvisors.com
Website: MandAPlaybook.com/consulting