## Slide 1
SALES POST-MERGER INTEGRATION
KICKOFF

## Slide 2
Strategic Intent & Goals
Protect Revenue
Ensure less than 2% churn for top 100 accounts during transition.
Drive Growth
Build $100M in new joint pipeline value by Day 100.
Unified Engine
Transform into a high-velocity global sales force.
© 100-Day Advisors MandAPlaybook.com
2

## Slide 3
Vision of the End State
Unified Organization
Single Global Sales Org under the CRO by Day 100. Hybrid leadership model (15% shared roles) supports the transition.
Integrated Systems
Salesforce as the sole CRM by Day 60. Unified RevOps platform live by Day 60 for full pipeline visibility.
© 100-Day Advisors MandAPlaybook.com
3

## Slide 4
Integration Timeline
Phase 1: Pre-Planning
Day -60 to 0 Clean room analysis & org design approval.
Phase 2: Day 1
Close Legal close & joint leadership town hall.
Phase 2: Execution
Day 61 to 100 Complete rep training Full CRM migration & commission go-live.
© 100-Day Advisors MandAPlaybook.com
4

## Slide 5
Extent of Integration
Area
Level
Timeline
Key Outcome
Organization
High
Day 1-90
Unified global reporting structure
Systems
High
Day 1-60
Single CRM (Salesforce) migration
Compensation
High
Day 1-60
Unified commission plan go-live
Brand
High
Day 1-100
Updated collateral & identity
© 100-Day Advisors MandAPlaybook.com
5

## Slide 6
Non-Negotiables
No Pre-Close Outreach All client communications must be approved by Legal/Comms prior to July 1.
No Shadow Systems All deal tracking must occur in Salesforce; no external spreadsheets allowed.
Talent Retention Priority Retention bonuses disbursed within 14 days; no hiring freezes on key roles.
© 100-Day Advisors MandAPlaybook.com
6

## Slide 7
Risks & Mitigations
Risk
Impact
Mitigation Plan
Talent Attrition
High
Immediate retention bonuses & career pathing.
Customer Churn
High
"War Room" for top 100 accounts & defense kits.
CRM Delay
High
Dual migration path & dedicated validation team.
Comp Discontent
High
"At least equivalent" guarantee for 12 months.
© 100-Day Advisors MandAPlaybook.com
7

## Slide 8
Next Steps & Action Items
Priorities for leadership alignment:
Jan 9: Confirm Taskforce Leads
April 30: CRM Integrated
April 30: Finalize Org Structure
© 100-Day Advisors MandAPlaybook.com
8

## Slide 9
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com
11
9