## Slide 1
IMO WORKSTREAM
KICKOFF MEETING

## Slide 2: TABLE OF CONTENTS
02
Why we need to start now
Operational discovery
Structure of discovery
Background
Deal objectives
Guiding principles
End states
Acquired co. Integration governance structure
Communications
High-priority initiatives
Integration planning process overview
Integration communication deliverables
Critical information needs at outset of integration
Meeting cadence [all times et]
Upcoming meetings / major dates
Process
Next steps
© 100-Day Advisors MandAPlaybook.com

## Slide 3: BACKGROUND
Acquired Co. is $120m revenue & 800 people (HQ: Houston)
Acquired Co. is $20m revenue and 100+ people
(HQ: San Antonio)
Dan Fillen is the Integration Lead
The deal is not closed yet – but target is January 11 Announcement on January 11 (Day 1)
Integration is high priority over the next few months
03
© 100-Day Advisors MandAPlaybook.com

## Slide 4: DEAL OBJECTIVES
Expands revenue streams by improving our market position in California
Places special focus on cross selling and service enhancement.
Creates the necessary scale to establish a market presence that leads to larger
projects, increased revenue and improved financial resilience.
Improves ability to mitigate risk and adapt to change.
More diversified geographic footprint reduces impacts of geopolitical risk.
Captures digital delivery competitive advantages.
Creates an integration playbook that can be repeated and replicated for future M&A.
Collaboratively align on best practices.
Capture benefits of scale and optimizes operations.
04
© 100-Day Advisors MandAPlaybook.com

## Slide 5: GUIDING PRINCIPLES
Integration leadership is committed to: - Transparency and predictability - Clarity, direction and decisions - Consistency across the new combined organization and program
Frequent and transparent communication
Create a robust integration plan to reach the strategic objectives while prioritizing revenue synergies.
Maintain business momentum.
Focus on the things we need to change. Search for synergies in every functional area of the newly created organization Everybody’s contributions are needed for success.
Do no harm.
We are all working in the best interest of the combined organization. Provide benefit of the doubt to decision making.
Discuss and challenge but accept and support the decision. Focus on the company and not individual the best interests
5
05
© 100-Day Advisors MandAPlaybook.com

## Slide 6: END STATES
RESPECT ACQUIRED CO. AND DON’T BREAK THINGS
 | DAY 1 | DAY 30 | END STATE
Organization reporting structure & “how to work” | Org reporting integrated | Phasing in best practices and capturing synergies | Fully Integrated
Branding | No change. | No change. | Fully Integrated
ULTIMATE GOAL:
FULL INTEGRATION AND SINGLE GO-TO-MARKET APPROACH
06
© 100-Day Advisors MandAPlaybook.com

## Slide 7: ACQUIRED CO. INTEGRATION
GOVERNANCE STRUCTURE
Senior leadership approves plans and provides guidance
Lead all integration planning and execution activities for functional areas
Ensure completion and adherence to the scope identified for workstream area(s) in charters
Manage all assigned initiatives / tasks
Update integration plans and track issues Acquired Co. establish any sub-teams
required for workstream completion
Work with other team resources to determine interdependencies
Adhere to pre-close rules of engagement
CEO, Acquirer, CEO Acquired Co COO, Acquirer VP, Acquirer
Coordinates teams, sets
pace, prioritizes work,
brings methodology,
and manages
interdependencies
STEERING COMMITTEE
WORKSTREAM LEADS
Acquirer Integration Sponsor CEO Acquired Co.
Communications
INTEGRATION MANAGEMENT OFFICE (IMO)
Ops | BD | Comms | Finance | Human Resource | Legal | Information Technology
07
© 100-Day Advisors MandAPlaybook.com

## Slide 8: COMMUNICATIONS
APPROACH:
IMO and Comms will drive and manage development of Day 1 and Day 90 communication deliverables
We will work with each team to customize materials for their specific stakeholder audiences
All stakeholders will hear the news from us (Acquired Co. and Acquirer leaders)
Comms team will begin reaching out to each team to begin materials development and customization
RATIONALE:
Much of the messaging is common (e.g., key message points, FAQs), thus centralizing development ensures consistency
Communications deliverables are time-consuming to produce. This approach takes some of the burden off work teams to allow them to focus more on workplans
NEXT STEPS:
08
© 100-Day Advisors MandAPlaybook.com

## Slide 9: HIGH-PRIORITY INITIATIVES
Ensure all preparation has been completed for a smooth Day 1 / Week 1
Avoid any unnecessary disruptions to the business
Limit uncertainties by providing direction
Example Day 1 Mandatories
Day 1 Communications Employee onboarding Payroll
Financial change of control and LOA/DOA requirements
IT Connectivity and access
Compliance requirements (e.g., safety) Brand/signage no change
Facilities security
Bank signatory changes
Organizational alignment/reporting structure (for Day 1)
Example Day 30 Mandatories
Assessment requirements (systems, people, processes, things you need to learn fast)
Organizational alignment and staffing roll-out initiatives High priority policy & process alignment
Financial and treasury initiatives related to close Ongoing communications & updates
“Enabling initiatives” (must be complete to allow other work to start)
09
© 100-Day Advisors MandAPlaybook.com

## Slide 10: INTEGRATION COMMUNICATION DELIVERABLES
Master Documents Supporting Guides
Comm Planning Doc
Key Messages Log
Audience Matrix
FAQs by audience/function
“What’s Changing” Log
Media/Investor Guide Customer Guide Supplier Guide
Employee Guide
Social Media Guides
Ongoing (90-day) Guidance
Update cadence Announcement support
Delivery & Support
Day 1 Zoom meeting agenda
Day 1 Zoom meeting content support Day 1 Intranet messaging
Day 1 Guides
Employee Resource Guide (PDF)
Key Messages
Company overview (scale, vision, principles) Leadership info/org chart (high level) “What’s Changing”
Key Contacts by function
Day 1 Critical policies, processes Branding Guidelines (if needed) FAQs
10
© 100-Day Advisors MandAPlaybook.comc

## Slide 11: WHY WE NEED TO START NOW
BUT THE PAY-OFF IS BIG:
Integration effort will be well-organized from Day 1 Pursuit of quick wins and synergies begin Day 1 Positive momentum is achieved
Integration strategy, org structure, and communications plan needs to be determined before acquisition is publicly announced.
It takes time to train the team and kick off integration planning
11
© 100-Day Advisors MandAPlaybook.com

## Slide 12: OPERATIONAL DISCOVERY
WHAT IT IS
An approach to understand each other’s operations and inform the integration of Acquired Co. and Acquirer
Business Process examples: Lead generation, Quote-to-Cash, Proposal Development
HOW TO DO IT
Each workstream should determine if/where operational discovery is needed (focus on synergies)
Approach:
Determine areas of discovery and develop list of questions/requests;
Answer the questions/requests in writing and share in a meeting (e.g., Acquirer shares its lead generation process with Acquired Co. counterparts)
Optionally invite other workstreams that may have an interest in the topic
Record meeting / take notes.
Store recordings / meeting notes / other artifacts in MS Teams under your
workstream.
12
© 100-Day Advisors MandAPlaybook.com

## Slide 13: STRUCTURE OF DISCOVERY
2) IMO will organize discovery sessions:
3). Virtual Data Room access [how to get it)
1) Objectives:
Obtain information relevant for the integration when
Minimize asking the same question or making the same
13
© 100-Day Advisors MandAPlaybook.com

## Slide 14: CRITICAL INFORMATION
NEEDS AT OUTSET OF INTEGRATION
Org Chart(s)
Assignment of SteerCo
Member / Workstream Leads.
For Payroll/Benefits: Payroll
Register and Claims History.
IT Architecture
Data on Projects, Personnel and Financials
Marketing Materials
14
© 100-Day Advisors MandAPlaybook.com

## Slide 15: MEETING CADENCE [ALL TIMES CST]
TUESDAY
MONDAY
Integration management office [IMO]
WEDNESDAY
THURSDAY
FRIDAY
Weekly
Weekly
Weekly
Weekly
Smartsheet updates due
1 pm: Operations, Legal
1 30 pm: Bus. Development
2 pm: Finance, IT
3: 30 pm: Human Resources
4 pm: IMO
workstream leads meeting [WLM]
workstream 1-on-1s meeting with IMO
Smartsheet updates
Coordinates teams, sets pace, prioritizes work, bring methodology, and manages interdependencies
Cover items that are relevant for all workstreams, e.g., project management related, steering committee decisions, etc.
Go in-depth on integration tasks, issues, risks, dependencies, decisions needed
Smartsheet work plan updates due every Friday by cod. The inputs are used to develop reporting for following wee.
15
1 pm: Workstream Leads Meeting
© 100-Day Advisors MandAPlaybook.com

## Slide 16: UPCOMING MEETINGS / MAJOR DATES
Complete Team Charters and Draft Day 1 & Day 30 Plan
Workstream Weekly Mtg
Acquirer
Kick Off
Acquired Co. Kick Off
Dec 21
Dec 16
Dec 9
Dec 2
Dec 23
Dec 30
Jan 6
Jan 11
Day 1
Day 30 Plan Validation
Read out of Day 1 &
Day 30 Plans
Day 30 Plan Validation
/Communications Plan Read out
Welcome Week/Day 1
16
© 100-Day Advisors MandAPlaybook.com

## Slide 17: PROCESS
Develop public engagement strategy and plan to support decision and inform stakeholders.
17
1
2
3
4
Gain an understanding of technical work completed to date.
Evaluate suggestions and other alternatives.
Perform cost/benefit analysis to inform decision.
Develop public engagement strategy and plan to support decision and inform stakeholders.
© 100-Day Advisors MandAPlaybook.com

## Slide 18: NEXT STEPS
Topic | Action | Templates / Resources | Complete by Date
Kick-Off with Workstream Leads | Need to identify workstream leads and schedule | MS Teams | TBD
Workstream Charters | Create Charters leveraging previous integrations. | MS Teams | TBD
Draft Workplan |  | Smartsheet | TBD
Draft work plan using key milestones as anchors of activities.
18
© 100-Day Advisors MandAPlaybook.com

## Slide 19: NEXT STEPS
Topic | Action | Templates / Resources | Complete by Date
Review and provide input on Charters, Day 1 and Day 30 Plans | Input your tasks that need to be done or started to Day 30 [Oct 11] into Smartsheet. Include contents for all columns. Discuss dependencies with affected workstreams. | Smartsheet | Friday, Dec 23
Training of Acquired Co. Team | Focus on Smartsheet and other tools in use | Zoom | Tuesday, Dec 22
Introduction Meeting (Acquirer/Acquired Co.) | Acquired Co. and Acquirer integration team members introduce themselves | Zoom | Tuesday, Dec 22
Inputs to / Review of Comms Materials, (Biz Dev, Ops, Services Groups, HR) | Send Dan and/or Bill required inputs. |  | Friday, Dec 23
Start using RAID log in MS Teams[Risks, Actions, Issues, Decisions) | Input major risks, issues, and decisions. | Smartsheet | Dec 23
19
© 100-Day Advisors MandAPlaybook.com

## Slide 20: thank you
contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com
© 100-Day Advisors MandAPlaybook.com