## Slide 1
M&A DAY 1 SALES
INTEGRATION

## Slide 2: Agenda
DAY 1
GENERAL INFORMATION
SALES APPROACH
OPERATIONS
OVERSIGHT
ACTIVITIES
© 100-Day Advisors MandAPlaybook.com

## Slide 3: Day 1 General Information
Customer contact will commence as soon as the press releases goes out on Day 1. Each director has been assigned the responsibility of dissemination of customer connects
Day 1 is primarily about employee and customer communications – we will depend on standard comms followed by our direct client calls:
Messages to clients will be aligned with marketing and organization
Messages to staff critical, org structure, and key personnel roles etc., will depend on other overall decisions and preceding communications
We have agreed on our commercial and operating principles, including new sales scenarios and client onboarding. In summary,
Between now and Day 1, the clean team is compiling customer lists and working on producing joint pipeline reports. We will identify overlapping customers and develop plan for contacting for Day 1.
There will be a single response to RFPs and requests for quotes
All open deals will be reviewed by commercial team along with sales
We will align pricing to have parity between the organizations
We will not compete as two different organizations (externally or internally). The team is working with Finance in regard to the mechanics of new salespeople commissions to reduce internal competition
Deals will be booked using existing process and systems until teams are notified otherwise
© 100-Day Advisors MandAPlaybook.com
3

## Slide 4: Day 1 Sales Approach
We will need a process to manage the financial reporting, revenue, incentivization etc. (Finance stream to advise)
Detail
We will be seen as a cohesive business unit on Day 1
We will agree on the communication method for existing clients during the client list collection exercise
We will agree on the communication method for Acquiree’s new logo during the client list analysis exercise
We do not want duplicate/different quotes going to prospects or clients from each company
We will set up a pricing sub-committee for shared clients on Day 1. In reality we cannot change existing pricing structures on Day 1 but we want try to be consistent for new clients on Day 1 (existing and prospects)
We will combine the pipelines for monitoring prospects
We will have a joint sales deck for presentations/pitches
We will setup a mechanism to agree what infrastructure/systems new customers will be onboarded to. Repeat business for existing clients goes on existing infrastructure/systems (Acquirer or Acquiree)

## Slide 5: Day 1 Operations
Detail
We cannot disrupt service to clients on Day 1
We do need to acknowledge the deal with staff and have appropriate communications (briefings, standardized FAQ’s etc.)
All staff work in usual locations, following current BAU model
There are no reporting line changes or team structural changes on Day 1 – that will be planned changes following organization structure announcements post close
Current managerial structure to be honored and included in comms / escalation – but needs to still allow quick decision making for any escalations at a local level
Give existing clients new business will go on existing infrastructure, billing will come from this platform (Acquirer or Acquiree)
Existing materials (quotes, legal docs, MSA’s etc.) to be use. There is no harmonization of legal documentation in the near term
We will agree on revenue budget process with Finance for recognizing revenue across Acquirer/Acquiree so we can make the right decision on where to onboard clients regardless of incentives
There will be a ‘command and control’ structure in place for Day 1 and subsequent days for a period of time
We will follow the business as usual process for reporting incidents
Integration related incidents will be escalated to the IMO (War Room process)

## Slide 6: Day 1 Oversight
We will manage Day 1 so we can:
Incident Management:
Monitor client calls for any underlying issues about the transaction Keep in touch with staff
Keep in touch with staff
Keep senior management informed how things are going
Escalate any major issues to senior management
Enable sales leads to keep in touch with and regularly talk to other employees across regions
Any integration related incidents will be escalated to the IMO (War Room process)
© 100-Day Advisors MandAPlaybook.com

## Slide 7: Day 1 Activities
Align sales communications with corporate communications, including announcements from CEO, standard client letters, press releases, internet/intranet updates
Roll out of the organizational structure and schedule of calls and visits by business unit leads
Once the press release is issued, we start client calls
Conduct client calls per the client list/allocation exercise
Follow Business As Usual processes, management, and escalations on Day 1
Communicate progress on client calls
© 100-Day Advisors MandAPlaybook.com

## Slide 8
contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting
8