## Slide 1
CAPTURING POST-MERGER
INTEGRATION LESSONS LEARNED

## Slide 2: AGENDA
LESSONS LEARNED OVERVIEW
LESSONS LEARNED EXAMPLE TIMING AND APPROACH
01
© 100-Day Advisors MandAPlaybook.com

## Slide 3: LESSONS LEARNED OVERVIEW
WHY DO WE DO IT
Enhance the outcomes of the current integration
Further enhance planning and execution of future integrations
WHAT TO CAPTURE
Key learnings that relate to the integration planning and execution of this deal to date
Categorize by: Approach, Customer Experience, Employee Experience, Project Management, Schedule, Scope, Value Drivers, etc.
Cover items that went particularly well, and items that could be done better
02
© 100-Day Advisors MandAPlaybook.com

## Slide 4: LESSONS LEARNED EXAMPLE (2)
CATEGORY
Project Management
Areas to improve: importing data, linking interdependencies, simplify predecessors & successors input and tracking, wider representation at IMO meetings and/or better dissemination, better task granularity (tasks, subtasks)
Success to carry forward: Dashboards, weekly 1:1 meetings, conditional formatting in Smartsheet
Area to improve: Limit the scope of early planning to Day 1, specify what was not in scope
Area to improve: Define organization much charter
Success to repeat: 1:1s with Integration Leader, excellent collaboration
24
Scope
4
Approach
6
NUMBER OF RESPONSES (34)
DOCUMENT
03
© 100-Day Advisors MandAPlaybook.com

## Slide 5: TIMING AND APPROACH
Start now while it is still fresh
Engage PMs/Other Team Members to submit lessons
Immediately actionable lessons to be reviewed in Workstream 1-1s
Future updates may include workstream team members, not just leaders
Update at key points in time as the integration progresses (Day 30, at year-end, etc.)
04
© 100-Day Advisors MandAPlaybook.com

## Slide 6
06
contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com
05