## Slide 1
CROSS-BORDER FINANCE
POST-MERGER INTEGRATION KICKOFF

## Slide 2
Finance Integration
Content
Mission Statement
3
Non-Negotiables
4
Phase 1: Americas
5-10
Phase 2: EMEA
11-18
© 100-Day Advisors MandAPlaybook.com

## Slide 3
Mission Statement
Integration Planning and Execution
We will plan and execute the integration of the finance functions of our companies.
Efficient Implementation
Additional Responsibilities
We will also be responsible for:
Assimilation of the EVA philosophy into the Acquired Co. organization
Tracking synergies (cost and EVA) for all integration teams
We will complete the integration quickly and support the integration teams and upper management
© 100-Day Advisors MandAPlaybook.com

## Slide 4
Non-Negotiables
1
Payroll and benefits are centralized in the U.S.
2
Acquired Co. will adopt the Acquirer’s health insurance program
3
Business planning will be the Acquirer’s process
4
Hyperion will be the financial reporting system used
5
Treasury will be centralized
6
Risk management will be centralized
7
Peoplesoft will be implemented at Acquired Co. within 12 months
8
Performance management and succession planning processes will be centralized
9
Fiscal year will be December 31
© 100-Day Advisors MandAPlaybook.com

## Slide 5
Phase 1 Integration in Americas
Purpose
Establish a finance organization that meets its service needs as efficiently and cost effectively as possible
Objective
Adopt best practice processes of both companies and implement action those processes to achieve expected synergies
Value Drivers
Streamline activities, centralize functions, and eliminate redundancies
Main Synergies
Reduced headcount and eliminate duplicate outside services
Main Costs
Severance
© 100-Day Advisors MandAPlaybook.com

## Slide 6
Implementation Schedule
1
8
Coord. Aug close process
Establish initial treasury link
2
9
Implement tax reorg.
Coord. ongoing close process
3
10
Harmonize business plan process
Change audit firm to E&Y
4
11
Coord. external audit strategy
Integrate accounting policies
5
12
Coord. consistent acct. class
Complete consol. of treasury
6
1 - 5
Complete B/S audit
Integrate Acquired. Co. A/R
Integrate customer finance
Dev. Acquired Co. EVA program
Communicate tax rptg. reqmts.
© 100-Day Advisors MandAPlaybook.com

## Slide 7
Summary of Cost Synergies (000)
Projects/ actions
Comp. Date
SG&A Headcount Reduction
Other Expense Reductions
Total Imp Expense
Total Imp Capex
Savings 2025
Full Year Savings
Reduction Working Capital
Reorganization - salaries
12/31
11
$690
Severance
$690
$690
Reorganization - fringe
12/31
$210
Severance
$210
$20
Consolidate audit process
9/30
None
$265
None
$265
$265
Reduce duplicate consultant usage
10/31
None
$120
None
$120
$120
Reduce legal Fees
10/31
None
$200
None
$200
$200
Reduce bank fees
12/31
None
$270
None
$270
$270
Reduce Acq. Co Corporate admin
10/31
None
$1,100
None
$1,100
$1,100
Consolidate actuarial services
12/31
None
$100
None
$100
$100
Total
11
$2,955
$2,955
$2,765
© 100-Day Advisors MandAPlaybook.com

## Slide 8
Key Organizational Changes
Centralize Accounts Receivable
Centralize Accounts Receivable function within the Americas region
Establish Trade Finance
Establish Trade Finance function within the Americas region
Headcount Reduction
Headcount reduction of 11 within the Acquired Co. finance group (37% reduction)
© 100-Day Advisors MandAPlaybook.com

## Slide 9
Key Issues & Assumptions
Employee Morale
Decline in employee morale due to uncertainty
Cultural Differences
Cultural and business process differences between companies and locations
Integration Timeline
Speed of integration not as quick as expected
IS Requirements
IS requirements for centralization of Accounts Receivable function
© 100-Day Advisors MandAPlaybook.com

## Slide 10
Necessary Process Maps
Cash Request/Signature
Authority
Cash Management
Centralized A/R Credit and Collection
Month-End Closing Process
Acquired Co. month-end 2 to 3-day statement closing process
Fixed Asset Management
Fixed asset acquisition, reporting,
and tracking
Annual Business Planning
Business planning process
© 100-Day Advisors MandAPlaybook.com

## Slide 11
Phase 2 Integration in EMEA
Purpose
Establish a combined finance organization that meets its service needs as efficiently and cost effectively as possible.
Objective
Adopt best practice processes of both companies and implement action plans to adopt those processes and achieve synergies.
Value Drivers
Streamlining of activities, centralization of functions and elimination of redundancies.
Main Synergies
Reduced headcount and elimination of duplicate outside services.
Main Costs
Severance.
© 100-Day Advisors MandAPlaybook.com

## Slide 12
EMEA Key Proposed Modifications
Legal Entity Reduction
Reduce number of legal entities
Accounting Centralization
Centralize accounting and control of Acquired Co. in UK, Germany, and France
European Finance Management
Centralize management of European finance group (reinforced trade finance, centralized hedging, cash pooling, legal and tax, reporting and consolidation)
Controller Organization Alignment
Align controller's organization with the EMEA organization to be announced (consider disconnecting legal entity and country results)
Asian Support
Asian finance requirements to be addressed by local competencies with EMEA support where required
© 100-Day Advisors MandAPlaybook.com

## Slide 13
EMEA Open Points with Potential Impact on Synergies
Legal Structure Commitment
Commitment not to change the legal structure of Acquired Co before next year may delay the reduction of the number of legal entities
Tax Implications
Tax implications of new legal structures/organization need to be considered
IT Facilitation
IT facilitation of combined processes to be analyzed in detail given the two existing systems
HR Review
HR review of timing of communication to be completed
Organizational Adaptations
Information on global organization and key managers might lead to modifications of proposed financial organization to adapt to non- anticipated situations
Netherlands Entity
Review feasibility of Netherlands without creating a legal entity
Transfer Pricing
Formalize transfer pricing policy (EMEA and US)
© 100-Day Advisors MandAPlaybook.com

## Slide 14
EMEA Summary of Synergies (000)
Projects/actions
Comp. Date
SG&A Headcount Reduction
Other Expense Reductions
Total Imp Expense
Total Imp Capex
Savings 2025
Full Year Savings
Reduction Working Capital
Consolidate Acqd. Co. German Finance functions into one
4/1
5
$125
$0
$188
$251
Continue standalone headcount reduction in German Finance team
4/1
10
$250
$0
$337
$450
Transfer Baan expert to IT department
1/1
1
$0
$0
$100
$100
Cancel eastern countries’ accountants (treated through Germany)
4/1
2
$10
$0
$18
$25
Consolidate UK finance functions into one
4/1
2
$40
$0
$50
$75
Consolidate Acquired Co. France finance functions into France
12/31
4
$35
$0
$140
$140
Decrease in France controllers
12/31
4
$150
$0
$180
$180
Decrease in France A/P headcounts
6/1
3
$120
$0
$70
$120
Transfer of accounting to UK
12/31
1
$23
$0
$45
$45
Closing of German plant and stop of accounting
7/1
1
$7
$0
$14
$28
Trade Financing person in Germany
4/1
-1
$0
$0
-$80
-$110
Simplify service control in France
4/1
2
$35
$0
$52
$70
Total
34
$795
$1,114
$1,374
© 100-Day Advisors MandAPlaybook.com

## Slide 15
EMEA Synergy Comments
Cost Reduction Estimates
Cost reduction initially estimated at 50 K€ per person, i.e.. 1.7 M€ for 34 persons while actual computation based on payroll cost of identified persons only reaches 1.4 M€
Additional Savings
Additional savings linked to closing of locations/legal entities, such as audit fees, decrease in IT rentals (less computers), decrease in accounting costs in Australia representing K€ 0.25 already taken into account by other teams
Adjusted Savings
The initial 2.0 M€ full year saving is therefore limited to 1.4 M€ to avoid overstatement
© 100-Day Advisors MandAPlaybook.com

## Slide 16
EMEA Necessary Process Maps
Cash Management
Comprehensive process for managing across European operations
Trade Financing
Structured approach to financing international trade activities
Merged Accounting Processes
Accounting processes in merged accounting departments to be developed for each country
Fixed Asset Management
Fixed asset acquisition, reporting, and tracking
Legal Coordination
Coordination with corporate legal department with adequate power delegations
© 100-Day Advisors MandAPlaybook.com

## Slide 17
Support to Asia Pacific
6
Support Areas
Key areas where EMEA finance
will support Asia Pacific operations
24/7
Availability
Continuous support across time zones
EMEA finance group will continue to provide support to Asia for:
Legal issues
Tax issues
Treasury issues (cash and hedging)
Trade financing schemes
Technical support on US GAAP's, EVA
IT support (see IT team)
© 100-Day Advisors MandAPlaybook.com

## Slide 18
Finance-Oriented Communication
Banks
Banks communication (new cash pool, hedging, legal structures, level of financial information available)
Trade Finance
Trade finance communication (contact to be established to explain new organization)
Tax Administration
Tax administration (follow up of legal restructuring)
Insurance
Insurance (already done)
Auditors
Statutory auditors (in process)
Customers & Suppliers
New A/R and sales admin departments to be disclosed to customers
Same for suppliers if contacts have changed (including bank account numbers)
Internal
Internal communication to be accelerated with key people
© 100-Day Advisors MandAPlaybook.com

## Slide 19
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting
11
19