## Slide 1
INTEGRATION END STATES
Accomplished
In Progress
Not Yet Due
© Copyright 100-Day Advisors | Integration End States
DAY 30 STATUS REPORT
100-DAY POST-MERGER INTEGRATION PLAYBOOK

## Slide 2
END STATE SCORECARD — DAY 30
Summary status across all seven workstreams — 28 end states tracked
Workstream
✓ Accomplished
◑ In Progress
○ Not Yet Due
Overall Status
Human Resources
3
3
2
38%
Information Technology
2
3
3
25%
Finance
4
—
—
100%
Legal
2
2
—
50%
Sales
2
2
—
50%
Communications
2
1
1
50%
IMO
1
2
1
25%
© Copyright 100-Day Advisors | Integration End States
2

## Slide 3
HUMAN RESOURCES
END STATES — DAY 30 STATUS
✓ Done
◑ Partial
○ Pending
✓ Done
FOR THE BOARD
Headcount synergies confirmed against deal model at Day 100 gate
Benefit cost savings locked and reported to CFO
HR integration summary delivered: workforce metrics, open items, BAU handoff
✓ Done
FOR MANAGERS
Clear reporting lines effective from Day 1 — no ambiguity about who reports to whom
Talking points, Q&A guides, and escalation paths in hand before first employee conversation
HR hotline and integration intranet live with answers to common questions
◑ Partial
FOR ACQUIRED EMPLOYEES
First paycheck correct, on time, and from the right entity
Benefits enrolled, coverage active, and carrier contacts known
One handbook, one set of policies, one HR team to call
◑ Partial
FOR HR TEAM
HRIS fully migrated; all employee records in combined system of record
Combined HR dashboard live: headcount, attrition, open roles, cost metrics
Retrospective complete; lessons documented in M&A playbook before team disperses
© Copyright 100-Day Advisors | Integration End States | Human Resources
3

## Slide 4
INFORMATION TECHNOLOGY
END STATES — DAY 30 STATUS
✓ Done
◑ Partial
○ Pending
◑ Partial
FOR SHAREHOLDERS
$675K annual IT cost synergy run-rate confirmed and published in Day 100 scorecard
Cost-to-achieve spend within budget; CTA vs. plan variance accepted by CFO
Combined IT operating model sustainable within BAU budget
◑ Partial
FOR CUSTOMERS
Zero service disruption experienced during integration period
SOC 2 / ISO 27001 certifications confirmed covering combined entity — no lapse in coverage
Customer-facing systems and support channels fully operational and unified
◑ Partial
FOR VENDORS
All change-of-control clauses resolved; no contracts in default or emergency renegotiation
Vendor consolidation roadmap executed; combined entity operating on rationalized contracts
IT vendor relationships transitioned from two contacts to one combined entity relationship
◑ Partial
FOR EMPLOYEES
Single set of IT tools, policies, and support processes for all staff
IT onboarding / offboarding process unified and documented
Helpdesk volumes returned to pre-integration baseline; no open Day 1 access issues
© Copyright 100-Day Advisors | Integration End States | Information Technology
4

## Slide 5
FINANCE
END STATES — DAY 30 STATUS
✓ Done
◑ Partial
○ Pending
✓ Done
FOR THE BOARD
Phase 1 synergy realization report delivered; actuals vs. deal model locked
First combined financial close executed without restatement
Finance integration summary: cost-to-achieve vs. budget, synergies confirmed, open items handed to BAU
✓ Done
FOR THE CFO
ERP-of-record selected; all downstream systems integration sequenced
Combined FP&A planning cycle operational; first combined budget complete
All tax elections, NOL confirmations, and post-close entity restructuring done
✓ Done
FOR FINANCE TEAM MEMBERS
One chart of accounts, one reporting framework, one set of approval thresholds
Acquired finance team fully onboarded to acquirer systems, tools, and processes
Combined Finance org structure final; roles and reporting lines confirmed
✓ Done
FOR THE BUSINESS
Vendors paid on time, customers invoiced without interruption throughout
Management reporting provides combined entity view from Day 1
No material control gaps or compliance issues attributable to integration
© Copyright 100-Day Advisors | Integration End States | Finance
5

## Slide 6
LEGAL
END STATES — DAY 30 STATUS
✓ Done
◑ Partial
○ Pending
✓ Done
FOR SHAREHOLDERS
All regulatory approvals obtained; no post-close remedy or divestiture required
Legal synergies confirmed — outside counsel consolidation and litigation reserve reductions locked
No undisclosed liabilities surfaced post-close that materially affect deal economics
✓ Done
FOR CUSTOMERS
All customer contracts consented, novated, or assigned without interruption to service
Data privacy rights and processing agreements honored under the combined entity from Day 1
Combined entity's contract terms published and counterparties notified
◑ Partial
FOR VENDORS & PARTNERS
All material vendor contracts transitioned; change-of-control clauses resolved
Government contracts novated with agency consent; no lapse in performance authority
Unified contract templates and approval authority in place for new agreements
◑ Partial
FOR EMPLOYEES
Unified code of conduct, employment policies, and handbooks live for all staff
WARN Act and Works Council obligations met; no statutory violations
Single legal escalation path and RACI understood by all workstream leads
© Copyright 100-Day Advisors | Integration End States | Legal
6

## Slide 7
SALES
END STATES — DAY 30 STATUS
✓ Done
◑ Partial
○ Pending
✓ Done
FOR SHAREHOLDERS
Revenue synergies confirmed against deal model at Day 100 gate review
Cross-sell pipeline established and tracking separately from organic growth
Combined sales org operating within BAU budget; no integration carryover costs
✓ Done
FOR CUSTOMERS
Single point of contact, consistent service levels, and no contract disruption
CEO-level communication delivered to all top accounts on Day 1
Combined QBR cadence established; customers engaged on combined capabilities
◑ Partial
FOR CHANNEL PARTNERS
Single combined partner program with rationalized tiers and clear rules of engagement
Duplicate agreements in same territories eliminated; no double-payment of commissions
Named single point of contact at combined entity for all partner inquiries
◑ Partial
FOR EMPLOYEES
Every rep has one manager, one territory, one quota, and one CRM from Day 1
Combined comp plan in place; no significant pay disparities between legacy populations
Combined onboarding complete; all reps certified on CRM before full cutover
© Copyright 100-Day Advisors | Integration End States | Sales
7

## Slide 8
COMMUNICATIONS
END STATES — DAY 30 STATUS
✓ Done
◑ Partial
○ Pending
✓ Done
FOR SHAREHOLDERS
Combined entity narrative established in financial media; deal rationale understood
Day 100 integration success story issued; synergy and retention data anchors the coverage
All investor communications completed without securities disclosure gaps or corrections
✓ Done
FOR CUSTOMERS
Every customer account contacted before the press release; no deal news from external sources
Combined entity brand and service commitments communicated and confirmed
No deal-related customer churn attributable to communications failure
◑ Partial
FOR MEDIA & REGULATORS
Inaccurate Day 1 trade coverage corrected via journalist briefings with on-record statements
Single designated spokesperson across all media inquiries through Day 100
All regulatory communications completed on Legal-approved timeline; no filing gaps
◑ Partial
FOR EMPLOYEES
Every employee received leadership communication before hearing the news externally
Integration intranet site active with current FAQ, org chart, and workstream updates
Day 100 pulse survey shows comprehension and sentiment at or above Day 1 baseline
© Copyright 100-Day Advisors | Integration End States | Communications
8

## Slide 9
IMO
END STATES — DAY 30 STATUS
✓ Done
◑ Partial
○ Pending
◑ Partial
FOR THE BOARD
Day 100 close-out report delivered with locked synergy baseline
All open integration items formally transferred to BAU owners
Integration lessons documented and incorporated into M&A playbook
◑ Partial
FOR THE STEERING COMMITTEE
All workstreams certified complete or formally deferred at Day 100 gate
No unresolved close-blocking risks carried into BAU
Integration budget closed; actuals vs. plan variance accepted by CFO
✓ Done
FOR WORKSTREAM LEADS
Every workstream plan formally closed or handed off with named BAU owner
All cross-workstream dependencies resolved; no open blockers
RAID log closed; all items resolved, accepted, or formally transferred
◑ Partial
FOR EMPLOYEES
Integration is visibly finished — no lingering uncertainty about org, roles, or tools
Communication cadence transitions from integration to BAU rhythm
Every employee knows who owns their workstream going forward
© Copyright 100-Day Advisors | Integration End States | IMO
9

## Slide 10
DAY 30: WHAT'S WORKING,
WHAT COMES NEXT
All Day 1 and Week 1 end states achieved across every workstream
Finance is the standout — all end state items fully accomplished at Day 30
HR, IT, Sales, Legal, and IMO are on track with active in-progress items
Day 100 gate deliverables — retrospectives, close-out reports, BAU handoffs — are not yet due
Priority: journalist correction briefings (Comms) and government contract novation (Legal)
© Copyright 100-Day Advisors | Integration End States
10

## Slide 11
100-DAY ADVISORS
Accelerating M&A Integrations
MandAPlaybook.com
inquiries@MandAPlaybook.com
11