## Finance Integration Plan
100-DAY FINANCE POST-MERGER INTEGRATION PLAN | [13 empty] | Click on + sign (above the top row on right) to see synergy columns
TODAY'S DATE: T+30 (30 DAYS POST-CLOSE)
Risk Level | Status | % Complete |  |  | Links
High | Not Started | 0% |  |  | Day 1 Checklist
Medium | Delayed | 25% |  |  | Milestones
Low | On Track | 50% |  |  | RAID Log (Includes Plan Assumptions)
| Complete | 75% |  |  | Next 14 Days
|  | 100% |  |  | Executive Dashboard
ID# | Category | Milestone | Phase | Assigned To | Task | Notes | Timing Anchor | Start | Finish | Status | Complete | Critical Path | Issues/Blockers | Risk Level | Team Dependency | Synergy Description | Synergy ($K) | Cost To Achieve ($K) | Synergy ($K) Realized | Actual Cost To Achieve ($K)
FIN-001 | Governance & Planning | Finance Lead Appointed | Pre-Close | CFO / Finance Workstream Lead | Identify Finance integration workstream lead and determine members of the Finance integration team | Finance workstream lead is the single accountable owner for all Finance integration deliverables; select individuals with both Finance expertise and change management capacity | T-59 | 1/2 | 1/10 | Complete | 100% | CP – Close | Finance workstream lead must be identified and available before integration kickoff; if the role is filled internally from a team with significant BAU responsibilities, capacity conflict is the most common cause of delayed Finance integration milestones | High | Executive Sponsor, HR | [5 empty] | 2
FIN-002 | Governance & Planning | Finance Integration Governance Established | Pre-Close | VP Finance / Controller | Review data privacy and confidentiality protocols for pre-close sharing | Clean room protocols apply pre-close; confirm what data can be shared without HSR or regulatory risk | T-53 | 1/8 | 1/12 | Complete | 100% |  | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | High | Legal, Compliance
FIN-003 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Assess normalized working capital requirements for the combined entity | NWC peg drives post-close settlement; errors here result in dollar-for-dollar price adjustments | T-51 | 1/10 | 1/20 | Complete | 100% |  |  | Medium | IMO, Legal
FIN-004 | Governance & Planning | Finance Integration Governance Established | Pre-Close | CFO / Finance Workstream Lead | Attend IMO Kickoff Meeting | Finance workstream lead attends to align on integration timeline, governance structure, and Finance workstream priorities; bring an initial list of Finance integration dependencies on HR (payroll, benefits), IT (ERP, systems), and Legal (regulatory filings, tax) | T-50 | 1/11 | 1/11 | Complete | 100% |  |  | Low | IMO
FIN-005 | Governance & Planning | Finance Integration Governance Established | Pre-Close | VP FP&A / Integration Manager | Receive access to integration data room and document repository | Pre-close access restrictions apply; confirm with Legal which financial data can be reviewed in the clean room vs. restricted; focus initial review on publicly available financial information and audited financial statements already disclosed to the acquirer under the NDA | T-49 | 1/12 | 1/13 | Complete | 100% |  |  | Low | IT, Legal
FIN-006 | Governance & Planning | Finance Integration Governance Established | Pre-Close | CFO / Finance Workstream Lead | Hold Finance Integration Kickoff Meeting | Kickoff agenda: Finance integration timeline, Day 1 close checklist and priorities, reporting deadlines, escalation process, and workstream RACI; distribute agenda 24 hours in advance and circulate meeting notes within 48 hours | T-49 | 1/12 | 1/12 | Complete | 100% |  |  | Low | IMO
FIN-007 | Governance & Planning | Finance Charter Approved | Pre-Close | VP Finance / Controller | Develop the Finance workstream integration charter and confirm team roles and responsibilities | Charter defines scope boundary between Finance workstream and other workstreams (HR, IT, etc.) | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | IMO
FIN-008 | Integration Management | Finance Integration Plan Locked | Pre-Close | VP FP&A / Integration Manager | Develop Finance integration plan (tasks, milestones, RAID log, Day 1 checklist) . Plan of record will be at 3/31. Significant plan changes subsequent to that date must go through formal change approval process. | Finance integration plan is the workstream's operating document; update weekly and share with IMO coordinator | T-49 | 1/12 | 3/31 | Complete | 100% |  |  | Medium | IMO
FIN-009 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Confirm all insurance policies — D&O, E&O, general liability, property — and coverage limits | Confirm tail coverage for D&O; verify property values reflect current replacement cost, not historical cost | T-49 | 1/12 | 1/21 | Complete | 100% |  |  | Medium | Legal
FIN-010 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Identify any material weaknesses or significant deficiencies noted by auditors | Prior auditor management letters are early indicators of control risk; request all letters for last 3 years | T-49 | 1/12 | 1/21 | Complete | 100% |  | Material weaknesses identified by target's prior auditors must be disclosed in the acquirer's next SEC filing if not remediated; escalate immediately to CFO and General Counsel — requires board audit committee awareness | High | External Auditor
FIN-011 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review external auditor relationship, audit fees, and most recent management letter | Auditor change post-acquisition is common and introduces timeline risk; engage combined entity auditor early | T-49 | 1/12 | 1/21 | Complete | 100% |  |  | Low | External Auditor
FIN-012 | Accounting & Financial Reporting | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review chart of accounts structure and identify gaps or conflicts with acquirer | COA mapping errors cause misclassified expenses and restatement risk; require Finance lead sign-off on final mapping | T-49 | 1/12 | 1/21 | Complete | 100% |  |  | Medium | IT
FIN-013 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Confirm sales tax, VAT, and indirect tax compliance across all jurisdictions | Multi-state and international indirect tax compliance is frequently a gap in smaller targets; obtain nexus study | T-49 | 1/12 | 1/23 | Complete | 100% |  |  | Medium | Legal
FIN-014 | Governance & Planning | Finance Integration Governance Established | Pre-Close | VP FP&A / Integration Manager | Define Finance integration success metrics and KPIs | KPIs should include: close timeline, synergy realization, systems cutover, and staff retention | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | IMO
FIN-015 | Governance & Planning | Finance Integration Governance Established | Pre-Close | VP Finance / Controller | Circulate integration roles and responsibilities to all finance team members — confirm who owns each workstream task and who escalates to whom | RACI must include both legacy finance teams; shared ownership is a common accountability gap | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Medium | HR, IMO
FIN-016 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Identify any unusual cash movements or related-party transactions | Related-party transactions at non-arm's-length rates must be restated; flag for tax and legal review | T-46 | 1/15 | 1/22 | Complete | 100% |  | Unusual cash movements or related-party loans at non-arm's-length rates require restatement before any closing price adjustment; if undisclosed, they trigger SPA indemnity claims | High | Legal
FIN-017 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Assess quality of earnings — confirm reported EBITDA reflects true operating performance | QoE adjustments directly impact purchase price; engage specialist advisors for complex revenue or cost structures | T-46 | 1/15 | 2/22 | Complete | 100% |  | Seller may resist reclassifying addbacks that inflate EBITDA; engage QoE advisor early — disputes over addbacks directly affect purchase price and often require SPA representations to resolve | High | Legal
FIN-018 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review and validate purchase price and deal economics vs. original investment thesis | Validate IRR, MOIC, and payback assumptions against due diligence findings; flag any variance above 10% to CFO | T-46 | 1/15 | 2/22 | Complete | 100% |  | If due diligence findings produce EBITDA adjustments exceeding agreed thresholds, purchase price renegotiation or additional SPA representations may be required; Finance must present findings to CFO before final price is locked | High | Legal
FIN-019 | Treasury & Cash Management | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review and validate net working capital peg and adjustment mechanism | NWC peg typically negotiated as trailing 12-month average; confirm definition with Legal before signing SPA | T-46 | 1/15 | 2/27 | Complete | 100% |  | NWC peg is typically negotiated as a trailing 12-month average but sellers often propose a higher peg using peak periods; if the definition is disputed at close, the SPA mechanism governs | High | Legal
FIN-020 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | VP FP&A / Integration Manager | Design the synergy tracking framework — template, cadence, and reporting process | Include a cost-to-achieve column for each synergy | T-44 | 1/17 | 1/24 | Complete | 100% |  |  | Medium | IMO
FIN-021 | Governance & Planning |  | Pre-Close | VP FP&A / Integration Manager | Launch weekly Finance workstream status meeting — same day, same time each week | Consistent meeting cadence is critical for cross-workstream coordination; skip no meetings in the first 60 days | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
FIN-022 | Integration Management |  | Pre-Close | VP Finance / Controller | Update Executive Dashboard weekly | Dashboard is the primary reporting tool for IMO and steering committee; Finance lead owns the Finance rows | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
FIN-023 | Integration Management |  | Pre-Close | VP FP&A / Integration Manager | Update status of integration plan weekly | Weekly update includes task status, RAID log changes, and any budget variances; due Thursday by 4 PM | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
FIN-024 | Integration Management |  | Pre-Close | VP FP&A / Integration Manager | Attend weekly IMO Meeting and discuss issues and status | Finance lead reports on task completion, RAID log, and budget status; escalate blockers requiring IMO or Steering Committee decision | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
FIN-025 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Identify any net operating loss carryforwards and confirm availability post-close | NOL carryforwards are often partially or fully limited by Section 382; quantify the annual limitation | T-42 | 1/19 | 1/27 | Complete | 100% |  | Section 382 annual limitation on NOL utilization is calculated based on the stock value at close and the long-term tax-exempt rate; limitations can reduce the value of carried losses by 80–90% | High | Legal | NOL utilization — confirmed carryforwards offset future taxable income, reducing cash tax payments | 50 | 10 | 25 | 5
FIN-026 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review deferred tax assets and liabilities and confirm recoverability | DTAs may be limited under IRC Section 382 post-acquisition; engage tax counsel before signing | T-42 | 1/19 | 1/31 | Complete | 100% |  | Deferred tax assets tied to losses may be significantly impaired by the ownership change under IRC Section 382; engage tax counsel to model the annual limitation before signing — overvalued DTAs are a common purchase price dispute | High | Legal
FIN-027 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review most recent interim (monthly/quarterly) financial statements | Compare interim results to budget and prior year to identify trend breaks not visible in annual statements | T-42 | 1/19 | 1/31 | Complete | 100% |  |  | Medium | IMO
FIN-028 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Analyze revenue trends, gross margin, and EBITDA over the last 5 years | Disaggregate by product, geography, and customer concentration; | T-42 | 1/19 | 1/31 | Complete | 100% |  | Margin compression is a common diligence surprise in acquisitions — revenue may be growing while gross margin is quietly declining due to product mix shift, pricing concessions, or rising COGS; a margin trend that is not identified before close will surface in the first combined earnings report and cannot be explained away as an integration artifact | High | IMO
FIN-029 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Identify and assess all non-recurring, one-time, or extraordinary items | Addbacks must be defensible to auditors and lenders; document each item with source evidence | T-42 | 1/19 | 1/31 | Complete | 100% |  |  | Medium | Legal
FIN-030 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review management accounts and board reporting packages | Board packs often reveal business issues not visible in financial statements — review at least 8 quarters | T-42 | 1/19 | 1/31 | Complete | 100% |  |  | Low | IMO
FIN-031 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review accounts receivable aging and identify overdue or disputed balances | Identify any receivables that have been factored or pledged as collateral; confirm DSO vs. industry benchmark | T-42 | 1/19 | 1/31 | Complete | 100% |  |  | Medium | IMO
FIN-032 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review accounts payable aging and confirm payment terms with key vendors | Early payment discounts may offset costs | T-42 | 1/19 | 1/31 | Complete | 100% |  |  | Low | IMO
FIN-033 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Obtain and review financial statements for the last 3–5 years | Request audited statements where available; flag any audit qualifications or restatements for immediate escalation | T-42 | 1/19 | 1/31 | Complete | 100% |  | Target company may resist providing full audited financials outside of a formal data room — confirm access protocol with Legal before requesting; if target is private, audited statements may not exist and compilation financials require additional QoE procedures | High | Legal, IMO
FIN-034 | Compliance & Regulatory | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Identify all regulatory and statutory filing requirements and deadlines | Include SEC, state, local, and international filings; map deadlines into IMO master calendar | T-42 | 1/19 | 2/23 | Complete | 100% | CP – Day 1 Readiness |  | Medium | Legal
FIN-035 | Accounting & Financial Reporting | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Document accounting policy differences across both entities — revenue recognition, inventory valuation, depreciation, lease accounting, goodwill impairment, and other material accounting methodology differences | Gap analysis output drives policy alignment decisions; document divergences in writing for auditor reference | T-41 | 1/20 | 2/3 | Complete | 100% |  | Undocumented or unreconciled accounting policy differences (revenue recognition, depreciation, leases, goodwill) create restatement risk when the first combined financial statements are prepared; differences that are not documented before Day 1 are discovered during close and delay the first combined reporting cycle | High | Legal
FIN-036 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Analyze working capital trends and identify seasonal or structural fluctuations | Seasonal working capital swings affect the NWC peg calculation; model at least 12 months of monthly data | T-39 | 1/22 | 2/3 | Complete | 100% |  |  | Medium | IT
FIN-037 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review all off-balance-sheet items, commitments, and contingencies | Off-balance-sheet items include operating leases pre-ASC 842, take-or-pay contracts, and pension obligations | T-39 | 1/22 | 2/6 | Complete | 100% |  | Confirm with target's auditor that all off-balance-sheet items are disclosed. | High | Legal
FIN-038 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review all letters of credit, guarantees, and contingent financial obligations | Letters of credit and guarantees may require lender consent on change of control; flag immediately to Legal | T-39 | 1/22 | 2/6 | Complete | 100% |  | Missing required consent from lenders can create high legal exposure | High | Legal
FIN-039 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Confirm all debt obligations and covenants | Covenant compliance must be confirmed at close; some covenants are automatically breached by a change of control | T-39 | 1/22 | 2/6 | Complete | 100% |  | Change-of-control provisions in debt agreements can trigger automatic acceleration or require lender consent to waive; Legal and Finance must confirm covenant compliance before signing — failure to obtain waivers can block close | High | Legal
FIN-040 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Identify any change-of-control clauses that may be triggered by the transaction | Change-of-control provisions can trigger debt acceleration, contract termination, or consent requirements | T-39 | 1/22 | 2/6 | Complete | 100% |  | Key customer contracts, software licenses, and government agreements often contain change-of-control clauses requiring notice or consent within 30–60 days of close; failure to notify counterparties in time can trigger termination rights | High | Legal
FIN-041 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review accrued liabilities, provisions, and contingent liabilities on the balance sheet | Environmental, warranty, and litigation reserves are common diligence surprises; require supporting schedules | T-39 | 1/22 | 2/6 | Complete | 100% |  |  | Medium | Legal
FIN-042 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Identify all pending or threatened litigation and quantify potential financial exposure | Obtain litigation schedule from Legal; quantify range of outcomes and determine whether reserves are adequate | T-39 | 1/22 | 2/6 | Complete | 100% |  | Undisclosed or under reserved litigation is a top source of post-close disputes; require a complete litigation schedule from target's General Counsel and compare against reserves on the balance sheet — material gaps require SPA indemnity coverage | High | Legal
FIN-043 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Identify any open tax audits, disputes, or outstanding tax liabilities | Open audits create closing risk; confirm whether indemnity coverage in the SPA covers pre-close tax periods | T-39 | 1/22 | 2/6 | Complete | 100% |  | Open IRS or state tax audits may be closing conditions under the SPA; if audits are in progress, confirm whether escrow or indemnity is required — unresolved audits in excess of threshold amounts can delay or prevent close | High | Legal
FIN-044 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review federal, state, and local tax returns for the last 3–5 years | Focus on unusual deductions, elections, and positions that may not survive IRS scrutiny post-acquisition | T-39 | 1/22 | 2/13 | Complete | 100% |  | IRS and state tax penalties for late or incorrect filings can be substantial and are assessed against the combined entity from the date of the filing error regardless of which predecessor entity created the problem; unidentified tax exposures in the target's returns become the combined entity's liability at close | High | Legal
FIN-045 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Review internal controls framework and assess adequacy for combined entity | Material weaknesses require remediation before first combined audit; factor timeline into integration plan | T-36 | 1/25 | 2/13 | Complete | 100% |  | If target's external auditors have issued a material weakness opinion, remediation must be underway before the first combined audit period; remediation timelines of 6–12 months are common — factor into integration planning | High | External Auditor
FIN-046 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Assess target company compliance with financial regulations (SEC, PCAOB, FINRA if applicable) | PCAOB inspections and SEC comment letters on prior filings are key risk signals; review before signing | T-36 | 1/25 | 2/13 | Complete | 100% |  |  | Medium | Legal, Compliance
FIN-047 | Accounting & Financial Reporting | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Confirm compliance with all applicable financial reporting standards (GAAP/IFRS) | Confirm whether target reports under IFRS or local GAAP; conversion to US GAAP may be required | T-36 | 1/25 | 2/3 | Complete | 100% |  |  | Low | Legal, Compliance
FIN-048 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP FP&A / Integration Manager | Review inventory valuation and obsolescence risk | Obsolete inventory write-downs affect purchase price; require physical count and third-party valuation if material | T-35 | 1/26 | 2/6 | Complete | 100% |  |  | Medium | IMO
FIN-049 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | VP Finance / Controller | Ensure synergy owners are assigned to initiatives so there is accountability for each initiative | One owner per synergy line item; co-ownership creates accountability gaps and missed targets | T-35 | 1/26 | 2/27 | Complete | 100% |  |  | Medium | IMO
FIN-050 | Compliance & Regulatory | Compliance Program Integrated | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Identify change of control triggers in key contracts and tax agreements | Change-of-control triggers must be identified before Day 1; some require third-party consent within a defined window | T-32 | 1/29 | 2/23 | Complete | 100% | CP – Day 1 Readiness | Change-of-control trigger identification must be completed before Day 1 — some contract clauses require counterparty notice within 5–10 business days of close; missed notice windows can result in automatic contract termination or loss of tax agreements | High | Legal
FIN-051 | Integration Management | Employee Comms Guide Approved | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Review drafts of the M&A Employee Communication Guide (includes talking points, guidance for team conversations, and Q&A / FAQ covering anticipated questions) | Review for tone accuracy around finance-specific topics; provide written feedback to Comm Lead within 72 hours | T-29 | 2/1 | 2/27 | Complete | 100% | CP – Day 1 Readiness |  | Medium | Communications
FIN-052 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Assess tax structure of the deal and confirm optimal post-close entity structure | Tax structure drives post-close cash taxes and integration complexity; alternatives include stock vs. asset election | T-29 | 2/1 | 2/20 | Complete | 100% |  | Post-close entity structure (stock vs. asset treatment, check-the-box elections) must be decided before signing because some elections are irrevocable; tax counsel and M&A counsel must align before the SPA is executed | High | Legal | Tax structure optimization — post-close entity rationalization reduces effective tax rate and simplifies compliance | 75 | 20 | 30 | 10
FIN-053 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Assess financial systems landscape — platforms, versions, and integration complexity | A parallel-run period may be required with significant IT resource commitment | T-29 | 2/1 | 2/27 | Complete | 100% |  | System incompatibility is the top financial integration risk; assess data migration complexity before Day 1 | High | IT
FIN-054 | Accounting & Financial Reporting | Accounting Policy Alignment Complete | Pre-Close | VP FP&A / Integration Manager | Map chart of accounts across both entities and agree on combined structure | Agree on a single target COA before Day 1 reporting; avoid dual-COA approaches beyond the first close | T-29 | 2/1 | 2/27 | Complete | 100% |  |  | Medium | IT
FIN-055 | Systems & Technology | Day 1 Finance Readiness Confirmed | Pre-Close | VP Finance / Controller | Confirm payroll provider, processing schedule, and payroll continuity plan for all employees | Confirm cutover date, employee data file format, and payroll funding mechanism with HR and payroll provider | T-29 | 2/1 | 2/15 | Complete | 100% |  | Payroll provider requires 30+ days to onboard a new client entity; if bank account changes are also required, ACH authorization lead times add further delay — initiate no later than 45 days before first payroll run | High | HR, Legal
FIN-056 | Accounting & Financial Reporting | Opening Balance Sheet Finalized | Pre-Close | VP FP&A / Integration Manager | Complete purchase accounting entries and preliminary opening balance sheet | Engage external auditor early; preliminary OBS requires fair value of all assets and liabilities | T-28 | 2/2 | 3/31 | Complete | 100% |  | Preliminary opening balance sheet requires third-party fair value appraisals for intangibles and fixed assets; appraisal firm must be engaged at least 30 days before close or Day 1 OBS will be estimated only | High | Legal
FIN-057 | Synergy Tracking & Realization | Synergy Realization (Phase 1) Report Done | Pre-Close | VP Finance / Controller | Ensure cost synergies are validated on an ongoing basis by synergy owners | Validation requires owner sign-off on baseline, target, and cost-to-achieve; unvalidated synergies should not be reported to investors | T-26 | 2/4 | 6/10 | On Track | 75% |  |  | Medium | IMO, All Workstreams
FIN-058 | Due Diligence | Finance Due Diligence Complete | Pre-Close | VP Finance / Controller | Complete lease and real estate obligation review — identify consolidation or exit opportunities | Identify leases subject to ASC 842 and flag any with change-of-control or assignment restrictions | T-24 | 2/6 | 2/20 | Complete | 100% |  |  | Medium | Legal, IMO | Office and corporate real estate consolidation — exiting overlapping office leases in markets where both entities have a presence; scope covers office and corporate facilities only; data center facility exit savings are captured separately under the IT workstream data center migration initiative | 50 | 15 |  | 5
FIN-059 | Governance & Planning | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Prepare investor FAQ and analyst briefing materials covering synergies, integration costs, and timeline | Investor FAQ must be aligned with the synergy model; discrepancies with public guidance are a legal risk | T-24 | 2/6 | 2/25 | Complete | 100% | CP – Day 1 Readiness | Investor FAQ figures must be cross-checked against the deal model, public filings, and earnings guidance; any discrepancy between the FAQ and other investor-facing materials creates legal risk — General Counsel must approve final version | High | IR, Legal
FIN-060 | Governance & Planning | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | CFO / Finance Workstream Lead | Assess acquisition financing structure and ensure closing funds are committed and available | Confirm funding source, wire instructions, and backup funding mechanism at least 5 days before closing | T-23 | 2/7 | 2/22 | Complete | 100% | CP – Day 1 Readiness | Acquisition financing must be fully committed at least 5 business days before closing; any lender condition not satisfied by closing date risks deal termination — Finance must manage lender relationships actively through signing to close | High | Legal
FIN-061 | Organization & Talent | Org Design Complete | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Establish interim finance org chart and confirm reporting lines for combined team | Interim org chart prevents reporting confusion on Day 1; distribute to HR and payroll before close | T-15 | 2/15 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Finance staff at the acquired company who do not know their reporting line on Day 1 will seek informal answers from their legacy manager — and the informal hierarchy that forms in the first week is significantly harder to undo than the formal one; a Finance team operating without clear authority lines on Day 1 will also make payment authorization and approval decisions in an ad hoc way, creating audit exposure from the first day of combined operations | High | HR
FIN-062 | Accounting & Financial Reporting | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Build a pro forma combined P&L and balance sheet for Day 1 management review | Pro forma P&L is the primary financial management tool on Day 1 | T-12 | 2/18 | 2/27 | Complete | 100% | CP – Day 1 Readiness | If delayed, management will be operating without combined financial visibility on Day 1 | High | IMO
FIN-063 | Accounting & Financial Reporting | Synergy Tracking Active | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Set up integration cost tracking codes in the general ledger before Day 1 | Reclassification of integration costs is an audit risk | T-12 | 2/18 | 2/23 | Complete | 100% | CP – Day 1 Readiness |  | Medium | IMO
FIN-064 | Compliance & Regulatory | Compliance Program Integrated | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Establish the combined company's delegation of authority and financial approval thresholds | Delegation of authority matrix governs who can bind the combined entity; must be active on Day 1 | T-11 | 2/19 | 2/26 | Complete | 100% | CP – Day 1 Readiness |  | Medium | Legal, Executive Sponsor
FIN-065 | Accounting & Financial Reporting | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Confirm earnout and contingent consideration payment tracking mechanisms | Earnout mechanics must be documented in the GL from Day 1; retroactive setup creates audit and legal risk | T-10 | 2/20 | 2/25 | Complete | 100% | CP – Day 1 Readiness | Earnout measurement periods begin on Day 1 under most SPAs; failure to establish tracking mechanisms on Day 1 creates disputes about the measurement baseline — Finance must confirm the earnout definition, metrics, and reporting protocol with Legal before close | High | Legal
FIN-066 | Treasury & Cash Management | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Set up interim intercompany settlement mechanism for Day 1 | Document the intercompany settlement rate and approval process; this mechanism is temporary — sunset by Day 30 | T-8 | 2/22 | 2/27 | Complete | 100% | CP – Day 1 Readiness |  | Medium | IT
FIN-067 | Compliance & Regulatory | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Confirm purchasing and spend approval controls will be active on Day 1 | Verify approval limits are loaded in acquirer's procurement system before any target-entity purchase orders are processed | T-8 | 2/22 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Acquirer's spend approval system (ERP or procurement tool) must be configured with target-entity cost centers and approval hierarchies before Day 1; IT must confirm provisioning no later than T-3 days | High | IT, Procurement
FIN-068 | Systems & Technology | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Confirm revenue recognition and billing processes will be operational on Day 1 | Test billing system end-to-end before Day 1; revenue leakage on Day 1 is a material risk | T-8 | 2/22 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Revenue collection cannot be interrupted on Day 1; billing system cutover must be tested in full before close — any failure to invoice on Day 1 creates immediate cash flow impact and customer escalation risk | High | Sales, IT
FIN-069 | Accounting & Financial Reporting | PPA Valuation Finalized | Pre-Close | CFO / Finance Workstream Lead | Finalize purchase price allocation (PPA) valuation and audit sign-off purchase | PPA drives goodwill, intangibles, and deferred tax entries; delays here cascade into every financial statement line | T-5 | 2/25 | 5/15 | On Track | 75% |  | Final PPA requires completed intangible asset valuation (customer relationships, technology, trade names) from a qualified third-party appraiser; delays in engaging the appraiser are the most common PPA bottleneck — engage no later than signing | High | Legal
FIN-070 | Treasury & Cash Management | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Validate combined entity bank account signatories and confirm wire transfer authorities will be active on Day 1 | Wire transfer authority must be active before the combined entity can fund payroll, make vendor payments, or execute any treasury transaction on Day 1; confirm with the bank at least 48 hours before close and test with a small internal transfer | T-4 | 2/26 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Wire transfer authority must be active before the combined entity can fund payroll, make vendor payments, or execute any treasury transaction on Day 1; failure to confirm with the bank before close means the combined entity cannot make financial commitments on Day 1, creating immediate operational paralysis | High | IMO, All Workstreams
FIN-D1 | Integration Management | Day 1 Finance Readiness Confirmed | Pre-Close (Day 1 Readiness) | CFO / Finance Workstream Lead | Finance Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | Workstream lead formally certifies Day 1 readiness to the IMO; this gate must be green for every workstream before the IMO signs off on close; any open item at this gate is either resolved or escalated to the steering committee as a close-blocking risk | T-3 | 2/27 | 2/27 | Complete | 100% | CP – Close | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | High | IMO, All Workstreams
FIN-071 | Governance & Planning | Day 1 Finance Integration Complete | Day 1 / Week 1 | VP FP&A / Integration Manager | Distribute Day 1 finance communications to all staff in both companies | Distribute before markets open on Day 1; coordinate timing with press release and employee all-hands | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  |  | Medium | IR, Communications
FIN-072 | Accounting & Financial Reporting | Day 1 Finance Integration Complete | Day 1 / Week 1 | VP Finance / Controller | Confirm accounts payable payment run is executed on schedule and no vendor payments are disrupted by the system cutover | Run AP payment cycle as normal on Day 1; confirm with IT that the AP module is live and processing before approving the payment run; flag any vendors on payment hold due to the cutover and communicate expected payment dates | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  |  | Medium | HR, IT
FIN-073 | Accounting & Financial Reporting | Day 1 Finance Integration Complete | Day 1 / Week 1 | VP Finance / Controller | Brief the acquired finance team on acquirer's reporting tools, systems, templates, operating procedures, expense reporting cutoffs, and T&E policy | Focus on reporting deadlines, chart of accounts, and approval authorities; distribute written reference guide same day | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  |  | Low | HR, IMO
FIN-074 | Compliance & Regulatory | Compliance Program Integrated | Day 1 / Week 1 | VP Finance / Controller | Confirm financial controls framework applies to acquired entity immediately | Controls must extend to target entity on Day 1 with no gap; obtain written confirmation from Internal Audit | Day 1 (Close) | 3/2 | 3/3 | Complete | 100% |  | If target's internal controls are materially weaker than acquirer's, a compensating control framework must be in place on Day 1; absence of controls over target entity in the first reporting period creates SOX exposure | High | IT, Legal
FIN-075 | Compliance & Regulatory | Compliance Program Integrated | Day 1 / Week 1 | VP Finance / Controller | Review and align travel and entertainment policies across both organizations | Flag materially different policies for CFO decision | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  |  | Low | HR
FIN-076 | Compliance & Regulatory | Tax Filing Obligations Complete | Day 1 / Week 1 | VP Finance / Controller | Submit required tax notifications to relevant authorities post-close | Notifications to IRS, state tax authorities, and foreign tax agencies have strict post-close deadlines | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  |  | Medium | Legal
FIN-077 | Treasury & Cash Management | Treasury Integration Complete | Day 1 / Week 1 | VP Finance / Controller | Confirm billing and invoicing continuity — no disruption to cash collection | Billing disruption on Day 1 is the fastest path to customer escalation | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  | Any disruption to customer billing on Day 1 creates immediate AR aging risk; billing system cutover must be tested end-to-end — no cutover without confirmed parallel-run success | High | IMO, IT
FIN-078 | Treasury & Cash Management | Treasury Integration Complete | Day 1 / Week 1 | VP Finance / Controller | Finalize treasury centralization — all cash pooling, FX management, and banking unified | Treasury centralization captures yield and reduces banking fees; target full centralization by Day 30 | Day 1 (Close) | 3/2 | 4/2 | On Track | 25% |  | Treasury centralization requires bank account consolidation, updated authorized signatories, and cash pool enrollment — each requiring bank processing time of 10–15 business days | High | IT, Legal | Treasury centralization savings — consolidating cash pooling, eliminating duplicate banking relationships, and centralizing FX management reduces annual banking fees and yield drag | 25 | 8 | 10 | 4
FIN-079 | Compliance & Regulatory | Compliance Program Integrated | Day 1 / Week 1 | VP Finance / Controller | Align financial code of conduct and conflicts of interest policies | Distribute updated code of conduct to all finance staff in both entities; | Day 1 (Close) | 3/2 | 3/31 | Complete | 100% |  |  | Medium | HR, Legal
FIN-080 | Compliance & Regulatory | Compliance Program Integrated | Day 1 / Week 1 | VP FP&A / Integration Manager | Confirm insurance policies are updated to reflect combined entity | Provide combined entity certificate of insurance to key customers and lenders during Week 1 | T+1 | 3/3 | 3/9 | Complete | 100% |  |  | Medium | Legal
FIN-081 | Accounting & Financial Reporting | Management Reporting Live | Day 1 / Week 1 | VP FP&A / Integration Manager | Confirm FP&A budget process and timeline for combined entity | Align budget cycle start date and template format with both entities' FP&A teams before distributing | T+1 | 3/3 | 3/6 | Complete | 100% |  |  | Low | IMO
FIN-082 | Accounting & Financial Reporting | Accounting Policy Alignment Complete | To Day 100 | VP Finance / Controller | Align accounting policies across acquirer and target | Acquirer accounting policies take precedence in a standard acquisition; target entity adopts acquirer policies effective close date; document all differences in a policy gap register and ensure external auditor reviews the alignment plan before the first combined close | T+8 | 3/10 | 3/31 | Complete | 100% |  | Exceptions require CFO approval and external auditor concurrence | High | Legal, IMO
FIN-083 | Systems & Technology | Systems Integration Complete | To Day 100 | VP Finance / Controller | Define combined entity financial system architecture and ERP consolidation approach — assess both legacy systems and select the platform of record | Define whether target will be migrated into acquirer's ERP or run on separate instance; decision drives entire systems timeline | T+8 | 3/10 | 3/31 | Complete | 100% |  | ERP architecture decision (migrate target into acquirer's system vs. maintain separate instance) must be made within 30 days of close; delayed decision blocks all downstream systems integration tasks and extends integration timeline | High | IT
FIN-084 | Compliance & Regulatory | Tax Filing Obligations Complete | To Day 100 | VP Finance / Controller | Confirm tax IDs, state registrations, and legal entity identifiers are updated | EIN, state tax ID, and entity identifiers drive payroll, tax filings, and banking — confirm all are updated | T+8 | 3/10 | 4/15 | On Track | 75% |  |  | Medium | Legal
FIN-085 | Systems & Technology | Payroll Live for All Employees | To Day 100 | VP Finance / Controller | Migrate acquired company payroll onto acquirer's payroll system or confirm bridge arrangement | Payroll is the most operationally critical finance task post-close — a payroll error on the first pay cycle creates immediate employee relations issues and legal exposure; run a full parallel payroll cycle before cutover, validate every employee record individually, and have a manual backup process ready; confirm payroll funding with treasury 5 business days before first pay date | T+8 | 3/10 | 3/31 | Complete | 100% |  | Payroll system migration must be tested with a parallel payroll run before cutover; any error in employee data, tax withholding, or bank routing information will result in missed or incorrect pay — employee trust is irreparably damaged by payroll failures | High | HR, IT
FIN-086 | Governance & Planning | Compliance Program Integrated | To Day 100 | VP Finance / Controller | Prepare and file required SEC disclosures (proxy, registration statement, 8-K) | Confirm filing deadlines with Legal and IR; late SEC filings trigger material weakness risk | T+8 | 3/10 | 4/30 | On Track | 50% |  | Combined entity registration statements and proxy materials require coordination between Finance, Legal, and IR; any accounting restatements or unresolved audit matters will delay filing and may trigger SEC comment letters | High | Legal
FIN-087 | Accounting & Financial Reporting | Management Reporting Live | To Day 100 | VP FP&A / Integration Manager | Define the consolidated management reporting package format and content | Management reporting package format must be agreed before the first combined close; retroactive changes are costly | T+8 | 3/10 | 3/20 | Complete | 100% |  |  | Medium | IMO
FIN-088 | Compliance & Regulatory | Tax Filing Obligations Complete | To Day 100 | VP Finance / Controller | Assess and integrate sales and use tax compliance programs | Sales tax nexus may expand significantly post-acquisition; assess economic nexus thresholds in all states | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium | Legal, IMO
FIN-089 | Accounting & Financial Reporting | Accounting Policy Alignment Complete | To Day 100 | VP Finance / Controller | Establish combined entity bad debt reserve methodology | Align with credit and collections policy; ensure reserve methodology is approved by external auditor before first consolidated close | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium | Sales
FIN-090 | Accounting & Financial Reporting | Accounting Policy Alignment Complete | To Day 100 | VP Finance / Controller | Standardize month-end journal entry process and approval workflows | Obtain target company's current close checklist and compare task by task; do not discard target process until gaps are mapped | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Low | IT
FIN-091 | Compliance & Regulatory | Compliance Program Integrated | To Day 100 | VP Finance / Controller | Establish unified credit and collections policy and apply across all customer accounts | Credit limits and collections procedures must be communicated to all customer-facing teams before going live | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium | IMO, Sales
FIN-092 | Compliance & Regulatory | Day 100 Finance Integration Complete | To Day 100 | VP FP&A / Integration Manager | Confirm all regulatory and statutory financial filings are current and compliant | Maintain a filing tracker with owner, due date, and jurisdiction for each obligation | T+8 | 3/10 | 6/10 | On Track | 50% |  |  | Medium | Legal, Compliance
FIN-093 | Compliance & Regulatory | Compliance Program Integrated | To Day 100 | VP Finance / Controller | Assess financial data security and access control requirements | Review data access controls against acquirer's security standards | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium | IT, Legal
FIN-094 | Compliance & Regulatory | Compliance Program Integrated | To Day 100 | VP Finance / Controller | Establish data governance standards for financial master data (vendor, customer, GL) | Vendor, customer, and employee master data governance prevents duplicate records and downstream reporting errors | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium | IT
FIN-095 | Systems & Technology | Systems Integration Complete | To Day 100 | VP Finance / Controller | Complete vendor contract consolidation review and identify top savings opportunities | Vendor consolidation is often the fastest cost synergy to realize; identify top 20 duplicated spend categories first | T+8 | 3/10 | 4/1 | Complete | 100% |  |  | Medium | IMO | Vendor spend consolidation — combined purchasing volume drives price concessions across G&A, facilities, and professional services vendors; explicitly excludes IT tool vendors already captured in the IT workstream consolidation initiatives, Communications agency spend captured in the Comms workstream, Legal outside counsel captured in the Legal workstream, and HR system vendors (HRIS, payroll processor, ATS, LMS) captured in the HR workstream HRIS integration initiative | 50 | 10 |  | 3
FIN-096 | Integration Management | Org Design Complete | To Day 100 | VP FP&A / Integration Manager | Identify finance staff retention risks and flag critical roles for retention planning | Retention risk is highest in the first 30 days; flag critical roles to HR for retention bonus consideration | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium | HR
FIN-097 | Treasury & Cash Management | Treasury Integration Complete | To Day 100 | VP Finance / Controller | Execute net working capital true-up calculation per SPA and initiate settlement process | NWC true-up is a contractual obligation with a defined deadline in the SPA; late submission forfeits the right | T+8 | 3/10 | 5/2 | On Track | 75% |  | NWC true-up is a contractual obligation with a defined submission window (typically 60–90 days post-close per the SPA); if Finance misses the submission deadline, the right to claim a purchase price adjustment may be forfeited | High | Legal
FIN-098 | Synergy Tracking & Realization | Synergy Realization (Phase 1) Report Done | To Day 100 | VP FP&A / Integration Manager | Track revenue synergy pipeline and cross-sell initiatives | Revenue synergies typically lag cost synergies by 6–12 months; track pipeline by stage, not just closed revenue | T+10 | 3/12 | 6/10 | On Track | 50% |  |  | Medium | Sales
FIN-099 | Accounting & Financial Reporting | Management Reporting Live | To Day 100 | VP Finance / Controller | Confirm month-end close calendar and assign ownership for first combined close. The first combined close will take longer than subsequent closes. | First combined close is a key risk event — run a pre-close dry-run at T-3 days | T+13 | 3/15 | 3/28 | Complete | 100% |  | First combined close calendar cannot be finalized until system cutover date is determined | High | IT, IMO
FIN-100 | Systems & Technology | Systems Integration Complete | To Day 100 | VP Finance / Controller | Implement combined entity accounts payable process and issue vendor communications | Vendor master data must be cleansed before go-live; duplicate vendors are the top AP integration failure mode | T+13 | 3/15 | 3/31 | Complete | 100% |  |  | Medium | IT
FIN-101 | Accounting & Financial Reporting | Opening Balance Sheet Finalized | To Day 100 | VP FP&A / Integration Manager | Establish goodwill and intangible asset tracking schedules | Goodwill impairment testing schedule must align with audit timing; flag any indefinite-lived intangibles for separate disclosure | T+13 | 3/15 | 3/31 | Complete | 100% |  |  | Medium | External Auditor
FIN-102 | Accounting & Financial Reporting | Accounting Policy Alignment Complete | To Day 100 | VP Finance / Controller | Align depreciation and amortization policies and update fixed asset registers | Useful life assumptions must be consistent across both entities; differences require a catch-up depreciation entry | T+13 | 3/15 | 3/31 | Complete | 100% |  |  | Low | External Auditor
FIN-103 | Accounting & Financial Reporting | Management Reporting Live | To Day 100 | VP FP&A / Integration Manager | Implement combined management reporting and KPI dashboards | KPI dashboard must reflect combined entity from first reporting period; avoid publishing two separate reports | T+13 | 3/15 | 3/31 | Complete | 100% |  |  | Medium | IT
FIN-104 | Accounting & Financial Reporting | Management Reporting Live | To Day 100 | VP FP&A / Integration Manager | Align forecasting methodologies and planning cycles across combined entity | Differing planning horizons (e.g., rolling vs. annual) must be reconciled; recommend adopting acquirer's methodology | T+13 | 3/15 | 4/1 | Complete | 100% |  |  | Low | IMO
FIN-105 | Integration Management | Synergy Realization (Phase 1) Report Done | To Day 100 | VP FP&A / Integration Manager | Manage integration budget vs. actuals and flag overruns | Track integration spend against approved budget by category; flag overruns above 10% to CFO within 48 hours | T+13 | 3/15 | 5/31 | On Track | 50% |  |  | Low | IMO
FIN-106 | Compliance & Regulatory | Compliance Program Integrated | To Day 100 | VP FP&A / Integration Manager | Complete SOX initial scoping compliance assessment | Engage external SOX advisors if target was not previously SOX-compliant; scoping determines control testing timeline | T+14 | 3/16 | 5/2 | On Track | 50% |  | SOX scoping must be completed within 60 days of close to meet the first-year accelerated filer deadline; if target had no prior SOX program, remediation timeline may extend 12–18 months and require external SOX advisory support | High | Legal
FIN-107 | Treasury & Cash Management | Treasury Integration Complete | To Day 100 | VP Finance / Controller | Consolidate investment portfolios and short-term securities | Consolidation may trigger taxable events; engage treasury and tax counsel before liquidating any positions | T+14 | 3/16 | 4/1 | Complete | 100% |  |  | Low | Legal
FIN-108 | Compliance & Regulatory | Day 100 Finance Integration Complete | To Day 100 | VP Finance / Controller | Consolidate insurance policies — eliminate redundant coverage and renegotiate combined rates | Broker review required; eliminate duplicate D&O, property, and liability coverage to capture cost synergy | T+18 | 3/20 | 5/31 | On Track | 25% |  |  | Low | Legal | Insurance premium reduction — eliminating overlapping coverage across combined entity | 50 | 5
FIN-109 | Treasury & Cash Management | Treasury Integration Complete | To Day 100 | VP Finance / Controller | Optimize combined working capital and cash conversion cycle | Working capital optimization is often the fastest cash flow synergy; benchmark combined DSO and DPO vs. peers | T+26 | 3/28 | 4/15 | On Track | 25% |  |  | Medium | Sales, IMO | Working capital optimization — DSO reduction and DPO extension through combined entity scale and renegotiated terms releases trapped working capital and improves free cash flow | 50 | 15 |  | 5
FIN-110 | Accounting & Financial Reporting | Opening Balance Sheet Finalized | To Day 100 | VP FP&A / Integration Manager | Complete the first consolidated month-end close for the combined entity; The first combined close will take longer than subsequent closes. | Parallel-run validation recommended for first close; use target company's books as a check on consolidated output | T+30 | 4/1 | 4/24 | On Track | 25% |  | First consolidated close requires mapped chart of accounts, completed purchase accounting entries, and a functioning consolidated reporting tool | High | IT
FIN-111 | Systems & Technology | ERP Consolidation Complete | To Day 100 | VP Finance / Controller | Complete ERP consolidation and sunset legacy systems | Legacy system sunset must be sequenced after data archiving and audit trail preservation | T+30 | 4/1 | 5/31 | On Track | 25% |  | Legacy system decommissioning cannot occur until all historical data is archived, audit trails are preserved, and all users are trained on the new system; premature decommissioning creates compliance and audit risk | High | IT | ERP consolidation and legacy system sunset — migrating to a single ERP eliminates dual license fees, hosting costs, and maintenance overhead for both legacy ERP platforms; scope covers ERP and core finance systems only; non-ERP application savings are captured in the IT workstream | 75 | 60 |  | 20
FIN-112 | Systems & Technology | Day 100 Finance Integration Complete | To Day 100 | VP Finance / Controller | Eliminate all remaining duplicate finance processes, tools, and reporting streams | Duplicate processes create cost and confusion; use a process inventory to track elimination status | T+30 | 4/1 | 5/31 | On Track | 25% |  |  | Medium | IT | Duplicate finance system and process elimination — consolidating standalone FP&A planning tools, BI/reporting platforms, and close management software onto a single combined stack; scope covers non-ERP finance tools only (ERP consolidation savings are captured separately); eliminates duplicate vendor fees, data reconciliation overhead, and parallel reporting runs | 50 | 20 |  | 5
FIN-113 | Accounting & Financial Reporting | Synergy Realization (Phase 1) Report Done | To Day 100 | VP Finance / Controller | Track one-time restructuring charges and ensure proper P&L classification | Restructuring charges must be classified consistently as one-time for non-GAAP reconciliation purposes | T+30 | 4/1 | 5/31 | On Track | 25% |  |  | Low | Legal
FIN-114 | Treasury & Cash Management | Treasury Integration Complete | To Day 100 | VP Finance / Controller | Review and renegotiate credit facilities and revolving credit lines | Combined entity purchasing power and credit profile typically supports better pricing on credit facilities; engage banking advisors to benchmark existing terms against market; prioritize renegotiating the largest facility first; any covenant changes require Legal review before signing | T+30 | 4/1 | 4/30 | On Track | 25% |  |  | Medium | Legal | Interest expense reduction — combined credit profile supports lower spread on revolving credit facility | 50 | 10 | 15 | 5
FIN-D30 | Integration Management | 30-Day Finance Review Complete | To Day 100 | VP FP&A / Integration Manager | Finance Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | IMO-led review of Finance workstream at Day 30; confirm all Day 1 tasks closed, RAID log current, synergy owners active, and no unresolved blockers threatening Day 100 delivery | T+30 | 4/1 | 4/3 | On Track | 50% |  | If the Day 30 check reveals open tasks, unresolved blockers, or synergy owners not yet active, the integration team has 70 days to correct course — but the Day 30 review must force honest status reporting; teams that report green when yellow or red create hidden risk that surfaces at Day 100 when it is too late to recover | High | IMO, All Workstreams
FIN-115 | Systems & Technology | Systems Integration Complete | To Day 100 | VP FP&A / Integration Manager | Conduct final vendor contract review — confirm all consolidations and renegotiations complete | Confirm all renegotiated terms are reflected in the vendor master before the contract closeout date | T+31 | 4/2 | 5/31 | Not Started | 0% |  |  | Low | IMO
FIN-116 | Synergy Tracking & Realization | Synergy Realization (Phase 1) Report Done | To Day 100 | VP FP&A / Integration Manager | Assess stranded costs from synergy actions and develop mitigation plan | Stranded costs are frequently overlooked; a vacated lease, orphaned system licenses, or retained headcount can offset the full synergy benefit | T+34 | 4/5 | 5/31 | Not Started | 0% |  | Stranded costs frequently offset 20–40% of gross cost synergies; failure to model and mitigate stranded costs will cause Finance to report synergy realization below guidance | High | HR, IMO
FIN-117 | Accounting & Financial Reporting | FP&A Process Unified | To Day 100 | VP Finance / Controller | Complete unified FP&A process — one budget, one forecast, one reporting cycle | Milestone confirming full FP&A integration; verify single planning tool, single budget, and single reporting output | T+39 | 4/10 | 5/31 | Not Started | 0% |  |  | Low | IMO
FIN-118 | Synergy Tracking & Realization | Synergy Realization (Phase 1) Report Done | To Day 100 | VP FP&A / Integration Manager | Report updated post-close synergy realization plan with revised timing and cost-to-achieve estimates | Update timing assumptions based on actual integration progress; do not carry original plan dates without review | T+39 | 4/10 | 4/16 | Not Started | 0% |  |  | Medium | IMO, All Workstreams
FIN-119 | Accounting & Financial Reporting | First Combined 10-Q Filed | To Day 100 | VP Finance / Controller | Prepare first combined Form 10-Q quarterly report | Confirm which entity files and whether target is a registrant; carve-out financials may be required | T+44 | 4/15 | 5/12 | Not Started | 0% |  |  | Medium | Legal, IR
FIN-120 | Compliance & Regulatory | Day 100 Finance Integration Complete | To Day 100 | VP Finance / Controller | Rationalize and integrate internal audit function | Determine whether internal audit co-source or in-house model applies to combined entity | T+44 | 4/15 | 5/31 | Not Started | 0% |  |  | Medium | Legal, IMO | Internal audit function rationalization — combining two internal audit teams eliminates duplicate FTEs, co-source spend, and redundant audit committee reporting overhead | 25 | 8 |  | 3
FIN-121 | Integration Management | Org Design Complete | To Day 100 | VP Finance / Controller | Complete finance team restructuring — all roles filled, redundancies resolved, structure final | Confirm all open roles are filled or formally eliminated before Day 100 governance close-out | T+44 | 4/15 | 5/31 | Not Started | 0% |  |  | Medium | HR | Finance headcount rationalization — elimination of duplicate roles across combined finance organization | 50 | 35
FIN-122 | Governance & Planning | FP&A Process Unified | To Day 100 | VP FP&A / Integration Manager | Prepare integration progress update for quarterly earnings call — synergy delivery and integration KPIs | Finance lead provides supporting data; IR owns the script — coordinate at least two weeks before the call | T+44 | 4/15 | 5/1 | Not Started | 0% |  | Public synergy guidance must reconcile to the internal synergy model; any disconnect between what is communicated to investors and what Finance is tracking internally creates securities law exposure — CFO and General Counsel must approve before release | High | Legal, IR, C-Level Executives
FIN-123 | Systems & Technology | Systems Integration Complete | To Day 100 | VP Finance / Controller | Validate AP/AR processes and vendor/customer master data | Duplicate vendor records are the most common AP integration issue; deduplicate before loading into combined system | T+49 | 4/20 | 4/30 | Not Started | 0% |  |  | Medium | IT
FIN-124 | Accounting & Financial Reporting | FP&A Process Unified | To Day 100 | VP FP&A / Integration Manager | Deliver reforecast incorporating first full month of combined entity actuals | First reforecast incorporates actual Day 1 results and updated synergy assumptions | T+54 | 4/25 | 5/1 | Not Started | 0% |  |  | Medium | All Workstreams
FIN-125 | Systems & Technology | Systems Integration Complete | To Day 100 | VP Finance / Controller | Integrate fixed assets system and conduct combined asset verification | Physical verification reduces insurance over-coverage and identifies assets not on the books | T+55 | 4/26 | 5/31 | Not Started | 0% |  |  | Low | IMO, IT
FIN-126 | Accounting & Financial Reporting | Day 100 Finance Integration Complete | To Day 100 | VP Finance / Controller | Begin preparing first combined annual report (10-K) with SEC — assign sections, confirm auditor scope, and set filing timeline | Coordinate filing timeline with external auditor and legal counsel | T+60 | 5/1 | 6/10 | Not Started | 0% |  | First combined 10-K is a high-visibility deliverable | High | Legal
FIN-127 | Systems & Technology | Systems Integration Complete | To Day 100 | VP FP&A / Integration Manager | Execute financial data migration testing and parallel run validation | Run at least one full parallel cycle before cutover | T+60 | 5/1 | 5/31 | Not Started | 0% |  | Parallel run failures are the leading cause of ERP integration delays; if data migration testing reveals integrity issues, cutover must be postponed — ensure a rollback plan is documented before any production migration begins | High | IT
FIN-128 | Synergy Tracking & Realization | Synergy Realization (Phase 1) Report Done | To Day 100 | VP FP&A / Integration Manager | Deliver final synergy realization report to Steering Committee and Board | Final synergy report feeds the Board narrative and any post-close investor communications; CFO reviews before distribution | T+60 | 5/1 | 6/10 | Not Started | 0% | CP – Day 100 | Final synergy report is a board deliverable; if synergy realization is materially below guidance, the CFO and Finance workstream lead must present a recovery plan to the board audit committee before the report is distributed externally | High | IR, Legal
FIN-129 | Accounting & Financial Reporting | FP&A Process Unified | To Day 100 | VP FP&A / Integration Manager | Deliver first fully integrated quarterly business review to executive team | The first combined close will take longer than subsequent closes. First QBR establishes the operating rhythm for the combined entity; include both legacy teams in the review | T+63 | 5/4 | 5/15 | Not Started | 0% |  |  | Medium | Sales
FIN-130 | Accounting & Financial Reporting | Day 100 Finance Integration Complete | To Day 100 | VP FP&A / Integration Manager | Finalize combined entity budget for the remainder of the fiscal year | Budget must reflect synergy cost-to-achieve and one-time integration charges; approved by CFO and Board | T+69 | 5/10 | 5/31 | Not Started | 0% |  | Combined budget cannot be finalized until synergy cost-to-achieve amounts are confirmed by each workstream lead; unresolved synergy assumptions result in a budget that does not reconcile to the deal model — CFO must resolve open items before Board submission | High | IMO
FIN-131 | Compliance & Regulatory | Tax Filing Obligations Complete | To Day 100 | VP Finance / Controller | File short-period tax returns for acquired entity as required | Short-period return covers the period from target's year-start to acquisition date; timing affects tax liability | T+76 | 5/17 | 6/10 | Not Started | 0% |  |  | Medium | Legal
FIN-132 | Compliance & Regulatory | Tax Filing Obligations Complete | To Day 100 | VP FP&A / Integration Manager | Prepare and file all required federal, state, and local tax returns for the combined entity's first filing period post-close — confirm jurisdictions, deadlines, and preparer assignments | Short-period returns and transaction-triggered filings have firm deadlines; engage outside tax counsel | T+79 | 5/20 | 6/10 | Not Started | 0% |  | Missed tax filing deadlines trigger automatic penalties and interest from the first day of non-compliance; in a combined entity covering multiple jurisdictions, the deadline calendar for federal, state, and local filings must be centrally tracked — a missed filing in any jurisdiction creates an exposure that compounds daily | High | Legal
FIN-133 | Synergy Tracking & Realization | Day 100 Finance Integration Complete | To Day 100 | VP FP&A / Integration Manager | Report on 100-Day synergy initiatives and confirm realization against deal model — primary synergy deliverable for the Day 100 Finance gate review; locks in the synergy baseline for ongoing tracking | Day 100 synergy report is a key investor deliverable; must reconcile to guidance provided at deal announcement | T+90 | 5/31 | 6/10 | Not Started | 0% | CP – Day 100 |  | Medium | IMO, All Workstreams
FIN-134 | Integration Management | Day 100 Finance Integration Complete | To Day 100 | VP FP&A / Integration Manager | Conduct Day 100 Finance integration retrospective — document lessons learned across accounting, FP&A, treasury, tax, and systems; findings presented at the Day 100 Finance gate review | Retrospective output updates the M&A playbook; document what slowed down or caused rework | T+91 | 6/1 | 6/10 | Not Started | 0% | CP – Day 100 |  | Low | IMO
FIN-135 | Integration Management | Day 100 Finance Integration Complete | To Day 100 | VP FP&A / Integration Manager | Close out all integration cost tracking codes — produce final integration P&L and cost-to-achieve summary; delivered as part of the Day 100 Finance gate close-out package | Final integration cost report is a required deliverable for the CFO and auditors; include all one-time charges | T+93 | 6/3 | 6/10 | Not Started | 0% | CP – Day 100 |  | Low | IMO
FIN-D100 | Integration Management | Day 100 Finance Integration Complete | To Day 100 | CFO / Finance Workstream Lead | Finance Day 100 Integration Gate — confirm all integration tasks complete or formally deferred, synergy baseline locked, BAU transition signed off | Final IMO gate for Finance workstream; all remaining open items must be formally accepted as BAU or escalated; this row closes the integration for the Finance workstream | T+98 | 6/8 | 6/10 | Not Started | 0% | CP – Day 100 | A delayed Day 100 gate triggers the risk that integration-mode governance and reporting continue beyond the intended window, increasing integration fatigue and cost | High | IMO, All Workstreams

## Day 1 Checklist
FINANCE M&A DAY 1 / WEEK 1 CHECKLIST (Pre-Close (Day 1 Readiness) and Day 1/Week 1 Phases)
TODAY'S DATE: T+30
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Milestones
Low | On Track | RAID Log
| Complete | Next 14 Days
Executive Dashboard
☐ Done | Task ID | Phase | Task Description | Assigned To | Risk Level | Timing Anchor | Start | Finish | Status | Milestone
☑ | FIN-034 | Pre-Close (Day 1 Readiness) | Identify all regulatory and statutory filing requirements and deadlines | VP Finance / Controller | Medium | T-42 | 1/19 | 2/23 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-050 | Pre-Close (Day 1 Readiness) | Identify change of control triggers in key contracts and tax agreements | VP Finance / Controller | High | T-32 | 1/29 | 2/23 | Complete | Compliance Program Integrated
☑ | FIN-051 | Pre-Close (Day 1 Readiness) | Review drafts of the M&A Employee Communication Guide (includes talking points, guidance for team conversations, and Q&A / FAQ covering anticipated questions) | VP FP&A / Integration Manager | Medium | T-29 | 2/1 | 2/27 | Complete | Employee Comms Guide Approved
☑ | FIN-059 | Pre-Close (Day 1 Readiness) | Prepare investor FAQ and analyst briefing materials covering synergies, integration costs, and timeline | VP FP&A / Integration Manager | High | T-24 | 2/6 | 2/25 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-060 | Pre-Close (Day 1 Readiness) | Assess acquisition financing structure and ensure closing funds are committed and available | CFO / Finance Workstream Lead | High | T-23 | 2/7 | 2/22 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-061 | Pre-Close (Day 1 Readiness) | Establish interim finance org chart and confirm reporting lines for combined team | VP Finance / Controller | High | T-15 | 2/15 | 2/27 | Complete | Org Design Complete
☑ | FIN-063 | Pre-Close (Day 1 Readiness) | Set up integration cost tracking codes in the general ledger before Day 1 | VP FP&A / Integration Manager | Medium | T-12 | 2/18 | 2/23 | Complete | Synergy Tracking Active
☑ | FIN-062 | Pre-Close (Day 1 Readiness) | Build a pro forma combined P&L and balance sheet for Day 1 management review | VP FP&A / Integration Manager | High | T-12 | 2/18 | 2/27 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-064 | Pre-Close (Day 1 Readiness) | Establish the combined company's delegation of authority and financial approval thresholds | VP Finance / Controller | Medium | T-11 | 2/19 | 2/26 | Complete | Compliance Program Integrated
☑ | FIN-065 | Pre-Close (Day 1 Readiness) | Confirm earnout and contingent consideration payment tracking mechanisms | VP Finance / Controller | High | T-10 | 2/20 | 2/25 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-066 | Pre-Close (Day 1 Readiness) | Set up interim intercompany settlement mechanism for Day 1 | VP Finance / Controller | Medium | T-8 | 2/22 | 2/27 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-067 | Pre-Close (Day 1 Readiness) | Confirm purchasing and spend approval controls will be active on Day 1 | VP FP&A / Integration Manager | High | T-8 | 2/22 | 2/27 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-068 | Pre-Close (Day 1 Readiness) | Confirm revenue recognition and billing processes will be operational on Day 1 | VP Finance / Controller | High | T-8 | 2/22 | 2/27 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-070 | Pre-Close (Day 1 Readiness) | Validate combined entity bank account signatories and confirm wire transfer authorities will be active on Day 1 | VP Finance / Controller | High | T-4 | 2/26 | 2/27 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-D1 | Pre-Close (Day 1 Readiness) | Finance Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | CFO / Finance Workstream Lead | High | T-3 | 2/27 | 2/27 | Complete | Day 1 Finance Readiness Confirmed
☑ | FIN-071 | Day 1 / Week 1 | Distribute Day 1 finance communications to all staff in both companies | VP FP&A / Integration Manager | Medium | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 Finance Integration Complete
☑ | FIN-074 | Day 1 / Week 1 | Confirm financial controls framework applies to acquired entity immediately | VP Finance / Controller | High | Day 1 (Close) | 3/2 | 3/3 | Complete | Compliance Program Integrated
☑ | FIN-072 | Day 1 / Week 1 | Confirm accounts payable payment run is executed on schedule and no vendor payments are disrupted by the system cutover | VP Finance / Controller | Medium | Day 1 (Close) | 3/2 | 3/6 | Complete | Day 1 Finance Integration Complete
☑ | FIN-073 | Day 1 / Week 1 | Brief the acquired finance team on acquirer's reporting tools, systems, templates, operating procedures, expense reporting cutoffs, and T&E policy | VP Finance / Controller | Low | Day 1 (Close) | 3/2 | 3/6 | Complete | Day 1 Finance Integration Complete
☑ | FIN-075 | Day 1 / Week 1 | Review and align travel and entertainment policies across both organizations | VP Finance / Controller | Low | Day 1 (Close) | 3/2 | 3/6 | Complete | Compliance Program Integrated
☑ | FIN-076 | Day 1 / Week 1 | Submit required tax notifications to relevant authorities post-close | VP Finance / Controller | Medium | Day 1 (Close) | 3/2 | 3/6 | Complete | Tax Filing Obligations Complete
☑ | FIN-077 | Day 1 / Week 1 | Confirm billing and invoicing continuity — no disruption to cash collection | VP Finance / Controller | High | Day 1 (Close) | 3/2 | 3/6 | Complete | Treasury Integration Complete
☑ | FIN-079 | Day 1 / Week 1 | Align financial code of conduct and conflicts of interest policies | VP Finance / Controller | Medium | Day 1 (Close) | 3/2 | 3/31 | Complete | Compliance Program Integrated
☐ | FIN-078 | Day 1 / Week 1 | Finalize treasury centralization — all cash pooling, FX management, and banking unified | VP Finance / Controller | High | Day 1 (Close) | 3/2 | 4/2 | On Track | Treasury Integration Complete
☑ | FIN-081 | Day 1 / Week 1 | Confirm FP&A budget process and timeline for combined entity | VP FP&A / Integration Manager | Low | T+1 | 3/3 | 3/6 | Complete | Management Reporting Live
☑ | FIN-080 | Day 1 / Week 1 | Confirm insurance policies are updated to reflect combined entity | VP FP&A / Integration Manager | Medium | T+1 | 3/3 | 3/9 | Complete | Compliance Program Integrated

## Milestones
FINANCE M&A MILESTONES
TODAY'S DATE: T+30
Status | Links
Not Started | Integration Plan
Delayed | Day 1 Checklist
On Track | RAID Log
Complete | Next 14 Days
Executive Dashboard
Milestone ID | Category | Phase | Assigned To | Milestone | Timing Anchor | Finish | Status | Critical Path
MS-001 | Governance & Planning | Pre-Close | CFO / Finance Workstream Lead | Finance Lead Appointed | T-51 | 1/10 | Complete | CP – Close
MS-002 | Governance & Planning | Pre-Close | VP Finance / Controller | Finance Integration Governance Established | T-42 | 1/19 | Complete
MS-003 | Governance & Planning | Pre-Close | VP Finance / Controller | Finance Charter Approved | T-42 | 1/19 | Complete
MS-004 | Due Diligence | Pre-Close | VP FP&A / Integration Manager | Finance Due Diligence Complete | T-3 | 2/27 | Complete
MS-005 | Compliance & Regulatory | Pre-Close (Day 1 Readiness) | VP Finance / Controller | Day 1 Finance Readiness Confirmed | T-3 | 2/27 | Complete | CP – Day 1 Readiness
MS-006 | Synergy Tracking & Realization | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Synergy Tracking Active | T-3 | 2/27 | Complete
MS-007 | Communications | Pre-Close (Day 1 Readiness) | VP FP&A / Integration Manager | Employee Comms Guide Approved | T-3 | 2/27 | Complete | CP – Day 1 Readiness
MS-008 | Integration Management | Day 1 / Week 1 | VP FP&A / Integration Manager | Day 1 Finance Integration Complete | T+4 | 3/6 | Complete
MS-009 | Accounting & Financial Reporting | To Day 100 | VP FP&A / Integration Manager | Accounting Policy Alignment Complete | T+29 | 3/31 | Complete | CP – Day 100
MS-010 | Compensation & Benefits | To Day 100 | VP Finance / Controller | Payroll Live for All Employees | T+29 | 3/31 | Complete
MS-011 | Integration Management | To Day 100 | VP FP&A / Integration Manager | Finance Integration Plan Locked | T+29 | 3/31 | Complete |  | CP – Day 100
MS-012 | Accounting & Financial Reporting | To Day 100 | VP FP&A / Integration Manager | Management Reporting Live | T+30 | 4/1 | Complete |  | CP – Day 100
MS-013 | Integration Management | To Day 100 | VP FP&A / Integration Manager | 30-Day Finance Review Complete | T+32 | 4/3 | On Track |  | CP – Day 100
MS-014 | Accounting & Financial Reporting | To Day 100 | VP FP&A / Integration Manager | Opening Balance Sheet Finalized | T+53 | 4/24 | Not Started
MS-015 | Compliance & Regulatory | To Day 100 | VP Finance / Controller | Compliance Program Integrated | T+61 | 5/2 | Not Started | CP – Day 100
MS-016 | Treasury & Cash Management | To Day 100 | VP Finance / Controller | Treasury Integration Complete | T+61 | 5/2 | Not Started
MS-017 | Accounting & Financial Reporting | To Day 100 | VP Finance / Controller | First Combined 10-Q Filed | T+71 | 5/12 | Not Started
MS-018 | Accounting & Financial Reporting | To Day 100 | CFO / Finance Workstream Lead | PPA Valuation Finalized | T+74 | 5/15 | Not Started
MS-019 | Integration Management | To Day 100 | VP Finance / Controller | Org Design Complete | T+90 | 5/31 | Not Started | CP – Day 100
MS-020 | Systems & Technology | To Day 100 | VP Finance / Controller | Systems Integration Complete | T+90 | 5/31 | Not Started
MS-021 | Systems & Technology | To Day 100 | VP Finance / Controller | ERP Consolidation Complete | T+90 | 5/31 | Not Started
MS-022 | Accounting & Financial Reporting | To Day 100 | VP Finance / Controller | FP&A Process Unified | T+90 | 5/31 | Not Started
MS-023 | Compliance & Regulatory | To Day 100 | VP Finance / Controller | Tax Filing Obligations Complete | T+100 | 6/10 | Not Started
MS-024 | Synergy Tracking & Realization | To Day 100 | VP Finance / Controller | Synergy Realization (Phase 1) Report Done | T+100 | 6/10 | Not Started
MS-025 | Integration Management | To Day 100 | VP FP&A / Integration Manager | Day 100 Finance Integration Complete | T+100 | 6/10 | Not Started | CP – Day 100

## RAID Log
FINANCE M&A RAID LOG (RAID = Risks, Assumptions, Issues, Dependencies)
TODAY'S DATE: T+30
RAID Type | Status | Links
Risk | Open | Integration Plan
Issue | Closed | Day 1 Checklist
Dependency | Active | Milestones
Assumption | Validated | Next 14 Days
Executive Dashboard
RAID Type | RAID ID | Related Task ID | Milestone | Owner | Task Description | Issues/Blockers | Status | Mitigation/Action | Timing Anchor | Finish
Assumption | RAID-001 | FIN-001 | Finance Lead Appointed | CFO | The Finance workstream lead and core integration team members will remain available and engaged throughout the full 100-day integration window — it is assumed that key Finance personnel in both entities have been identified, are willing to participate, and will not depart before or immediately after close | If the Finance workstream lead or critical Finance staff depart at or near close, the combined entity loses institutional knowledge of legacy accounting policies, system configurations, vendor relationships, and financial processes that cannot be fully captured in documentation; every downstream integration task from charter development through the final 10-K preparation depends on stable Finance team leadership | Active | CFO to confirm availability and commitment of Finance workstream lead and top 5 critical Finance personnel before close; initiate retention discussions for any at-risk team members identified during due diligence | T-51 | 1/10
Risk | RAID-002 | FIN-001 | Finance Lead Appointed | CFO / Finance Workstream Lead | Identify Finance integration workstream lead and determine members of the Finance integration team | Finance workstream lead must be identified and available before integration kickoff; if the role is filled internally from a team with significant BAU responsibilities, capacity conflict is the most common cause of delayed Finance integration milestones | Closed | Name the Finance workstream lead before integration kickoff and confirm capacity allocation; if filled internally, secure backfill for BAU responsibilities to prevent capacity conflict from becoming the primary integration bottleneck | T-51 | 1/10
Risk | RAID-003 | FIN-002 | Finance Integration Governance Established | VP Finance / Controller | Review data privacy and confidentiality protocols for pre-close sharing | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | Closed | Conduct a formal clean room briefing for all Finance team members before any data sharing begins; Legal to issue written protocols specifying what data can be reviewed, by whom, and under what conditions; document all pre-close data access | T-49 | 1/12
Dependency | RAID-004 | FIN-010 | Finance Due Diligence Complete | VP Finance / Controller | Identify any material weaknesses or significant deficiencies noted by auditors | Material weaknesses identified by target's prior auditors must be disclosed in the acquirer's next SEC filing if not remediated; escalate immediately to CFO and General Counsel — requires board audit committee awareness | Closed | Obtain the target's audit reports including any management letters before close; if a material weakness exists, assess scope with the combined entity's external auditor and develop a remediation roadmap before first combined 10-Q filing | T-40 | 1/21
Risk | RAID-005 | FIN-016 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Identify any unusual cash movements or related-party transactions | Unusual cash movements or related-party loans at non-arm's-length rates require restatement before any closing price adjustment; if undisclosed, they trigger SPA indemnity claims | Closed | Require target management to provide a written representation that all related-party transactions are fully disclosed and at arm's-length; escalate any exceptions to CFO and Legal before SPA signing; add to rep and warranty scope | T-39 | 1/22
Risk | RAID-006 | FIN-025 | Finance Due Diligence Complete | VP Finance / Controller | Identify any net operating loss carryforwards and confirm availability post-close | Section 382 annual limitation on NOL utilization is calculated based on the stock value at close and the long-term tax-exempt rate; limitations can reduce the value of carried losses by 80–90% | Closed | Engage external tax counsel to model Section 382 annual NOL limitation immediately; calculate the limitation based on stock value at close; quantify the NPV impact of restricted NOL utilization and incorporate into the deal model | T-34 | 1/27
Risk | RAID-007 | FIN-026 | Finance Due Diligence Complete | VP Finance / Controller | Review deferred tax assets and liabilities and confirm recoverability | Deferred tax assets tied to losses may be significantly impaired by the ownership change under IRC Section 382; engage tax counsel to model the annual limitation before signing — overvalued DTAs are a common purchase price dispute | Closed | Engage external tax counsel to assess DTA recoverability under the post-close ownership structure; model the valuation allowance impact on the opening balance sheet; confirm treatment with external auditor before preliminary PPA is released | T-30 | 1/31
Risk | RAID-008 | FIN-028 | Finance Due Diligence Complete | VP Finance / Controller | Analyze revenue trends, gross margin, and EBITDA over the last 5 years | Margin compression is a common diligence surprise in acquisitions — revenue may be growing while gross margin is quietly declining due to product mix shift, pricing concessions, or rising COGS; a margin trend that is not identified before close will surface in the first combined earnings report and cannot be explained away as an integration artifact | Closed | Require target management to provide gross margin by product line and customer segment; engage QoE advisor to validate margin trajectory; model the combined entity P&L using adjusted gross margin and flag any trends requiring price or cost action | T-30 | 1/31
Risk | RAID-009 | FIN-033 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Obtain and review financial statements for the last 3–5 years | Target company may resist providing full audited financials outside of a formal data room — confirm access protocol with Legal before requesting; if target is private, audited statements may not exist and compilation financials require additional QoE procedures | Closed | Require full audited financials for the prior 3 fiscal years as a closing condition in the SPA; if target resists, escalate to deal counsel; do not proceed to close without audited statements — unaudited financials create material restatement risk | T-30 | 1/31
Assumption | RAID-010 | FIN-056 | Opening Balance Sheet Finalized | VP Finance / Controller | The acquired company's financial statements are accurate, complete, and free of material misstatements — it is assumed that the quality of earnings assessment and pre-close due diligence have identified all material adjustments, and that no significant undisclosed liabilities, revenue recognition issues, or accounting policy differences will surface post-close that require material restatement | If material undisclosed accounting issues are discovered post-close, the purchase price allocation, opening balance sheet, and first combined financial statements will require revision; this creates regulatory exposure (SEC restatement), auditor relationship risk, and potential representations and warranties insurance claims; it also delays the first combined 10-Q and disrupts the integration timeline for all Finance workstream tasks that depend on clean financial data | Active | VP Finance / Controller to complete a rapid financial statement validation in the first 14 days post-close; any material differences between due diligence findings and actual financial position to be escalated to the CFO and General Counsel immediately; engage auditors to assess materiality of any differences within 5 business days of discovery | T+29 | 3/31
Risk | RAID-011 | FIN-035 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Document accounting policy differences across both entities — revenue recognition, inventory valuation, depreciation, lease accounting, goodwill impairment, and other material accounting methodology differences | Undocumented or unreconciled accounting policy differences (revenue recognition, depreciation, leases, goodwill) create restatement risk when the first combined financial statements are prepared; differences that are not documented before Day 1 are discovered during close and delay the first combined reporting cycle | Closed | Complete an accounting policy comparison across all material policies before close; document differences in a policy gap register; CFO to approve resolution approach for each gap; brief external auditor on combined entity accounting policies before Day 1 | T-27 | 2/3
Risk | RAID-012 | FIN-037 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Review all off-balance-sheet items, commitments, and contingencies | Confirm with target's auditor that all off-balance-sheet items are disclosed. | Closed | Require target management to provide a complete schedule of off-balance-sheet commitments with quantified financial exposure; confirm scope with external auditor; add unquantified contingencies to the rep and warranty insurance scope | T-24 | 2/6
Risk | RAID-013 | FIN-038 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Review all letters of credit, guarantees, and contingent financial obligations | Missing required consent from lenders can create high legal exposure | Closed | Obtain written confirmation from each lender that consent is not required or has been obtained before close; where consent is required, initiate outreach at least 60 days before close; do not proceed to close with unresolved lender consent requirements | T-24 | 2/6
Risk | RAID-014 | FIN-039 | Finance Due Diligence Complete | VP Finance / Controller | Confirm all debt obligations and covenants | Change-of-control provisions in debt agreements can trigger automatic acceleration or require lender consent to waive; Legal and Finance must confirm covenant compliance before signing — failure to obtain waivers can block close | Closed | Map all debt instruments to their change-of-control provisions immediately; engage deal counsel to assess acceleration risk; initiate lender consent process at least 60 days before close; confirm covenant compliance calculations for the combined entity | T-24 | 2/6
Risk | RAID-015 | FIN-040 | Finance Due Diligence Complete | VP Finance / Controller | Identify any change-of-control clauses that may be triggered by the transaction | Key customer contracts, software licenses, and government agreements often contain change-of-control clauses requiring notice or consent within 30–60 days of close; failure to notify counterparties in time can trigger termination rights | Closed | Complete a full contract-by-contract review of change-of-control clauses in all material customer, supplier, and license agreements; assign Legal to lead consent outreach for any agreement requiring counterparty approval before close | T-24 | 2/6
Risk | RAID-016 | FIN-042 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Identify all pending or threatened litigation and quantify potential financial exposure | Undisclosed or under reserved litigation is a top source of post-close disputes; require a complete litigation schedule from target's General Counsel and compare against reserves on the balance sheet — material gaps require SPA indemnity coverage | Closed | Require a complete litigation schedule from target management and outside counsel as a closing condition; quantify financial exposure for each matter; confirm reserve adequacy with external auditor; add undisclosed litigation to rep and warranty insurance scope | T-24 | 2/6
Risk | RAID-017 | FIN-043 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Identify any open tax audits, disputes, or outstanding tax liabilities | Open IRS or state tax audits may be closing conditions under the SPA; if audits are in progress, confirm whether escrow or indemnity is required — unresolved audits in excess of threshold amounts can delay or prevent close | Closed | Confirm the status of all open tax audits with target's tax counsel before close; negotiate SPA indemnity provisions that protect acquirer from pre-close tax liabilities; confirm that all open audit periods are included in the indemnity schedule | T-24 | 2/6
Risk | RAID-018 | FIN-044 | Finance Due Diligence Complete | VP Finance / Controller | Review federal, state, and local tax returns for the last 3–5 years | IRS and state tax penalties for late or incorrect filings can be substantial and are assessed against the combined entity from the date of the filing error regardless of which predecessor entity created the problem; unidentified tax exposures in the target's returns become the combined entity's liability at close | Closed | Obtain and review federal, state, and local tax returns for the last 5 years; flag any positions that appear aggressive or inconsistent with current law; engage external tax counsel to assess exposure; confirm all returns were timely filed and no extensions are open | T-17 | 2/13
Risk | RAID-019 | FIN-045 | Finance Due Diligence Complete | VP Finance / Controller | Review internal controls framework and assess adequacy for combined entity | If target's external auditors have issued a material weakness opinion, remediation must be underway before the first combined audit period; remediation timelines of 6–12 months are common — factor into integration planning | Closed | Obtain copy of internal controls assessment and any auditor communications regarding deficiencies; develop a remediation plan with Controller and external auditor; implement compensating controls on Day 1 where material weaknesses cannot be remediated before close | T-17 | 2/13
Dependency | RAID-020 | FIN-055 | Day 1 Finance Readiness Confirmed | VP Finance / Controller | Confirm payroll provider, processing schedule, and payroll continuity plan for all employees | Payroll provider requires 30+ days to onboard a new client entity; if bank account changes are also required, ACH authorization lead times add further delay — initiate no later than 45 days before first payroll run | Closed | Initiate payroll provider onboarding immediately — minimum 30-day lead time required; confirm bank account setup, tax ID registrations, and payroll funding mechanisms before the first pay cycle; run a parallel payroll cycle at least two weeks before cutover | T-15 | 2/15
Risk | RAID-021 | FIN-052 | Finance Due Diligence Complete | VP Finance / Controller | Assess tax structure of the deal and confirm optimal post-close entity structure | Post-close entity structure (stock vs. asset treatment, check-the-box elections) must be decided before signing because some elections are irrevocable; tax counsel and M&A counsel must align before the SPA is executed | Closed | Engage external tax counsel to determine optimal post-close entity structure before close; confirm check-the-box elections and IRC 338 decisions with tax counsel; document elections in board resolutions and file within required IRS deadlines | T-10 | 2/20
Risk | RAID-022 | FIN-017 | Finance Due Diligence Complete | VP Finance / Controller | Assess quality of earnings — confirm reported EBITDA reflects true operating performance | Seller may resist reclassifying addbacks that inflate EBITDA; engage QoE advisor early — disputes over addbacks directly affect purchase price and often require SPA representations to resolve | Closed | Engage a quality of earnings advisor early in the process; require target management to formally respond to all addback reclassifications in writing; model both adjusted and unadjusted EBITDA scenarios for purchase price sensitivity analysis | T-8 | 2/22
Risk | RAID-023 | FIN-018 | Finance Due Diligence Complete | VP FP&A / Integration Manager | Review and validate purchase price and deal economics vs. original investment thesis | If due diligence findings produce EBITDA adjustments exceeding agreed thresholds, purchase price renegotiation or additional SPA representations may be required; Finance must present findings to CFO before final price is locked | Closed | Model purchase price impact of any EBITDA adjustments exceeding 10% of deal thesis; escalate material findings to CFO and deal counsel immediately; confirm SPA price adjustment mechanism can accommodate material changes before close | T-8 | 2/22
Risk | RAID-024 | FIN-060 | Day 1 Finance Readiness Confirmed | CFO / Finance Workstream Lead | Assess acquisition financing structure and ensure closing funds are committed and available | Acquisition financing must be fully committed at least 5 business days before closing; any lender condition not satisfied by closing date risks deal termination — Finance must manage lender relationships actively through signing to close | Closed | Confirm financing commitments with lenders at least 10 business days before close; obtain executed commitment letters; confirm closing funds availability and wire instructions with treasury; have a contingency financing plan approved by CFO if primary funding falls through | T-8 | 2/22
Risk | RAID-025 | FIN-050 | Compliance Program Integrated | VP Finance / Controller | Identify change of control triggers in key contracts and tax agreements | Change-of-control trigger identification must be completed before Day 1 — some contract clauses require counterparty notice within 5–10 business days of close; missed notice windows can result in automatic contract termination or loss of tax agreements | Closed | Complete the change-of-control contract review before close; for any contract requiring counterparty consent, send written consent requests at least 30 days before close; track responses weekly and escalate unresolved consents to CFO and deal counsel | T-7 | 2/23
Risk | RAID-026 | FIN-059 | Day 1 Finance Readiness Confirmed | VP FP&A / Integration Manager | Prepare investor FAQ and analyst briefing materials covering synergies, integration costs, and timeline | Investor FAQ figures must be cross-checked against the deal model, public filings, and earnings guidance; any discrepancy between the FAQ and other investor-facing materials creates legal risk — General Counsel must approve final version | Closed | Complete investor FAQ and analyst briefing materials at least 5 business days before close; route through IR, Legal, and CFO for approval; cross-check all synergy figures against the deal model and confirm consistency with any public guidance already issued | T-5 | 2/25
Risk | RAID-027 | FIN-065 | Day 1 Finance Readiness Confirmed | VP Finance / Controller | Confirm earnout and contingent consideration payment tracking mechanisms | Earnout measurement periods begin on Day 1 under most SPAs; failure to establish tracking mechanisms on Day 1 creates disputes about the measurement baseline — Finance must confirm the earnout definition, metrics, and reporting protocol with Legal before close | Closed | Establish earnout tracking mechanisms in the GL and management reporting before close; assign the Controller as primary owner of earnout compliance; confirm measurement methodology with Legal and target management before Day 1 | T-5 | 2/25
Risk | RAID-028 | FIN-019 | Finance Due Diligence Complete | VP Finance / Controller | Review and validate net working capital peg and adjustment mechanism | NWC peg is typically negotiated as a trailing 12-month average but sellers often propose a higher peg using peak periods; if the definition is disputed at close, the SPA mechanism governs | Closed | Engage legal counsel to review NWC peg methodology and SPA adjustment mechanism before close; model high, base, and low NWC scenarios; assign Controller to lead true-up calculation with a target completion of Day 60 post-close | T-3 | 2/27
Risk | RAID-029 | FIN-053 | Finance Due Diligence Complete | VP Finance / Controller | Assess financial systems landscape — platforms, versions, and integration complexity | System incompatibility is the top financial integration risk; assess data migration complexity before Day 1 | Closed | Complete a full financial systems inventory documenting all platforms, versions, and integration touchpoints before close; prioritize systems on the Day 1 critical path; assign IT workstream lead to own the systems integration plan with Finance | T-3 | 2/27
Risk | RAID-030 | FIN-061 | Org Design Complete | VP Finance / Controller | Establish interim finance org chart and confirm reporting lines for combined team | Finance staff at the acquired company who do not know their reporting line on Day 1 will seek informal answers from their legacy manager — and the informal hierarchy that forms in the first week is significantly harder to undo than the formal one; a Finance team operating without clear authority lines on Day 1 will also make payment authorization and approval decisions in an ad hoc way, creating audit exposure from the first day of combined operations | Closed | Issue the interim org chart to all Finance managers on Day 1 before 9am local time; conduct a brief all-Finance team call on Day 1 to confirm reporting lines; assign an HR business partner to handle any employee concerns about the new structure in Week 1 | T-3 | 2/27
Risk | RAID-031 | FIN-062 | Day 1 Finance Readiness Confirmed | VP FP&A / Integration Manager | Build a pro forma combined P&L and balance sheet for Day 1 management review | If delayed, management will be operating without combined financial visibility on Day 1 | Closed | Complete the combined pro forma P&L and balance sheet with VP FP&A no later than 48 hours before Day 1; have CFO review and approve before distribution; distribute to all Finance managers and the executive team on Day 1 morning | T-3 | 2/27
Risk | RAID-032 | FIN-067 | Day 1 Finance Readiness Confirmed | VP FP&A / Integration Manager | Confirm purchasing and spend approval controls will be active on Day 1 | Acquirer's spend approval system (ERP or procurement tool) must be configured with target-entity cost centers and approval hierarchies before Day 1; IT must confirm provisioning no later than T-3 days | Closed | Configure the combined entity's spend approval workflow in the ERP before Day 1; test approval routing for all cost centers that will be active on Day 1; communicate the new approval thresholds and workflow to all Finance managers before close | T-3 | 2/27
Risk | RAID-033 | FIN-068 | Day 1 Finance Readiness Confirmed | VP Finance / Controller | Confirm revenue recognition and billing processes will be operational on Day 1 | Revenue collection cannot be interrupted on Day 1; billing system cutover must be tested in full before close — any failure to invoice on Day 1 creates immediate cash flow impact and customer escalation risk | Closed | Test billing and invoicing system end-to-end before Day 1 cutover; validate the customer master data migration with the Controller; confirm AR collection continuity with the combined entity's bank; have a manual invoicing backup process ready if the system fails on Day 1 | T-3 | 2/27
Dependency | RAID-034 | FIN-070 | Day 1 Finance Readiness Confirmed | VP Finance / Controller | Validate combined entity bank account signatories and confirm wire transfer authorities will be active on Day 1 | Wire transfer authority must be active before the combined entity can fund payroll, make vendor payments, or execute any treasury transaction on Day 1; failure to confirm with the bank before close means the combined entity cannot make financial commitments on Day 1, creating immediate operational paralysis | Closed | Hold the Day 1 Readiness review with all Finance workstream leads at least 48 hours before close; any item not green requires CFO decision to proceed or delay; document the readiness decision with a signed sign-off record | T-3 | 2/27
Risk | RAID-035 | FIN-D1 | Day 1 Finance Readiness Confirmed | CFO / Finance Workstream Lead | Finance Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | Closed | Hold the Day 1 Readiness Gate review with CFO and all Finance leads 48 hours before close; any critical gap identified at this gate requires an immediate escalation decision — proceed with compensating control, delay specific activity, or pause close | T-3 | 2/27
Issue | RAID-036 | FIN-077 | Treasury Integration Complete | VP Finance / Controller | Billing and invoicing continuity disrupted on Day 1 — the acquired company's billing system did not successfully connect to the acquirer's accounts receivable platform at open of business on close day; approximately 40 open invoices totaling an estimated $200K cannot be confirmed as transmitted, and three enterprise customers have reported receiving duplicate invoice notifications | A major invoicing gap on Day 1 directly impacts cash flow timing for the combined entity and creates customer-facing confusion that undermines confidence in the integration at the most visible moment; duplicate invoice notifications to enterprise customers risk triggering payment disputes, damaging relationships that the Sales team is simultaneously trying to protect; if the billing system connectivity issue is not resolved within 24 hours, the accounts receivable aging will show incorrect balances and the first combined financial close will require manual reconciliation adjustments | Closed | Treasurer to immediately convene a war room with Finance IT and the billing platform vendor to diagnose and resolve the connectivity failure; all affected customers to be contacted by the Finance team within 2 hours of issue identification to confirm invoice status and prevent duplicate payments; manual billing confirmation to be completed for all 40 open invoices by end of Day 1; Treasurer to provide status update to CFO every hour until resolved | T+4 | 3/6
Risk | RAID-037 | FIN-074 | Compliance Program Integrated | VP Finance / Controller | Confirm financial controls framework applies to acquired entity immediately | If target's internal controls are materially weaker than acquirer's, a compensating control framework must be in place on Day 1; absence of controls over target entity in the first reporting period creates SOX exposure | Closed | Implement the acquirer's financial controls framework for the acquired entity on Day 1; brief acquired Finance staff on key controls in Week 1; assign the Controller to complete a gap assessment within 30 days and report findings to CFO | T+1 | 3/3
Risk | RAID-038 | FIN-077 | Treasury Integration Complete | VP Finance / Controller | Confirm billing and invoicing continuity — no disruption to cash collection | Any disruption to customer billing on Day 1 creates immediate AR aging risk; billing system cutover must be tested end-to-end — no cutover without confirmed parallel-run success | Closed | Complete billing system cutover testing before Day 1; validate customer master data, pricing tables, and invoice templates in the new system; confirm AR lockbox and payment routing with treasury; monitor first 5 days of invoicing closely for errors | T+4 | 3/6
Assumption | RAID-039 | FIN-083 | Systems Integration Complete | VP Finance / Controller | The acquired company's financial systems are stable, adequately documented, and capable of producing clean data outputs for integration — it is assumed that the financial systems landscape assessment has identified all critical systems, integration points, and data quality issues, and that no material hidden technical debt or unsupported legacy systems will be discovered post-close that materially expand the ERP consolidation scope | If significant undisclosed technical debt, unsupported financial systems, or poor data quality is discovered post-close, the ERP consolidation scope expands materially and the first combined financial close may be delayed; the combined entity may be unable to produce reliable consolidated financial statements on schedule, creating SEC reporting risk and audit complications | Validated | VP Finance / Controller to conduct a rapid financial systems validation in the first 10 days post-close; any gap between the assessed systems landscape and actual state to be logged immediately and escalated to the CFO if it has budget or timeline implications; Finance IT team to assess impact on ERP consolidation timeline and adjust FIN-111 scope accordingly | T+29 | 3/31
Risk | RAID-040 | FIN-099 | Management Reporting Live | VP Finance / Controller | Confirm month-end close calendar and assign ownership for first combined close. The first combined close will take longer than subsequent closes. | First combined close calendar cannot be finalized until system cutover date is determined | Closed | Confirm the first combined close calendar with all Finance managers in Week 1; assign a close coordinator to track task completion; conduct a close readiness review at T-minus 5 days before first combined close; identify manual processes that will require additional time in the first cycle | T+26 | 3/28
Dependency | RAID-041 | FIN-056 | Opening Balance Sheet Finalized | VP FP&A / Integration Manager | Complete purchase accounting entries and preliminary opening balance sheet | Preliminary opening balance sheet requires third-party fair value appraisals for intangibles and fixed assets; appraisal firm must be engaged at least 30 days before close or Day 1 OBS will be estimated only | Closed | Engage valuation firm for intangible asset appraisals immediately — timeline is typically 60-90 days; confirm external auditor concurrence on valuation methodology before finalizing; preliminary opening balance sheet must be complete before first combined 10-Q | T+29 | 3/31
Risk | RAID-042 | FIN-082 | Accounting Policy Alignment Complete | VP Finance / Controller | Align accounting policies across acquirer and target | Exceptions require CFO approval and external auditor concurrence | Closed | Require target management sign-off on all accounting policy alignment decisions; obtain external auditor concurrence on any exceptions to acquirer policies; document policy decisions in writing before the first combined month-end close | T+29 | 3/31
Risk | RAID-043 | FIN-083 | Systems Integration Complete | VP Finance / Controller | Define combined entity financial system architecture and ERP consolidation approach — assess both legacy systems and select the platform of record | ERP architecture decision (migrate target into acquirer's system vs. maintain separate instance) must be made within 30 days of close; delayed decision blocks all downstream systems integration tasks and extends integration timeline | Closed | Complete the ERP architecture decision before Day 30; engage a systems integrator if a full migration is selected; begin data mapping and migration planning immediately; add ERP go-live to the integration critical path with weekly status reporting to CFO | T+29 | 3/31
Risk | RAID-044 | FIN-085 | Payroll Live for All Employees | VP Finance / Controller | Migrate acquired company payroll onto acquirer's payroll system or confirm bridge arrangement | Payroll system migration must be tested with a parallel payroll run before cutover; any error in employee data, tax withholding, or bank routing information will result in missed or incorrect pay — employee trust is irreparably damaged by payroll failures | Closed | Run a full parallel payroll cycle for at least two pay periods before cutover; validate every employee record individually; confirm payroll funding with treasury 5 business days before the first pay date; maintain a manual payroll backup process through the first 3 pay cycles | T+29 | 3/31
Dependency | RAID-045 | FIN-078 | Treasury Integration Complete | VP Finance / Controller | Finalize treasury centralization — all cash pooling, FX management, and banking unified | Treasury centralization requires bank account consolidation, updated authorized signatories, and cash pool enrollment — each requiring bank processing time of 10–15 business days | Open | Initiate bank account consolidation at least 60 days before close; confirm authorized signatories with legal counsel; test cash pooling sweep before Day 1; assign treasury to monitor combined entity cash daily for the first 30 days post-close | T+31 | 4/2
Risk | RAID-046 | FIN-D30 | 30-Day Finance Review Complete | VP FP&A / Integration Manager | Finance Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | If the Day 30 check reveals open tasks, unresolved blockers, or synergy owners not yet active, the integration team has 70 days to correct course — but the Day 30 review must force honest status reporting; teams that report green when yellow or red create hidden risk that surfaces at Day 100 when it is too late to recover | Open | Hold the Day 30 integration review as a formal meeting with CFO, all Finance leads, and IMO; require each workstream lead to provide a written RAG status update; any item rated red requires an escalation decision at the meeting with named owner and resolution deadline | T+32 | 4/3
Issue | RAID-047 | FIN-D30 | 30-Day Finance Review Complete | VP FP&A / Integration Manager | Day 30 Finance Integration Review has surfaced a material accounts receivable reconciliation gap — the combined entity's AR aging shows a major discrepancy between the acquirer's system and the acquired company's legacy AR ledger; 18 customer accounts appear in both systems with conflicting balances, and 6 accounts that should have been migrated are not appearing in the consolidated AR report | A major AR discrepancy at Day 30 means the combined entity cannot produce a reliable consolidated balance sheet; the first combined 10-Q depends on accurate AR balances and this issue, if unresolved, will require an auditor qualification or a delayed filing; the 6 missing customer accounts represent active receivables that are not being tracked in the consolidated system, creating a real cash collection gap; the 18 conflicting accounts may result in double-billing or missed collections depending on which system's balance is treated as authoritative | Open | VP Finance / Controller to assign a dedicated reconciliation team to resolve all 24 affected accounts within 10 business days; Finance IT to investigate the root cause of the migration failure for the 6 missing accounts and confirm whether any other accounts were dropped in the migration; all affected accounts to be flagged in the AR aging report with a reconciliation status indicator; Treasurer to assess whether the major discrepancy affects the net working capital true-up calculation under the SPA; CFO to be briefed on the issue and its 10-Q implications within 48 hours; FIN-D30 will not be marked complete until the reconciliation gap is fully resolved and documented | T+32 | 4/3
Dependency | RAID-048 | FIN-110 | Opening Balance Sheet Finalized | VP FP&A / Integration Manager | Complete the first consolidated month-end close for the combined entity; The first combined close will take longer than subsequent closes. | First consolidated close requires mapped chart of accounts, completed purchase accounting entries, and a functioning consolidated reporting tool | Open | Begin close preparation 10 days before the first combined month-end; confirm chart of accounts mapping is complete; ensure purchase accounting entries are posted before close begins; schedule a close status call with Controller and external auditor 5 days before close deadline | T+53 | 4/24
Risk | RAID-049 | FIN-086 | Compliance Program Integrated | VP Finance / Controller | Prepare and file required SEC disclosures (proxy, registration statement, 8-K) | Combined entity registration statements and proxy materials require coordination between Finance, Legal, and IR; any accounting restatements or unresolved audit matters will delay filing and may trigger SEC comment letters | Open | Assign a single owner for each SEC filing with a defined completion deadline; establish a filing calendar with Legal and IR covering all required disclosures through Day 100; confirm 8-K filing within 4 business days of close; all drafts require Legal and CFO sign-off before filing | T+59 | 4/30
Risk | RAID-050 | FIN-122 | FP&A Process Unified | VP FP&A / Integration Manager | Prepare integration progress update for quarterly earnings call — synergy delivery and integration KPIs | Public synergy guidance must reconcile to the internal synergy model; any disconnect between what is communicated to investors and what Finance is tracking internally creates securities law exposure — CFO and General Counsel must approve before release | Open | Align all public synergy guidance with the internal synergy model at least 2 weeks before the earnings call; have IR, CFO, and Legal review any synergy figures before they are disclosed publicly; document the bridge between internal model and public guidance | T+60 | 5/1
Risk | RAID-051 | FIN-097 | Treasury Integration Complete | VP Finance / Controller | Execute net working capital true-up calculation per SPA and initiate settlement process | NWC true-up is a contractual obligation with a defined submission window (typically 60–90 days post-close per the SPA); if Finance misses the submission deadline, the right to claim a purchase price adjustment may be forfeited | Open | Calculate the NWC true-up no later than Day 60 per SPA requirements; assign Controller as primary owner; have Legal review the calculation methodology against SPA language before submission; be prepared for dispute resolution process if target disputes the calculation | T+61 | 5/2
Risk |  | FIN-106 | Compliance Program Integrated | VP FP&A / Integration Manager | Complete SOX initial scoping compliance assessment | SOX scoping must be completed within 60 days of close to meet the first-year accelerated filer deadline; if target had no prior SOX program, remediation timeline may extend 12–18 months and require external SOX advisory support | Open | Engage a SOX advisor to complete initial scoping within 30 days of close; prioritize controls covering revenue, payroll, and financial reporting; establish a remediation plan for any control gaps; brief external auditor on the combined entity's SOX approach before first quarterly review | T+61 | 5/2
Dependency |  | FIN-069 | PPA Valuation Finalized | CFO / Finance Workstream Lead | Finalize purchase price allocation (PPA) valuation and audit sign-off purchase | Final PPA requires completed intangible asset valuation (customer relationships, technology, trade names) from a qualified third-party appraiser; delays in engaging the appraiser are the most common PPA bottleneck — engage no later than signing | Open | Engage valuation firm no later than Day 5 post-close; target preliminary PPA within 30 days of close and final PPA within 90 days; confirm external auditor sign-off timeline to ensure PPA is complete before Q1 10-Q filing | T+74 | 5/15
Risk |  | FIN-111 | ERP Consolidation Complete | VP Finance / Controller | Complete ERP consolidation and sunset legacy systems | Legacy system decommissioning cannot occur until all historical data is archived, audit trails are preserved, and all users are trained on the new system; premature decommissioning creates compliance and audit risk | Open | Complete all historical data archiving and audit trail documentation before decommissioning any legacy system; run parallel operations in both systems for at least one full close cycle; obtain Controller and external auditor sign-off before switching off the legacy ERP | T+90 | 5/31
Risk | RAID-050 | FIN-116 | Synergy Realization (Phase 1) Report Done | VP FP&A / Integration Manager | Assess stranded costs from synergy actions and develop mitigation plan | Stranded costs frequently offset 20–40% of gross cost synergies; failure to model and mitigate stranded costs will cause Finance to report synergy realization below guidance | Open | Model stranded costs for every planned synergy action before execution; require synergy owners to confirm net synergy after stranded cost offset; report net synergy realization to CFO monthly; flag any synergy where stranded cost exceeds 30% of gross savings for CFO review | T+90 | 5/31
Risk | RAID-051 | FIN-127 | Systems Integration Complete | VP FP&A / Integration Manager | Execute financial data migration testing and parallel run validation | Parallel run failures are the leading cause of ERP integration delays; if data migration testing reveals integrity issues, cutover must be postponed — ensure a rollback plan is documented before any production migration begins | Open | Complete data migration testing with at least two full parallel runs before the ERP cutover; document all reconciling items and obtain Controller sign-off before going live; maintain the legacy system in read-only mode for 90 days after cutover for audit reference | T+90 | 5/31
Risk | RAID-052 | FIN-130 | Day 100 Finance Integration Complete | VP FP&A / Integration Manager | Finalize combined entity budget for the remainder of the fiscal year | Combined budget cannot be finalized until synergy cost-to-achieve amounts are confirmed by each workstream lead; unresolved synergy assumptions result in a budget that does not reconcile to the deal model — CFO must resolve open items before Board submission | Open | Begin combined budget process no later than Day 30; require all workstream leads to submit confirmed cost-to-achieve estimates before the budget is finalized; CFO to approve the combined budget and present to the Board before the end of the integration period | T+90 | 5/31
Risk | RAID-053 | FIN-126 | Day 100 Finance Integration Complete | VP Finance / Controller | Begin preparing first combined annual report (10-K) with SEC — assign sections, confirm auditor scope, and set filing timeline | First combined 10-K is a high-visibility deliverable | Open | Assign section owners for the combined 10-K no later than Day 30; establish a filing calendar with Legal, Controller, and external auditor; conduct a pre-filing review with CFO and audit committee at least 2 weeks before the filing deadline | T+100 | 6/10
Risk | RAID-054 | FIN-128 | Synergy Realization (Phase 1) Report Done | VP FP&A / Integration Manager | Deliver final synergy realization report to Steering Committee and Board | Final synergy report is a board deliverable; if synergy realization is materially below guidance, the CFO and Finance workstream lead must present a recovery plan to the board audit committee before the report is distributed externally | Open | Begin synergy realization tracking against guidance in Month 1; provide the Steering Committee with monthly synergy status updates; if cumulative realization is tracking below guidance by Day 60, develop a recovery plan and present to the Board at Day 100 | T+100 | 6/10
Risk | RAID-055 | FIN-132 | Tax Filing Obligations Complete | VP FP&A / Integration Manager | Prepare and file all required federal, state, and local tax returns for the combined entity's first filing period post-close — confirm jurisdictions, deadlines, and preparer assignments | Missed tax filing deadlines trigger automatic penalties and interest from the first day of non-compliance; in a combined entity covering multiple jurisdictions, the deadline calendar for federal, state, and local filings must be centrally tracked — a missed filing in any jurisdiction creates an exposure that compounds daily | Open | Build a complete tax filing calendar covering all federal, state, and local deadlines for the first 12 months post-close; assign a named preparer for each filing; calendar all deadlines in the RAID log with 30-day and 7-day alerts; engage external tax counsel for all jurisdictions | T+100 | 6/10
Risk | RAID-056 | FIN-D100 | Day 100 Finance Integration Complete | CFO / Finance Workstream Lead | Day 100 Finance Integration Gate may not be achievable if synergy baselines remain unvalidated or open integration cost tracking codes in the GL are not closed before Day 100 — the formal BAU transition sign-off required to complete FIN-D100 depends on both being resolved, and slippage in either creates a risk that the gate cannot be executed on schedule | If synergy baselines are not locked at Day 100, the combined entity cannot report accurate synergy realization to the board or investors, and the synergy tracking model loses credibility; if integration cost tracking codes remain open, the P&L will continue to show integration-related charges that distort BAU operating performance — this affects management reporting, investor guidance, and the accuracy of the full-year financial statements; a delayed Day 100 gate also triggers the risk that integration-mode governance and reporting continue beyond the intended window, increasing integration fatigue and cost | Open | CFO / Finance Workstream Lead to begin a Day 100 readiness review at 7 days before the gate — to confirm all synergy initiatives are on track to produce validated baselines and all GL integration tracking codes have closure plans; any initiative at risk of missing the Day 100 gate to be escalated to the CFO immediately with a remediation plan; all integration cost tracking codes to be reviewed and either closed or formally transferred by T+95; FIN-D100 will not be marked complete until written CFO sign-off confirming all gate conditions are met | T+100 | 6/10

## Next 14 Days
FINANCE M&A NEXT 14 DAYS ACTIVITIES
TODAY'S DATE: T+30
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Day 1 Checklist
Low | On Track | Milestones
| Complete | RAID Log
Executive Dashboard
Task ID | Category | Phase | Assigned To | Description | Risk Level | Timing Anchor | Start | Finish | Status | Critical Path
FIN-110 | Accounting & Financial Reporting | To Day 100 | VP FP&A / Integration Manager | Complete the first consolidated month-end close for the combined entity; The first combined close will take longer than subsequent closes. | High | T+30 | 4/1 | 4/24 | On Track
FIN-111 | Systems & Technology | To Day 100 | VP Finance / Controller | Complete ERP consolidation and sunset legacy systems | High | T+30 | 4/1 | 5/31 | On Track
FIN-112 | Systems & Technology | To Day 100 | VP Finance / Controller | Eliminate all remaining duplicate finance processes, tools, and reporting streams | Medium | T+30 | 4/1 | 5/31 | On Track
FIN-113 | Accounting & Financial Reporting | To Day 100 | VP Finance / Controller | Track one-time restructuring charges and ensure proper P&L classification | Low | T+30 | 4/1 | 5/31 | On Track
FIN-114 | Treasury & Cash Management | To Day 100 | VP Finance / Controller | Review and renegotiate credit facilities and revolving credit lines | Medium | T+30 | 4/1 | 4/30 | On Track
FIN-D30 | Integration Management | To Day 100 | VP FP&A / Integration Manager | Finance Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | High | T+30 | 4/1 | 4/3 | On Track
FIN-115 | Systems & Technology | To Day 100 | VP FP&A / Integration Manager | Conduct final vendor contract review — confirm all consolidations and renegotiations complete | Low | T+31 | 4/2 | 5/31 | Not Started
FIN-116 | Synergy Tracking & Realization | To Day 100 | VP FP&A / Integration Manager | Assess stranded costs from synergy actions and develop mitigation plan | High | T+34 | 4/5 | 5/31 | Not Started
FIN-117 | Accounting & Financial Reporting | To Day 100 | VP Finance / Controller | Complete unified FP&A process — one budget, one forecast, one reporting cycle | Low | T+39 | 4/10 | 5/31 | Not Started
FIN-118 | Synergy Tracking & Realization | To Day 100 | VP FP&A / Integration Manager | Report updated post-close synergy realization plan with revised timing and cost-to-achieve estimates | Medium | T+39 | 4/10 | 4/16 | Not Started
FIN-119 | Accounting & Financial Reporting | To Day 100 | VP Finance / Controller | Prepare first combined Form 10-Q quarterly report | Medium | T+44 | 4/15 | 5/12 | Not Started
FIN-120 | Compliance & Regulatory | To Day 100 | VP Finance / Controller | Rationalize and integrate internal audit function | Medium | T+44 | 4/15 | 5/31 | Not Started
FIN-121 | Integration Management | To Day 100 | VP Finance / Controller | Complete finance team restructuring — all roles filled, redundancies resolved, structure final | Medium | T+44 | 4/15 | 5/31 | Not Started
FIN-122 | Governance & Planning | To Day 100 | VP FP&A / Integration Manager | Prepare integration progress update for quarterly earnings call — synergy delivery and integration KPIs | High | T+44 | 4/15 | 5/1 | Not Started

## Executive Dashboard
HR M&A MILESTONES REPORT | FINANCE M&A EXECUTIVE DASHBOARD
TODAY'S DATE: T+30 | TODAY'S DATE: T+30 (30 DAYS POST-CLOSE)
TASKS
|  |  | TOTAL TASKS |  | NOT STARTED |  | DELAYED |  | ON TRACK | COMPLETE
|  |  | 138 |  | 22 |  | 0 |  | 22 | 94
| MILESTONES |  |  | PROGRESS BY PHASE TASKS DONE/TASKS |  |  |  | RAID LOG |  | ANNUAL SYNERGIES
| Not Started | 12 |  | Pre-Close | 65/71 |  |  | Open Risks | 13 | Targeted Synergies | $600K
| Delayed | 0 |  | Days 1 / Week 1 | 10/11 |  |  | Open Items | 17 | Realized Synergies | $80K
| On Track | 1 |  | Days 8 -100 | 19/56 |  |  | Open Issues | 1 | Cost to Achieve Budget | $216K
| Complete | 12 | [5 empty] | Dependencies | 7 | Actual CTA | $65K
| CRITICAL PATH MILESTONES | [6 empty] | NEXT 14 DAYS |  | DAY 1 | TASKS DONE/TASKS
|  |  |  | Phase | Target Date | Status |  | Total | 14 | Day 1 Readiness | 15/15
| Finance Lead Appointed |  |  | Pre-Close | 1/10 | Complete |  | On Critical Path | 0 | Day 1 | 10/11
| Finance Integration Governance Established |  |  | Pre-Close | 1/19 | Complete
| Finance Charter Approved |  |  | Pre-Close | 1/19 | Complete |  | LINKS
| Finance Due Diligence Complete |  |  | Pre-Close | 2/27 | Complete |  | Integration Plan |  | Milestones | Next 14 Days
| Day 1 Finance Readiness Confirmed |  |  | Pre-Close (Day 1 Readiness) | 2/27 | Complete |  | Day 1 Checklist |  | RAID Log
| Synergy Tracking Active |  |  | Pre-Close (Day 1 Readiness) | 2/27 | Complete
| Accounting Policy Alignment Complete |  |  | To Day 100 | 3/31 | Complete
| Compliance Program Integrated |  |  | To Day 100 | 5/2 | Not Started
| Org Design Complete |  |  | To Day 100 | 5/31 | Not Started
| Day 100 Finance Integration Complete |  |  | To Day 100 | 6/10 | Not Started