## Slide 1
FOUNDATIONAL DECISIONS FOR
FINANCE PLAN

## Slide 2: AGENDA:
Interdependencies, Exit Criteria, and Key Measures
FINANCE
Scope
Milestones
Budget Process
Budget Process Differences
Update
© 100-Day Advisors MandAPlaybook.com

## Slide 3
Develop an efficient and sustainable financial reporting process for both stakeholders and management team for the combined company
Establish finance policies, procedures and clear delegation of authority for the combined company
Set the budget for consolidated company
Ensure compliance with external parties (Debt, Taxing Authorities, Jurisdictional Reporting)
Harmonized Finance Team Structure
Accounting: Establish Consolidated Reporting, Consolidation of Accounting Principles & Policies, Unified Month End/Quarterly/Annual Reporting, Purchase Accounting/Valuations
Treasury Management: Working Capital, Debt Management, Banking
Tax: Tax Strategy, Direct & Indirect Tax Compliance
FP & A: Annual Budget Process, Forecasting, Monthly Reporting KPI's
Internal Audit:
Billing & Collections: Information Gathering; Process
Supplier Management: Consolidation, Information Gathering; Process
Accounts Payable: Travel, Information Gathering; Process
FinTech: Customer Data
Out of Scope: Payroll (HR) and ERP Systems Integration
SCOPE
KEY OBJECTIVES
© 100-Day Advisors MandAPlaybook.com

## Slide 4: MILESTONES
FIRST 30
Complete External Financing
Combined Tax Structure Strategy
Evaluate Technology Landscape
Establish Performance Reporting (Actual, Budget, Forecasting)
Design Treasury Strategy
Perform Financial Consolidation Assessment & Tool Recommendation
Complete Global Chart of Accounts Mapping
Reconcile US GAAP to IFRS Accounting Principles
Consolidation of Accounting and Operational Policies
Establish a FY 2028 Audit Plan
Establish governance surrounding Billing/Collections
Consolidation of procurement policies & procedures
Assimilate Internal Audit Function
Establish Debt Compliance Reporting and Management
Determine vendor notification / communications requirements
YEAR-END 2028
PRE-CLOSE
Implement Agreed Upon Operational Governance Guidelines / "Approval Authority“
Execute Working Capital Management Policies
Finance Employee Communication Plan (Day 1 Introduction Plan)
DAY 1
Complete Management Reporting (Actuals vs Plan) including Pro Forma Reporting
Prepare Updated Budget 2028 & 2029
Facilitate Common Billing & Collection Governance Procedures
Execute Tax, Accounting & Treasury Acquisition Accounting
Implement Procurement Policies
Complete Treasury Strategies
Vendor notifications / communications
Harmonize 3- and 5-year financial plans
Aligned quarterly / year-end close process and reporting
Complete FY2028 Financial Audit(s)
Complete Tax Filings and Shareholder Distributions
Report Debt Compliance Packages
Finalize Tax strategies
BEYOND
Transition Supervisory Boards
Identify System & Process Synergies, including ERP Roadmap
© 100-Day Advisors MandAPlaybook.com

## Slide 5: INTERDEPENDENCIES, EXIT CRITERIA, AND KEY MEASURES
c
KEY MEASURES
TEAM
IMO EXIT CRITERIA
Complete Management Reporting (Actuals vs Plan) including Pro Forma Reporting
Prepare Updated Budget 2028 & 2029
Facilitate Common Billing & Collection Governance Procedures
Execute Tax, Accounting & Treasury Acquisition Accounting
Implement Procurement Policies
Complete Treasury Strategies
Vendor notifications / communications
Vendor notifications / communications
END STATES
KEY INTERDEPENDENCIES
Business Units
Steering Committee
Business Units
Information Technology
Human Resources
Sales & Marketing
Human Resources
Legal
Successful completion and external reporting requirements met
Completion accounts finalized and purchase price adjustment complete
Accounting policies aligned, controls assessment complete, remediation plan in place
Finance operations consolidation plan in place and being implemented
Treasury consolidation plan in place and being implemented
Budget set and communicated to all stakeholders
Regular monthly reporting provided to management to track Business Units against KPI's and targets
Synergy tracking established
Successful completion of direct/indirect tax filings
Meet Governance & Compliance Requirements
Successful execution of Finance Milestones (Pre-Close, Day 1, First 30…)
Employee Engagement & Retention within Finance
Finance operations harmonized
Consolidated policy & procedures implemented; control gaps remediated
Reporting requirements for Internal and External Stakeholders finalized
All corporate and business unit financial functions part of standard Internal Audit and Risk Management cycles
Tax Structure agreed upon and implemented
Operating as one Finance department
© 100-Day Advisors MandAPlaybook.com

## Slide 6: BUDGET PROCESS DIFFERENCES
GOALS & PHILOSOPHY
OTHER CONSIDERATIONS
TIMING
Targets to deliver established Acquirer EBITDA by BU and Shared Service
Decentralized process: autonomy for each BU and Shared Service
Each BU or Shared Service (ET vs. Non-IT) may have different planning processes
Restatements to prior year (i.e., management adjustments to 2028) Actuals for comparative management reporting in 2029)
Budget process for next year begins in July with refined forecast in September
Budget Targets set October
Budget activities ramp up November to achieve Target
Fine tuning & finalization in December
Reporting changes are incorporated in budget and any restatement of actuals for previous year takes place centrally in SAP
Acquirer
Acquirer
Targets are set up, if needed, after the initial submission by countries
Semi-centralized process: all countries follow general group guidelines and timelines but there is autonomy on local processes
Employee expenses are not calculated in systems
Budget process begins in August with refined forecast in September
Budget Targets set in November
Budget review with segments in November
Fine tuning & finalization in December
© 100-Day Advisors MandAPlaybook.com

## Slide 7: BUDGET PROCESS
System preparation and reporting instructions
Acquirer
Acquirer
System preparation & system opened
Budget production by BU / SS
Budget production (cont.)
Refined Targets Established
Initial Submission begins; goal to achieve Target
Bottom-up budget preparation by countries
Budget submission to group
Budget review and target proposal
Budget finalization
Initial draft submitted and P&L Delivered
Final budget submitted and P&L delivered
Include synergies & targets
Finalize combined budget
Final submission; budget finalization
Pre-Integration
Post-Integration
December
November
October
September
August
July
June
© 100-Day Advisors MandAPlaybook.com

## Slide 8: UPDATE
TO BE DETERMINED
NEXT STEPS
RISKS/ISSUES
KEY ACTIVITIES
Preliminary Entity/Tax Structure (as is)
Transfer Pricing & Other Policies/Procedure Review
Acquiree Entities EIN Registrations with US Jurisdictions
Identification of 3rd Party Service Providers
Valuation
  Conversion of accounting principles (IFRS to US GAAP)
Analysis of Financial Reporting/Analysis Tools and Capabilities
Business/Product Line Reporting
Resources & Availability Constraints (Summer Schedules)
Timing of Completion and Financial Reporting Obligations
Financial Systems Integration
Availability of Legal Entity Financial Detail (Multiple Systems)
Complexity of Legal Entity Structure to Maximize Tax Strategies
Analysis of IFRS to US GAAP
Acquisition Valuation(s)
Determine Optimal Legal Entity Structure (inc. Transfer Pricing)
Monthly Reporting Packages
FY2028 Financial Statement Audit Plan
Align Month End Closing Process & Timelines
Understand Global Liquidity Environment
Consolidation Financial Information
Level of Detail
Interaction of Multiple Accounting Systems
Management Reporting Structure
Budget, Forecast & 3 Year Plan Alignment
Consolidation of Duplicative Treasury Systems
Acquirer Entity Management & Compliance Tool
  Agreement on Consolidation of Treasury Systems
© 100-Day Advisors MandAPlaybook.com

## Slide 9
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting
11