## Slide 1: HUMAN RESOURCES M&A DELIVERABLES

## Slide 2: Agenda
M&A Change Readiness Assessment
M&A Impact Assessment
Week 1 Onboarding Plan
M&A Communications Plan
M&A Project Plan
© 100-Day Advisors MandAPlaybook.com

## Slide 3: M&A Change Readiness Assessment
Assess the likelihood of successful changes during the integration
Purpose
Change readiness survey
Results summary and action planning
Send pulse survey to employees every two weeks
Analyze results
Share results of the survey and action that will be taken in response
Deliverables
© 100-Day Advisors MandAPlaybook.com

## Slide 4: M&A Impact Assessment
Understand the extent and nature of the changes from the integration for each stakeholder group, assess their readiness for change, and how to influence/leverage them
Change impact assessment
Change mitigation strategies
Identify priority workstreams with most urgent need during IMO Kickoff meeting
Conduct interviews with each Functional Lead to learn:
  Differences between current and proposed future state
  Impact to stakeholders and the complexity of process and capability changes
  Communications to stakeholders and their training needs
  Potential risks and mitigating actions
Analyze impacts on stakeholder groups and recommend risk mitigation strategies
Purpose
Deliverables
© 100-Day Advisors MandAPlaybook.com

## Slide 5: Week 1 Onboarding Plan
Provide a positive experience rich with information for acquired company employees
Change management training
Information guides for employees, suppliers, and customers
Changes to benefits
Other changes impacting employees
Includes:
  Communications
  Welcome kits
  Change management training
  Acquirer’s norms and processes
Purpose
Deliverables
© 100-Day Advisors MandAPlaybook.com

## Slide 6: M&A Communications Plan
Keep stakeholders informed of integration changes and their importance, relevance, and benefits to achieve stakeholder support and advocacy
Communications plan
FAQs and core messages
Employee Day 1 playbook
  Develop plan to ensure stakeholder groups receives accurate, timely, tailored, clear information
  Leverage results of change impact assessment to make recommendations on communications and engagement opportunities
Purpose
Deliverables
© 100-Day Advisors MandAPlaybook.com

## Slide 7: M&A Project Plan
TOPIC | 13-JAN | 20-JAN | 27-FEB | 4-FEB | 11-FEB | 18-FEB | 25-FEB | 4-MAR | 11-MAR | 18-MAR | 25-MAR
Share change progress during weekly integration team meetings |  |  |  |  |  |  |  |  |  |  | 
Develop and support Day 1 communications |  |  |  |  |  |  |  |  |  |  | 
Continue to support week 2 and 3 communications and change plan |  |  |  |  |  |  |  |  |  |  | 
Align on plan and prioritized workstreams; begin scheduling interviews |  |  |  |  |  |  |  |  |  |  | 
Conduct change impact assessment interviews with workstream leads |  |  |  |  |  |  |  |  |  |  | 
Define upcoming changes and begin to understand impact on various stakeholders |  |  |  |  |  |  |  |  |  |  | 
Finalize change impact assessments |  |  |  |  |  |  |  |  |  |  | 
Develop onboarding strategies for leaders and the general population and engage employees |  |  |  |  |  |  |  |  |  |  | 
Launch change readiness pulse surveys and collect feedback |  |  |  |  |  |  |  |  |  |  | 
Update communications and change plan based on results of surveys |  |  |  |  |  |  |  |  |  |  | 
© 100-Day Advisors MandAPlaybook.com

## Slide 8
`
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting
8