## Slide 1
MERGER INTEGRATION
HUMAN RESOURCES KICKOFF MEETING

## Slide 2: Agenda
Key Decisions and Concerns
HR Plan
05
06
01
02
Integration Update
Charter
HR Integration Areas
Employee Engagement
HR Integration Steps
HR Interdependencies
07
08
03
04
© 100-Day Advisors MandAPlaybook.com

## Slide 3: Key Decisions and Concerns
س
Progress to Date
Developed Talent Inventory Tool for Org Development planning
Key Decision Made
Culture Framework Recommendations
Acquiree US employees move to Acquirer payroll & beneﬁts by 12/31/22
Key Decisions to Make
Org Structures
Risks
Coordination on new org
design/communication
Established HR Tracks and key milestones to be completed by month-end
س
HRIS System (Workday/Oracle)
س
Retention
Continued deep discovery discussions on key topics including HRIS, data, culture, global job framework
Workday – 2 year-renew
Global Job Framework Structure
Long pre-close (uncertainty)
Building strong relationships across teams
DOMO as data visualization tool
Global payroll/benefits (non-US)
Operating model clarity
© 100-Day Advisors MandAPlaybook.com

## Slide 4: Integration Update
Workstream Items
Key Decision to Make
Key Decision to Make
Risks
Workstream Items
Owners
​
Track Planning
Onsite Meeting
Davis
Brown
Onsite Meeting
Brown
Status
Key accomplishments since last meeting
Main areas of focus in the next few weeks
Tracks to meet over next 2-3 weeks and develop regular cadence to achieve plans.
Attend training, SMART Sheet access
Finalized 4-month plans Talked through culture, career architecture, talent management, talent assessment, HRIS systems and data analytics
4-month schedule created for all HR tracks and owners identified
Culture - finalize a recommendation for approach
Talent Inventory - finalize tool; plan for HR Director session
HRIS Systems – objective assessment to be completed (functionality/scalability/cost etc.)
Populate Smartsheet to create a Dashboard on execution
Cultural roadmap proposal finalized
Talent Inventory Tool finalized
Engagement Vendor
HRIS System
Culture Change Recommendations
© 100-Day Advisors MandAPlaybook.com

## Slide 5: Charter
Core Team Members
Workstream Project Manager
Dave Jones
Scope
In Scope
(HR sub-workstreams)
HR Strategy
Culture and Organization Talent Acquisition
Talent Management Learning and Development Performance Management Compensation and Beneﬁts HR Operations
HR Technology and Data Management
Overarching Objective
Identify and achieve unifying opportunities for employees.
Strive for seamless integration and enhance employee experiences.
Integration decisions to be approached objectively, taking into consideration better practices and maturity of approaches on both sides, ease of uniﬁcation, and scalability.
To identify and achieve cost synergy opportunities, especially in 3rd party provisions.
Speciﬁcally:
Partner with the business in making robust, fair people decisions during integration through sound talent assessments and retention strategies.
Partner with the business as it navigates through new org design, transformation and implementation
Maintain positive candidate and employee experience during the integration phase and beyond
Co-lead cultural integration and deﬁne uniﬁed purpose and values with leaders and business units
Inﬂuence with words and actions to create and maintain a safe and supportive work environment as we navigate changes and drive high levels of employee engagement
Deﬁne and implement HR policies, processes, and initiatives that support new company growth and higher performance
Deliver operational eﬃciency and eﬀectiveness in a uniﬁed HR function
Identify and achieve cost synergies
Team Lead(s)
Daniel Davis, Kay Brown, Bill Killinger
Bill Davis, Pat Sgafferl, Jim Morris
Jim Soldden
IMO Support
Team Resources
© 100-Day Advisors MandAPlaybook.com

## Slide 6: Charter
High Level Milestones
Cultural integration program
Global HR organizational structure implemented
Global performance management process uniﬁcation ratings
Conduct combined annual budget where possible
Global employee engagement platform
3rd party supplier uniﬁcation plan developed
Pre-Close
Full HR discovery complete
Company Organizational Structure identiﬁed Overall HR Organizational Structure identiﬁed Work Council/Statutory Consultation/Legal Requirements understood and prepared for
Key HR sub-workstreams process analysis completed and planning for uniﬁcation
opportunities commenced
Acculturation Plans developed and prepared for Day 1/First 30 Day implementation
Plan for Month 1 Uniﬁed People Dashboard
Day 1
Implement acculturation plan - Day 1 Actions
Activation of any required works council consultations, etc.
First 30
Continued Implementation of Acculturation Plan
Roll out uniﬁed people dashboard
Year-End 2028
Beyond
Global career architecture - Q1
Global talent acquisition process - Q1
Single HRIS Platform – TBD
Global performance management process
Global L & D eco-system
Payroll/Beneﬁt Vendor consolidation
Key Interdependencies
Financial Decisions
Connecting Organizations Together Technically
Coordination Across all Workstreams
Organizational Branding
Dependent on which Functions/Workstreams
Finance,
Technology
Communications,
Sales and Marketing
Exit Criteria (workstream eﬀorts may continue, but will no longer be supervised by IMO)
Newco cultural and talent roadmap established
HR processes uniﬁed
Major 3rd party integrations/synergies complete
Major milestones achieved
Key Measures
Strong Customer Satisfaction
Improved employee retention (esp. key talent)
Major synergies achieved
© 100-Day Advisors MandAPlaybook.com

## Slide 7: HR Integration Areas
HR Strategy
Culture +
Organization
Talent acquisition
Talent management
Learning & Development
Compensation
& beneﬁts
HR Operations
HR Technology
/ data mgmt.
Compliance / consultation
Employee
experience
Career Architecture philosophy
Purpose & values
Employer branding
Talent assessment
Training need analyses
Comp & Ben philosophy
Beneﬁts administration/ management
Systems integration
HR legal
(Engagement) surveys (incl. new hires/ exits)
Organizational design (Newco: change mgmt. and HR)
Acculturation
Employment agreements
D&I management
Manage competencies
Variable pay approach
Onboarding, right to work, I-9s, oﬀ boarding
Data analytics / HR data mgmt. / GDPR
Audit9
Comms & Change mgmt..
KPI setting & HR dashboard
Internal resourcing
Career architecture
Manage learning portfolio
Beneﬁts (insurances, pension, etc.)
Payroll admin, time and absence mgmt.., inc. LOA
Deﬁne guidelines
/ data standards
Staﬀ consultation
(ER / IR)
Philanthropy / charitable work
Workforce planning
New hire Onboarding
Succession planning
Deliver learning
LTIP
Global handbook
Contractor / contingent worker management
HR risk management
Sustainability (Judi)
Diversity & Belonging
Career Architecture
Merit cycle
HR helpdesk / ticketing
Retention plans
Manage employee performance
Coaching & mentoring
Third party agreements
Develop & Implement HR strategy
Handle disciplinary case
Immigration, expats
Career Architecture
Employee wellbeing initiatives
© 100-Day Advisors MandAPlaybook.com

## Slide 8: Key Decisions and Concerns
HR Plan
Status
Tracks
EVP
Talent
Acquisition
Workforce
Planning
Works Councils
Employee
consultation
Immigration/
global mobility/
ex-pats
Handbook
reconciliation
In coordination with comms WS create messaging for candidates for TA and hiring managers for pre-close and day 1
Share existing EVPs
Get appropriate people from HR and marketing to discuss how to begin to bring things together
Review hiring process in each organization for new roles and backfills
Aggregate open positions to determine where there is overlap
Work towards a plan for partnering with hiring managers especially in shared services/where talent assessments are occurring (to avoid additional redundancy)
Begin to share overarching processes to consider longer term roadmap, including employee screening
Finalize a talent assessment tool and train HRBPs/HR Directors
Partner with the business to finalize org structure
Utilize talent assessment tool to conduct workforce planning with the business
Begin mapping people to the new organization
Begin to create a workforce planning toolkit
Understand formal consultation process in each country and prepare strategy for each
Partner with HR Directors in Europe to informally partner with works councils to sign post as appropriate
Stay coordinated with workforce planning & talent assessment work
Prepare – if any – Day 1 communications, consultations, and contracts
Read the Acquiree global mobility policy
Prepare for any new ex-pat assignments
Begin discussions regarding immigration, global mobility, and ex-pat processes
Read the handbooks
Understand handbook approach (global vs. local)
Begin side-by-side assessment to determine magnitude of legal review/variances
Stay coordinated with audit on internal audit policies, code of conduct, etc.
© 100-Day Advisors MandAPlaybook.com

## Slide 9: Key Decisions and Concerns
HR Plan
Status
Tracks
Employee
Induction/
Onboarding
Talent
management
Learning and
development
Payroll
Benefits
HR Systems/
data analytics
Prepare for a unified interim induction plan for new hires hired after Day 1
Shared talent management strategy/philosophy, and maybe some processes defined/determined
Harmonize performance ratings scale and words among us internally
Side-by-side of competencies
Begin discussions on 3rd party contracts
Understand self-directed and ILT offerings/learning calendar
Coordinate relevant changes to competencies and any changes as a result of the culture workstream
Begin learning needs assessment
Identify key contacts in each country
Gather information from local payroll employees
Begin to discuss newco plan for payroll administration
Determine if possible/plan to integrate Jan. 1 for U.S
Identify key contacts in each country
Determine approach to complete discovery
Begin benefit discovery on both ends
Begin to discuss how to proceed
Complete HRIS comparison
Document in-system processes
Seek to understand finance system direction
Seek to understand technology integration plan and timeline
Complete gap analysis (by year end)
Make system decision (by year end)
Determine common data structure so we can begin to map combined organization in data analytics tool
© 100-Day Advisors MandAPlaybook.com

## Slide 10
HR Plan
Status
Tracks
Career
Architecture
Total Rewards
Contingent
workers
Employee
support
Engagement
surveys
Culture
Heath &
Wellbeing
HR Org
Structure
3rd party
agreements
Budgeting
Charity
DEI/D & B
Begin benefit discovery on both ends (base salaries, STI, LTI)
Begin to discuss how to proceed
Understand employee types and how used (contractor/employee/fixed term)
Coordinate with communications team on employee FAQs for Day 1
Determine harmonized global employee engagement platform
Harmonize purpose, vision, values, customer promise, cultural tenants, corporate story, mission
Prepare materials and plan for Day 1/first 30 days
Create longer cultural roadmap
Understand health and wellbeing structure and process (corporate and local)
Have an intro discovery meeting
End of quarter
3rd party supplier unification plan identified with timeline
Conduct annual combined budgeting where possible
Understand charity structure (corporate and local)
Have an intro discovery meeting
Understand DEI structure
Have an intro discovery meeting
Better understand approaches to job titles and career growth
Discuss true market pricing/bands
Begin discussions on a unified job and salary structure
Assess impact of tightening Acquirer range spread
Complete S-P-M analysis of Acquirer jobs
Conduct a translation exercise of Acquiree & Acquirer HR jobs

## Slide 11: HR Interdependencies
Sales & Marketing
Comms
Comms
Facilities
Finance
Field Unit
BUs / HR
HR
Sales & Marketing / HR
HR
HR
HR
HR
One Global Sales and Marketing organization structure
FAQs and key Day One and beyond information fed to us
Brand and culture deﬁned
Org. chart for the organization by location
HRIS / Payroll / Resource Planning
Finalized Org Chart
Overlap in insurance programs eliminated
Source
Dependent Function
Milestone
Legal
© 100-Day Advisors MandAPlaybook.com

## Slide 12: HR Integration Steps
Plan Integration
Launch survey
Prepare for Transition
Integration
Transition approach to establish one environment
Attribute identiﬁcation and set-up
Question mapping + selection
Survey delivery integration
Survey timeline and goals for upcoming year
Reﬁne resources and reinforce continuous listening practices across Acquirer and Acquiree
Learn through feedback and adapt for subsequent cycles
Parallel engagement survey deployed for Acquirer and Acquiree
Prioritize survey content to align with business strategy
Develop leader and employee playbook resources
Develop communication plan
RACI chart
Acquirer and Acquiree will be in one environment
Listening, learning, and acting on employee feedback
© 100-Day Advisors MandAPlaybook.com

## Slide 13: Employee Engagement
Acquirer and Acquiree will be on same HRIS
In the interim, Acquiree will follow existing format and Acquirer will begin with early adopters
Targeting next quarter to launch parallel engagement survey for all Acquirer and Acquiree employees
Continue targeted location-based surveys
© 100-Day Advisors MandAPlaybook.com

## Slide 14
thank you
contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting