## Slide 1: KICKOFF MEETING
M&A IMO

## Slide 2
Key Facts
Phases
Governance Structure
Due Diligence
Meeting Cadence
Data Sharing Rules
Tools
Next 30-Day Milestones
Agenda
© 100-Day Advisors MandAPlaybook.com

## Slide 3
MERGER OF EQUALS
KEY DATES
GENERAL THESIS
CULTURE
Acquiree and Acquirer are approximately equally-sized in terms of revenue
Companies will combine to form “NewCo” (Branding and Legal Structure TBD)
Aug 1 Announcement of Intent to Merge
Oct 1 Closing and “Day 1”
Leverage Cross-Selling Opportunities, Integrations, Digitization
Identify and Realize Benefits and Synergies
Capitalize on “Newcos” strengths to drive growth
Bridge, Integrate, Enhance
Expand Employee Focused, Customer Service Oriented Culture
Key Facts
© 100-Day Advisors MandAPlaybook.com

## Slide 4: Phase 1
SCOPE
ACTIVITIES
High-Level Planning
4 weeks
IMO Structure
IMO Kickoff
Due Diligence
Day 1 Planning
Resourcing
Integration Roadmap and Milestone Plan
Operationalize IMO team
Due Diligence
Risk Identification
Day 1 Mandatories and Planning
Integration Roadmap and Milestones
© 100-Day Advisors MandAPlaybook.com

## Slide 5: Phase 2
SCOPE
ACTIVITIES
Detailed Planning/ Day 1 Readiness
4 weeks
Detailed Workstream Planning
Communications
Dependency Identification
Synergy/Benefits Realization Plan
Detailed Functional Plans
Communication Plans
Dependencies Coordinated and Managed
Master Consolidated Plan
© 100-Day Advisors MandAPlaybook.com

## Slide 6: Phase 3
SCOPE
ACTIVITIES
Implementation
Day 1-100
Execute Integration Plan
Reporting
Adjustments
Plan Implementation
Monitoring, Controlling, Reporting
Analysis, Refinement, Adjustment
Commission/Decommission
Benefits Realization
© 100-Day Advisors MandAPlaybook.com

## Slide 7
Governance Model
Decision Executives
Steering Committee
Integration Management Office
Workstream Leads/Sponsors
Project Managers/Leads
Contributors/Stakeholders
PHASE 2
PHASE 3
PHASE 1
© 100-Day Advisors MandAPlaybook.com

## Slide 8
Due Diligence Request List Items by Function
Functional Lead Discussions/Data and Process Reviews
Preparation/IMO Team Review of Diligence Report
Activities
Due Diligence
Executive Team Diligence Report Readout
Analysis/Recommendations
Agreed High-Level Integration Strategy and Approach
Create Diligence Reports as basis for Strategic Decisions and Planning
Objective
Document/Analyze Current State of each Entity
People, Product, Technology, Process, Spend, Capabilities, Culture
Scope
© 100-Day Advisors MandAPlaybook.com

## Slide 9
Each workstream must be represented in all meetings – by the Lead or high-level representative
Sub-function Team Status Reports Submitted per Team Lead Requirements
Individual Integration Workstream Leads 1-on-1 Meetings with IMO to be scheduled throughout the week as needed
Cross Workstream Status follow-ups by IMO
Monday
Tuesday
Wednesday
Thursday
Friday
Meeting Cadence
Workstream Status Reports
Due by Wednesday 5PM
Joint IMO Update (Leads1) (Weekly)
1 Hour
Objectives:
Status
Resolve Issues
Interdependencies
General Communication and Direction from IMO
IMO Team Meeting:
(Workstream Leads)
45 Min
Objectives:
Activity Status
Impediments
Risks
Steering Committee Meeting:
1 Hour
Objectives:
Status
Items Requiring Attention/Executive Decisions
IMO Team Meeting:
(Workstream Leads)
45 Min
Objectives:
Activity Status
Impediments
Risks
© 100-Day Advisors MandAPlaybook.com

## Slide 10
Data Sharing
Secure Data Room
Establish IMO Workspace/Collaboration Space/Repository
Data Classification Requirements (Financials, Employee Census Data, etc.)
Meeting Privacy/ Calendar Visibility
© 100-Day Advisors MandAPlaybook.com

## Slide 11
Tools
Calendar/ Scheduling
Messaging
Conferencing
Document Storage
Project Management/ Planning
© 100-Day Advisors MandAPlaybook.com

## Slide 12
Predecessor Workstream
BU1
BU2
BU3
Compliance
Comms
Finance
HR
Sales & Mktg
IT
Legal
Facilities
On-track
Recoverable
Completed
Unrecoverable
Sales & Marketing
Branding plan and direction
Harmonize Product/Service
Harmonize Go-To-Market
Branding plan and direction
Harmonize fees, pitches, supporting processes
Harmonize cross sell strategy and processes
Finance, IT
Define Billing Workflow
IT
Deliver Outsourcing Contract & Negotiations Guide
Legal
Eval and Choose System Solution
Define Onboarding Process & Requirements
Compliance & Risk, IT
Define Customer Service Process & Requirements
Define Onboarding process and steps/workflow
Compliance & Risk
Define Global Policy and Local Reqs
Comms, IT
Harmonize Go-To-Market (Sales, Mktg & Pricing)
Socialize Intra-Office Charter
Banking Control
Legal
Communications
Employee Comms Plan/Workbook
Customer Comms Plan/Workbook
endor Comms Plan/Workbook
Sales & Marketing, Comms
Customer Comms Plan/Workbook
Biz Partner Comms Plan/Workbook
HR
8/19 Determine additional recruitment needs for 3 hubs
List of Acquirer employees requiring Acquiree sys access
Review Change Mgmt & Tech Stack needs
CLOSE
Next 30-Day Milestones

## Slide 13
thank you
contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com