## IT Integration Plan
100-DAY INFORMATION TECHNOLOGY POST-MERGER INTEGRATION PLAN | [13 empty] | Click on + sign (above the top row on right) to see synergy columns
TODAY'S DATE: T+30 (30 DAYS POST-CLOSE)
Risk Level | Status | % Complete |  |  | Links
High | Not Started | 0% |  |  | Day 1 Checklist
Medium | Delayed | 25% |  |  | Milestones
Low | On Track | 50% |  |  | RAID Log (Includes Plan Assumptions)
| Complete | 75% |  |  | Next 14 Days
|  | 100% |  |  | Executive Dashboard
ID# | Category | Milestone | Phase | Assigned To | Task | Notes | Timing Anchor | Start | Finish | Status | Complete | Critical Path | Issues/Blockers | Risk Level | Team Dependency | Synergy Description | Synergy ($K) | Cost To Achieve ($K) | Synergy ($K) Realized | Actual Cost To Achieve ($K)
IT-001 | Governance & Planning | IT Lead Appointed | Pre-Close | IT Workstream Lead | Identify IT integration workstream lead and determine members of the IT integration team | Lead must be appointed before integration kickoff; IT Lead is the single accountable owner for all IT deliverables — without this role filled, every downstream task lacks an owner; prioritize people with relationships in both legacy IT orgs; integration requires trust across teams that may be unfamiliar with each other's environments and working styles | T-59 | 1/2 | 1/10 | Complete | 100% | CP – Close | IT workstream lead must be identified and available before integration kickoff; without a named IT Lead, there is no accountable owner for systems assessment, Day 1 readiness, or the ERP and HRIS integration workstreams — every IT integration dependency stalls without this role in seat | High | HR, IMO | [5 empty] | 2
IT-002 | Governance & Planning | IT Integration Governance Established | Pre-Close | Cybersecurity & Compliance Lead | Review data privacy and confidentiality protocols for pre-close sharing | Pre-close data sharing is subject to HSR clean room rules; any IT staff with access to target company systems or data must be briefed on what they can and cannot do — violations carry regulatory and legal consequences | T-53 | 1/8 | 1/12 | Complete | 100% |  | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | High | Legal, Compliance
IT-003 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Workstream Lead | Review IT organizational structure and headcount | Flag IT headcount with specialized skills that are not duplicated in the acquirer's team; losing these individuals before knowledge transfer is complete creates irreversible gaps | T-51 | 1/10 | 1/23 | Complete | 100% |  |  | Medium | HR | IT headcount rationalization — combining two IT organizations eliminates overlapping specialist roles | 200 | 60
IT-004 | Integration Management | IT Integration Governance Established | Pre-Close | IT Workstream Lead | Attend IMO Kickoff Meeting | Bring a written IT workstream summary; use kickoff to surface cross-workstream dependencies with Comms, HR, Finance, and Sales that will require IT support | T-50 | 1/11 | 1/11 | Complete | 100% |  |  | Low | IMO
IT-005 | Governance & Planning | IT Integration Governance Established | Pre-Close | Applications & Digital Workplace Lead | Receive access to integration data room and IT workstream templates and document repository | Establish version control and access permissions from day one; document naming conventions early — a disorganized data room becomes a bottleneck as artifact volume grows | T-49 | 1/12 | 1/13 | Complete | 100% |  |  | Low | Legal
IT-006 | Governance & Planning | IT Integration Governance Established | Pre-Close | IT Workstream Lead | Hold IT Integration Kickoff Meeting | Agenda should cover: RACI confirmation, Day 1 critical path, clean room constraints, and priorities for the first 30 days; distribute agenda 24 hours in advance | T-49 | 1/12 | 1/12 | Complete | 100% |  |  | Low | IMO
IT-007 | Governance & Planning | IT Integration Governance Established | Pre-Close | IT Workstream Lead | Define IT integration success metrics and KPIs | KPIs should include: Day 1 system uptime, employee login success rate, service desk ticket volume, application rationalization progress, and synergy realization vs. plan | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | IMO
IT-008 | Governance & Planning | IT Charter Approved | Pre-Close | IT Workstream Lead | Develop the IT workstream integration charter and confirm team roles and responsibilities | Charter must define the boundary between IT workstream and Finance (ERP ownership), HR (HRIS ownership), and Sales (CRM ownership) — overlapping ownership of enterprise systems is the most common IT integration conflict | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | IMO
IT-009 | Due Diligence | IT Due Diligence Complete | Pre-Close | Infrastructure & Cloud Lead | Assess network topology, connectivity, and bandwidth capacity | Network topology assessment determines latency, redundancy, and bandwidth constraints for all Day 1 connectivity tasks; gaps discovered post-close require expensive emergency procurement | T-49 | 1/12 | 1/23 | Complete | 100% |  | If the target restricts network topology data in the clean room, IT will be designing Day 1 connectivity based on assumptions rather than engineering data — require Legal to explicitly scope network architecture documentation into the data room access agreement before signing | High | Finance
IT-010 | Due Diligence | IT Due Diligence Complete | Pre-Close | Infrastructure & Cloud Lead | Inventory hardware assets, data centers, and hosting arrangements | Include end-of-life dates for all hardware; assets past end-of-support on Day 1 create security and compliance risk that must be remediated before the combined environment is certified | T-49 | 1/12 | 1/30 | Complete | 100% |  |  | Medium | Finance
IT-011 | Due Diligence | IT Due Diligence Complete | Pre-Close | Applications & Digital Workplace Lead | Inventory all enterprise applications and SaaS subscriptions | Capture contract expiry dates, per-seat pricing, and change-of-control clauses for every application; overlapping SaaS subscriptions are typically the fastest IT cost synergy to realize | T-49 | 1/12 | 1/30 | Complete | 100% |  | An incomplete SaaS inventory means the combined entity will continue paying for duplicate subscriptions it cannot see; require the target's procurement team to provide a complete software spend report with contract terms as a condition of data room access, not as a follow-up request | High | Legal, Procurement
IT-012 | Due Diligence | IT Due Diligence Complete | Pre-Close | Applications & Digital Workplace Lead | Assess core business systems compatibility | Focus on systems that must interoperate on Day 1: email, directory services, VPN, payroll, and finance; incompatible authentication protocols are the most common Day 1 blocker | T-49 | 1/12 | 2/26 | Complete | 100% |  | The highest-consequence incompatibility is authentication — if the two companies cannot federate identity on Day 1, every employee login fails; require IT to complete a protocol-level compatibility test (not just a platform inventory) and document a Day 1 workaround for any gap found before the go/no-go review | High | Finance
IT-013 | Governance & Planning | IT Integration Plan Locked | Pre-Close | IT Workstream Lead | Develop IT integration plan (tasks, milestones, RAID log, Day 1 checklist) | IT integration plan is the operating document for the entire workstream; update weekly, share with IMO coordinator by Thursday, and treat stale tasks as a red flag. Plan of record will be at 3/31. Significant plan changes subsequent to that date must go through formal change approval process. | T-49 | 1/12 | 3/31 | Complete | 100% |  |  | Medium | IMO
IT-014 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review data architecture, databases, and data governance maturity | Data architecture gaps — undocumented schemas, shadow databases, manual data feeds — are the leading cause of post-close data integration failures; document every data flow, not just primary systems | T-48 | 1/13 | 1/30 | Complete | 100% |  | Undocumented data flows become a data migration failure when the integration team discovers mid-migration that a critical downstream report relies on a manual feed no one knew existed; require target IT to attest in writing that the data architecture review is complete before DD sign-off | High | Legal
IT-015 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review cloud platform usage (AWS, Azure, GCP) and cloud cost structure | Cloud cost management maturity varies widely; target companies often have unoptimized reserved instance coverage, orphaned resources, and unused licenses that represent immediate savings | T-48 | 1/13 | 2/6 | Complete | 100% |  |  | Medium | Finance
IT-016 | Due Diligence | IT Due Diligence Complete | Pre-Close | Cybersecurity & Compliance Lead | Review data privacy program (GDPR, CCPA, HIPAA) and compliance gaps | If target operates under HIPAA, GDPR, or CCPA, the acquirer inherits compliance obligations on Day 1; gaps in target's privacy program must be remediated before close or the acquirer assumes undisclosed regulatory risk | T-48 | 1/13 | 2/13 | Complete | 100% |  | Compliance gaps inherited at close cannot be disclaimed after the fact; if the target has an active HIPAA or GDPR deficiency, the acquirer must either remediate before close, escrow funds for post-close remediation, or factor the penalty exposure into the purchase price — this is a deal-term issue, not just an IT task | High | Legal, Compliance
IT-017 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review IT vendor contracts, licenses, and software agreements | Change-of-control clauses in enterprise software agreements can trigger immediate price renegotiation or license termination; identify affected vendors at least 30 days before close to allow renegotiation | T-48 | 1/13 | 2/25 | Complete | 100% |  | Vendor change-of-control clauses are triggered at close, not when IT discovers them; if these agreements are not mapped before signing, the combined entity may face license suspension or emergency renegotiation from a position of weakness on Day 1 — Legal must complete the vendor contract review before the SPA is executed | High | Legal, Procurement
IT-018 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Estimate future IT spend and total cost of ownership | Build the TCO model on a per-system basis so rationalization decisions have a financial baseline; blended IT cost estimates obscure which investments are worth retaining | T-48 | 1/13 | 2/25 | Complete | 100% |  |  | Medium | Finance
IT-019 | Due Diligence | IT Due Diligence Complete | Pre-Close | Cybersecurity & Compliance Lead | Review IT compliance certifications (SOC 2, ISO 27001, PCI-DSS) | SOC 2 and ISO 27001 certifications have defined audit scopes; confirm whether the combined entity's certification will require re-scoping and what the timeline and cost implications are | T-47 | 1/14 | 2/13 | Complete | 100% |  | Customers with contractual requirements for SOC 2 compliance will ask whether the combined entity's certification covers them; if the answer is unknown at Day 1, those customers will escalate — confirm the new audit scope with the certifying auditor before close and communicate the timeline to affected customers before the press release goes out | High | Legal, Compliance
IT-020 | Systems & Technology | Systems Integration Complete | Pre-Close | Applications & Digital Workplace Lead | Develop application and SaaS rationalization strategy and portfolio roadmap | Rationalization strategy should produce a three-category output: keep (run on combined platform), migrate (move to surviving system), retire (decommission with data archive); all other decisions are downstream of this | T-47 | 1/14 | 2/27 | Complete | 100% |  | The rationalization strategy is only as good as the inventory it is built on; if application inventory is delayed or incomplete, every 'retire' decision in this strategy risks decommissioning a system that is still in active use — do not present this strategy to leadership until the full inventory has been independently verified | High | Finance, IMO
IT-021 | Systems & Technology | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Assess SDLC maturity and software delivery practices of target | SDLC maturity assessment output determines whether combined engineering teams can collaborate safely from Day 1 or need a transition period with separate release cycles | T-45 | 1/16 | 2/23 | Complete | 100% |  |  | Low | Engineering
IT-022 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | IT Integration Coordinator | Estimate initial IT cost synergies (licenses, infra, headcount) | Synergy estimates must distinguish between one-time savings (decommission costs avoided) and recurring run-rate savings (license reduction, headcount, infrastructure); investors care about run-rate | T-45 | 1/16 | 2/26 | Complete | 100% |  |  | Medium | Finance, Procurement
IT-023 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | Applications & Digital Workplace Lead | Develop IT integration cost-to-achieve (CTA) budget | CTA budget must include: migration tooling, parallel-run infrastructure, consulting fees, employee training, and severance for redundant IT roles — understating CTA is the most common IT integration budget failure | T-45 | 1/16 | 2/26 | Complete | 100% |  |  | Medium | Finance
IT-024 | IT Infrastructure | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Cybersecurity & Compliance Lead | Assess and remediate critical vulnerability findings | Remediation must be complete before Day 1; acquiring a company with unpatched critical vulnerabilities transfers full legal liability to the acquirer — prioritize by CVSS score and customer data exposure | T-44 | 1/17 | 2/27 | Complete | 100% | CP – Day 1 Readiness | The acquirer cannot assert it was unaware of inherited vulnerabilities after close; any CVSS 9.0+ finding identified in diligence that is not remediated before Day 1 must be formally accepted with a documented risk treatment plan signed by the CISO — undocumented acceptance is not acceptance | High | Cybersecurity
IT-025 | Due Diligence | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review disaster recovery and business continuity capabilities | If target's RTO and RPO commitments do not meet acquirer's standards, interim mitigation must be in place before Day 1; a DR gap discovered during an actual outage post-close is a board-level event | T-43 | 1/18 | 2/21 | Complete | 100% |  | An RTO gap is not a theoretical risk — it means the combined entity cannot recover within its contractual SLA if a critical system fails in the first 30 days; identify the specific systems where target's BCP falls short and require a written interim mitigation plan from IT leadership before Day 1, not after | High | Legal
IT-026 | Integration Management | Day 100 IT Integration Complete | Pre-Close | IT Integration Coordinator | Launch weekly IT workstream status meeting — same day, same time each week | Same day and time every week without exception; first missed meeting signals the cadence is optional | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
IT-027 | Integration Management | Day 100 IT Integration Complete | Pre-Close | IT Integration Coordinator | Update Executive Dashboard weekly | IT rows on the dashboard are owned by the IT Lead; RAG status must reflect current reality — optimistic reporting delays executive awareness of issues that require intervention | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
IT-028 | Integration Management | Day 100 IT Integration Complete | Pre-Close | IT Integration Coordinator | Update status of integration plan and RAID log weekly | RAID log is the most important risk management tool in the IT workstream; new risks added by Thursday so IMO can incorporate into steering committee reporting | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
IT-029 | Integration Management | Day 100 IT Integration Complete | Pre-Close | IT Workstream Lead | Attend IMO Meeting every week to discuss issues and status | Bring the IT issues log and any cross-workstream blockers requiring IMO escalation | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
IT-030 | Due Diligence | IT Due Diligence Complete | Pre-Close | Cybersecurity & Compliance Lead | Review identity and access management (IAM) architecture | IAM architecture incompatibilities — Active Directory vs. LDAP, different MFA standards, conflicting role hierarchies — are the root cause of most Day 1 login and access failures | T-42 | 1/19 | 2/1 | Complete | 100% |  | The IAM incompatibility that is hardest to fix is MFA policy — if the target uses SMS-based MFA and the acquirer requires hardware tokens or authenticator apps, there is no fast migration path; every day this is unresolved after Day 1 is a day the target's users operate at a lower security standard inside the combined perimeter | High | Legal, Compliance
IT-031 | Systems & Technology | IT Due Diligence Complete | Pre-Close | Applications & Digital Workplace Lead | Inventory source code repositories and version control systems | Undocumented private repositories are a common IP and security risk; ensure all repositories are accounted for before any engineering team access changes are made | T-41 | 1/20 | 2/6 | Complete | 100% |  |  | Low | Legal
IT-032 | Systems & Technology | Systems Integration Complete | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Define cloud strategy and migration roadmap for combined entity | Cloud strategy decision (multi-cloud, single-cloud, or hybrid) must be made before any infrastructure migration begins; changing strategy mid-migration is significantly more expensive than choosing correctly upfront | T-41 | 1/20 | 2/27 | Complete | 100% |  | The cloud architecture decision is one of the few IT decisions that cannot be reversed cheaply — committing to a cloud provider or multi-cloud model without a migration cost model means the combined entity will discover the true cost only after vendor contracts are signed; require Finance sign-off on the TCO model before any cloud architecture is committed | High | Finance, IMO
IT-033 | IT Infrastructure | IT Infrastructure Consolidated | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Assess data center footprint and define consolidation strategy | Data center consolidation is typically the largest single IT cost synergy; quantify the fully-loaded cost of each facility (lease, power, cooling, headcount) before committing to a consolidation sequence | T-40 | 1/21 | 2/25 | Complete | 100% |  | A synergy number built on incomplete facility cost data — missing lease exit penalties, decommission costs, or headcount transfer costs — will be revised downward when Finance runs due diligence on the consolidation plan; obtain fully-loaded facility cost data from both real estate and Finance teams before publishing any consolidation synergy estimate to leadership | High | Finance, IMO
IT-034 | Synergy Tracking & Realization | Synergy Tracking Active | Pre-Close | IT Workstream Lead | Assign owners for each IT synergy | Each synergy line item must have a single named owner — shared ownership creates accountability gaps; the owner is responsible for measurement, reporting, and delivery | T-35 | 1/26 | 2/27 | Complete | 100% |  |  | Low | Finance
IT-035 | IT Infrastructure | Systems Integration Complete | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Develop network integration architecture and design for combined entity | Network architecture is the foundation on which every other Day 1 IT task depends; design must account for failover, latency requirements, and bandwidth peaks on Day 1 when traffic patterns will be abnormal | T-30 | 1/31 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Network architecture that has not been reviewed by both legacy network teams will have blind spots; require the target's network architect to formally review and sign off on the combined design before it is presented to the steering committee — an unreviewed design that fails on Day 1 is a much larger problem than a delayed design | High | IMO
IT-036 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Assist Communications team in drafting answers to Day 1 IT FAQs | IT perspective on FAQ answers is critical for questions about system access, email migration, device policy, and data privacy; assist Communications team in drafting answers and review for technical accuracy before distribution | T-25 | 2/5 | 2/24 | Complete | 100% |  |  | Medium | Communications
IT-037 | Systems & Technology | IT Due Diligence Complete | Pre-Close | IT Integration Coordinator | Review HRIS and payroll systems compatibility | HRIS and payroll system incompatibilities must be resolved before Day 1; a payroll failure on the first pay cycle of the combined entity is an immediate employee relations crisis and potential legal violation | T-23 | 2/7 | 2/27 | Complete | 100% |  | A HRIS compatibility gap that is discovered post-close and cannot be bridged with a parallel-run means employees may be on two separate payroll systems indefinitely; the cost and timeline of HRIS integration must be confirmed before close, not after, because it directly affects the benefit harmonization timeline that HR is planning around | High | HR, Finance
IT-038 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Applications & Digital Workplace Lead | Design unified onboarding and offboarding IT process | Onboarding process must cover Day 1 access provisioning for new hires joining the combined entity; a broken onboarding process is the first IT experience for every employee who joins post-close | T-22 | 2/8 | 2/25 | Complete | 100% | CP – Day 1 Readiness |  | Medium | HR
IT-039 | Systems & Technology | Systems Integration Complete | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Define unified device management (MDM/UEM) strategy | MDM strategy determines how employee devices will be managed, secured, and remotely wiped; incompatible MDM platforms create a security gap where one population's devices are unmanaged | T-20 | 2/10 | 2/23 | Complete | 100% | CP – Day 1 Readiness |  | Medium | HR | Unified device management — consolidating to a single MDM/UEM platform eliminates duplicate per-device licensing and reduces IT administration overhead | 25 | 10
IT-040 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Provide input on drafts of M&A Employee Communication Guide (includes talking points, guidance for team conversations) in preparation for Day 1 | IT-specific questions to address: what email platform will I use, will my devices change, what systems will I have access to, and who do I call if something breaks | T-20 | 2/10 | 2/27 | Complete | 100% |  |  | Medium | Communications
IT-041 | Systems & Technology | Systems Integration Complete | Pre-Close | Infrastructure & Cloud Lead | Define combined entity data governance framework and policies | Data governance framework determines who owns, classifies, and controls access to data across the combined entity; gaps here create regulatory risk (GDPR, CCPA) and audit findings | T-15 | 2/15 | 3/31 | Complete | 100% |  | Data ownership disputes between Finance, Sales, HR, and IT are the most common reason data governance frameworks stall; schedule a cross-functional data ownership workshop within the first 30 days and escalate any unresolved ownership conflict to the CFO — frameworks without resolved ownership are shelf ware | High | All Workstreams
IT-042 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Complete device provisioning for all acquired employees | Device provisioning for large acquired workforces requires weeks of lead time; if devices cannot be provisioned before Day 1, establish a clear interim access plan so employees are not blocked from working | T-15 | 2/15 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Device provisioning that relies on shipping hardware to employee home addresses introduces customs, carrier, and address-accuracy risks that can delay delivery by 1–2 weeks beyond the expected date; build the provisioning schedule from confirmed ship dates, not order dates | High | HR
IT-043 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Workstream Lead | Conduct Day 1 IT war-room dry run with full team | Dry run must test every Day 1 task in sequence and under realistic conditions; issues discovered in the dry run have days to be resolved — issues discovered on Day 1 must be fixed under live pressure | T-14 | 2/16 | 2/26 | Complete | 100% | CP – Day 1 Readiness | A dry run that only tests individual components in sequence does not surface the failures that happen when all systems run simultaneously under combined-entity load; the single most valuable thing the dry run can do is generate a live ticket backlog — if the service desk cannot clear that backlog within two hours during the dry run, it cannot probably clear it on Day 1 either | High | All Workstreams
IT-044 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Set up interim data sharing and reporting infrastructure for Day 1 | Interim data sharing must be established within clean room constraints pre-close; design it to be replaced, not extended — interim infrastructure that becomes permanent is an integration debt | T-13 | 2/17 | 2/27 | Complete | 100% | CP – Day 1 Readiness |  | Medium | Legal, IMO
IT-045 | Systems & Technology | IT Due Diligence Complete | Pre-Close | Infrastructure & Cloud Lead | Assess CI/CD pipeline and DevOps toolchain compatibility | Toolchain incompatibilities that are not resolved before combined engineering teams begin working together result in broken builds, deployment conflicts, and lost productivity | T-12 | 2/18 | 2/27 | Complete | 100% |  |  | Medium | Engineering
IT-046 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Confirm first-day IT service desk operating model and escalation paths | Service desk must be staffed and tested before Day 1; acquired employees will flood the helpdesk with access and connectivity questions in the first hour — under-staffing on Day 1 creates a backlog that persists for weeks | T-10 | 2/20 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A service desk that is not staffed before the first employee's laptop fails on Day 1 cannot be stood up fast enough to prevent the backlog from compounding; confirm staffing levels, escalation contacts, and ticket routing at least one week before Day 1 — any gap found in that confirmation window still has time to be fixed | High | HR
IT-049 | IT Infrastructure | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Confirm Day 1 network connectivity between acquirer and target offices | Network connectivity test must be conducted under full traffic load; Day 1 bandwidth demand will be higher than any previous test due to the combined user population accessing systems simultaneously | T-6 | 2/24 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Testing connectivity at off-peak hours on the day before Day 1 does not validate performance under the peak load of both organizations authenticating simultaneously at 8 AM; run the full-load connectivity test at least one week before Day 1 so there is time to add bandwidth or adjust routing before the real deadline | High | Facilities
IT-050 | Systems & Technology | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Stand up IT service desk on Day 1 with combined coverage | Service desk ticket volume on Day 1 will be 3–5x normal; pre-stage responses for the top 20 anticipated issues and staff with senior engineers who can resolve novel problems in real time | T-6 | 2/24 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Tier 1 help desk agents who have been trained on only one entity's environment will escalate every cross-environment incident to Tier 2, saturating senior engineers with tickets that should be resolvable at Tier 1; run cross-environment training sessions for all help desk staff in the week before Day 1 and validate coverage before the service desk goes live | High | HR
IT-051 | IT Infrastructure | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Establish secure network interconnect between acquirer and target Day 1 | Network interconnect must include failover routing; a single-path interconnect that fails on Day 1 takes down communication between both entities simultaneously | T-6 | 2/24 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A network interconnect designed for average daily traffic will degrade under the spike of two organizations communicating across a newly connected link for the first time; test the interconnect at 150% of projected peak load and confirm failover actually routes traffic before Day 1, not after the primary link saturates | High | Network Carriers
IT-052 | IT Infrastructure | Day 1 IT Readiness Confirmed | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Verify all acquired employees have Day 1 Minimum Viable Access — email, HR portal, and primary line-of-business apps; full access provisioning to roll out in waves through Week 1 | Credential verification must cover every authentication system: VPN, email, ERP, CRM, and any application with SSO; a rep who cannot access their sales tools on Day 1 cannot sell | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% | CP – Day 1 Readiness | A user who cannot authenticate on Day 1 will call the help desk, which will already be handling 3–5x normal volume; the authentication failure rate from the dry run is the most reliable predictor of Day 1 service desk load — treat any dry run failure rate above 2% as a blocker requiring executive escalation | High | HR
IT-053 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Integration Coordinator | Activate IT integration war room and stand up command center for Day 1 | War room must be staffed from 6 AM on Day 1 with a clear command structure; every IT issue escalates to the war room first — do not allow individual teams to troubleshoot in isolation | T-5 | 2/25 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A war room that is stood up on the morning of Day 1 without prior rehearsal will lose 30–60 minutes to logistics (who has the bridge line, who can see the dashboard, who approves emergency changes) while live incidents queue up; the war room command structure must be rehearsed in the dry run, not improvised on Day 1 | High | IMO
IT-054 | Systems & Technology | Day 1 / Week 1 IT Integration Complete | Pre-Close (Day 1 Readiness) | Infrastructure & Cloud Lead | Enable unified email and calendar access for all staff Day 1 | Email and calendar access is the single most visible IT deliverable on Day 1; test with a sample of acquired-company users at least 48 hours before cutover — do not discover provisioning failures on Day 1 | T-4 | 2/26 | 2/27 | Complete | 100% | CP – Day 1 Readiness | Email provisioning failures are not recoverable quickly because they involve directory services, MX records, and spam filtering — all of which have propagation delays measured in hours, not minutes; confirm that provisioning for all acquired users has completed at least 24 hours before Day 1 so that any failures have time to be resolved before employees arrive | High | HR
IT-D1 | Integration Management | Day 1 IT Readiness Confirmed | Pre-Close (Day 1 Readiness) | IT Workstream Lead | IT Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | Workstream lead formally certifies Day 1 readiness to the IMO; this gate must be green for every workstream before the IMO signs off on close; any open item at this gate is either resolved or escalated to the steering committee as a close-blocking risk | T-3 | 2/27 | 2/27 | Complete | 100% | CP – Day 1 Readiness | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | High | IMO, All Workstreams
IT-055 | IT Infrastructure | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Brief staff on Day 1 cybersecurity protocols and acceptable use policies | Focus on the most common Day 1 cybersecurity failures: phishing emails impersonating the acquirer, credential stuffing on newly provisioned accounts, and unauthorized data exfiltration by departing employees | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  |  | Medium | HR, Cybersecurity
IT-056 | Integration Management | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | IT Integration Coordinator | Send Day 1 all-staff IT welcome communication to combined entity employees | Welcome communication sets the tone for IT's relationship with the combined employee base; focus on what support is available and who to contact — not on the technical complexity of the integration | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  |  | Low | Communications
IT-057 | IT Infrastructure | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | Infrastructure & Cloud Lead | Confirm all office network connectivity is live and stable at open of business | Test connectivity from every office location, not just headquarters; remote offices frequently have connectivity issues that are not caught in central testing | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  | Remote offices are the gap in almost every Day 1 IT test plan because they are assumed to inherit the fix applied at headquarters; assign a named IT contact at every acquired office location with instructions to confirm connectivity at 7 AM on Day 1 and escalate immediately if anything is down | High | Facilities
IT-058 | IT Infrastructure | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Extend SIEM and threat detection to acquired company environment on Day 1 — confirm all endpoints and network segments are covered under unified monitoring | SIEM extension is non-negotiable on Day 1; a threat that originates in the target environment and propagates to the acquirer's network cannot be detected without unified visibility | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  | A threat actor who knows both companies are in an integration transition will target the newly connected link between environments specifically because monitoring is likely to have gaps in the first 24 hours; SIEM coverage of the target environment must be confirmed active, not just configured, before any network interconnect goes live | High | Cybersecurity
IT-059 | IT Infrastructure | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Validate all IT controls are active in combined environment | IT controls validation must cover: access provisioning, change management, patch management, and audit logging; gaps in any of these create SOX and audit exposure from the first reporting period | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  | IT controls that pass individually may fail when tested in the combined environment due to permission inheritance issues, group policy conflicts, or role assignment overlaps; require the CISO to run a combined-environment controls test — not just an attestation. | High | Finance
IT-060 | Systems & Technology | Email & Collaboration Unified | Day 1 / Week 1 | Applications & Digital Workplace Lead | Deploy unified collaboration platform to all combined staff — confirm access, licensing, and data migration from legacy tools before decommissioning | If both companies use different collaboration platforms, decide on a single standard before Day 1 and communicate the migration plan to employees at the all-hands — running two platforms simultaneously degrades productivity and security | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  |  | Medium | HR
IT-061 | IT Infrastructure | Compliance Program Integrated | Day 1 / Week 1 | Cybersecurity & Compliance Lead | Finalize and publish unified IT acceptable use policy | Acceptable use policy must address the combined entity's specific risk profile; a generic policy that does not reflect the actual systems employees use will be ignored | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  |  | Low | Legal, HR
IT-062 | Systems & Technology | Day 1 / Week 1 IT Integration Complete | Day 1 / Week 1 | IT Integration Coordinator | Conduct end-user IT orientation sessions for acquired employees | Orientation sessions must cover the top five things employees need to do on their first day: log in, access email, connect to VPN, submit a ticket if something breaks, and find the IT self-service portal | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  |  | Low | HR
IT-047 | IT Infrastructure | Systems Integration Complete | Day 1 / Week 1 | Infrastructure & Cloud Lead | Assess server and storage infrastructure and develop rationalization roadmap — ensure Day 1 stability; full rationalization delivered in phases by Day 60 | Prioritize server rationalization by workload type: consolidate like-for-like workloads first, then address application dependencies before decommissioning hardware | Day 1 (Close) | 3/2 | 4/30 | On Track | 75% | CP – Day 100 |  | Medium | Finance | Server and storage rationalization assessment — cost identification only; savings realized through IT-091 data center migration | 0 | 20
IT-048 | IT Infrastructure | IT Service Management Framework Established | Day 1 / Week 1 | Applications & Digital Workplace Lead | Establish interim DNS trust relationships and directory connectivity for Day 1; full Active Directory and DNS unification to follow in controlled migration by Day 30 | DNS and directory services must be tested in a staging environment before Day 1 cutover; a DNS failure on Day 1 can prevent all authenticated access across the combined entity | Day 1 (Close) | 3/2 | 3/31 | Complete | 100% | CP – Day 100 | DNS is the dependency that everything else depends on; a DNS failure does not just break one application — it breaks authentication, email, internal name resolution, and any service discovery that relies on DNS; do not proceed with any production DNS cutover without a tested, documented rollback procedure that can be executed in under 15 minutes | High | Network Carriers
IT-063 | Systems & Technology | Systems Integration Complete | To Day 100 | IT Integration Coordinator | Assess ERP landscape across both entities and define combined entity ERP architecture — evaluate consolidation vs. migration options before committing to approach | ERP architecture decision — retain acquirer's ERP, migrate to target's, or implement a new platform — is the single most consequential IT decision in the integration; it drives timeline, cost, and all downstream data migration work | T+8 | 3/10 | 3/31 | Complete | 100% |  | The ERP decision determines every subsequent timeline in the applications integration; a decision that slips from 30 days to 60 days post-close does not delay the ERP migration by 30 days — it delays every downstream task that depends on it, typically extending the total integration timeline by 3–6 months for each month of delay | High | Finance
IT-064 | Systems & Technology | Systems Integration Complete | To Day 100 | Applications & Digital Workplace Lead | Conduct data quality assessment on acquired company systems — identify data integrity issues, duplicates, and gaps before migration begins | Data quality assessment results determine the feasibility of every planned data migration; poor data quality discovered post-migration is significantly more expensive to remediate than fixing it pre-migration | T+8 | 3/10 | 3/31 | Delayed | 25% |  |  | Medium | Finance, Sales, HR
IT-065 | Systems & Technology | IT Service Management Framework Established | To Day 100 | Applications & Digital Workplace Lead | Assess and select unified ITSM platform for the combined entity — evaluate both current tools against requirements, select the system of record, and plan migration of open tickets and historical data | ITSM platform selection drives all downstream incident, change, and problem management processes; evaluate based on integration capability with existing monitoring tools, not just feature set | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium | Finance
IT-066 | Systems & Technology | IT Service Management Framework Established | To Day 100 | Applications & Digital Workplace Lead | Implement unified incident management and escalation process | Unified incident management is the most employee-visible IT service process; inconsistent escalation paths between legacy teams cause delayed resolution and frustrated end users | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium
IT-067 | Systems & Technology | Systems Integration Complete | To Day 100 | IT Integration Coordinator | Build revenue bridge and reporting data pipeline for combined entity | Revenue bridge data pipeline is required before the first combined earnings call; Finance cannot report on combined revenue without a validated reconciliation between the two legacy systems | T+8 | 3/10 | 4/15 | On Track | 75% |  | Finance's first earnings call after close will require combined revenue data; if the data pipeline is not built and validated against both legacy systems before that call, the CFO will either miss the deadline or present unvalidated numbers — neither is acceptable; | High | Finance, Sales
IT-068 | Synergy Tracking & Realization | Synergy Realization Report Phase 1 Complete | To Day 100 | IT Integration Coordinator | Identify overlapping vendor relationships and consolidation opportunities | Vendor consolidation roadmap should include contract expiry dates; renegotiating before expiry with combined leverage avoids auto-renewal at legacy pricing | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium | Finance, Procurement
IT-069 | IT Infrastructure | Compliance Program Integrated | To Day 100 | Cybersecurity & Compliance Lead | Review and rationalize privileged access accounts across combined entity | Privileged access rationalization is the highest-risk security task post-close; former target-company IT administrators who retain elevated access they no longer need represent a significant insider threat vector | T+8 | 3/10 | 3/31 | Complete | 100% |  | Privileged access rationalization is time-sensitive because every day a former target-company administrator retains elevated rights is a day they can access systems they no longer have a business reason to access; set a 30-day post-close deadline for full rationalization and treat any account that cannot be certified as active and necessary within that window as immediately suspended | High | Cybersecurity | Privileged access reduction — eliminating unnecessary elevated accounts reduces both security risk and per-seat licensing cost for PAM (privileged access management) tools | 25 | 5
IT-070 | IT Infrastructure | Systems Integration Complete | To Day 100 | Infrastructure & Cloud Lead | Deploy unified network monitoring and observability tools | Unified observability is a prerequisite for effective incident response in the combined environment; running separate monitoring tools means incidents that cross the boundary between environments go undetected | T+8 | 3/10 | 4/1 | Complete | 100% |  |  | Medium |  | Network monitoring tool consolidation — retiring duplicate observability platforms and consolidating to a single tool reduces licensing cost and analyst overhead | 25 | 10
IT-071 | Systems & Technology | Systems Integration Complete | To Day 100 | IT Integration Coordinator | Integrate HRIS and migrate employee data to unified HR platform | Employee data migration must be validated against payroll, benefits, and compliance records before go-live; a single field mapping error can affect hundreds of employees' pay or benefits | T+8 | 3/10 | 4/30 | On Track | 75% |  | An HRIS migration that completes with a 98% record accuracy rate sounds acceptable until you realize 2% of 500 employees is 10 people with incorrect payroll data; require 100% field-level validation on pay rate, tax withholding, direct deposit routing, and benefit elections before any migration is declared complete | High | HR, Finance
IT-072 | Systems & Technology | IT Service Management Framework Established | To Day 100 | IT Integration Coordinator | Conduct IT staff cross-training on combined environment | Cross-training must focus on the systems that are most different between the two environments; staff who know only their legacy environment cannot support the combined entity's infrastructure | T+10 | 3/12 | 4/30 | On Track | 75% |  |  | Low | HR
IT-073 | Systems & Technology | Systems Integration Complete | To Day 100 | Applications & Digital Workplace Lead | Define unified software development standards and coding guidelines | Coding standards alignment reduces code review friction and onboarding time for engineers moving between legacy teams; agree on the combined standard within 30 days of close | T+13 | 3/15 | 3/31 | Complete | 100% |  |  | Low | Engineering
IT-074 | Systems & Technology | Systems Integration Complete | To Day 100 | Applications & Digital Workplace Lead | Map CRM data fields and define data migration rules | Field mapping errors in CRM migration cause broken reports, misclassified opportunities, and lost historical context; require a data steward sign-off on every field mapping decision before migration | T+13 | 3/15 | 4/1 | Complete | 100% |  | A field mapping that looks correct in the staging environment may produce different results in production due to data type mismatches, null value handling, or picklist value differences; require a production-equivalent validation run using a representative sample of real records — not test data — before the field mapping is approved as final | High | Finance, Sales
IT-075 | IT Infrastructure | Compliance Program Integrated | To Day 100 | Infrastructure & Cloud Lead | Test disaster recovery failover for mission-critical systems | DR failover test must be conducted under realistic load conditions; a test that passes on a lightly loaded system may fail under the combined entity's production traffic volume | T+15 | 3/17 | 3/24 | Complete | 100% |  | A DR test that passes at single-entity load provides no useful information about combined-entity behavior; the test only validates what it tests, and a mission-critical system that handles twice the transaction volume post-merger may behave very differently under failover conditions — require the test to run at combined-entity peak load or classify the result as untested | High | Cybersecurity
IT-076 | Systems & Technology | IT Service Management Framework Established | To Day 100 | Infrastructure & Cloud Lead | Complete IT staff role alignment and skills gap assessment | Skills gap assessment should identify roles where the combined IT team lacks coverage entirely — these gaps are more urgent than duplicate roles and should drive both hiring and cross-training decisions | T+17 | 3/19 | 4/30 | On Track | 25% |  |  | Low | HR
IT-077 | Synergy Tracking & Realization | Synergy Realization Report Phase 1 Complete | To Day 100 | IT Integration Coordinator | Begin renegotiation of largest IT vendor contracts using combined scale | Lead renegotiation with data: combined entity spend, utilization rates, and benchmark pricing from comparable companies — vendors will not voluntarily offer better terms without commercial pressure | T+18 | 3/20 | 5/31 | On Track | 25% |  |  | Medium | Legal, Procurement
IT-078 | Systems & Technology | IT Service Management Framework Established | To Day 100 | Infrastructure & Cloud Lead | Develop combined entity IT helpdesk operating procedures | Procedures must reflect the actual combined environment, not one entity's legacy process; procedures that do not match reality are ignored by helpdesk staff within 30 days | T+18 | 3/20 | 4/30 | On Track | 25% |  |  | Low
IT-079 | IT Infrastructure | IT Infrastructure Consolidated | To Day 100 | Infrastructure & Cloud Lead | Begin data center consolidation planning — finalize migration sequence, decommission schedule, hardware disposition plan, and vendor contracts before execution begins | Sequence data center consolidation after data migration and application rationalization have been made; migrating to a data center that will itself be retired is wasted effort | T+29 | 3/31 | 5/31 | On Track | 25% |  |  | Medium | Finance, IMO
IT-080 | Synergy Tracking & Realization | Synergy Realization Report Phase 1 Complete | To Day 100 | IT Integration Coordinator | Track SaaS license consolidation savings against deal model | Track at the individual SaaS contract level, not in aggregate; blended tracking obscures which contracts have been rationalized and which are still running in parallel | T+29 | 3/31 | 5/31 | On Track | 25% |  |  | Medium | Finance, Procurement | SaaS license consolidation — rationalizing duplicate SaaS subscriptions across both entities eliminates redundant tool spend on overlapping productivity, analytics, and project management platforms | 100 | 15
IT-081 | Systems & Technology | Systems Integration Complete | To Day 100 | Applications & Digital Workplace Lead | Migrate acquired-company accounts into combined entity CRM of record and validate data integrity | Validate migrated CRM records against the source system before decommissioning; a sample of 5% of records is insufficient — validate 100% of high-value opportunity and contact records | T+30 | 4/1 | 4/30 | On Track | 25% |  | CRM records that are migrated in the wrong order — active pipeline before historical data — create a window where reps are working in the new system without the context of prior customer interactions; the migration order is not a technical preference, it is a business requirement that Sales Operations must confirm in writing before migration begins | High | Finance, Sales
IT-082 | Integration Management | 30-Day IT Integration Review Complete | To Day 100 | IT Integration Coordinator | Conduct Day 30 IT integration health check and risk reassessment — system uptime, helpdesk ticket trends, open security items, and synergy tracking; primary input to the Day 30 IT gate review | Day 30 health check should assess: actual vs. planned task completion, RAID log status, synergy realization, employee satisfaction with IT support, and top open risks | T+30 | 4/1 | 4/7 | On Track | 25% |  |  | Medium | IMO
IT-083 | Systems & Technology | Compliance Program Integrated | To Day 100 | Cybersecurity & Compliance Lead | Establish data retention and disposition schedule for combined entity | Retention schedules must align with the most restrictive jurisdiction the combined entity operates in; a shorter retention schedule applied to data subject to a longer legal hold creates compliance exposure | T+30 | 4/1 | 4/15 | On Track | 25% |  |  | Low | Legal, Compliance
IT-084 | Systems & Technology | IT Service Management Framework Established | To Day 100 | IT Integration Coordinator | Design unified IT service management (ITSM) operating model | ITSM operating model must define ownership boundaries for infrastructure that spans both legacy environments; ambiguous ownership causes incidents to fall between teams | T+30 | 4/1 | 4/30 | On Track | 25% |  |  | Medium
IT-085 | IT Infrastructure | IT Infrastructure Consolidated | To Day 100 | IT Integration Coordinator | Review and consolidate internet and WAN service provider contracts | WAN consolidation typically yields 20–40% reduction in connectivity spend; negotiate with incumbent carriers using combined entity volume — do not renegotiate each entity's contracts independently | T+30 | 4/1 | 5/31 | On Track | 25% |  |  | Medium | Legal, Procurement | Internet and WAN consolidation — combining connectivity contracts under a single provider at combined entity volume yields improved pricing and eliminates duplicate circuits | 25 | 10
IT-086 | Systems & Technology | Systems Integration Complete | To Day 100 | Applications & Digital Workplace Lead | Migrate chart of accounts and financial master data to ERP | Chart of accounts migration is a Finance-owned deliverable with IT execution; Finance must approve the final COA mapping before any data is moved — post-migration reclassification is an audit risk | T+30 | 4/1 | 5/31 | On Track | 25% |  | COA migration errors are not just accounting problems — they generate incorrect financial statements that may require restatement; the COA mapping must be reviewed and signed off by both the Finance workstream lead and the external auditor before any financial data is moved, not after migration is complete | High | Finance
IT-087 | Systems & Technology | Systems Integration Complete | To Day 100 | Applications & Digital Workplace Lead | Complete ERP full integration or migration to single platform | ERP full integration or migration is the most complex, long-duration IT task in the integration; begin planning no later than Day 14 and maintain a dedicated project manager through completion | T+30 | 4/1 | 5/31 | On Track | 25% |  | ERP migrations that are declared complete before the first month-end close frequently reveal data integrity problems that surface only when the accounting team runs reconciliations; the ERP migration should not be signed off until it has successfully processed at least one complete close cycle, including journal entries, allocations, and financial statement generation | High | Finance
IT-088 | Systems & Technology | Systems Integration Complete | To Day 100 | Infrastructure & Cloud Lead | Complete product and customer data integration and deduplication | Customer and product data deduplication is prerequisite to any cross-sell motion; duplicate records cause double-counting in pipeline reporting and duplicate outreach to the same customer | T+30 | 4/1 | 5/31 | On Track | 25% |  | Without agreed deduplication rules, IT will make arbitrary choices about which record survives a conflict; those choices will produce incorrect customer master data that Sales, Finance, and Marketing will discover over the following months through bad pipeline reports, duplicate invoices, and misdirected outreach — business rules must be defined and approved before a single record is touched | High | Sales, Finance, Legal
IT-D30 | Integration Management | 30-Day IT Integration Review Complete | To Day 100 | IT Workstream Lead | IT Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | IMO-led review of IT workstream at Day 30; confirm all Day 1 tasks closed, RAID log current, synergy owners active, and no unresolved blockers threatening Day 100 delivery | T+30 | 4/1 | 4/3 | On Track | 50% |  | If the Day 30 check reveals open tasks, unresolved blockers, or synergy owners not yet active, the integration team has 70 days to correct course — but the Day 30 review must force honest status reporting; teams that report green when yellow or red create hidden risk that surfaces at Day 100 when it is too late to recover | High | IMO, All Workstreams
IT-089 | Synergy Tracking & Realization | Synergy Realization Report Phase 1 Complete | To Day 100 | IT Integration Coordinator | Complete IT vendor contract renegotiation and track savings | Final renegotiation savings should be compared against the deal model assumption; variances above 10% must be escalated to the CFO and IT Lead within 48 hours | T+31 | 4/2 | 5/31 | Not Started | 0% |  |  | Low | Legal, Procurement
IT-090 | Systems & Technology | Systems Integration Complete | To Day 100 | Applications & Digital Workplace Lead | Deploy unified telephony platform across combined entity | Telephony migration is often deprioritized until post-Day 30; if this is the approach, communicate clearly which phone system employees should use in the interim to avoid confusion | T+42 | 4/13 | 4/30 | Not Started | 0% |  |  | Medium | HR | Telephony platform consolidation — migrating both companies onto a single telephony system eliminates duplicate platform licenses, support contracts, and per-user fees; combined entity purchasing volume supports better carrier pricing; savings are net of migration costs which are captured in CTA | 25 | 15
IT-091 | IT Infrastructure | IT Infrastructure Consolidated | To Day 100 | Infrastructure & Cloud Lead | Execute data center migration — migrate all workloads to consolidated infrastructure, retire legacy hardware, confirm facility exit, and validate no stranded costs remain | Data center migration is the highest-risk infrastructure task; require a validated rollback plan, a parallel-run period, and cutover approval from the business owner of every migrated workload | T+60 | 5/1 | 5/31 | Not Started | 0% |  | The difference between a planned data center migration and an emergency migration is the rollback plan; a migration that begins without a tested, documented procedure for reverting every migrated workload within a defined window is not a planned migration — it is an irreversible cutover with a risk profile the business has not accepted | High | Finance, IMO | Data center migration delivers facility exit savings from consolidating two data centers into one — eliminating lease, power, cooling, and maintenance costs on the retired facility | 200 | 100
IT-092 | Compliance & Regulatory | Compliance Program Integrated | To Day 100 | Cybersecurity & Compliance Lead | Complete annual security risk assessment for combined entity | Security risk assessment scope must explicitly include the combined entity's perimeter; assessments conducted on only one entity's environment will miss cross-entity attack surfaces | T+60 | 5/1 | 5/31 | Not Started | 0% |  | A security assessment that covers only the acquirer's legacy perimeter has a blind spot the size of the acquired company's entire network; assessors should be explicitly scoped to include the combined perimeter, with a separate deliverable that maps all newly introduced attack surfaces from the integration — assessors who are not told about the acquisition may not know to look | High | Cybersecurity, Legal
IT-093 | Systems & Technology | IT Service Management Framework Established | To Day 100 | IT Service Management Framework Established | Complete ITSM platform migration and retire legacy ticketing tools | Retire legacy ticketing systems only after confirming all historical ticket data has been migrated or archived; audit trails in old tickets are frequently referenced in compliance reviews | T+60 | 5/1 | 5/31 | Not Started | 0% |  |  | Medium | Finance | ITSM tool consolidation — retiring the legacy ticketing and service management platform and migrating all data to the combined entity ITSM system eliminates duplicate vendor fees, reduces IT support overhead, and provides a single pane of glass for incident and change management across the combined entity | 25 | 10
IT-094 | Synergy Tracking & Realization | Synergy Realization Report Phase 1 Complete | To Day 100 | IT Workstream Lead | Finalize IT run-rate synergy baseline for annual operating plan | Run-rate baseline is the foundation for the combined entity's IT cost budget; errors here propagate into the annual operating plan and investor guidance | T+77 | 5/18 | 5/31 | Not Started | 0% |  |  | Low | Finance
IT-095 | IT Infrastructure | IT Infrastructure Consolidated | To Day 100 | Infrastructure & Cloud Lead | Complete network convergence — retire all legacy connectivity | Legacy network connections are a security and cost liability; accelerate retirement by mapping all dependencies before setting a hard cutover date | T+78 | 5/19 | 5/31 | Not Started | 0% |  |  | Medium | IMO | Legacy circuit decommissioning — savings captured in IT-085 WAN/internet consolidation contract; no incremental synergy recorded here to avoid double-count | 0 | 15
IT-096 | Synergy Tracking & Realization | Day 100 IT Integration Complete | To Day 100 | IT Integration Coordinator | Publish IT synergy realization 100-Day scorecard — confirms which IT cost synergies have been realized, which are on track, and which are at risk; delivered as part of the Day 100 IT gate review package | Scorecard should show: planned vs. actual synergy by category, cost-to-achieve spend vs. budget, and open items carrying into BAU — distribute to CFO, IT Lead, and IMO | T+81 | 5/22 | 6/5 | Not Started | 0% | CP – Day 100 |  | Low | Finance, IMO
IT-097 | Systems & Technology | Day 100 IT Integration Complete | To Day 100 | Applications & Digital Workplace Lead | Conduct final IT integration health check and stakeholder review | Final health check deliverable should include a recommendation on what, if anything, should carry into the BAU IT operating model vs. what should be closed out | T+84 | 5/25 | 6/5 | Not Started | 0% |  |  | Low | IMO
IT-098 | Systems & Technology | Systems Integration Complete | To Day 100 | Applications & Digital Workplace Lead | Decommission redundant applications post-data migration | Decommission only after confirming all data has been migrated, validated, and archived; maintain read-only access for 90 days post-decommission for audit and compliance purposes | T+91 | 6/1 | 6/9 | Not Started | 0% |  |  | Medium | Finance, IMO | Non-ERP SaaS and application rationalization savings — decommissioning redundant SaaS tools, point solutions, and departmental applications; ERP consolidation savings are captured separately under the Finance workstream ERP consolidation initiative to avoid double-counting | 25 | 10
IT-D100 | Integration Management | Day 100 IT Integration Complete | To Day 100 | IT Workstream Lead | IT Day 100 Integration Gate — confirm all integration tasks complete or formally deferred, synergy baseline locked, BAU transition signed off | Final IMO gate for IT workstream; all remaining open items must be formally accepted as BAU or escalated; this row closes the integration for the IT workstream | T+98 | 6/8 | 6/10 | Not Started | 0% | CP – Day 100 | A workstream that reaches Day 100 with open items must either formally complete them or accept them into BAU with a named owner and timeline; items that are neither closed nor formally accepted become permanent integration debt — they resurface as operational problems without a clear owner or resolution path | High | IMO, All Workstreams

## Day 1 Checklist
IT M&A DAY 1 / WEEK 1 CHECKLIST - Pre-Close (Day 1 Readiness) and Day 1/Week 1 Phases
TODAY'S DATE: T+30
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Milestones
Low | On Track | RAID Log
| Complete | Next 14 Days
Executive Dashboard
☐ Done | Task ID | Phase | Task Description | Assigned To | Risk Level | Timing Anchor | Start | Finish | Status | Milestone
☑ | IT-024 | Pre-Close (Day 1 Readiness) | Assess and remediate critical vulnerability findings | Cybersecurity & Compliance Lead | High | T-44 | 1/17 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-032 | Pre-Close (Day 1 Readiness) | Define cloud strategy and migration roadmap for combined entity | Infrastructure & Cloud Lead | High | T-41 | 1/20 | 2/27 | Complete | Systems Integration Complete
☑ | IT-033 | Pre-Close (Day 1 Readiness) | Assess data center footprint and define consolidation strategy | Infrastructure & Cloud Lead | High | T-40 | 1/21 | 2/25 | Complete | IT Infrastructure Consolidated
☑ | IT-035 | Pre-Close (Day 1 Readiness) | Develop network integration architecture and design for combined entity | Infrastructure & Cloud Lead | High | T-30 | 1/31 | 2/27 | Complete | Systems Integration Complete
☑ | IT-036 | Pre-Close (Day 1 Readiness) | Assist Communications team in drafting answers to Day 1 IT FAQs | IT Integration Coordinator | Medium | T-25 | 2/5 | 2/24 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-038 | Pre-Close (Day 1 Readiness) | Design unified onboarding and offboarding IT process | Applications & Digital Workplace Lead | Medium | T-22 | 2/8 | 2/25 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-039 | Pre-Close (Day 1 Readiness) | Define unified device management (MDM/UEM) strategy | IT Integration Coordinator | Medium | T-20 | 2/10 | 2/23 | Complete | Systems Integration Complete
☑ | IT-040 | Pre-Close (Day 1 Readiness) | Provide input on drafts of M&A Employee Communication Guide (includes talking points, guidance for team conversations) in preparation for Day 1 | IT Integration Coordinator | Medium | T-20 | 2/10 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-042 | Pre-Close (Day 1 Readiness) | Complete device provisioning for all acquired employees | IT Integration Coordinator | High | T-15 | 2/15 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-043 | Pre-Close (Day 1 Readiness) | Conduct Day 1 IT war-room dry run with full team | IT Workstream Lead | High | T-14 | 2/16 | 2/26 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-044 | Pre-Close (Day 1 Readiness) | Set up interim data sharing and reporting infrastructure for Day 1 | Infrastructure & Cloud Lead | Medium | T-13 | 2/17 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-046 | Pre-Close (Day 1 Readiness) | Confirm first-day IT service desk operating model and escalation paths | IT Integration Coordinator | High | T-10 | 2/20 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-049 | Pre-Close (Day 1 Readiness) | Confirm Day 1 network connectivity between acquirer and target offices | Infrastructure & Cloud Lead | High | T-6 | 2/24 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-050 | Pre-Close (Day 1 Readiness) | Stand up IT service desk on Day 1 with combined coverage | Infrastructure & Cloud Lead | High | T-6 | 2/24 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-051 | Pre-Close (Day 1 Readiness) | Establish secure network interconnect between acquirer and target Day 1 | Infrastructure & Cloud Lead | High | T-6 | 2/24 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-053 | Pre-Close (Day 1 Readiness) | Activate IT integration war room and stand up command center for Day 1 | IT Integration Coordinator | High | T-5 | 2/25 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-054 | Pre-Close (Day 1 Readiness) | Enable unified email and calendar access for all staff Day 1 | Infrastructure & Cloud Lead | High | T-4 | 2/26 | 2/27 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-D1 | Pre-Close (Day 1 Readiness) | IT Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | IT Workstream Lead | High | T-3 | 2/27 | 2/27 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-048 | Day 1 / Week 1 | Establish interim DNS trust relationships and directory connectivity for Day 1; full Active Directory and DNS unification to follow in controlled migration by Day 30 | Applications & Digital Workplace Lead | High | Day 1 (Close) | 3/2 | 3/31 | Complete | IT Service Management Framework Established
☑ | IT-052 | Day 1 / Week 1 | Verify all acquired employees have Day 1 Minimum Viable Access — email, HR portal, and primary line-of-business apps; full access provisioning to roll out in waves through Week 1 | Cybersecurity & Compliance Lead | High | Day 1 (Close) | 3/2 | 3/6 | Complete | Day 1 IT Readiness Confirmed
☑ | IT-055 | Day 1 / Week 1 | Brief staff on Day 1 cybersecurity protocols and acceptable use policies | Cybersecurity & Compliance Lead | Medium | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-056 | Day 1 / Week 1 | Send Day 1 all-staff IT welcome communication to combined entity employees | IT Integration Coordinator | Low | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-057 | Day 1 / Week 1 | Confirm all office network connectivity is live and stable at open of business | Infrastructure & Cloud Lead | High | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-058 | Day 1 / Week 1 | Extend SIEM and threat detection to acquired company environment on Day 1 — confirm all endpoints and network segments are covered under unified monitoring | Cybersecurity & Compliance Lead | High | Day 1 (Close) | 3/2 | 3/2 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-059 | Day 1 / Week 1 | Validate all IT controls are active in combined environment | Cybersecurity & Compliance Lead | High | Day 1 (Close) | 3/2 | 3/6 | Complete | Day 1 / Week 1 IT Integration Complete
☑ | IT-060 | Day 1 / Week 1 | Deploy unified collaboration platform to all combined staff — confirm access, licensing, and data migration from legacy tools before decommissioning | Applications & Digital Workplace Lead | Medium | Day 1 (Close) | 3/2 | 3/6 | Complete | Email & Collaboration Unified
☑ | IT-061 | Day 1 / Week 1 | Finalize and publish unified IT acceptable use policy | Cybersecurity & Compliance Lead | Low | Day 1 (Close) | 3/2 | 3/6 | Complete | Compliance Program Integrated
☑ | IT-062 | Day 1 / Week 1 | Conduct end-user IT orientation sessions for acquired employees | IT Integration Coordinator | Low | Day 1 (Close) | 3/2 | 3/6 | Complete | Day 1 / Week 1 IT Integration Complete
☐ | IT-047 | Day 1 / Week 1 | Assess server and storage infrastructure and develop rationalization roadmap — ensure Day 1 stability; full rationalization delivered in phases by Day 60 | Infrastructure & Cloud Lead | Medium | Day 1 (Close) | 3/2 | 4/30 | On Track | Systems Integration Complete

## Milestones
INFORMATION TECHNOLOGY M&A MILESTONES
TODAY'S DATE: T+30
Status | Links
Not Started | Integration Plan
Delayed | Day 1 Checklist
On Track | RAID Log
Complete | Next 14 Days
Executive Dashboard
Milestone ID | Category | Phase | Assigned To | Milestone | Timing Anchor | Finish | Status | Critical Path
MS-001 | Governance & Planning | Pre-Close | IT Workstream Lead | IT Lead Appointed | T-51 | 1/10 | Complete | CP – Close
MS-002 | Governance & Planning | Pre-Close | Cybersecurity & Compliance Lead | IT Integration Governance Established | T-42 | 1/19 | Complete
MS-003 | Governance & Planning | Pre-Close | IT Workstream Lead | IT Charter Approved | T-42 | 1/19 | Complete
MS-004 | Due Diligence | Pre-Close | IT Workstream Lead | IT Due Diligence Complete | T-3 | 2/27 | Complete
MS-005 | IT Infrastructure | Pre-Close (Day 1 Readiness) | Cybersecurity & Compliance Lead | Day 1 IT Readiness Confirmed | T-3 | 2/27 | Complete | CP – Day 1 Readiness
MS-006 | Synergy Tracking & Realization | Pre-Close | IT Integration Coordinator | Synergy Tracking Active | T-3 | 2/27 | Complete
MS-007 | IT Infrastructure | Day 1 / Week 1 | Infrastructure & Cloud Lead | Day 1 / Week 1 IT Integration Complete | T+4 | 3/6 | Complete | CP – Day 1
MS-008 | Systems & Technology | Day 1 / Week 1 | Applications & Digital Workplace Lead | Email & Collaboration Unified | T+4 | 3/6 | Complete
MS-009 | Governance & Planning | To Day 100 | IT Workstream Lead | IT Integration Plan Locked | T+29 | 3/31 | Complete
MS-010 | Integration Management | To Day 100 | IT Integration Coordinator | 30-Day IT Integration Review Complete | T+36 | 4/7 | On Track
MS-011 | Systems & Technology | To Day 100 | Applications & Digital Workplace Lead | IT Service Management Framework Established | T+59 | 4/30 | Not Started
MS-012 | IT Infrastructure | To Day 100 | Infrastructure & Cloud Lead | IT Infrastructure Consolidated | T+90 | 5/31 | Not Started | CP – Day 100
MS-013 | IT Infrastructure | To Day 100 | Cybersecurity & Compliance Lead | Compliance Program Integrated | T+90 | 5/31 | Not Started
MS-014 | Synergy Tracking & Realization | To Day 100 | IT Integration Coordinator | Synergy Realization Report Phase 1 Complete | T+90 | 5/31 | Not Started
MS-015 | Systems & Technology | To Day 100 | Applications & Digital Workplace Lead | Systems Integration Complete | T+99 | 6/9 | Not Started | CP – Day 100
MS-016 | Integration Management | To Day 100 | IT Integration Coordinator | Day 100 IT Integration Complete | T+100 | 6/10 | Not Started | CP – Day 100

## RAID Log
IT M&A RAID LOG (RAID = Risks, Assumptions, Issues, Dependencies)
TODAY'S DATE: T+30
RAID Type | Status | Links
Risk | Open | Integration Plan
Issue | Closed | Day 1 Checklist
Dependency | Active | Milestones
Assumption | Validated | Next 14 Days
Executive Dashboard
RAID Type | RAID ID | Related Task ID | Milestone | Owner | Task Description | Issues/Blockers | Status | Mitigation/Action | Timing Anchor | Finish
Risk | RAID-001 | IT-001 | IT Lead Appointed | IT Workstream Lead | Identify IT integration workstream lead and determine members of the IT integration team | IT workstream lead must be identified and available before integration kickoff; without a named IT Lead, there is no accountable owner for systems assessment, Day 1 readiness, or the ERP and HRIS integration workstreams — every IT integration dependency stalls without this role in seat | Closed | Escalate workstream lead appointment to CIO immediately; role must be named and capacity confirmed before integration kickoff; if filled from within the IT organization, secure backfill for BAU responsibilities to prevent the integration becoming a secondary priority from day one | T-51 | 1/10
Assumption | RAID-002 | IT-001 | IT Lead Appointed | IT Workstream Lead | Key acquired company IT personnel — including IT leadership, systems administrators, and critical application owners — will remain available and cooperative through the integration period and will not depart before or immediately after close | If the acquired company's IT leadership or critical systems administrators depart at or near close, the combined entity loses the primary source of institutional knowledge on legacy systems, undocumented configurations, and vendor relationships that are not fully captured in documentation; every integration task that requires access to, migration of, or decommissioning of acquired company systems depends on this assumption; departure of key IT staff would significantly slow the Day 1 Readiness tasks and the To Day 100 systems integration workstreams | Active | IT Workstream Lead to identify the top 5 critical IT personnel at the acquired company and confirm retention status before close; initiate knowledge transfer sessions for each critical role beginning at T-30; document all undocumented configurations, access credentials, and vendor contacts in a centralized IT knowledge base before close; if key personnel cannot be retained, engage a systems integrator to provide bridging coverage for their functional areas | T-51 | 1/10
Risk | RAID-003 | IT-002 | IT Integration Governance Established | Cybersecurity & Compliance Lead | Review data privacy and confidentiality protocols for pre-close sharing | A Sales team member who contacts a named customer or accesses customer pricing data before close — using information from the data room without understanding the clean room restrictions — exposes the deal to gun-jumping allegations; the risk is not the intent but the document trail, which regulators can cite regardless of whether harm was intended | Closed | Issue a written clean team protocol to every IT team member before any pre-close data sharing begins; Legal to specify exactly what data can be reviewed, by whom, and under what conditions; prohibit any IT team member from using clean room data to contact customers, inform pricing decisions, or brief the sales team before close | T-49 | 1/12
Assumption | RAID-004 | IT-005 | IT Integration Governance Established | IT Workstream Lead | Acquired company IT infrastructure is stable, adequately documented, and free of material undisclosed technical debt — it is assumed that pre-close systems assessments have surfaced all end-of-life systems, unsupported software, and known infrastructure gaps, and that no material issues will emerge post-close that significantly expand the integration scope beyond what was planned | This assumption underpins the integration timeline and budget — if significant undisclosed technical debt, unsupported operating systems, or undocumented shadow IT environments are discovered post-close, the integration scope, cost, and timeline will require material revision; every downstream integration task that depends on the systems assessment (IT-005 through IT-020) is at risk if this assumption is violated | Active | IT Workstream Lead to conduct a rapid infrastructure validation within the first 14 days post-close to confirm all systems are as represented in due diligence; any gap between actual infrastructure and the assessed state to be logged in the RAID register and escalated to the IMO Leader within 48 hours of discovery; Finance to be notified immediately if the gap has budget implications | T-48 | 1/13
Risk | RAID-005 | IT-009 | IT Due Diligence Complete | Infrastructure & Cloud Lead | Assess network topology, connectivity, and bandwidth capacity | If the target restricts network topology data in the clean room, IT will be designing Day 1 connectivity based on assumptions rather than engineering data — require Legal to explicitly scope network architecture documentation into the data room access agreement before signing | Closed | Negotiate clean room access to network topology data as early as possible; if the target refuses, escalate to deal counsel to clarify what infrastructure data is permissible under the LOI; build Day 1 network architecture from the public-facing information available and plan a rapid validation exercise within the first 48 hours of close | T-38 | 1/23
Risk | RAID-006 | IT-011 | IT Due Diligence Complete | Applications & Digital Workplace Lead | Inventory all enterprise applications and SaaS subscriptions | An incomplete SaaS inventory means the combined entity will continue paying for duplicate subscriptions it cannot see; require the target's procurement team to provide a complete software spend report with contract terms as a condition of data room access, not as a follow-up request | Closed | Require the target to provide a complete SaaS inventory as a closing condition, certified by their CTO or IT lead; cross-reference against AP invoices and SSO audit logs after close to identify shadow IT; prioritize duplicate SaaS discovery in the first 30 days as it is the fastest synergy to realize | T-31 | 1/30
Risk | RAID-007 | IT-014 | IT Due Diligence Complete | IT Integration Coordinator | Review data architecture, databases, and data governance maturity | Undocumented data flows become a data migration failure when the integration team discovers mid-migration that a critical downstream report relies on a manual feed no one knew existed; require target IT to attest in writing that the data architecture review is complete before DD sign-off | Closed | Require target IT to provide an entity-relationship diagram and data dictionary for all production systems before close; escalate any refusal to deal counsel; use the data architecture assessment to build the migration sequencing plan — systems with undocumented dependencies must be migrated last | T-31 | 1/30
Assumption | RAID-008 | IT-010 | IT Due Diligence Complete | IT Workstream Lead | Neither entity will undertake material ERP upgrades, platform migrations, major infrastructure changes, or additional acquisitions during the 100-day integration window that would conflict with, delay, or require rework of the IT integration workstreams | The 100-day IT integration plan assumes a stable BAU technology environment in both entities; if either entity launches a major ERP upgrade, cloud migration, or new acquisition during the integration window, the IT integration team will be resource-constrained and the integration timeline will slip; this is a particularly high risk for the acquirer entity, where BAU IT project backlogs may have been deprioritized in anticipation of the deal closing and may now re-enter the queue simultaneously with integration work | Active | IT Workstream Lead to confirm with the CIO that all major IT projects in both entities are either paused, descoped, or resource-fenced for the 100-day integration window; any new project request with IT resource dependency to be reviewed by the IT Workstream Lead before approval during the integration period; if a business-critical BAU project cannot be deferred, IT Workstream Lead to formally assess the impact on integration capacity and escalate to IMO Leader and CIO | T-31 | 1/30
Dependency | RAID-009 | IT-030 | IT Due Diligence Complete | Cybersecurity & Compliance Lead | Review identity and access management (IAM) architecture | The IAM incompatibility that is hardest to fix is MFA policy — if the target uses SMS-based MFA and the acquirer requires hardware tokens or authenticator apps, there is no fast migration path; every day this is unresolved after Day 1 is a day the target's users operate at a lower security standard inside the combined perimeter | Closed | Map the IAM architecture comparison as the first technical output of the integration — complete before close even if it requires additional clean room access; resolve MFA policy conflicts by adopting the more stringent standard; do not permit any SSO federation before the IAM policies are reconciled | T-29 | 2/1
Risk | RAID-010 | IT-016 | IT Due Diligence Complete | Cybersecurity & Compliance Lead | Review data privacy program (GDPR, CCPA, HIPAA) and compliance gaps | Compliance gaps inherited at close cannot be disclaimed after the fact; if the target has an active HIPAA or GDPR deficiency, the acquirer must either remediate before close, escrow funds for post-close remediation, or factor the penalty exposure into the purchase price — this is a deal-term issue, not just an IT task | Closed | Complete a gap-to-remediation analysis for every compliance deficiency identified before close; assign a named owner and deadline for each gap; do not assume the acquirer's compliance posture covers the target — the combined entity's compliance profile is the union of both, not the acquirer's alone | T-17 | 2/13
Risk | RAID-011 | IT-019 | IT Due Diligence Complete | Cybersecurity & Compliance Lead | Review IT compliance certifications (SOC 2, ISO 27001, PCI-DSS) | Customers with contractual requirements for SOC 2 compliance will ask whether the combined entity's certification covers them; if the answer is unknown at Day 1, those customers will escalate — confirm the new audit scope with the certifying auditor before close and communicate the timeline to affected customers before the press release goes out | Closed | Obtain copies of all SOC 2 reports and penetration test results before close; assess the gap between the target's current certification scope and what customers contractually require; develop a combined certification roadmap within the first 30 days and communicate timeline to customer-facing teams | T-17 | 2/13
Risk | RAID-012 | IT-025 | IT Due Diligence Complete | IT Integration Coordinator | Review disaster recovery and business continuity capabilities | An RTO gap is not a theoretical risk — it means the combined entity cannot recover within its contractual SLA if a critical system fails in the first 30 days; identify the specific systems where target's BCP falls short and require a written interim mitigation plan from IT leadership before Day 1, not after | Closed | Test the target's DR capability against the acquirer's RTO/RPO standards before close, not after; if the target cannot meet the combined entity's recovery requirements, build a remediation plan with a hard deadline before the first mission-critical workload is run on target infrastructure | T-9 | 2/21
Risk | RAID-013 | IT-017 | IT Due Diligence Complete | IT Integration Coordinator | Review IT vendor contracts, licenses, and software agreements | Vendor change-of-control clauses are triggered at close, not when IT discovers them; if these agreements are not mapped before signing, the combined entity may face license suspension or emergency renegotiation from a position of weakness on Day 1 — Legal must complete the vendor contract review before the SPA is executed | Closed | Require the target to deliver a complete vendor contract schedule with change-of-control provisions highlighted before close; initiate consent outreach at least 30 days before close for any contract that requires counterparty approval; do not close without knowing which vendors can terminate on change-of-control | T-5 | 2/25
Risk | RAID-014 | IT-033 | IT Infrastructure Consolidated | Infrastructure & Cloud Lead | Assess data center footprint and define consolidation strategy | A synergy number built on incomplete facility cost data — missing lease exit penalties, decommission costs, or headcount transfer costs — will be revised downward when Finance runs due diligence on the consolidation plan; obtain fully-loaded facility cost data from both real estate and Finance teams before publishing any consolidation synergy estimate to leadership | Closed | Obtain actual facility cost data — lease rates, decommissioning penalties, power costs, exit terms — before finalizing the data center synergy number; build three scenarios: keep, migrate, co-locate; do not commit to a facility exit timeline until the migration sequence and application dependencies are fully mapped | T-5 | 2/25
Risk | RAID-015 | IT-012 | IT Due Diligence Complete | Applications & Digital Workplace Lead | Assess core business systems compatibility | The highest-consequence incompatibility is authentication — if the two companies cannot federate identity on Day 1, every employee login fails; require IT to complete a protocol-level compatibility test (not just a platform inventory) and document a Day 1 workaround for any gap found before the go/no-go review | Closed | Prioritize authentication compatibility as the first systems assessment — federated SSO or LDAP directory incompatibility is the longest lead-time item to resolve; escalate any authentication architecture conflict to the IT Workstream Lead immediately | T-4 | 2/26
Risk | RAID-016 | IT-043 | Day 1 IT Readiness Confirmed | IT Workstream Lead | Conduct Day 1 IT war-room dry run with full team | A dry run that only tests individual components in sequence does not surface the failures that happen when all systems run simultaneously under combined-entity load; the single most valuable thing the dry run can do is generate a live ticket backlog — if the service desk cannot clear that backlog within two hours during the dry run, it cannot probably clear it on Day 1 either | Closed | Conduct the dry run as a full end-to-end simulation covering simultaneous failures — network latency, authentication errors, service desk overload, and application outages occurring at the same time; record every decision and escalation path exercised; use the dry run output to update the war room runbook before Day 1 | T-4 | 2/26
Risk | RAID-017 | IT-020 | Systems Integration Complete | Applications & Digital Workplace Lead | Develop application and SaaS rationalization strategy and portfolio roadmap | The rationalization strategy is only as good as the inventory it is built on; if application inventory is delayed or incomplete, every 'retire' decision in this strategy risks decommissioning a system that is still in active use — do not present this strategy to leadership until the full inventory has been independently verified | Closed | Validate the application inventory against SSO logs, AP invoices, and engineering asset registers before finalizing the rationalization strategy; categorize every application as Keep, Replace, Retire, or Migrate before close; assign a named owner to every application in the portfolio before rationalization decisions are locked | T-3 | 2/27
Risk | RAID-018 | IT-024 | Day 1 IT Readiness Confirmed | Cybersecurity & Compliance Lead | Assess and remediate critical vulnerability findings | The acquirer cannot assert it was unaware of inherited vulnerabilities after close; any CVSS 9.0+ finding identified in diligence that is not remediated before Day 1 must be formally accepted with a documented risk treatment plan signed by the CISO — undocumented acceptance is not acceptance | Closed | Treat every critical or high vulnerability inherited at close as an immediate remediation requirement; assign a named owner and a 30-day deadline for every CVSS 7.0+ finding; brief the Board on inherited vulnerability exposure at the first post-close board meeting; confirm cyber insurance covers combined entity perimeter from Day 1 | T-3 | 2/27
Risk | RAID-019 | IT-032 | Systems Integration Complete | Infrastructure & Cloud Lead | Define cloud strategy and migration roadmap for combined entity | The cloud architecture decision is one of the few IT decisions that cannot be reversed cheaply — committing to a cloud provider or multi-cloud model without a migration cost model means the combined entity will discover the true cost only after vendor contracts are signed; require Finance sign-off on the TCO model before any cloud architecture is committed | Closed | Present the cloud architecture recommendation — including a 3-year TCO model covering migration costs, licensing, egress fees, and ongoing operational costs for each viable option — to the CIO and CFO before any cloud vendor is selected; require Finance sign-off on the TCO model before the architecture decision is locked; do not allow any workload migration to begin until the cloud strategy is approved; once committed, assign a named cloud architect to own the migration roadmap with a formal quarterly review cadence through Day 100 | T-3 | 2/27
Risk | RAID-020 | IT-035 | Systems Integration Complete | Infrastructure & Cloud Lead | Develop network integration architecture and design for combined entity | Network architecture that has not been reviewed by both legacy network teams will have blind spots; require the target's network architect to formally review and sign off on the combined design before it is presented to the steering committee — an unreviewed design that fails on Day 1 is a much larger problem than a delayed design | Closed | Require both legacy network teams to review the integration architecture design jointly before Day 1; schedule a joint technical review session with network leads from both companies at least 10 days before close; document all known blind spots and assign a monitoring plan for each | T-3 | 2/27
Risk | RAID-021 | IT-037 | IT Due Diligence Complete | IT Integration Coordinator | Review HRIS and payroll systems compatibility | A HRIS compatibility gap that is discovered post-close and cannot be bridged with a parallel-run means employees may be on two separate payroll systems indefinitely; the cost and timeline of HRIS integration must be confirmed before close, not after, because it directly affects the benefit harmonization timeline that HR is planning around | Closed | Test the HRIS integration in a sandbox environment before any production payroll data is touched; confirm the parallel-run period covers at least two full payroll cycles; escalate any data mapping gap to HR and Finance immediately | T-3 | 2/27
Risk | RAID-022 | IT-042 | Day 1 IT Readiness Confirmed | IT Integration Coordinator | Complete device provisioning for all acquired employees | Device provisioning that relies on shipping hardware to employee home addresses introduces customs, carrier, and address-accuracy risks that can delay delivery by 1–2 weeks beyond the expected date; build the provisioning schedule from confirmed ship dates, not order dates | Closed | Begin device provisioning at least 2 weeks before close for remote and international employees; confirm shipping addresses for every acquired employee before ordering hardware; assign an IT technician to each major office location for Day 1 on-site support; maintain a 10% hardware buffer for provisioning failures | T-3 | 2/27
Risk | RAID-023 | IT-046 | Day 1 IT Readiness Confirmed | IT Integration Coordinator | Confirm first-day IT service desk operating model and escalation paths | A service desk that is not staffed before the first employee's laptop fails on Day 1 cannot be stood up fast enough to prevent the backlog from compounding; confirm staffing levels, escalation contacts, and ticket routing at least one week before Day 1 — any gap found in that confirmation window still has time to be fixed | Closed | Confirm service desk staffing levels, shift coverage, and escalation paths at least 5 business days before Day 1; conduct a load test simulation using historical ticket volumes from both entities; publish the service desk number and hours to all acquired employees before the Day 1 all-staff communication goes out | T-3 | 2/27
Risk | RAID-024 | IT-049 | Day 1 IT Readiness Confirmed | Infrastructure & Cloud Lead | Confirm Day 1 network connectivity between acquirer and target offices | Testing connectivity at off-peak hours on the day before Day 1 does not validate performance under the peak load of both organizations authenticating simultaneously at 8 AM; run the full-load connectivity test at least one week before Day 1 so there is time to add bandwidth or adjust routing before the real deadline | Closed | Test network connectivity under realistic load — concurrent VPN sessions, video calls, file transfers — at least 48 hours before Day 1; identify the 5 applications most sensitive to latency and test each individually; build explicit failover paths for the top 3 connectivity failure scenarios | T-3 | 2/27
Risk | RAID-025 | IT-050 | Day 1 IT Readiness Confirmed | Infrastructure & Cloud Lead | Stand up IT service desk on Day 1 with combined coverage | Tier 1 help desk agents who have been trained on only one entity's environment will escalate every cross-environment incident to Tier 2, saturating senior engineers with tickets that should be resolvable at Tier 1; run cross-environment training sessions for all help desk staff in the week before Day 1 and validate coverage before the service desk goes live | Closed | Staff the combined service desk with agents trained on both environments before Day 1 — any agent who can only support one entity's environment will be a bottleneck; pre-populate the knowledge base with the top 50 expected Day 1 questions from acquired employees; publish the service desk contact to all acquired employees 24 hours before close | T-3 | 2/27
Risk | RAID-026 | IT-051 | Day 1 IT Readiness Confirmed | Infrastructure & Cloud Lead | Establish secure network interconnect between acquirer and target Day 1 | A network interconnect designed for average daily traffic will degrade under the spike of two organizations communicating across a newly connected link for the first time; test the interconnect at 150% of projected peak load and confirm failover actually routes traffic before Day 1, not after the primary link saturates | Closed | Size the network interconnect for peak load, not average load — Day 1 generates 3-5x normal cross-entity traffic as employees access each other's systems for the first time; build bandwidth monitoring alerts that fire at 70% utilization so IT can act before the link is saturated | T-3 | 2/27
Risk | RAID-027 | IT-053 | Day 1 IT Readiness Confirmed | IT Integration Coordinator | Activate IT integration war room and stand up command center for Day 1 | A war room that is stood up on the morning of Day 1 without prior rehearsal will lose 30–60 minutes to logistics (who has the bridge line, who can see the dashboard, who approves emergency changes) while live incidents queue up; the war room command structure must be rehearsed in the dry run, not improvised on Day 1 | Closed | Activate the war room 24 hours before Day 1, not the morning of; confirm all communication channels, escalation paths, and access to monitoring dashboards are operational before the war room goes live; assign a war room commander with authority to make decisions without further approval during the Day 1 window | T-3 | 2/27
Risk | RAID-028 | IT-054 | Day 1 / Week 1 IT Integration Complete | Infrastructure & Cloud Lead | Enable unified email and calendar access for all staff Day 1 | Email provisioning failures are not recoverable quickly because they involve directory services, MX records, and spam filtering — all of which have propagation delays measured in hours, not minutes; confirm that provisioning for all acquired users has completed at least 24 hours before Day 1 so that any failures have time to be resolved before employees arrive | Closed | Test email provisioning end-to-end for at least 10% of acquired employees 48 hours before Day 1; confirm directory synchronization is complete before any email provisioning is activated; have a manual provisioning procedure ready for any account that fails automated provisioning; monitor mail queue depth continuously on Day 1 | T-3 | 2/27
Risk | RAID-029 | IT-D1 | Day 1 IT Readiness Confirmed | IT Workstream Lead | IT Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | Closed | Conduct the IT Day 1 Readiness Gate with CIO and all IT workstream leads 48 hours before close; any incomplete task requires an immediate escalation decision — proceed with a compensating control, delay the specific activity, or pause close; document every gate decision with sign-offs and a named owner for any open item | T-3 | 2/27
Risk | RAID-030 | IT-057 | Day 1 / Week 1 IT Integration Complete | Infrastructure & Cloud Lead | Confirm all office network connectivity is live and stable at open of business | Remote offices are the gap in almost every Day 1 IT test plan because they are assumed to inherit the fix applied at headquarters; assign a named IT contact at every acquired office location with instructions to confirm connectivity at 7 AM on Day 1 and escalate immediately if anything is down | Closed | Test connectivity at every remote office, not just headquarters — remote office failures are the most common Day 1 surprise; confirm ISP circuit status and on-site IT contact at each location; have a 4G/LTE failover option ready and pre-tested for any location without redundant connectivity | Day 1 (Close) | 3/2
Risk | RAID-031 | IT-058 | Day 1 / Week 1 IT Integration Complete | Cybersecurity & Compliance Lead | Extend SIEM and threat detection to acquired company environment on Day 1 — confirm all endpoints and network segments are covered under unified monitoring | A threat actor who knows both companies are in an integration transition will target the newly connected link between environments specifically because monitoring is likely to have gaps in the first 24 hours; SIEM coverage of the target environment must be confirmed active, not just configured, before any network interconnect goes live | Closed | Extend SIEM coverage to the target environment to establish a threat baseline; brief the SOC on the combined entity perimeter and expected network traffic patterns; define alert thresholds appropriate for Day 1 traffic volumes — normal thresholds will generate false positives at scale | Day 1 (Close) | 3/2
Issue | RAID-032 | IT-057 | Day 1 / Week 1 IT Integration Complete | Infrastructure & Cloud Lead | Network connectivity not fully stable at open of business on Day 1 — acquired company office locations in two regions are reporting intermittent VPN failures and latency spikes; combined entity employees at those sites cannot reliably access cloud applications, shared drives, or the collaboration platform as of 7 AM on close day | Employees who cannot connect to core systems on Day 1 cannot access email, HR portals, or the IT welcome communication that was scheduled to land at 8 AM; VPN instability in acquired locations means those employees are effectively dark on the most visible day of the integration — this is the exact scenario that creates lasting negative impressions about the acquiring company's IT capability; if the issue persists past the all-hands meeting, acquired employees will have no reliable access to the systems they are being told will make them more productive | Closed | IT Workstream Lead has been notified and network operations team is investigating in real time — a war room bridge has been opened with the network and infrastructure team and acquired company IT contacts; all acquired-company employees at affected sites have been redirected to mobile hotspot access as an interim measure until VPN is restored; IT Workstream Lead to provide status update to IMO Leader every 30 minutes until resolved; if not resolved within 2 hours, escalate to CIO for vendor emergency support engagement; IT-057 close-out will not be marked complete until written confirmation of full connectivity stability is received from all affected locations | Day 1 (Close) | 3/2
Risk | RAID-033 | IT-052 | Day 1 IT Readiness Confirmed | Cybersecurity & Compliance Lead | Verify all acquired employees have Day 1 Minimum Viable Access — email, HR portal, and primary line-of-business apps; full access provisioning to roll out in waves through Week 1 | A user who cannot authenticate on Day 1 will call the help desk, which will already be handling 3–5x normal volume; the authentication failure rate from the dry run is the most reliable predictor of Day 1 service desk load — treat any dry run failure rate above 2% as a blocker requiring executive escalation | Closed | Test authentication end-to-end for a representative sample of acquired employees in every geography at least 24 hours before Day 1; assign a dedicated authentication support queue separate from the main help desk; have a break-glass access procedure ready for Day 1 authentication failures that cannot be resolved within 30 minutes | T+4 | 3/6
Risk | RAID-034 | IT-059 | Day 1 / Week 1 IT Integration Complete | Cybersecurity & Compliance Lead | Validate all IT controls are active in combined environment | IT controls that pass individually may fail when tested in the combined environment due to permission inheritance issues, group policy conflicts, or role assignment overlaps; require the CISO to run a combined-environment controls test — not just an attestation. | Closed | Test controls in the combined environment, not individually — the most common control failure occurs at integration points between the two environments; assign a control validation checklist to the Cybersecurity Lead with a sign-off requirement before Day 1 is declared ready | T+4 | 3/6
Risk | RAID-035 | IT-075 | Compliance Program Integrated | Infrastructure & Cloud Lead | Test disaster recovery failover for mission-critical systems | A DR test that passes at single-entity load provides no useful information about combined-entity behavior; the test only validates what it tests, and a mission-critical system that handles twice the transaction volume post-merger may behave very differently under failover conditions — require the test to run at combined-entity peak load or classify the result as untested | Closed | Test DR under combined-entity load using the merged application dependency map, not individual system tests; confirm that the RTO/RPO for the combined entity meets contractual SLA obligations for all customer contracts; present DR test results to the CIO before any production workload is migrated to consolidated infrastructure | T+22 | 3/24
Dependency | RAID-036 | IT-048 | IT Service Management Framework Established | Applications & Digital Workplace Lead | Establish interim DNS trust relationships and directory connectivity for Day 1; full Active Directory and DNS unification to follow in controlled migration by Day 30 | DNS is the dependency that everything else depends on; a DNS failure does not just break one application — it breaks authentication, email, internal name resolution, and any service discovery that relies on DNS; do not proceed with any production DNS cutover without a tested, documented rollback procedure that can be executed in under 15 minutes | Closed | Build and validate a rollback plan for DNS changes that can be executed in under 15 minutes; conduct DNS validation as early as possible | T+29 | 3/31
Risk | RAID-037 | IT-041 | Systems Integration Complete | Infrastructure & Cloud Lead | Define combined entity data governance framework and policies | Data ownership disputes between Finance, Sales, HR, and IT are the most common reason data governance frameworks stall; schedule a cross-functional data ownership workshop within the first 30 days and escalate any unresolved ownership conflict to the CFO — frameworks without resolved ownership are shelf ware | Closed | Establish data ownership for every production data domain before any cross-entity data sharing begins; use a formal RACI for data governance decisions that includes Finance, Sales, HR, and IT; do not permit any data pipeline to be built for production use before ownership and quality standards are agreed | T+29 | 3/31
Dependency | RAID-038 | IT-063 | Systems Integration Complete | IT Integration Coordinator | Assess ERP landscape across both entities and define combined entity ERP architecture — evaluate consolidation vs. migration options before committing to approach | The ERP decision determines every subsequent timeline in the applications integration; a decision that slips from 30 days to 60 days post-close does not delay the ERP migration by 30 days — it delays every downstream task that depends on it, typically extending the total integration timeline by 3–6 months for each month of delay | Closed | Make the ERP architecture decision before Day 30 and communicate it to Finance, HR, and the IMO immediately; delay in the ERP decision delays every downstream application timeline; engage a systems integrator at close if a full ERP migration is selected | T+29 | 3/31
Risk | RAID-039 | IT-069 | Compliance Program Integrated | Cybersecurity & Compliance Lead | Review and rationalize privileged access accounts across combined entity | Privileged access rationalization is time-sensitive because every day a former target-company administrator retains elevated rights is a day they can access systems they no longer have a business reason to access; set a 30-day post-close deadline for full rationalization and treat any account that cannot be certified as active and necessary within that window as immediately suspended | Closed | Every day a former target-company administrator retains elevated access to production systems is an unmitigated insider threat risk; require dual approval for any privileged access extension beyond Day 7; report access rationalization progress to the CISO weekly | T+29 | 3/31
Issue | RAID-040 | IT-064 | Systems Integration Complete | Applications & Digital Workplace Lead | Data quality assessment at Day 30 has surfaced critical gaps in acquired company master data — customer records contain an estimated 23% duplicate rate, product codes are inconsistently formatted across four legacy systems, and financial data mappings between the acquired ERP and the combined entity ERP of record contain 14 unresolved field-level conflicts that will produce incorrect consolidation reports if not remediated before the first combined financial close | A 23% customer record duplicate rate in the CRM means roughly 1 in 4 customer outreach actions post-close will be redundant, erroneous, or potentially sent to the wrong contact — this directly undermines the cross-sell synergy model which assumes clean customer data as its foundation; the 14 ERP field conflicts are the more urgent issue: if they are not resolved before the first combined financial close, the consolidated P&L will contain errors that require manual correction and may require restatement; the IT team identified these issues during IT-064 but they were not surfaced in pre-close due diligence, which means the scope of the CRM and ERP integration workstreams must now be expanded | Open | Data & Analytics Lead to produce a full remediation plan for master data quality by T+37, prioritizing the 14 ERP field conflicts as P1 given the financial close dependency; CRM duplicate remediation to be scoped into the IT-074 CRM data migration workstream with a revised finish date if needed; Finance to be briefed on ERP field conflicts within 48 hours and to confirm whether the first combined financial close can proceed with manual adjustments or whether the close timeline must be extended; IT Workstream Lead to add master data quality as a standing agenda item on the weekly IT steering committee until all P1 items are resolved | T+29 | 3/31
Risk | RAID-041 | IT-074 | Systems Integration Complete | Applications & Digital Workplace Lead | Map CRM data fields and define data migration rules | A field mapping that looks correct in the staging environment may produce different results in production due to data type mismatches, null value handling, or picklist value differences; require a production-equivalent validation run using a representative sample of real records — not test data — before the field mapping is approved as final | Closed | Run a production-equivalent data migration test before any live CRM data is touched; validate deduplication rules against a statistically significant sample of real records, not test data; require Sales leadership to sign off on the deduplication methodology before migration begins — Sales operations disputes are the most common source of CRM migration rework | T+30 | 4/1
Risk | RAID-042 | IT-D30 | 30-Day IT Integration Review Complete | IT Workstream Lead | IT Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | If the Day 30 check reveals open tasks, unresolved blockers, or synergy owners not yet active, the integration team has 70 days to correct course — but the Day 30 review must force honest status reporting; teams that report green when yellow or red create hidden risk that surfaces at Day 100 when it is too late to recover | Open | Conduct the Day 30 check as a formal meeting with CIO and all IT workstream leads; require each lead to provide a written RAG status update; any item rated Red requires a named owner and resolution deadline agreed at the meeting; present synergy tracking data at the Day 30 check — if savings are behind plan, develop a recovery plan before Day 60 | T+32 | 4/3
Risk | RAID-043 | IT-067 | Systems Integration Complete | IT Integration Coordinator | Build revenue bridge and reporting data pipeline for combined entity | Finance's first earnings call after close will require combined revenue data; if the data pipeline is not built and validated against both legacy systems before that call, the CFO will either miss the deadline or present unvalidated numbers — neither is acceptable; | Open | Build and test the revenue data pipeline in a staging environment before the first close; confirm with Finance exactly what data fields are required for the earnings report; establish a daily data quality check that Finance can run independently to catch pipeline errors before the reporting deadline | T+44 | 4/15
Risk | RAID-044 | IT-071 | Systems Integration Complete | IT Integration Coordinator | Integrate HRIS and migrate employee data to unified HR platform | An HRIS migration that completes with a 98% record accuracy rate sounds acceptable until you realize 2% of 500 employees is 10 people with incorrect payroll data; require 100% field-level validation on pay rate, tax withholding, direct deposit routing, and benefit elections before any migration is declared complete | Open | Require a field-by-field HRIS validation before any employee data is used for payroll, benefits, or reporting; run at least two parallel payroll cycles before decommissioning any legacy HRIS; maintain legacy HRIS in read-only mode for 60 days after migration for audit reference | T+59 | 4/30
Risk | RAID-045 | IT-081 | Systems Integration Complete | Applications & Digital Workplace Lead | Migrate acquired-company accounts into combined entity CRM of record and validate data integrity | CRM records that are migrated in the wrong order — active pipeline before historical data — create a window where reps are working in the new system without the context of prior customer interactions; the migration order is not a technical preference, it is a business requirement that Sales Operations must confirm in writing before migration begins | Open | Migrate CRM accounts in the correct sequence: active pipeline records first, then historical data, then archived accounts; validate each batch with a sample check before proceeding to the next; assign a Sales Operations manager as the CRM migration owner with authority to pause migration if data quality falls below the agreed threshold | T+59 | 4/30
Risk | RAID-046 | IT-086 | Systems Integration Complete | Applications & Digital Workplace Lead | Migrate chart of accounts and financial master data to ERP | COA migration errors are not just accounting problems — they generate incorrect financial statements that may require restatement; the COA mapping must be reviewed and signed off by both the Finance workstream lead and the external auditor before any financial data is moved, not after migration is complete | Open | Complete a chart of accounts reconciliation before any financial data is migrated; require the Controller to sign off on the COA mapping before migration begins; run a parallel close in both systems after migration to validate that combined financials match expectations | T+90 | 5/31
Risk | RAID-047 | IT-087 | Systems Integration Complete | Applications & Digital Workplace Lead | Complete ERP full integration or migration to single platform | ERP migrations that are declared complete before the first month-end close frequently reveal data integrity problems that surface only when the accounting team runs reconciliations; the ERP migration should not be signed off until it has successfully processed at least one complete close cycle, including journal entries, allocations, and financial statement generation | Open | Conduct the first full month-end close in the new ERP before declaring the migration complete — not a parallel run, a live close; identify and resolve all ERP issues within the first close cycle | T+90 | 5/31
Risk | RAID-048 | IT-088 | Systems Integration Complete | Infrastructure & Cloud Lead | Complete product and customer data integration and deduplication | Without agreed deduplication rules, IT will make arbitrary choices about which record survives a conflict; those choices will produce incorrect customer master data that Sales, Finance, and Marketing will discover over the following months through bad pipeline reports, duplicate invoices, and misdirected outreach — business rules must be defined and approved before a single record is touched | Open | Agree deduplication rules with Finance, Sales, and Marketing before any migration begins; document every data quality exception discovered during deduplication with the business owner's approval; build a post-migration data quality scorecard and review it with the CIO before the combined entity data is used for any customer-facing purpose | T+90 | 5/31
Risk | RAID-049 | IT-091 | IT Infrastructure Consolidated | Infrastructure & Cloud Lead | Execute data center migration — migrate all workloads to consolidated infrastructure, retire legacy hardware, confirm facility exit, and validate no stranded costs remain | The difference between a planned data center migration and an emergency migration is the rollback plan; a migration that begins without a tested, documented procedure for reverting every migrated workload within a defined window is not a planned migration — it is an irreversible cutover with a risk profile the business has not accepted | Open | Conduct a full application dependency mapping before the first workload is migrated; sequence migrations from least-critical to most-critical with a minimum 5-business-day validation window between each batch; maintain the source data center in a warm standby state for 30 days after final migration before any decommissioning begins | T+90 | 5/31
Risk | RAID-050 | IT-092 | Compliance Program Integrated | Cybersecurity & Compliance Lead | Complete annual security risk assessment for combined entity | A security assessment that covers only the acquirer's legacy perimeter has a blind spot the size of the acquired company's entire network; assessors should be explicitly scoped to include the combined perimeter, with a separate deliverable that maps all newly introduced attack surfaces from the integration — assessors who are not told about the acquisition may not know to look | Open | Scope the security risk assessment to cover the combined entity perimeter — not just the acquirer's legacy environment; engage an external assessor for objectivity; deliver the assessment report to the CISO and CIO before Day 100 gate and confirm all critical findings have a named owner and remediation deadline | T+90 | 5/31
Risk | RAID-051 | IT-D100 | Day 100 IT Integration Complete | IT Workstream Lead | IT Day 100 Integration Gate — confirm all integration tasks complete or formally deferred, synergy baseline locked, BAU transition signed off | A workstream that reaches Day 100 with open items must either formally complete them or accept them into BAU with a named owner and timeline; items that are neither closed nor formally accepted become permanent integration debt — they resurface as operational problems without a clear owner or resolution path | Open | Conduct the IT Day 100 gate as a formal milestone with CIO and all IT workstream leads; require written close-out status from each lead; any open item must be assigned to a named BAU IT owner with a defined resolution timeline before the gate is approved and the integration team is stood down | T+100 | 6/10

## Next 14 Days
INFORMATION TECHNOLOGY M&A NEXT 14 DAYS ACTIVITIES
TODAY'S DATE: T+30
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Day 1 Checklist
Low | On Track | Milestones
| Complete | RAID Log
Executive Dashboard
Task ID | Category | Phase | Assigned To | Description | Risk Level | Timing Anchor | Start | Finish | Status | Critical Path
IT-081 | Systems & Technology | To Day 100 | Applications & Digital Workplace Lead | Migrate acquired-company accounts into combined entity CRM of record and validate data integrity | High | T+30 | 4/1 | 4/30 | On Track
IT-082 | Integration Management | To Day 100 | IT Integration Coordinator | Conduct Day 30 IT integration health check and risk reassessment — system uptime, helpdesk ticket trends, open security items, and synergy tracking; primary input to the Day 30 IT gate review | Medium | T+30 | 4/1 | 4/7 | On Track
IT-083 | Systems & Technology | To Day 100 | Cybersecurity & Compliance Lead | Establish data retention and disposition schedule for combined entity | Low | T+30 | 4/1 | 4/15 | On Track
IT-084 | Systems & Technology | To Day 100 | IT Integration Coordinator | Design unified IT service management (ITSM) operating model | Medium | T+30 | 4/1 | 4/30 | On Track
IT-085 | IT Infrastructure | To Day 100 | IT Integration Coordinator | Review and consolidate internet and WAN service provider contracts | Medium | T+30 | 4/1 | 5/31 | On Track
IT-086 | Systems & Technology | To Day 100 | Applications & Digital Workplace Lead | Migrate chart of accounts and financial master data to ERP | High | T+30 | 4/1 | 5/31 | On Track
IT-087 | Systems & Technology | To Day 100 | Applications & Digital Workplace Lead | Complete ERP full integration or migration to single platform | High | T+30 | 4/1 | 5/31 | On Track
IT-088 | Systems & Technology | To Day 100 | Infrastructure & Cloud Lead | Complete product and customer data integration and deduplication | High | T+30 | 4/1 | 5/31 | On Track
IT-D30 | Integration Management | To Day 100 | IT Workstream Lead | IT Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | High | T+30 | 4/1 | 4/3 | On Track
IT-089 | Synergy Tracking & Realization | To Day 100 | IT Integration Coordinator | Complete IT vendor contract renegotiation and track savings | Low | T+31 | 4/2 | 5/31 | Not Started
IT-090 | Systems & Technology | To Day 100 | Applications & Digital Workplace Lead | Deploy unified telephony platform across combined entity | Medium | T+42 | 4/13 | 4/30 | Not Started

## Executive Dashboard
HR M&A MILESTONES REPORT | INFORMATION TECHNOLOGY M&A EXECUTIVE DASHBOARD
TODAY'S DATE: T+30
TASKS
|  |  | TOTAL TASKS |  | NOT STARTED |  | DELAYED |  | ON TRACK | COMPLETE
|  |  | 101 |  | 11 |  | 1 |  | 22 | 67
| MILESTONES |  |  | PROGRESS BY PHASE TASKS DONE/TASKS |  |  |  | RAID LOG |  | ANNUAL SYNERGIES
| Not Started | 6 |  | Pre-Close |  | 48/52 |  | Open Risks | 10 | Targeted Synergies | $675K
| Delayed | 0 |  | Days 1 / Week 1 |  | 10/11 |  | Open Items | 12 | Realized Synergies | $0K
| On Track | 1 |  | Days 8 -100 |  | 9/38 |  | Open Issues | 1 | Cost to Achieve Budget | $280K
| Complete | 9 | [5 empty] | Dependencies | 3 | Actual CTA | $0K
[8 empty] | Assumptions | 3
| CRITICAL PATH MILESTONES | [6 empty] | NEXT 14 DAYS |  | DAY 1 | TASKS DONE/TASKS
|  |  |  | Phase | Target Date | Status |  | Total | 11 | Day 1 Readiness | 18/18
| IT Lead Appointed |  |  | Pre-Close | 1/10 | Complete |  | On Critical Path | 0 | Day 1 | 10/11
| IT Integration Governance Established |  |  | Pre-Close | 1/19 | Complete
| IT Charter Approved |  |  | Pre-Close | 1/19 | Complete |  | LINKS
| IT Due Diligence Complete |  |  | Pre-Close | 2/27 | Complete |  | Integration Plan |  | Milestones | Next 14 Days
| Day 1 IT Readiness Confirmed |  |  | Pre-Close (Day 1 Readiness) | 2/27 | Complete |  | Day 1 Checklist |  | RAID Log
| Synergy Tracking Active |  |  | Pre-Close | 2/27 | Complete
| Day 1 / Week 1 IT Integration Complete |  |  | Day 1 / Week 1 | 3/6 | Complete
| Email & Collaboration Unified |  |  | Day 1 / Week 1 | 3/6 | Complete
| IT Integration Plan Locked |  |  | To Day 100 | 3/31 | Complete
| 30-Day IT Integration Review Complete |  |  | To Day 100 | 4/7 | On Track
| IT Service Management Framework Established |  |  | To Day 100 | 4/30 | Not Started
| IT Infrastructure Consolidated |  |  | To Day 100 | 5/31 | Not Started
| Compliance Program Integrated |  |  | To Day 100 | 5/31 | Not Started
| Synergy Realization Report Phase 1 Complete |  |  | To Day 100 | 5/31 | Not Started
| Systems Integration Complete |  |  | To Day 100 | 6/9 | Not Started
| Day 100 IT Integration Complete |  |  | To Day 100 | 6/10 | Not Started