## Legal Integration Plan
100-DAY LEGAL 100-DAY POST-MERGER INTEGRATION PLAN | [13 empty] | Click on + sign (above the top row on right) to see synergy columns
TODAY'S DATE: T+30
Risk Level | Status | % Complete |  | Links
High | Not Started | 0% |  | Day 1 Checklist
Medium | Delayed | 25% |  | Milestones
Low | On Track | 50% |  | RAID Log (Includes Plan Assumptions)
| Complete | 75% |  | Next 14 Days
|  | 100% |  | Executive Dashboard
ID# | Category | Milestone | Phase | Assigned To | Task | Notes | Timing Anchor | Start | Finish | Status | Complete | Critical Path | Issues/Blockers | Risk Level | Team Dependency | Synergy Description | Synergy ($K) | Cost To Achieve ($K) | Synergy ($K) Realized | Actual Cost To Achieve ($K)
LEG-001 | Governance & Planning | Legal Lead Appointed | Pre-Close | General Counsel | Identify Legal workstream lead and determine members of the Legal integration team | Legal Lead must be in seat before LOI signing; GC or deputy GC should be designated | T-59 | 1/2 | 1/10 | Complete | 100% | CP – Close | Without a named Legal Lead, every pre-close legal task has no accountable owner; the IMO cannot escalate legal issues and every cross-workstream task requiring legal clearance will stall | High | Executive Sponsor, IMO
LEG-002 | Governance & Planning | Privilege Protocols Established | Pre-Close | General Counsel | Establish attorney-client privilege protocols for legally sensitive integration communications | Identify which integration discussions require attorney involvement to earn privilege protection — regulatory strategy, litigation exposure, workforce reduction planning, and merger rationale are the primary categories; brief all workstream leads on what must be routed through Legal counsel before committing to writing | T-54 | 1/7 | 1/9 | Complete | 100% | CP – Close | An integration planning document that is not properly privileged — because it was drafted by non-lawyers or shared outside the privilege — becomes discoverable in any subsequent litigation; integration plans discussing acquisition rationale, synergy assumptions, or workforce reduction strategies are particularly sensitive | High | IMO
LEG-003 | Governance & Planning | Legal Integration Governance Established | Pre-Close | Legal Integration Manager | Attend IMO Kickoff Meeting | Use kickoff to align Legal workstream with integration timeline and other workstream leads; Legal has approval gates on nearly every other workstream | T-50 | 1/11 | 1/11 | Complete | 100% |  |  | Low | IMO
LEG-004 | Governance & Planning | Legal Integration Governance Established | Pre-Close | General Counsel | Hold Legal Integration Kickoff Meeting | Brief Legal team on scope, timeline, clean room protocols, and workstream responsibilities; assign sub-workstream leads for corporate, contracts, employment, IP, and regulatory | T-49 | 1/12 | 1/12 | Complete | 100% |  |  | Low | IMO
LEG-005 | Governance & Planning | Legal Data Room Access | Pre-Close | Legal Integration Manager | Receive access to integration data room and document repository | Confirm VDR credentials for all Legal team members | T-49 | 1/12 | 1/13 | Complete | 100% |  |  | Low | IMO
LEG-006 | Governance & Planning | Legal Charter Approved | Pre-Close | General Counsel | Develop the Legal workstream integration charter | Charter must define Legal mandate, decision rights, approval thresholds, and escalation path to GC and Steering Committee; IMO approves all charters | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | IMO
LEG-007 | Governance & Planning | Legal Integration Governance Established | Pre-Close | General Counsel | Define Legal workstream integration success metrics and KPIs | Track: contract review completion rate, regulatory filing timeliness, open litigation items resolved, integration milestones with legal dependency cleared on schedule | T-49 | 1/12 | 1/19 | Complete | 100% |  |  | Low | IMO
LEG-008 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Litigation Counsel | Identify and assess all pending, threatened, and contingent litigation | Review all disclosed litigation, arbitration, regulatory investigations; quantify exposure for each matter; flag matters that could affect deal economics or regulatory approval | T-49 | 1/12 | 2/14 | Complete | 100% |  | Litigation not identified or underestimated in due diligence becomes a post-close liability that was not priced into the deal; an ongoing regulatory investigation that was minimized in disclosure can result in a consent decree constraining combined-entity operations in ways the deal model did not anticipate | High | Finance
LEG-009 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Employment Counsel | Review all employment agreements, severance plans, and equity arrangements | Flag golden parachute provisions, CIC payments, non-compete agreements, and retention agreements for all employees; quantify total CIC exposure for executives (executive comp accessible pre-close); confirm which agreements transfer or terminate at close. Note: Sales rep compensation amounts and commission structures are restricted pre-close — non-executive employment agreement comp review limited to structural terms until post-close. | T-49 | 1/12 | 2/14 | Complete | 100% |  | A change-in-control payment obligation not identified before close creates an unexpected cash outflow on Day 1; a senior executive whose agreement terminates automatically at close may claim constructive dismissal if not properly novated | High | HR, Finance
LEG-010 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Corporate Counsel | Review corporate governance documents, board minutes, and ownership structure | Confirm cap table accuracy; review board minutes for undisclosed commitments, side letters, or oral agreements; verify corporate authorizations required for the transaction | T-49 | 1/12 | 2/14 | Complete | 100% |  | A corporate authorization defect — a board resolution that did not have quorum, a shareholder vote that did not reach the required threshold, a subsidiary that was not properly included in the transaction structure — cannot be cured after close; the combined entity may be operating under documents that are facially valid but legally defective | High
LEG-011 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Regulatory Counsel | Identify all regulatory licenses, permits, and approvals that must transfer or be re-obtained | Licenses that do not automatically transfer at close create gaps in operating authority; some jurisdictions require re-application; government contracts may require novation approval | T-49 | 1/12 | 2/14 | Complete | 100% |  | A regulatory license that lapses at close — because it was not re-applied for before the transfer — creates a period during which the combined entity cannot legally conduct the licensed activity; revenue from that activity stops the day the license expires | High | Government Affairs, Finance
LEG-012 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Commercial Counsel | Identify all contracts requiring consent to assignment at close | Review all material contracts for assignment restrictions; prioritize by revenue at risk; develop consent strategy for each; begin outreach to key counterparties | T-49 | 1/12 | 2/14 | Complete | 100% |  | A contract with an assignment restriction not identified before close gives the counterparty the right to terminate upon the assignment at close; a large customer or critical supplier who exercises this right on Day 1 creates an immediate operational and revenue crisis | High | Sales, Finance, Procurement
LEG-013 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Employment Counsel | Identify all union agreements, Works Councils, and collective bargaining obligations | Works Council consultation is legally required before informing employees in many EU jurisdictions; failure to consult can result in injunctions that delay or block the transaction; identify all CBA obligations that must be assumed | T-49 | 1/12 | 2/14 | Complete | 100% |  |  | Medium | HR, IMO
LEG-014 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Litigation Counsel | Assess and quantify all contingent liabilities and open litigation | Prepare litigation reserve recommendations for Finance; assess likelihood of success and exposure for each matter; flag matters where settlement before close may be advantageous | T-49 | 1/12 | 2/14 | Complete | 100% |  | A contingent liability that was not properly assessed and reserved creates a post-close earnings surprise when the reserve is established; the first time the combined entity discloses a material litigation reserve that was not disclosed in the deal announcement, it signals that due diligence was inadequate — damaging investor confidence at the most critical moment of post-close execution | High | Finance
LEG-015 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Commercial Counsel | Audit all software licenses for change-of-control and transfer restrictions | Enterprise software licenses frequently contain change-of-control clauses that require vendor consent or result in termination; cloud and SaaS contracts often restrict the number of permitted entities | T-49 | 1/12 | 2/14 | Complete | 100% |  | An enterprise software license that terminates automatically at close — because the vendor change-of-control clause was not identified and consent not obtained — can leave the combined entity without access to a mission-critical system on Day 1 | High | Finance, IT, Procurement
LEG-016 | Compliance & Regulatory | Regulatory Approvals Obtained | Pre-Close | Regulatory Counsel | File all required pre-closing regulatory notifications and obtain approvals | File HSR, CFIUS if applicable, and all international competition filings; track all regulatory review periods; advise Steering Committee on regulatory risk to deal timeline | T-49 | 1/12 | 3/1 | Complete | 100% | CP – Close |  | Medium | Finance, IMO
LEG-017 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Commercial Counsel | Review and map all material contracts of the target company | Identify all contracts over materiality threshold; flag change-of-control clauses, evergreen terms, and unfavorable provisions; prioritize by revenue at risk | T-49 | 1/12 | 3/31 | Complete | 100% |  | A material contract not identified in due diligence that contains an unfavorable term — unlimited liability, exclusivity restriction, or change-of-control termination right — cannot be renegotiated post-close from strength; the combined entity learns of its exposure through contract performance, not proactive review | High | Finance, Sales
LEG-018 | Due Diligence | Legal Due Diligence Complete | Pre-Close | IP Counsel | Audit intellectual property ownership, registrations, and licensing arrangements | Confirm ownership of all patents, trademarks, copyrights, and trade secrets; identify third-party IP used under license; flag any IP not properly assigned to the target entity | T-48 | 1/13 | 2/14 | Complete | 100% |  | IP that appears owned by the target but is licensed or jointly owned creates a post-close dispute with the original owner; a patent that is invalid or improperly assigned in a key product line exposes the combined entity to infringement claims from the day it takes ownership | High | IT, Finance
LEG-019 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Data Privacy Counsel | Review data privacy compliance posture and identify cross-border data transfer risks | Review GDPR, CCPA, and jurisdiction-specific privacy obligations; assess data processing agreements with third parties; flag data transfers that may be restricted post-close | T-48 | 1/13 | 2/14 | Complete | 100% |  | A GDPR violation in the target operations becomes the combined entity violation at close; fines of up to 4% of global annual revenue are assessed against the entity that owns the data at the time of the finding, not the entity that created the problem | High | HR, IT
LEG-020 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Compliance Counsel | Assess anti-corruption, sanctions, and export control compliance | Review FCPA, UK Bribery Act, OFAC sanctions, and export control compliance; flag third-party relationships or government contracts creating exposure; assess compliance program adequacy | T-48 | 1/13 | 2/14 | Complete | 100% |  | Anti-corruption or sanctions exposure inherited at close cannot be remediated retroactively; the acquirer assumes successor liability for FCPA violations from the date of acquisition regardless of when the violations occurred | High | Finance, Government Affairs
LEG-021 | Due Diligence | Legal Due Diligence Complete | Pre-Close | Antitrust Counsel | Conduct antitrust and competition law analysis across all relevant jurisdictions | Identify overlapping product markets; assess HSR filing requirements and equivalent international filings; flag potential remedy requirements; advise on clean team protocols | T-48 | 1/13 | 2/14 | Complete | 100% | CP – Close |  | Low | Finance, Sales, IMO
LEG-022 | Compliance & Regulatory | Regulatory Approvals Obtained | Pre-Close | Securities Counsel | Prepare and file all required securities law disclosures | Draft and file 8-K and other SEC disclosures; coordinate with IR and Finance on disclosure timing; confirm Reg FD compliance throughout pre-close period | T-42 | 1/19 | 2/27 | Complete | 100% | CP – Close | A selective disclosure of material non-public information to any person before the required public filing — regardless of how informal the communication — constitutes a Reg FD violation that the SEC can act on without regard to whether the recipient traded on the information | High | IR, Finance, Communications
LEG-023 | Governance & Planning | Regulatory Approvals Obtained | Pre-Close | Corporate Counsel | Obtain all required board and shareholder approvals for the transaction | Confirm board authorization requirements in each entity governing documents; confirm shareholder vote threshold and timing; prepare all resolutions and supporting documentation | T-42 | 1/19 | 2/27 | Complete | 100% | CP – Close |  | Medium | Finance
LEG-024 | Governance & Planning | Pricing & Contract Harmonization Complete | Pre-Close | Commercial Counsel | Develop contract harmonization roadmap for post-close execution | Map all customer, supplier, and partner contracts to the combined entity standard terms; identify contracts requiring renegotiation vs. those that can run to natural expiry | T-42 | 1/19 | 2/27 | Complete | 100% |  | A contract estate managed without a harmonization roadmap will be renegotiated reactively — when contracts expire or counterparties raise issues — rather than proactively; reactive renegotiation consistently produces worse economic outcomes than planned renegotiation, and misses the window of combined-entity leverage that exists in the first 90 days | High | Sales, Finance, Procurement
LEG-025 | Compliance & Regulatory | Regulatory Approvals Obtained | Pre-Close | Regulatory Counsel | Identify and manage state and local regulatory approval requirements | State-level approvals vary by industry; regulated industries often require state approval in addition to federal; flag any state approvals with long lead times | T-42 | 1/19 | 3/1 | Complete | 100% | CP – Close | A state regulatory approval that is not identified before close cannot be obtained retroactively while the combined entity is already operating; the combined entity operates without authorization during the approval period, exposing it to regulatory enforcement, fines, and potential forced divestiture in that state | High | Government Affairs, Finance
LEG-026 | Governance & Planning | Legal Integration Governance Established | Pre-Close | Legal Integration Manager | Develop Legal integration plan (tasks, milestones, RAID log, Day 1 checklist) and update it weekly | Share updates with IMO for master plan consolidation; update weekly and ensure all sub-workstream leads contribute their section by Thursday for Friday IMO review | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Medium | IMO
LEG-027 | Integration Management | Day 100 Legal Integration Complete | Pre-Close | Legal Integration Manager | Conduct weekly Legal workstream status meeting | Weekly internal meeting to track open items, escalate blockers, and update integration plan status | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
LEG-028 | Integration Management | Day 100 Legal Integration Complete | Pre-Close | Legal Integration Manager | Attend weekly IMO Meeting to discuss issues and share status | Legal must attend every IMO meeting given cross-workstream dependencies; flag any legal blocker threatening the integration timeline | T-42 | 1/19 | 6/10 | On Track | 50% |  |  | Low | IMO
LEG-029 | Synergy Tracking & Realization | Synergy Tracking Established | Pre-Close | General Counsel | Ensure synergy owners are assigned and synergy tracking model is validated | Legal should validate that synergy assumptions involving contract renegotiation, litigation resolution, and regulatory savings have named owners and are based on realistic legal assessments | T-35 | 1/26 | 2/27 | Complete | 100% |  |  | Medium | Finance, IMO
LEG-030 | Compliance & Regulatory | Legal Due Diligence Complete | Pre-Close | IP Counsel | Complete trademark and brand clearance in all operating jurisdictions | Combined brand strategy requires trademark clearance in all markets; any brand name not cleared before use creates an infringement risk; coordinate with Marketing on brand transition timeline | T-35 | 1/26 | 2/27 | Complete | 100% |  | A combined brand name used in commerce before trademark clearance is obtained in a jurisdiction creates an unregistered use that a prior registrant can challenge; rebranding after a cease-and-desist is more expensive than clearing the name before use | High | Communications, Marketing
LEG-031 | Compliance & Regulatory | Works Council Consultation Complete | Pre-Close | Employment Counsel | Initiate and complete Works Council consultation before any employee announcement | Works Council consultation is a statutory requirement in Germany, France, the Netherlands, Belgium, and most EU member states — failure to consult before any announcement or integration action affecting represented employees is an unfair labor practice that can result in injunctions, fines, and forced reversal. | T-35 | 1/26 | 2/27 | Complete | 100% | CP – Day 1 Readiness |  | Medium | HR, IMO
LEG-032 | Compliance & Regulatory | Compliance Program Integrated | Pre-Close | Compliance Counsel | Develop combined compliance program framework | Integrate compliance programs of both entities; identify gaps and overlaps; align on whistleblower hotline, training, and code of conduct | T-35 | 1/26 | 3/31 | Complete | 100% |  |  | Medium | HR, Finance, IT
LEG-033 | Compliance & Regulatory | Pricing & Contract Harmonization Complete | Pre-Close | Regulatory Counsel | Review and novate all government contracts requiring agency consent | Government contracts typically do not automatically transfer at close; novation approval from the contracting agency must be obtained before the combined entity begins performance | T-35 | 1/26 | 5/31 | On Track | 75% |  |  | Low | Government Affairs, Finance
LEG-034 | Synergy Tracking & Realization | Synergy Tracking Established | Pre-Close | Legal Integration Manager | Establish synergy tracking framework for regulatory cost savings | Legal and Finance must co-own the synergy tracking model for regulatory savings; legal costs to be eliminated post-close must be confirmed and baseline-adjusted | T-35 | 1/26 | 6/10 | On Track | 50% |  |  | Medium | Finance, IMO
LEG-035 | Compliance & Regulatory | Compliance Program Integrated | Pre-Close | Data Privacy Counsel | Draft and publish combined data privacy policy and employee notice | Combined entity must publish a unified privacy policy before processing any combined data; employee notice required in many jurisdictions | T-28 | 2/2 | 2/27 | Complete | 100% |  |  | Medium | HR, IT, Communications
LEG-036 | Organization & Talent | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | Employment Counsel | Confirm Day 1 employment status for all acquired employees | Confirm whether acquired employees transfer automatically (TUPE/WARN), require new offer letters, or must be terminated and rehired; jurisdiction-specific requirements vary significantly | T-28 | 2/2 | 2/27 | Complete | 100% | CP – Day 1 Readiness | An employee not properly transitioned at close — because the legal mechanism for transfer was not confirmed in advance — may have an immediate claim for constructive dismissal, wrongful termination, or breach of employment contract | High | HR, Finance
LEG-037 | Compliance & Regulatory | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | Employment Counsel | Review and finalize severance and CIC payment obligations | Confirm total CIC payment exposure for all executives; obtain board authorization for any payments not pre-authorized; ensure payments comply with IRC 409A and golden parachute rules. Note: Legal has pre-close access to executive compensation — full CIC exposure quantification for executives is permissible pre-close. Non-executive sales rep compensation is restricted to structural review only pre-close. | T-28 | 2/2 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A CIC payment made without proper board authorization is potentially a breach of fiduciary duty; a payment that does not comply with IRC 409A timing rules creates a 20% excise tax on the recipient and a potential deduction disallowance for the payor — the combined entity inherits the tax exposure of its predecessor's payment practices | High | HR, Finance
LEG-038 | Integration Management | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | Legal Integration Manager | Circulate pre-close legal integration RACI to all workstreams | All workstream leads must know which Legal sub-team to contact for approvals, contract review, employment questions, regulatory issues, and IP matters; RACI prevents bottlenecks | T-28 | 2/2 | 2/27 | Complete | 100% | CP – Day 1 Readiness |  | Medium | IMO, All Workstreams
LEG-039 | Integration Management | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | Employment Counsel | Review and legally clear the M&A Employee Communication Guide | Legal must review all employee-facing Day 1 communications for compliance with WARN Act, Works Council obligations, and employment law before distribution; flag any statement that creates a legal commitment or exposure | T-20 | 2/10 | 2/25 | Complete | 100% | CP – Day 1 Readiness | An employee communication that makes a promise about job security, benefits continuation, or role assignment that is later not honored creates a promissory estoppel or breach of contract claim; Legal clearance ensures communications inform without creating unintended legal obligations | High | HR, Communications, IMO
LEG-040 | Compliance & Regulatory | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | Regulatory Counsel | Confirm all operating licenses and permits are valid at close | Conduct final audit of all licenses; confirm transfer or reissuance where required; flag any license not in good standing | T-20 | 2/10 | 2/27 | Complete | 100% | CP – Day 1 Readiness | An operating license that is suspended, revoked, or not transferred at close means the combined entity cannot legally conduct the licensed activity from Day 1; revenue from that activity stops the day the license transfer fails | High | Finance, Government Affairs
LEG-041 | Compliance & Regulatory | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | Employment Counsel | Confirm all non-compete and non-solicitation agreements are enforceable in relevant jurisdictions | Non-compete enforceability varies dramatically by state and country; confirm key executives are subject to enforceable restrictions before announcing the transaction | T-20 | 2/10 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A key executive who signs a non-compete that is unenforceable in their jurisdiction can join a direct competitor the day after closing without legal consequence; the acquirer who paid a premium for the executive's customer relationships and institutional knowledge has no legal remedy when those assets walk out the door | High | HR, Finance
LEG-042 | Compliance & Regulatory | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | Regulatory Counsel | Confirm all regulatory pre-approval conditions have been satisfied | Confirm all conditions attached to regulatory approvals have been met; file all required closing condition certifications; notify regulators of close date as required | T-10 | 2/20 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A regulatory approval that carries a condition the combined entity has not satisfied — even a condition it believes it has satisfied — gives the regulator grounds to revisit the approval post-close; regulators who find a closing condition was not met have reopened transactions months after close and imposed additional remedies | High | Finance
LEG-043 | Integration Management | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | Legal Integration Manager | Draft and distribute Day 1 Legal playbook covering roles, escalation paths, and decision authority for all Day 1 legal activities | Final pre-close review of all open legal items; confirm all required approvals, consents, and filings are complete; confirm no legal blocker prevents Day 1 execution | T-10 | 2/20 | 2/27 | Complete | 100% | CP – Day 1 Readiness | A legal blocker discovered on Day 1 — an approval not obtained, a consent not received, a filing not made — cannot be remediated after the transaction has closed; the combined entity must operate under the constraint, often at significant cost or legal exposure | High | IMO
LEG-044 | Integration Management | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | General Counsel | Brief Legal team on Day 1 roles and protocols | All Legal team members must know their Day 1 tasks, escalation path, and the key questions each workstream is likely to ask; Legal fielding questions without preparation will give inconsistent answers | T-8 | 2/22 | 2/27 | Complete | 100% | CP – Day 1 Readiness |  | Medium
LEG-D1 | Integration Management | Day 1 Legal Readiness Confirmed | Pre-Close (Day 1 Readiness) | General Counsel | Legal Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | Workstream lead formally certifies Day 1 readiness to the IMO; this gate must be green for every workstream before the IMO signs off on close; any open item at this gate is either resolved or escalated to the steering committee as a close-blocking risk | T-3 | 2/27 | 2/27 | Complete | 100% | CP – Close | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | High | IMO, All Workstreams
LEG-045 | Integration Management | Closing Documents Executed | Day 1 / Week 1 | General Counsel | Execute all Day 1 legal closing documents | Confirm execution of merger agreement, ancillary documents, officer certificates, and closing condition certifications; coordinate with Deal Counsel on closing sequence | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% | CP – Close | A closing document that is unsigned, executed by the wrong party, or executed without the required authority means the transaction has not legally closed in the manner the parties intended; the combined entity begins operating under an incomplete transaction structure, and correcting the defect after operations have begun is significantly more complicated than requiring proper execution before close | High | Finance
LEG-046 | Integration Management | Day 1 / Week 1 Legal Integration Complete | Day 1 / Week 1 | Legal Integration Manager | Send Day 1 integration status update to IMO | Confirm all Day 1 legal tasks completed; flag any unresolved items with owner and timeline; Legal status update is a required input to the IMO Day 1 debrief | Day 1 (Close) | 3/2 | 3/2 | Complete | 100% |  |  | Low | IMO
LEG-047 | Compliance & Regulatory | WARN Notifications Issued | Day 1 / Week 1 | Employment Counsel | Complete Day 1 WARN Act and equivalent statutory notifications | WARN Act requires 60 days notice before mass layoffs affecting 50+ employees; equivalent notice periods apply in EU, UK, and other jurisdictions; coordinate notification timing with HR and Communications | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% |  |  | Medium | HR, Finance, Communications
LEG-048 | Compliance & Regulatory | Day 1 / Week 1 Legal Integration Complete | Day 1 / Week 1 | General Counsel | Confirm all legal entity structures are properly established | Confirm all required subsidiary formations, mergers, and dissolutions have been completed; confirm all entity-level authorizations are in place | Day 1 (Close) | 3/2 | 3/6 | Complete | 100% | CP – Close | A legal entity that was dissolved, merged, or formed incorrectly creates tax, regulatory, and contractual complications that are discovered when the combined entity files its first tax return, applies for a permit, or is sued — not at the moment the structural error was made; entity structure defects discovered post-filing are expensive to correct and may require regulatory re-approval | High | Finance | Legal entity rationalization — eliminating redundant legal entities reduces state registration fees, annual report filings, registered agent costs, and tax compliance overhead across the combined entity footprint | 100 | 25
LEG-049 | Compliance & Regulatory | Pricing & Contract Harmonization Complete | Day 1 / Week 1 | Commercial Counsel | Execute contract novation and assignment for all required agreements | Obtain counterparty consent or execute novation for all contracts requiring assignment; prioritize revenue-generating customer contracts and operationally critical supplier contracts | Day 1 (Close) | 3/2 | 3/20 | Complete | 100% | CP – Day 100 | A contract that is assigned without the required counterparty consent is voidable at the counterparty's election; a major customer or critical supplier who discovers their contract was transferred without consent has a contractual basis to terminate that they did not have before the transaction closed — the novation failure creates the very termination risk that consent was designed to prevent | High | Sales, Finance, Procurement
LEG-050 | Compliance & Regulatory | Compliance Program Integrated | Day 1 / Week 1 | Employment Counsel | Align employee handbooks and conduct policies across combined entity | Adopt unified code of conduct, disciplinary procedures, and workplace policies; file required policy updates with Works Councils; train HR managers on new policies | Day 1 (Close) | 3/2 | 3/31 | Complete | 100% |  |  | Medium | HR, Communications
LEG-051 | Compliance & Regulatory | Compliance Program Integrated | Day 1 / Week 1 | Compliance Counsel | Establish unified legal hold and document retention policy | Combined entity must maintain legal holds for all matters inherited at close; failure to preserve documents after a litigation hold creates spoliation exposure | Day 1 (Close) | 3/2 | 3/31 | Complete | 100% |  |  | Medium | HR, IT, Finance
LEG-052 | Compliance & Regulatory | Day 100 Legal Integration Complete | To Day 100 | Litigation Counsel | Transfer all ongoing litigation responsibilities to combined entity legal team | Outside counsel managing ongoing matters must be confirmed or replaced; conflict checks required for all outside counsel firms; document retention obligations for all ongoing matters must be transferred | T+8 | 3/10 | 3/31 | Complete | 100% |  |  | Medium | Finance | Litigation portfolio consolidation — reassessing acquired company litigation and claims post-close, eliminating duplicative reserve provisions where the same exposure is reserved in both entities, and consolidating outside counsel on active matters to reduce duplicative legal spend | 25 | 5
LEG-053 | Compliance & Regulatory | Compliance Program Integrated | To Day 100 | Data Privacy Counsel | Execute cross-border data transfer agreements for all international data flows | EU Standard Contractual Clauses or adequacy decisions must be in place for all personal data transferred from EEA to third countries; GDPR requires lawful basis for all post-close data processing | T+8 | 3/10 | 4/15 | On Track | 50% | CP – Day 100 |  | Medium | HR, IT
LEG-054 | Compliance & Regulatory | Pricing & Contract Harmonization Complete | To Day 100 | Commercial Counsel | Standardize contract templates and approval authority matrix | Adopt combined entity standard terms for customer, vendor, and partner agreements; define approval thresholds by contract value and risk level; train Sales and Procurement on new templates | T+8 | 3/10 | 4/30 | On Track | 50% | CP – Day 100 |  | Medium | Sales, Finance, Procurement
LEG-055 | Compliance & Regulatory | IP Assignment Complete | To Day 100 | IP Counsel | Execute assignment and transfer of all IP to combined entity | File patent, trademark, and copyright assignments in all relevant registries; ensure all inventors and authors have executed valid assignment agreements; update all IP ownership records | T+8 | 3/10 | 4/30 | On Track | 50% |  | IP that is used but not formally assigned to the combined entity gives the original owner — including a former employee, a co-founder, or a prior employer — a colorable claim of ownership; a patent infringement or trade secret misappropriation claim against a key product line, filed by a party who can demonstrate the IP was never validly assigned, creates an existential product liability that cannot be settled cheaply | High | Finance, IT
LEG-056 | Integration Management | Day 100 Legal Integration Complete | To Day 100 | Legal Integration Manager | Select and implement combined entity legal matter management system | Consolidate legal matter tracking, billing, and document management into a single system; ensure all inherited matters are transferred to the combined system | T+8 | 3/10 | 4/30 | On Track | 50% |  |  | Medium | Finance, IT, Procurement
LEG-057 | Compliance & Regulatory | Pricing & Contract Harmonization Complete | To Day 100 | Commercial Counsel | Review and renegotiate top 20 vendor and supplier contracts and consolidate | Review all remaining vendor contracts post-close; identify further consolidation and exit opportunities; report final vendor rationalization savings to Finance | T+14 | 3/16 | 5/31 | On Track | 25% |  |  | Low | Finance, Procurement | Outside counsel spend consolidation — combining two legal departments allows rationalization of duplicate outside counsel relationships, law firm panel reduction, and combined-volume billing rate improvements; no other workstream claims legal department cost savings | 250 | 15
LEG-058 | Synergy Tracking & Realization | Day 100 Legal Integration Complete | To Day 100 | Legal Integration Manager | Track and report legal synergy realization against deal model | Monitor progress against legal cost synergies including litigation reserve reductions, outside counsel spend consolidation, and regulatory cost savings | T+30 | 4/1 | 6/10 | On Track | 25% |  |  | Low | Finance, IMO
LEG-D30 | Integration Management | 30-Day Legal Review Complete | To Day 100 | General Counsel | Legal Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | IMO-led review of Legal workstream at Day 30; confirm all Day 1 tasks closed, RAID log current, synergy owners active, and no unresolved blockers threatening Day 100 delivery | T+30 | 4/1 | 4/3 | On Track | 75% | CP – Day 100 | If the Day 30 check reveals open tasks, unresolved blockers, or synergy owners not yet active, the integration team has 70 days to correct course — but the Day 30 review must force honest status reporting; teams that report green when yellow or red create hidden risk that surfaces at Day 100 when it is too late to recover | High | IMO, All Workstreams
LEG-059 | Integration Management | Day 100 Legal Integration Complete | To Day 100 | Legal Integration Manager | Document Legal integration lessons learned for M&A playbook — these findings feed into the Day 100 Legal gate review and are shared with the IMO for future deal playbook updates | Capture what worked, what was missed, and what should be done differently; share with IMO for master playbook update | T+93 | 6/3 | 6/10 | Not Started | 0% |  |  | Low | IMO
LEG-D100 | Integration Management | Day 100 Legal Integration Complete | To Day 100 | General Counsel | Legal Day 100 Integration Gate — confirm all integration tasks complete or formally deferred, synergy baseline locked, BAU transition signed off | Final IMO gate for Legal workstream; all remaining open items must be formally accepted as BAU or escalated; this row closes the integration for the Legal workstream | T+98 | 6/8 | 6/10 | Not Started | 0% | CP – Day 100 |  | High | IMO, All Workstreams

## Day 1 Checklist
LEGAL M&A DAY 1 / WEEK 1 CHECKLIST (Pre-Close (Day 1 Readiness), and Day 1/Week 1 Phases)
TODAY'S DATE: T+30
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Milestones
Low | On Track | RAID Log
| Complete | Next 14 Days
Executive Dashboard
☑ | Task ID | Phase | Task Description | Assigned To | Risk Level | Timing Anchor | Start | Finish | Status | Milestone
☑ | LEG-036 | Pre-Close (Day 1 Readiness) | Confirm Day 1 employment status for all acquired employees | Employment Counsel | High | T-28 | 2/2 | 2/27 | Complete | CP – Day 1 Readiness
☑ | LEG-037 | Pre-Close (Day 1 Readiness) | Review and finalize severance and CIC payment obligations | Employment Counsel | High | T-28 | 2/2 | 2/27 | Complete | CP – Day 1 Readiness
☑ | LEG-038 | Pre-Close (Day 1 Readiness) | Circulate pre-close legal integration RACI to all workstreams | Legal Integration Manager | Medium | T-28 | 2/2 | 2/27 | Complete | CP – Day 1 Readiness
☑ | LEG-039 | Pre-Close (Day 1 Readiness) | Review and legally clear the M&A Employee Communication Guide | Employment Counsel | High | T-20 | 2/10 | 2/25 | Complete | CP – Day 1 Readiness
☑ | LEG-040 | Pre-Close (Day 1 Readiness) | Confirm all operating licenses and permits are valid at close | Regulatory Counsel | High | T-20 | 2/10 | 2/27 | Complete | CP – Day 1 Readiness
☑ | LEG-041 | Pre-Close (Day 1 Readiness) | Confirm all non-compete and non-solicitation agreements are enforceable in relevant jurisdictions | Employment Counsel | High | T-20 | 2/10 | 2/27 | Complete | CP – Day 1 Readiness
☑ | LEG-042 | Pre-Close (Day 1 Readiness) | Confirm all regulatory pre-approval conditions have been satisfied | Regulatory Counsel | High | T-10 | 2/20 | 2/27 | Complete | CP – Day 1 Readiness
☑ | LEG-043 | Pre-Close (Day 1 Readiness) | Draft and distribute Day 1 Legal playbook covering roles, escalation paths, and decision authority for all Day 1 legal activities | Legal Integration Manager | High | T-10 | 2/20 | 2/27 | Complete | CP – Day 1 Readiness
☑ | LEG-044 | Pre-Close (Day 1 Readiness) | Brief Legal team on Day 1 roles and protocols | General Counsel | Medium | T-8 | 2/22 | 2/27 | Complete | CP – Day 1 Readiness
☑ | LEG-D1 | Pre-Close (Day 1 Readiness) | Legal Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | General Counsel | High | T-3 | 2/27 | 2/27 | Complete | CP – Close
☑ | LEG-051 | Day 1 / Week 1 | Establish unified legal hold and document retention policy | Compliance Counsel | Medium | Day 1 (Close) | 3/2 | 3/31 | Complete
☑ | LEG-045 | Day 1 / Week 1 | Execute all Day 1 legal closing documents | General Counsel | High | Day 1 (Close) | 3/2 | 3/2 | Complete | CP – Close
☑ | LEG-046 | Day 1 / Week 1 | Send Day 1 integration status update to IMO | Legal Integration Manager | Low | Day 1 (Close) | 3/2 | 3/2 | Complete
☑ | LEG-047 | Day 1 / Week 1 | Complete Day 1 WARN Act and equivalent statutory notifications | Employment Counsel | Medium | Day 1 (Close) | 3/2 | 3/6 | Complete
☑ | LEG-049 | Day 1 / Week 1 | Execute contract novation and assignment for all required agreements | Commercial Counsel | High | Day 1 (Close) | 3/2 | 3/20 | Complete | CP – Day 100
☑ | LEG-050 | Day 1 / Week 1 | Align employee handbooks and conduct policies across combined entity | Employment Counsel | Medium | Day 1 (Close) | 3/2 | 3/31 | Complete
☑ | LEG-048 | Day 1 / Week 1 | Confirm all legal entity structures are properly established | General Counsel | High | Day 1 (Close) | 3/2 | 3/6 | Complete | CP – Close

## Milestones
LEGAL M&A MILESTONES
TODAY'S DATE: T+30
Status | Links
Not Started | Integration Plan
Delayed | Day 1 Checklist
On Track | RAID Log
Complete | Next 14 Days
Executive Dashboard
Milestone ID | Category | Phase | Assigned To | Milestone | Timing Anchor | Finish | Status | Critical Path
MS-001 | Governance & Planning | Pre-Close | General Counsel | Legal Lead Appointed | T-51 | 1/10 | Complete | CP – Close
MS-002 | Governance & Planning | Pre-Close | Legal Integration Manager | Legal Data Room Access | T-48 | 1/13 | Complete
MS-003 | Governance & Planning | Pre-Close | Legal Integration Manager | Legal Integration Governance Established | T-42 | 1/19 | Complete
MS-004 | Governance & Planning | Pre-Close | General Counsel | Legal Charter Approved | T-42 | 1/19 | Complete
MS-005 | Compliance & Regulatory | Pre-Close | General Counsel | Privilege Protocols Established | T-52 | 1/9 | Complete | CP – Close
MS-006 | Due Diligence | Pre-Close | Litigation Counsel | Legal Due Diligence Complete | T-3 | 2/27 | Complete | CP – Close
MS-007 | Synergy Tracking & Realization | Pre-Close | General Counsel | Synergy Tracking Established | T-3 | 2/27 | Complete
MS-008 | Compliance & Regulatory | Pre-Close | Employment Counsel | Works Council Consultation Complete | T-3 | 2/27 | Complete | CP – Day 1 Readiness
MS-009 | Compliance & Regulatory | Pre-Close (Day 1 Readiness) | Employment Counsel | Day 1 Legal Readiness Confirmed | T-3 | 2/27 | Complete | CP – Day 1 Readiness
MS-010 | Compliance & Regulatory | Pre-Close | Regulatory Counsel | Regulatory Approvals Obtained | T-1 | 3/1 | Complete | CP – Close
MS-011 | Integration Management | Day 1 / Week 1 | General Counsel | Closing Documents Executed | Day 1 (Close) | 3/2 | Complete | CP – Close
MS-012 | Compliance & Regulatory | Day 1 / Week 1 | Employment Counsel | WARN Notifications Issued | T+4 | 3/6 | Complete
MS-013 | Integration Management | Day 1 / Week 1 | Legal Integration Manager | Day 1 / Week 1 Legal Integration Complete | T+4 | 3/6 | Complete | CP – Close
MS-014 | Integration Management | To Day 100 | General Counsel | 30-Day Legal Review Complete | T+32 | 4/3 | On Track | CP – Day 100
MS-015 | Compliance & Regulatory | Pre-Close | Compliance Counsel | Compliance Program Integrated | T+44 | 4/15 | On Track
MS-016 | Compliance & Regulatory | To Day 100 | IP Counsel | IP Assignment Complete | T+59 | 4/30 | Not Started
MS-017 | Compliance & Regulatory | Pre-Close | Commercial Counsel | Pricing & Contract Harmonization Complete | T+90 | 5/31 | Not Started | CP – Close
MS-018 | Integration Management | To Day 100 | Legal Integration Manager | Day 100 Legal Integration Complete | T+100 | 6/10 | Not Started | CP – Day 100

## RAID Log
LEGAL M&A RAID LOG (RAID = Risks, Assumptions, Issues, Dependencies)
TODAY'S DATE: T+30
RAID Type | Status | Links
Risk | Open | Integration Plan
Issue | Closed | Day 1 Checklist
Dependency | Active | Milestones
Assumption | Validated | Next 14 Days
Executive Dashboard
RAID Type | RAID ID | Related Task ID | Milestone | Owner | Task Description | Issues/Blockers | Status | Mitigation/Action | Timing Anchor | Finish
Risk | RAID-001 | LEG-002 | Privilege Protocols Established | General Counsel | Establish attorney-client privilege protocols for legally sensitive integration communications | An integration planning document that is not properly privileged — because it was drafted by non-lawyers or shared outside the privilege — becomes discoverable in any subsequent litigation; integration plans discussing acquisition rationale, synergy assumptions, or workforce reduction strategies are particularly sensitive | Closed | Issue privilege protocol memo to all integration team members before any pre-close data sharing begins; require Legal Integration Manager to co-ordinate all integration documents through a privileged legal structure; prohibit non-lawyers from drafting integration strategy documents; treat any inadvertent disclosure immediately under a claw-back agreement | T-52 | 1/9
Risk | RAID-002 | LEG-001 | Legal Lead Appointed | General Counsel | Identify Legal workstream lead and determine members of the Legal integration team | Without a named Legal Lead, every pre-close legal task has no accountable owner; the IMO cannot escalate legal issues and every cross-workstream task requiring legal clearance will stall | Closed | Escalate Legal Lead appointment to General Counsel and Executive Sponsor immediately; role must be named and capacity confirmed before integration kickoff; if filled internally, secure backfill for BAU responsibilities to prevent integration work from becoming a secondary priority | T-51 | 1/10
Risk | RAID-003 | LEG-008 | Legal Due Diligence Complete | Litigation Counsel | Identify and assess all pending, threatened, and contingent litigation | Litigation not identified or underestimated in due diligence becomes a post-close liability that was not priced into the deal; an ongoing regulatory investigation that was minimized in disclosure can result in a consent decree constraining combined-entity operations in ways the deal model did not anticipate | Closed | Require target management to disclose all litigation — pending, threatened, and settled in the last 3 years — with outside counsel name, estimated exposure, and reserve amount; obtain a legal rep from deal counsel certifying disclosure completeness; include undisclosed litigation in rep and warranty insurance scope; build a post-close litigation tracking register before Day 1 | T-16 | 2/14
Risk | RAID-004 | LEG-009 | Legal Due Diligence Complete | Employment Counsel | Review all employment agreements, severance plans, and equity arrangements | A change-in-control payment obligation not identified before close creates an unexpected cash outflow on Day 1; a senior executive whose agreement terminates automatically at close may claim constructive dismissal if not properly novated | Closed | Model all CIC payment scenarios — single-trigger, double-trigger, and modified single-trigger — before signing the SPA; confirm the price adjustment mechanism can absorb maximum CIC exposure; require employment counsel to review all executive agreements before close; do not execute any retention or separation agreement without General Counsel approval | T-16 | 2/14
Risk | RAID-005 | LEG-010 | Legal Due Diligence Complete | Corporate Counsel | Review corporate governance documents, board minutes, and ownership structure | A corporate authorization defect — a board resolution that did not have quorum, a shareholder vote that did not reach the required threshold, a subsidiary that was not properly included in the transaction structure — cannot be cured after close; the combined entity may be operating under documents that are facially valid but legally defective | Closed | Require deal counsel to certify that all board and shareholder resolutions authorizing the transaction are properly executed with quorum and required approval thresholds; obtain a legal opinion on corporate authority from target's counsel before close; do not proceed with closing document execution until all authorization defects are resolved | T-16 | 2/14
Dependency | RAID-006 | LEG-011 | Legal Due Diligence Complete | Regulatory Counsel | Identify all regulatory licenses, permits, and approvals that must transfer or be re-obtained | A regulatory license that lapses at close — because it was not re-applied for before the transfer — creates a period during which the combined entity cannot legally conduct the licensed activity; revenue from that activity stops the day the license expires | Closed | Require target management to provide a complete regulatory license schedule with expiry dates, transferability conditions, and re-application lead times before clean room access | T-16 | 2/14
Dependency | RAID-007 | LEG-012 | Legal Due Diligence Complete | Commercial Counsel | Identify all contracts requiring consent to assignment at close | A contract with an assignment restriction not identified before close gives the counterparty the right to terminate upon the assignment at close; a large customer or critical supplier who exercises this right on Day 1 creates an immediate operational and revenue crisis | Closed | Require target management to flag all contracts with assignment restrictions or change-of-control clauses in the initial data room; track consent status weekly with Legal Integration Manager; escalate any refused consent to General Counsel immediately | T-16 | 2/14
Risk | RAID-008 | LEG-014 | Legal Due Diligence Complete | Litigation Counsel | Assess and quantify all contingent liabilities and open litigation | A contingent liability that was not properly assessed and reserved creates a post-close earnings surprise when the reserve is established; the first time the combined entity discloses a material litigation reserve that was not disclosed in the deal announcement, it signals that due diligence was inadequate — damaging investor confidence at the most critical moment of post-close execution | Closed | Require target outside counsel to provide a complete litigation schedule with current reserve amounts certified by CFO; engage independent valuation counsel to stress-test reserves on the three largest exposures; include unquantified contingent liabilities in the rep and warranty insurance scope; confirm post-close litigation management responsibility is assigned before Day 1 | T-16 | 2/14
Dependency | RAID-009 | LEG-015 | Legal Due Diligence Complete | Commercial Counsel | Audit all software licenses for change-of-control and transfer restrictions | An enterprise software license that terminates automatically at close — because the vendor change-of-control clause was not identified and consent not obtained — can leave the combined entity without access to a mission-critical system on Day 1 | Closed | Require IT to provide a complete enterprise software inventory — vendor, product, seats, annual cost, change-of-control provision — before close; negotiate consent or alternative arrangements before close; do not migrate any licensed software before vendor consent is confirmed | T-16 | 2/14
Risk | RAID-010 | LEG-018 | Legal Due Diligence Complete | IP Counsel | Audit intellectual property ownership, registrations, and licensing arrangements | IP that appears owned by the target but is licensed or jointly owned creates a post-close dispute with the original owner; a patent that is invalid or improperly assigned in a key product line exposes the combined entity to infringement claims from the day it takes ownership | Closed | Require IP Counsel to review all IP registrations, ownership assignments, and joint development agreements before close; confirm that all employee invention assignment agreements are in place and enforceable; identify any IP that is jointly owned or licensed exclusively to a third party before close; include IP ownership representations in the SPA | T-16 | 2/14
Dependency | RAID-011 | LEG-019 | Legal Due Diligence Complete | Data Privacy Counsel | Review data privacy compliance posture and identify cross-border data transfer risks | A GDPR violation in the target operations becomes the combined entity violation at close; fines of up to 4% of global annual revenue are assessed against the entity that owns the data at the time of the finding, not the entity that created the problem | Closed | Complete a data privacy gap assessment against GDPR, CCPA, and all applicable local laws before close; for cross-border data transfers from the EU and UK, confirm that a valid transfer mechanism is in place | T-16 | 2/14
Risk | RAID-012 | LEG-020 | Legal Due Diligence Complete | Compliance Counsel | Assess anti-corruption, sanctions, and export control compliance | Anti-corruption or sanctions exposure inherited at close cannot be remediated retroactively; the acquirer assumes successor liability for FCPA violations from the date of acquisition regardless of when the violations occurred | Closed | Require target management to provide FCPA, UK Bribery Act, and OFAC sanctions compliance certifications and all government agency correspondence for the last 5 years — not 3 — as successor liability reaches back further; run OFAC and EU sanctions screening on all key personnel, major customers, and suppliers before any wire transfer is authorized | T-16 | 2/14
Assumption | RAID-013 | LEG-009 | Legal Due Diligence Complete | General Counsel | Acquired company General Counsel and senior legal staff will remain available and cooperative throughout the integration period — it is assumed that key legal personnel with institutional knowledge of legacy contracts, ongoing litigation, regulatory relationships, and corporate history will not depart before or immediately after close | If the acquired company's legal team departs at or near close, the combined entity loses the primary source of institutional knowledge on matters that cannot be fully captured in due diligence documents — undocumented litigation history, informal regulatory relationships, side letters, and oral commitments with counterparties that are not reflected in the contract repository; this assumption underpins every due diligence follow-up task and every post-close legal integration activity | Active | General Counsel to confirm retention status of acquired company's top 3 legal personnel before close; if any are departing, initiate knowledge transfer sessions for each of their key matter areas before their last day; include acquired company legal staff in Day 1 Legal playbook briefing (LEG-044) to establish relationships and begin knowledge transfer before close | T-16 | 2/14
Risk | RAID-014 | LEG-039 | Day 1 Legal Readiness Confirmed | Employment Counsel | Review and legally clear the M&A Employee Communication Guide | An employee communication that makes a promise about job security, benefits continuation, or role assignment that is later not honored creates a promissory estoppel or breach of contract claim; Legal clearance ensures communications inform without creating unintended legal obligations | Closed | Route the M&A Employee Communication Guide through Employment Counsel and General Counsel review before distribution; require Legal sign-off 5 days before the Day 1 communication release; flag any promise about role security, compensation, or benefits for explicit legal review — employee comms that create implied contracts are a significant post-close litigation risk | T-5 | 2/25
Dependency | RAID-015 | LEG-022 | Regulatory Approvals Obtained | Securities Counsel | Prepare and file all required securities law disclosures | A selective disclosure of material non-public information to any person before the required public filing — regardless of how informal the communication — constitutes a Reg FD violation that the SEC can act on without regard to whether the recipient traded on the information | Closed | Separate securities law filings from HSR/antitrust filings — they are governed by different agencies and timelines; require Securities Counsel to calendar all securities filings (8-K, proxy statement, Form S-4 if applicable) with deadlines at least 30 days in advance; require Antitrust Counsel to calendar HSR filing and waiting period separately; prohibit any selective disclosure of MNPI before required public filings | T-3 | 2/27
Risk | RAID-016 | LEG-024 | Pricing & Contract Harmonization Complete | Commercial Counsel | Develop contract harmonization roadmap for post-close execution | A contract estate managed without a harmonization roadmap will be renegotiated reactively — when contracts expire or counterparties raise issues — rather than proactively; reactive renegotiation consistently produces worse economic outcomes than planned renegotiation, and misses the window of combined-entity leverage that exists in the first 90 days | Closed | Complete the contract harmonization roadmap before Day 1 — categorizing every material contract as Keep As-Is, Novate to Combined Entity, Assign with Consent, or Terminate — and assign a named owner and deadline to each action; prioritize revenue-generating contracts and contracts with hard assignment deadlines first; present the roadmap to General Counsel for approval before close | T-3 | 2/27
Risk | RAID-017 | LEG-030 | Legal Due Diligence Complete | IP Counsel | Complete trademark and brand clearance in all operating jurisdictions | A combined brand name used in commerce before trademark clearance is obtained in a jurisdiction creates an unregistered use that a prior registrant can challenge; rebranding after a cease-and-desist is more expensive than clearing the name before use | Closed | Complete trademark clearance searches in every jurisdiction where the combined entity will use the brand before any public announcement; engage local trademark counsel in non-English speaking jurisdictions; do not launch any combined brand or product name before clearance is confirmed in all operating markets | T-3 | 2/27
Risk | RAID-018 | LEG-036 | Day 1 Legal Readiness Confirmed | Employment Counsel | Confirm Day 1 employment status for all acquired employees | An employee not properly transitioned at close — because the legal mechanism for transfer was not confirmed in advance — may have an immediate claim for constructive dismissal, wrongful termination, or breach of employment contract | Closed | Confirm the legal mechanism for employee transfer — TUPE, asset purchase transfer, or new employment agreement — in every jurisdiction where acquired employees are located at least 30 days before close; do not assume US-based employment transfer mechanisms apply to international employees; brief HR on jurisdiction-specific requirements before Day 1 | T-3 | 2/27
Risk | RAID-019 | LEG-037 | Day 1 Legal Readiness Confirmed | Employment Counsel | Review and finalize severance and CIC payment obligations | A CIC payment made without proper board authorization is potentially a breach of fiduciary duty; a payment that does not comply with IRC 409A timing rules creates a 20% excise tax on the recipient and a potential deduction disallowance for the payor — the combined entity inherits the tax exposure of its predecessor's payment practices | Closed | Model all CIC payment obligations — amount, trigger condition, timing, and tax treatment — before close; confirm that severance payments comply with 409A and ERISA; do not make any CIC or severance payment without General Counsel and CFO sign-off | T-3 | 2/27
Risk | RAID-020 | LEG-040 | Day 1 Legal Readiness Confirmed | Regulatory Counsel | Confirm all operating licenses and permits are valid at close | An operating license that is suspended, revoked, or not transferred at close means the combined entity cannot legally conduct the licensed activity from Day 1; revenue from that activity stops the day the license transfer fails | Closed | Confirm every operating license, permit, and regulatory approval is valid, transferable, and in the correct entity name; notify Regulatory Counsel immediately of any license that cannot be transferred before close; build a Day 1 contingency plan for any critical license that requires post-close transfer | T-3 | 2/27
Risk | RAID-021 | LEG-041 | Day 1 Legal Readiness Confirmed | Employment Counsel | Confirm all non-compete and non-solicitation agreements are enforceable in relevant jurisdictions | A key executive who signs a non-compete that is unenforceable in their jurisdiction can join a direct competitor the day after closing without legal consequence; the acquirer who paid a premium for the executive's customer relationships and institutional knowledge has no legal remedy when those assets walk out the door | Closed | Require Employment Counsel to assess NCA enforceability in every jurisdiction where key executives are located before close; do not rely on NCA provisions in California, Minnesota, North Dakota, or Oklahoma — they are unenforceable; develop alternative retention strategies for key employees in no-NCA jurisdictions | T-3 | 2/27
Risk | RAID-022 | LEG-042 | Day 1 Legal Readiness Confirmed | Regulatory Counsel | Confirm all regulatory pre-approval conditions have been satisfied | A regulatory approval that carries a condition the combined entity has not satisfied — even a condition it believes it has satisfied — gives the regulator grounds to revisit the approval post-close; regulators who find a closing condition was not met have reopened transactions months after close and imposed additional remedies | Closed | Require Regulatory Counsel to certify that all pre-approval conditions are satisfied at least 3 days before close; obtain written confirmation from each relevant regulatory body where possible; escalate any unsatisfied condition to General Counsel and the deal team immediately — closing without a satisfied condition can void the regulatory approval | T-3 | 2/27
Risk | RAID-023 | LEG-043 | Day 1 Legal Readiness Confirmed | Legal Integration Manager | Draft and distribute Day 1 Legal playbook covering roles, escalation paths, and decision authority for all Day 1 legal activities | A legal blocker discovered on Day 1 — an approval not obtained, a consent not received, a filing not made — cannot be remediated after the transaction has closed; the combined entity must operate under the constraint, often at significant cost or legal exposure | Closed | Circulate the Day 1 Legal playbook to General Counsel, IMO lead, and all Legal sub-team leads at least 3 days before close for review and sign-off; confirm every team member has read and acknowledged their Day 1 role; include the escalation path, decision authority matrix, and a named 24/7 contact for each legal sub-team | T-3 | 2/27
Risk | RAID-024 | LEG-D1 | Day 1 Legal Readiness Confirmed | General Counsel | Legal Day 1 Readiness Gate — confirm all Day 1 Readiness tasks complete, systems tested, communications ready, and no unresolved blockers prevent Day 1 execution | If any Day 1 Readiness task remains incomplete at this gate, the IMO must assess whether the gap is close-blocking; unresolved gaps here are the leading cause of Day 1 execution failures | Closed | Conduct the Legal Day 1 Gate 48 hours before close with General Counsel and IMO leadership; any gate item rated Red is a close blocker unless a specific compensating control is agreed; document every gate decision with sign-offs; assign a named owner and resolution deadline to every open item before the gate is approved | T-3 | 2/27
Risk | RAID-025 | LEG-025 | Regulatory Approvals Obtained | Regulatory Counsel | Identify and manage state and local regulatory approval requirements | A state regulatory approval that is not identified before close cannot be obtained retroactively while the combined entity is already operating; the combined entity operates without authorization during the approval period, exposing it to regulatory enforcement, fines, and potential forced divestiture in that state | Closed | Require Regulatory Counsel to confirm all state and local approvals are calendared ; initiate applications immediately for any approval with a lead time longer than 30 days; escalate any approval delay to General Counsel within 48 hours of identification | T-1 | 3/1
Assumption | RAID-026 | LEG-016 | Regulatory Approvals Obtained | Regulatory Counsel | All required regulatory pre-approvals will be obtained without conditions, remedies, or consent orders that materially alter the transaction structure, require divestitures, or impose ongoing behavioral obligations on the combined entity | If regulatory approvals are granted with conditions — including required divestitures, geographic restrictions, behavioral remedies, or firewall requirements — the legal integration scope changes materially; divestitures create parallel M&A processes; behavioral remedies require ongoing compliance monitoring that was not scoped into the Legal integration plan; firewall requirements constrain the pace and depth of integration and may invalidate synergy assumptions in the deal model | Active | Regulatory Counsel to monitor all pre-closing regulatory filings for any indication of conditional approval and immediately brief General Counsel and Executive Sponsor if any regulatory authority signals conditions; if conditions appear likely, convene an emergency Legal-Finance-IMO session to assess impact on integration scope, timeline, and deal model; plan for a conditional approval scenario with a separate work plan outline by T-42 | T-1 | 3/1
Risk | RAID-027 | LEG-045 | Closing Documents Executed | General Counsel | Execute all Day 1 legal closing documents | A closing document that is unsigned, executed by the wrong party, or executed without the required authority means the transaction has not legally closed in the manner the parties intended; the combined entity begins operating under an incomplete transaction structure, and correcting the defect after operations have begun is significantly more complicated than requiring proper execution before close | Closed | Confirm all documents are executed by the correct authorized signatories; build a closing document checklist with every required document and executed copy accounted for before the wire transfer is authorized | Day 1 (Close) | 3/2
Risk | RAID-028 | LEG-047 | WARN Notifications Issued | Employment Counsel | Confirm all legal entity structures are properly established | A legal entity that was dissolved, merged, or formed incorrectly creates tax, regulatory, and contractual complications that are discovered when the combined entity files its first tax return, applies for a permit, or is sued — not at the moment the structural error was made; entity structure defects discovered post-filing are expensive to correct and may require regulatory re-approval | Closed | Require Corporate Counsel to confirm all required entity formations, mergers, or dissolutions are legally effective before Day 1; obtain updated certificates of good standing for all key entities | T+4 | 3/6
Risk | RAID-029 | LEG-048 | Day 1 / Week 1 Legal Integration Complete | General Counsel | Execute contract novation and assignment for all required agreements | A contract that is assigned without the required counterparty consent is voidable at the counterparty's election; a major customer or critical supplier who discovers their contract was transferred without consent has a contractual basis to terminate that they did not have before the transaction closed — the novation failure creates the very termination risk that consent was designed to prevent | Closed | Confirm counterparty consent is obtained before executing any contract novation or assignment; require Commercial Counsel sign-off on each executed novation before the contract is treated as transferred; maintain a novation tracker updated daily | T+4 | 3/6
Issue | RAID-030 | LEG-048 | Day 1 / Week 1 Legal Integration Complete | General Counsel | Acquired company legal entity name conflict discovered on Day 1 — state filing searches in Texas and Colorado reveal the target's primary legal entity name is already registered by an unrelated third party in both states; the combined entity cannot conduct regulated business activity under that name in those jurisdictions without filing an amended entity name or registering a DBA | Operating under a conflicting entity name in Texas or Colorado creates state regulatory exposure and could result in contracts executed under that name being challenged; any regulated activity in those states — including invoicing, contract execution, and licensed operations — conducted under the conflicting name after Day 1 creates a compliance record that will require remediation; the longer this goes unresolved the more activity is tainted by the name conflict | Closed | General Counsel to engage local counsel in Texas and Colorado within 24 hours of Day 1 to confirm the scope of the conflict and file DBA registrations as interim relief; LEG-048 (confirm all legal entity structures are properly established) is the resolution vehicle — General Counsel to add entity name conflict remediation to the LEG-048 scope and confirm amended filings are submitted in both states before the 3/6 finish date; no contracts or regulated transactions should be executed under the conflicting entity name in Texas or Colorado until DBA registration is confirmed; Corporate Counsel to document all Day 1 activity in those states for the remediation record | T+4 | 3/6
Risk | RAID-031 | LEG-017 | Legal Due Diligence Complete | Commercial Counsel | Review and map all material contracts of the target company | A material contract not identified in due diligence that contains an unfavorable term — unlimited liability, exclusivity restriction, or change-of-control termination right — cannot be renegotiated post-close from strength; the combined entity learns of its exposure through contract performance, not proactive review | Closed | Require target management to provide a complete contract schedule — counterparty, term, notice period, change-of-control provision, and annual value | T+29 | 3/31
Risk | RAID-032 | LEG-D30 | 30-Day Legal Review Complete | General Counsel | Legal Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | If the Day 30 check reveals open tasks, unresolved blockers, or synergy owners not yet active, the integration team has 70 days to correct course — but the Day 30 review must force honest status reporting; teams that report green when yellow or red create hidden risk that surfaces at Day 100 when it is too late to recover | Open | Conduct the Day 30 Legal Review as a formal meeting with General Counsel and all Legal sub-team leads; require each lead to provide written RAG status on all open items; any Red item requires a named owner and resolution deadline agreed at the meeting; present synergy tracking status at the Day 30 review | T+32 | 4/3
Issue | RAID-033 | LEG-053 | Compliance Program Integrated | Data Privacy Counsel | Cross-border data transfer agreements stalling in two EU jurisdictions — Data Protection Authorities in Germany and France have not acknowledged Standard Contractual Clauses submitted pre-close; EU customer data is being processed post-close without a confirmed legal transfer mechanism, creating active GDPR regulatory exposure | Processing EU personal data without a valid transfer mechanism is a per-instance GDPR violation — it is not a future risk, it is an ongoing issue from Day 1 of post-close operations; GDPR penalties can reach 4% of global annual turnover; the combined entity cannot wait for DPA acknowledgment before acting — it must either pause EU data processing or implement an interim transfer mechanism; every day this remains unresolved increases regulatory exposure | Open | Data Privacy Counsel to immediately assess whether EU customer data processing can be isolated to EU-domiciled infrastructure while DPA acknowledgments are pending; engage local German and French privacy counsel within 48 hours to submit expedited DPA inquiries and document good-faith compliance efforts; implement Binding Corporate Rules as an interim transfer mechanism if SCCs cannot be confirmed within 10 business days; LEG-053 (execute cross-border data transfer agreements) is the resolution vehicle with a target finish of 4/15 — Data Privacy Counsel to confirm DPA acknowledgment is received and documented within LEG-053 before closing that task | T+44 | 4/15
Risk | RAID-034 | LEG-054 | Pricing & Contract Harmonization Complete | Commercial Counsel | Execute assignment and transfer of all IP to combined entity | IP that is used but not formally assigned to the combined entity gives the original owner — including a former employee, a co-founder, or a prior employer — a colorable claim of ownership; a patent infringement or trade secret misappropriation claim against a key product line, filed by a party who can demonstrate the IP was never validly assigned, creates an existential product liability that cannot be settled cheaply | Open | Confirm that all IP assignment agreements are executed with proper consideration in each jurisdiction — certain countries including Germany and France require separate employee consent for inventions made during employment, and blanket invention assignment clauses may not be enforceable; do not use or license any assigned IP until transfer registration is confirmed in each jurisdiction | T+59 | 4/30

## Next 14 Days
LEGAL M&A NEXT 14 DAYS ACTIVITIES
TODAY'S DATE: T+30
Risk Level | Status | Links
High | Not Started | Integration Plan
Medium | Delayed | Day 1 Checklist
Low | On Track | Milestones
| Complete | RAID Log
Executive Dashboard
Task ID | Category | Phase | Assigned To | Description | Risk Level | Timing Anchor | Start | Finish | Status | Critical Path
LEG-058 | Synergy Tracking & Realization | To Day 100 | Legal Integration Manager | Track and report legal synergy realization against deal model | Low | T+30 | 4/1 | 6/10 | On Track
LEG-D30 | Integration Management | To Day 100 | General Counsel | Legal Day 30 Integration Check — review progress against plan, confirm synergy tracking is live, flag open risks to IMO | High | T+30 | 4/1 | 4/3 | On Track | CP – Day 100

## Executive Dashboard
TODAY'S DATE: T+30 (60 DAYS BEFORE CLOSE — 1/1/2026)
LEGAL M&A INTEGRATION EXECUTIVE DASHBOARD
TODAY'S DATE: T+30
TASKS
|  |  | TOTAL |  | NOT STARTED |  | DELAYED |  | ON TRACK | COMPLETE
|  |  | 62 |  | 2 |  | 0 |  | 12 | 48
| MILESTONES |  |  | PROGRESS BY PHASE TASKS DONE/TASKS |  |  |  | RAID LOG SUMMARY |  | ANNUAL SYNERGIES
| Not Started | 3 |  | Pre-Close |  | 40/45 |  | Total Items | 34 | Targeted Synergies | $375K
| Delayed | 0 |  | Day 1/Week 1 |  | 7/7 |  | Open Risks | 2 | Realized Synergies | $0K
| On Track | 2 |  | Days 8-100 |  | 1/10 |  | Open Issues | 1 | CTA Budget | $45K
| Complete | 13 | [5 empty] | Dependencies | 5 | Actual CTA | $0K
[8 empty] | Assumptions | 2
| CRITICAL PATH MILESTONES | [6 empty] | NEXT 14 DAYS | 2 | DAY 1 | 10/10
|  |  |  | Phase | Target Date | Status |  | Total Tasks | 2 | Day 1 Readiness | 10/10
| Legal Lead Appointed |  |  | Pre-Close | 1/10 | Complete |  | On Critical Path | 1 | Day 1 / Week 1 | 7/7
| Legal Data Room Access |  |  | Pre-Close | 1/13 | Complete
| Legal Integration Governance Established |  |  | Pre-Close | 1/19 | Complete |  | LINKS
| Legal Charter Approved |  |  | Pre-Close | 1/19 | Complete |  | Integration Plan |  | Milestones | Next 14 Days
| Privilege Protocols Established |  |  | Pre-Close | 1/9 | Complete |  | Day 1 Checklist |  | RAID Log
| Legal Due Diligence Complete |  |  | Pre-Close | 2/27 | Complete
| Synergy Tracking Established |  |  | Pre-Close | 2/27 | Complete
| Works Council Consultation Complete |  |  | Pre-Close | 2/27 | Complete
| Day 1 Legal Readiness Confirmed |  |  | Pre-Close (Day 1 Readiness) | 2/27 | Complete
| Regulatory Approvals Obtained |  |  | Pre-Close | 3/1 | Complete
| Closing Documents Executed |  |  | Day 1 / Week 1 | 3/2 | Complete
| WARN Notifications Issued |  |  | Day 1 / Week 1 | 3/6 | Complete
| Day 1 / Week 1 Legal Integration Complete |  |  | Day 1 / Week 1 | 3/6 | Complete
| 30-Day Legal Review Complete |  |  | To Day 100 | 4/3 | On Track
| Compliance Program Integrated |  |  | Pre-Close | 4/15 | On Track
| IP Assignment Complete |  |  | To Day 100 | 4/30 | Not Started
| Pricing & Contract Harmonization Complete |  |  | Pre-Close | 5/31 | Not Started
| Day 100 Legal Integration Complete |  |  | To Day 100 | 6/10 | Not Started