## Slide 1
M&A DAY 1 TIMELINE, EVENTS &
COMMUNICATIONS

## Slide 2
Content
Key Milestones Timeline
April 19 Is the Day We Are One
Event Schedule April 20 And 21
Agenda for Global Town Hall
Guidance for Field Force and Shift Workers
Day One Employee Kits for Local Implementation
Day One Employee Welcome Package for All Employees
Day One Reporting Lines Reflected Minimal Change
Pay and Benefits “Grandfathered” Until January 26
Exceptions 2 “Grandfathering “
02

## Slide 3
03
Oct 30
Nov 17
Dec 5
Dec 12
Jan 8
Feb 6
Mar 6
Apr 19
Apr 20
Jun 20
Acquired Co. Board Accepts
Integration Kickoff Meeting
FTC Approval
Steering Committee Meeting
Nat’l Security Approval
European Union Clearance
Proposed Shareholder Vote
Proposed Day 1
(pending positive shareholder vote)
Day 60: all employees informed of job impact
SEC Proxy Mailed following SEC Agreement
Key Milestones Timeline

## Slide 4
04
April 19 is the Day We Are One
Vote
Close
Effective date
Day 1
Settlement
  Event
  Date
  Description
  April 19
  (morning)
  Acquired Co. shareholders council votes on Acquirer offer
April 19
  Legal agreement that all contractual conditions for the deal are met
  Deal irreversible, can start directing the company
April 19
  Certificate of merger submitted to State Secretary of Delaware
April 20
  Day 1 event & town halls
April 19/20
  Acquirer transfers funds to agent who pays out Acquired Co. shareholders

## Slide 5
05
Event Schedule April 20 & 21
8:00
10:00
12:00
14:00
16:00
9:00
11:00
13:00
15:00
17:00
18:00
7:00
19:00
20:00
21:00
22:00
23:00
24:00
8:00
10:00
12:00
14:00
16:00
9:00
11:00
13:00
15:00
17:00
18:00
7:00
19:00
20:00
21:00
22:00
23:00
24:00
Welcome Event/Luncheon
Prod Dev. town hall
Division town hall
TechOps
Swing Shift
HR office on site for Q&A
TechOps
Grave Shift
Commercial 1 Mtg.
Commercial 2 Mtg.
Swing Shift
TD&O
Tech Ops Town Hall
Grave Shift
Mfg
Quality Ops
Supply Chain
HR office on site for Q&A
Global Town Hall with
CEO and President
April 20
April 21

## Slide 6
06
Agenda for Global Town Hall
Timing
Topics
3 min
5 min
5 min
15 min
5 min
30 min
Motivational video
Welcome!
Overview of morning schedule/process
Video message from President
Welcome to Acquirer – One company
  Acquirer mission, values, strategy
  Overview of Acquirer’s structure/division
  Destinations of Acquired Co. business in Acquirer’s divisions – identifying the end-owners
Next steps in integration
Q&A

## Slide 7
07
Guidance for Field Force and Shift Workers
Field Force
Field force to remain in the field unless within 50 miles of an office
Day 1 welcome kits to personal addresses
Ensure access to the live webcast or replay to all remote personnel
  Back-up plan
    mail video > Day 1;
    Convene a telecon for FF
    1:1
Do not disrupt the shift patterns
Evening shift (in Europe) to attend regular Day 1 activities on the site
Following morning, shifts each day to have separate briefings by local management and view a video replay
Shift Workers
Sales managers and work stream leaders responsible for execution
Day 1 coordinator and respective site managers responsible for execution
Other critical operational functions will be handled through respective line managers (e.g. switch boards, etc.)

## Slide 8
08
Day 1 Employee Kits for Local Implementation
Welcome to the Acquirer-Acquired Co. Integration Kit
It contains useful reference/guidance material to ensure that a globally agreed consistent messaging is conveyed to all parts of the organization
This tool has been created to facilitate the handover of responsibility for the Acquirer-Acquired Co. merger (pre- and post-close) from the global integration team to local senior HR/Line managers
Background info
HR policies
Global plan & core process
Local planning from day 2 and beyond
Contacts for more help
FAQs

## Slide 9
09
  Welcome gift (travel clock)
  Welcome letters
    CEO and President
  Local schedule of activities
    Provided locally for first few days - including on-boarding
  FAQ document
    Top-line questions
  Acquirer fact sheet
  Organizational charts (new reporting structure)
  Overview of selection process
  IT Day 1 Fact sheet
Branded Welcome Kit Includes:
Day 1 Employee Welcome Package All Employees

## Slide 10
10
Day 1 Reporting Lines Reflect Minimal Change
  Changes reflect minimal disruption given Acquirer structure
    Each component of Acquired Co. will report to the unit in Acquirer accountable for the transition and for performance going forward*
    Approximately 50 Acquired Co. people will change reporting lines on Day 1, mostly senior managers
    Nearly all employees will report to same supervisor on Day 1
  Day 1 reporting lines will be clearly communicated on Day 1
    Summary charts included in Day 1 Welcome packages
    HR site contact on every site will have detailed list
* Minimal change in Europe on Day 1 due to legal and consultation considerations

## Slide 11
11
Current Acquired Co. HR policies will be “grandfathered” (i.e., remain intact until December 31, 2026)
Employee pay and benefits will also be “grandfathered” until December 31, 2026
Transition to Acquirer policies, compensation and benefits will be decided and communicated within the next 6 months
    Transition will be coordinated globally and determined based on local legislation
    Within 120 days after close, Acquirer will communicate job levels and pay ranges (Acquired Co. jobs slotted into Acquirer scheme)
Pay and Benefits “Grandfathered” Until Jan. 26

## Slide 12
12
Exceptions to “Grandfathering”
    Acquirer policies will be implemented upon deal close
  Acquired Co. associates transferred to an Acquirer’s site will transition to Acquirer policies and compensation & benefits upon transfer
  Acquired Co. associates will receive full Acquired Co. service credit for the purpose of Acquirer benefits with the exception being the pension fund
  Compensation & Benefits – related policies:
    Employee loans, relocation policy, international assignments
    All current cases will continue under the Acquired Co. policy, any new cases will follow Acquirer policy
  General (Non-HR) global policies (e.g., Code of Conduct, Corporate Citizenship, etc.)

## Slide 13
12
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting