## Slide 1
M&A Day 1
Worldwide

## Slide 2
Content
Day One Implementation
What Must Happen on Day One
Three Phases of Integrations
Managing Expectations
HR: Day One
Headquarters Day One Event Schedule
Day One at HQ Will Be Telecast Worldwide
IT Accessibility for Acquiree On Day One
02

## Slide 3
Day 1 Implementation
  Day One is an Event – Worldwide
    Plan Consistently Across All Sites
    Manage Expectations
    Deliver a Consistent Message
  Designed around 3 Core Goals
    Welcome to Acquirer
    Communicate Shared Vision
    Foster Collaboration Going Forward
03

## Slide 4
What Must Happen on Day One
Ensure Every Employee Knows Who He or She Reports to on Day One
Maintain Continuity of Payroll and Benefits Systems for All Employees
Ensure Managers and HR Staff Are Prepared to Answer Tough Employee Questions
Ensure Every Employee Knows Who His or Her HR Contact Is
Communicate Selection and Severance Policies
04

## Slide 5
Three Phases of Integrations
Responsibilities
Business leaders accountable for recommendations and implementation
Integration office manages and tracks overall process
Information gathering and hypothesis generation
Integration planning and decision making
Implementation
Timing
Key activities
Dec/Jan
Feb/Mar
Day One
Establish baseline for decision making
Generate initial hypothesis
Validate synergies
Recommend and approve integration approach
Produce detailed integration plans
Execute implementation plans
Progress tracking (synergies and milestones)
1
2
3
05

## Slide 6
Managing Expectations
Worldwide event
Welcome communication
Minimal reporting line changes
Phased IT accessibility
Financial control
06

## Slide 7
HR: Day One
Could Also Happen on Day One
Inform employees of key decisions
  Their status in selection process
  Site closures and timelines
  Layoffs (numbers and timelines)
Describe how personnel decisions are/will be made
Disseminate interview schedules
Describe outboarding process/severance for employees who will not remain with Acquirer
Distribute Day One welcome gifts
Distribute welcome packets
Gather feedback on Day One perceptions
Will Only Happen Later
Change HR policies
Change compensation
Change benefit packages
Begin out-placement process for employees being released
07

## Slide 8
Headquarters Day One Event Schedule
HR Help Line
Town Hall
CEO 8:00-9:00
Welcome event/luncheon 11:30-2:00
Division town hall 2:00-3:30
7:00
8:00
9:00
10:00
11:00
12:00
13:00
14:00
15:00
16:00
17:00
18:00
19:00
08

## Slide 9
Day One at HQ Will be Telecast Worldwide
Los Angeles
Various Remote Locations to be Announced Days 1 and 2 Activities Vary by Country
Consult country site coordinator for specific local plans surrounding the global town hall
8:00 – 9:00 am
Global town hall
2:00 – 3:30 pm
Division Town Hall
09

## Slide 10
IT Accessibility for Acquiree on Day One
Email
Application
Intranet
  Send and receive via current Acquiree email address securely
  Access to same tools and applications
  Migration over time communicated and trained
  Continue to access same Acquiree pages
  Access to key Acquirer sites
12

## Slide 11
10
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting