## Slide 1
M&A INTEGRATION KICKOFF MEEETING
MARKETING

## Slide 2
PLAN CONTENTS
Assumptions
Branding Strategy
Team Charters (Branding, Marketing, Communications)
End States
Branding Migration
Branding Integration Plan
Dependencies
Savings and Cost Estimates
Risks and Mitigating Actions
Open Issues
Key Actions by Team (Branding, Marketing, Communications)
© 100-Day Advisors MandAPlaybook.com

## Slide 3
ASSUMPTIONS
Marketing will be consolidated into one organization
Launch of one consolidated go-to-market plan for next year
Global Marketing will drive branding and development and sharing of best practices and regions will continue to drive development and execution of annual go-to-market plans
Brand will migrate to Acquirer beginning immediately upon close and migration will be complete by end of Q1 next year
All communication will be coordinated globally with opportunity for local customization to address region-specific issues
© 100-Day Advisors MandAPlaybook.com

## Slide 4
STRATEGY
BRANDING
One Brand – Acquirer’s
Broader meaning in solutions context
Same target audience
Relatively homogeneous needs globally
Desire for global solutions by partners and clients
Overlapping value proposition
Greater investment in broad awareness building
No legal or translation issues identified
© 100-Day Advisors MandAPlaybook.com

## Slide 5
TEAM CHARTER: BRANDING
Areas in Team’s Scope:
Definition of the brand architecture for the Company
Development and execution of the detailed brand transition plan
Identification and migration of all business elements (including signage, collateral, promotional items, business documents, etc.)
Development of a budget to cover the cost of migration
Development and execution of a plan to build excitement and support for the Acquirer’s brand with employees, clients, partners and the general public
Deliverables:
Clear articulation of the branding strategy and supporting rationale
Detailed articulation of the plan to migrate the brand to Acquirer
Flawless execution against plan
Redesigned materials in support of the new brand
Key Questions:
Need to understand the exact timing for the legal migration of the Acquiree company to the Acquirer company in EMEA, APAC and Canada as this impacts the ability to migrate the brand
What are the budget restrictions which will impact our ability to build awareness of the combined brand?
What will be the format of the employee meetings/rallies following the first of the year and can these be used as the launch of our combined brand, consolidated strategy, and go-to-market plan?
Charter Statement:
Development and execution of the strategy and plan for the migration of the Acquiree’s brand under the Acquirer’s brand.

## Slide 6
TEAM CHARTER: MARKETING
Areas within Team’s Scope:
All aspects of the integration of the Acquiree and Acquirer marketing organizations
Identification and elimination of redundancies in the organizations
Definition of roles, accountabilities, and reporting relationships to ensure clarity
Execution of the organization redesign
Development of the combined next year’s Go-To-Marketing plan
Identification of opportunities to drive increased supplier reimbursement through marketing Articulation of the plan to stakeholders
Flawless execution against those plans
Deliverables:
Detailed plan for the integration of the two companies’ marketing teams, including coordination with other functional leads to optimize the organization and eliminate duplication of effort and redundancies
Execution of that organizational plan
Detailed strategy and plan document articulating next year’s go-to-market plan
Execution of plans
Key Questions:
What is the optimal structure and reporting relationship for Business Intelligence and the Web / e-commerce?
What are the core competencies of each organization?
Which marketing functions should be global in scope and which should be regional?
What are the marketing needs of software publishers
Need to fully understand the current Acquiree contribution to overhead (particularly headcount) and how to minimize losses
Charter Statement:
Coordinated project plan for integrating the global marketing teams and consolidated go-to-market strategy / plans.
© 100-Day Advisors MandAPlaybook.com

## Slide 7
TEAM CHARTER: COMMUNICATIONS
Areas in Team’s Scope:
All aspects of communication relative to the acquisition and integration of Acquiree
Providing vehicles and coordinating with other integration teams to ensure important information is communicated on a timely basis
Definition and execution of all interim and on-going internal communication
Coordination and execution of all external communication to clients, partners and analysts/shareholders
Ensure employees feel informed and have a solid understanding of important developments that may impact them or their job
Deliverables:
Detailed communication plan for the integration to keep all key constituencies informed throughout the process (employees, clients, partners, shareholders, analysts)
Flawless execution against that plan
Key Questions:
How quickly can we migrate to a common intranet and website?
What are the expected and preferred communications means at Acquiree?
What are the employee and client concerns which must be addressed as part of the communications plan?
Charter Statement:
Coordinated strategy and project plan for communicating all important information relative to the acquisition and integration of Acquiree into the Acquirer ‘s business. Key constituents include employees, clients, partners and analysts/shareholders.

## Slide 8
END STATES
One consolidated Marketing organization
Business Intelligence and E-Commerce functions and reporting relationships clearly defined and re-organization implemented
One consolidated go-to-market plan per region
One consolidated and globally coordinated communication plan – new, consolidate strategy and plan will launch January 1
© 100-Day Advisors MandAPlaybook.com

## Slide 9
BRANDING
MIGRATION
Particular care paid to managing client perceptions and concerns
Encourages assimilation of employees’ attitude of one organization with aligned goals and a common culture
Communicates alignment with client and partner desire for more global solutions and routes to market
In APAC and non-UK EMEA, allows transition to take place when we can reassure clients that nothing else is changing
1.
2.
3.
4.
© 100-Day Advisors MandAPlaybook.com

## Slide 10
BRANDING INTEGRATION PLAN
Quickly establish one company brand name and image
Build excitement for and confidence in the new entity among key constituencies (employees, partners, clients and the market)
Build a sense of one team and one culture as quickly as possible
Minimize client confusion, disruption and lost revenue through the transition
Ensure reinforcement of the newly acquired capabilities
© 100-Day Advisors MandAPlaybook.com

## Slide 11
DEPENDENCIES
Dependency
Group(s) or Function(s)
Branding
IT, Facilities, Suppliers (of materials)
Communication
IT, Integration team leads
Marketing Organization Design
Geographic leads, Global Client Ops.
Go-to-Market Plans
Product Management, Sales
© 100-Day Advisors MandAPlaybook.com

## Slide 12
DEPENDENCIES
Item
One-time expenses or gains
Increases or Decreases to Ongoing Operating Expenses (annual basis)
Capital Expenditures
Comments
(include any information regarding timing)
Expenses
Gains
Increases
Decreases
1. Efficiencies gained through reductions in duplicate headcount
2. New signage, collateral, business materials, etc. to reflect the brand migration to Acquirer
3. Migration to common intranet
$300K
$125K
Month 2
Rough estimate
Rough estimate
$100K
Total
Rough estimate
$100K
$300K
$125K
© 100-Day Advisors MandAPlaybook.com

## Slide 13
RISKS AND MITIGATING ACTIONS
Risk
Mitigating Actions
1. Culture : Marketing is viewed very differently at Acquiree and is held accountable to different metrics. There will likely be some difficulty in transition to the New Acquirer among current employees.
To reduce risk we propose an inclusive approach in the development of next year’s marketing plans, and in integration planning and implementation. In addition, monthly department meetings will include updates on integration activities and will provide a forum for questions and feedback.
2. Service Level: there is risk that the consolidated customer satisfaction rating will not equal or exceed the sum of the current ratings attained by each organization.
We will establish current service levels and understand the value driving that attainment. We will work closely with PM and the Acquiree marketing team to put bridge plans to ensure attainment of customer satisfaction rating equal to or above current levels. Opportunity exists to target SMB to drive incremental service rating from existing Acquiree partners. We are working closely with PM to modify next year’s go-to-market plan as appropriate to maximize partner satisfaction and customer satisfaction rating attainment.
3. Communication: There is a risk that we will not communicate in the preferred manner to Acquiree employees and that key messages will not be “received”.
We are conducting a communications audit in September to understand Acquiree teammate communication preferences. Communication vehicles and plans will be modified as appropriate based upon the learning.
4. Loss of key employees: There is the risk that the uncertainty during the integration period will cause key employees to leave the organization.
Our intent is to move aggressively through the organization integration to minimize the length of time where such uncertainty exists. In addition, we are reaching out to key individuals to reassure them and communicate their value to the organization.
5. Client disintermediation: There is a risk that clients may become concerned about the potential for changes in the Acquiree value proposition, or for the loss of expertise in the unique capabilities relative to software due to the change in the brand name, and, as a result, they may leave the franchise.
The migration of the brand has been charted over a course of time (to be completed in six months). Throughout this process, client communication is a key component of the plan. We will reassure clients that their relationship is important to us and that we will maintain the unique competencies from Acquiree that they value. A comprehensive brand migration plan and supporting communication plan are in place.

## Slide 14
OPEN ISSUES
More thorough understanding of Acquiree marketing plan
  Full breakdown of current Acquiree marketing budget
  MDF activity and income details
  SR targets and income by vendor / publisher
Completion of next year’s go-to-marketing plan modifications
Implementation of Phase II (30/60/90 day) communication plan
Completion of brand transition planning
© 100-Day Advisors MandAPlaybook.com

## Slide 15
COMMUNICATION – KEY ACTIONS
Implement all Day One communication – done
Develop 30/60/90 Day communication materials – September 18
Field communications audit – completed by September 30
Establish regular cadence of meetings to identify communication needs – September 15
  Integration Newsletter
  Integration Bulletins
  Updates to Q&A
  Client presentation
Write Phase III plan – October 1
Phase III is the launch of a comprehensive, consolidated communications strategy and plan on Jan. 1
© 100-Day Advisors MandAPlaybook.com

## Slide 16
KEY ACTIONS
BRANDING
Communicate branding plan to integration team and marketing teams
Conduct audit of all materials and places with Acquiree logo
Develop detailed design and transition plan – done
  Detailed plan by “bucket” of activity to be completed by September 15
Conduct global trademark search of Acquirer and determine international appropriateness of name - done
Design and execute Phase I transition materials - done
Design Phase II transition materials - September 30
Phase II implementation – begins September 11
Determine transition of client transaction documents (invoice, statements, etc.) - September 30
© 100-Day Advisors MandAPlaybook.com

## Slide 17
MARKETING KEY ACTIONS
Meeting to share current organization design and functions / accountabilities – done for E-commerce and Marketing – pending for Business Intelligence
Develop design of global marketing team – September 20
  Roles and accountabilities – global versus regional
  Focus for development of best practices
  Areas of standardization and areas of customization
Design, communicate and launch integrated marketing organization – October 15
Develop, communicate and launch E-commerce organization – October 15
Develop, communicate and launch business intelligence organization – January 1
© 100-Day Advisors MandAPlaybook.com

## Slide 18
GO-TO MARKETING KEY ACTIONS
Meeting to share current go-to-market plans, discuss partner needs and identify potential issues – done
Development of integrated go-to-market plan – October 15
Partner Forum to “sell” plan – November 7-8
Implementation of plan – January 1
1.
2.
3.
4.
© 100-Day Advisors MandAPlaybook.com

## Slide 19
contact us
thank you
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com