## Sheet 1 - PMI_End_State_Log
POST-MERGER INTEGRATION END STATE LOG
Remaining Actions After Integration Team Disbandment
ID | Category | Task Description | Owner | Department | Priority | Status | Due Date | Dependencies | Notes
1 | Documentation & Archives | Archive all integration team meeting notes; decisions; and project documentation | Sarah Chen | PMO | High | In Progress | 2026-03-15 | IT to set up permanent archive location | Need to ensure all SharePoint folders are properly organized and access is granted to business unit leaders
2 | Documentation & Archives | Complete final integration lessons learned report | Michael Torres | PMO | High | Not Started | 2026-04-01 | Input from all former workstream leads | Compile feedback from all workstream leads. Document what worked; what didn't; and recommendations for future M&A
3 | Team Transition | Transition remaining open items to permanent business owners | Jennifer Park | PMO | Critical | In Progress | 2026-02-28 | Business unit acceptance required | Creating detailed handoff documents with context; history; and next steps for each item
4 | Team Transition | Officially disband integration steering committee | David Kim | Executive | Medium | Not Started | 2026-03-30 | All workstreams must report final status | Schedule final steering committee meeting to formally close out integration
5 | Communications | Send final all-employee communication announcing integration completion | Amanda Rodriguez | Communications | High | Not Started | 2026-03-15 | CEO approval required | Celebrate successes; acknowledge team efforts; outline what comes next
6 | Communications | Update external stakeholder communications (customers; investors; partners) | Robert Chang | Communications | Medium | Not Started | 2026-03-20 | Investor Relations sign-off | Ensure all external parties know integration is complete and who to contact going forward
7 | Systems & Access | Decommission legacy email addresses and redirect to new domain | Lisa Martinez | IT | Medium | Not Started | 2026-04-30 | All employees transitioned to new email | Set up auto-forwarding for 12 months; then disable old domain
8 | Systems & Access | Remove integration team members from temporary access/systems | James Wilson | IT Security | High | Not Started | 2026-03-10 | List of all temporary access grants | Revoke special permissions granted during integration. Audit to ensure no orphaned accounts
9 | Facilities & Real Estate | Finalize disposition of duplicate office locations | Patricia Lee | Real Estate | Medium | In Progress | 2026-05-31 | Legal approval on lease terminations | Three leases remain to be terminated or subleased. Legal review in progress
10 | Facilities & Real Estate | Remove all legacy company signage and branding from retained locations | Marcus Johnson | Facilities | Low | Not Started | 2026-04-15 | New signage design approved | Replace with unified branding. Schedule to minimize business disruption
11 | Financial & Legal | Close remaining legacy legal entities and bank accounts | Rachel Adams | Legal | High | In Progress | 2026-04-30 | Final tax clearances from state authorities | Four subsidiaries pending dissolution. Final tax filings required
12 | Financial & Legal | Complete final integration cost accounting and close project codes | Karen Thompson | Finance | Medium | Not Started | 2026-03-31 | All outstanding invoices processed | Reconcile all integration expenses; prepare final budget vs actual report
13 | Vendor & Contracts | Terminate or reassign contracts with integration-specific vendors | Steven Brooks | Procurement | Medium | Not Started | 2026-03-31 | Legal review of termination clauses | Consultants; temp agencies; and project management tools no longer needed
14 | HR & People | Return or reassign integration team members to permanent roles | Diana Foster | HR | Critical | In Progress | 2026-02-28 | Department heads confirm available positions | Ensure smooth transition. Recognition program for integration team contributions
15 | HR & People | Process final retention bonus payments for key integration personnel | Michael Torres | HR | High | Not Started | 2026-03-15 | CFO approval on final list | Verify eligibility criteria met. Coordinate with Payroll for March payment
16 | Knowledge Transfer | Complete knowledge transfer sessions for complex technical integrations | Alex Rivera | IT | High | In Progress | 2026-03-20 | SMEs available for training sessions | Document tribal knowledge before integration team members return to regular roles
17 | Governance | Update corporate governance documents to reflect post-merger structure | David Kim | Legal | High | Not Started | 2026-04-15 | Board approval at next meeting | Bylaws; operating agreements; delegation of authority - all need final updates
18 | Reporting & Metrics | Prepare final synergy realization report for Board and investors | Jennifer Park | Finance | Critical | Not Started | 2026-04-01 | Data from all business units | Compare actual synergies achieved vs. deal model projections
19 | Insurance & Risk | Consolidate all insurance policies under single corporate entity | Thomas Wright | Risk Management | Medium | In Progress | 2026-05-01 | Insurance broker proposal review | Working with broker to cancel redundant policies and update coverage
20 | Culture & Change | Conduct post-integration employee survey to assess culture integration | Amanda Rodriguez | HR | Medium | Not Started | 2026-04-30 | Survey vendor selection | Measure employee sentiment; identify remaining cultural friction points
© 100-Day Advisors MandAPlaybook.com