## Cover
POST-MERGER INTEGRATION LESSONS LEARNED EXAMPLES

## SHEET1
Post-Merger Integration Lessons Learned Examples
Issue / Observation | Lessons Learned / Recommendation | Impact Type | Impact Severity | Stakeholder
Version Control - challenge keeping track of changes to milestones; often overwriting each others changes | Push changes to a central owner or use SharePoint for edits; either way need to share changes with stakeholders | Schedule | Low | IMO
Integration Strategy - not well defined by deal / function (e.g. early back and forth with Finance on full integration timing) | Need to better set expectations by deal / function for integration and allow teams to present justification for exceptions | Schedule / Budget | High | Functional Leads
Not planning during g due diligence | Phase diligence and planning to fit the objective (light or full integration)
Reporting - leadership only wants to see the major milestones; too many milestones clutters the timeline slide | Keep the critical milestone list to major deliverables; consolidate where feasible | Schedule | Low | IMO
Resource Constrained between deal and running the business (e.g., year/quarter/month end reporting for Finance) | Need to resource balance between RTB (Run the Business) and deal work to allow teams time to properly do due diligence, planning and execution | Schedule | Medium | IMO
Unclear strategy for managing the plan (e.g. project plans vs critical milestones and how they connect to timeline, dashboard, Steerco updates). Also, what are the expectations for managing to a plan (i.e. scope, schedule and/or budget). Schedule seems the most flexible while consideration of how much it costs to execute is not managed at all. | Need to define a process that the stakeholders (functional leads, deal leads, SteerCo) understand how it works and get what they need as inputs and outputs. | Reporting | Low | IMO
Uncertainty related to which plan teams are expected to manage or be measured by… (some teams rely on and expect to be managed by their project plans and others simply haven't used their project plans). | Set clear standards for defining and managing to a plan. When the plan dates are managed by the IMO it does not take into consideration running the business efforts. It is preferable to have the functions set dates as they know their workloads better than the IMO. | Schedule / Reporting | Medium | IMO
The team loses any insight into dependency mapping or cost when we transition to the Critical Milestones. | We need to either add dependency mapping capability and/or cost to the Critical Milestone tracker or pull reporting from the functional project plans | Schedule / Reporting | High | IMO
Past due milestones results in an outdated milestone list and lack of drive to close things in a timely manner. Execs have noted when items are past due and green, which leaves more questions than answers. | Need to chase updates to better understand when a past-due milestone really is a issue because of a true deadline or critical dependency or is something that can slip. | Schedule | Medium | IMO
Unclear deliverables - too often titles / descriptions were not well defined with a clear output or deliverable in mind. | Milestones should clearly state when a deliverable is a plan vs execution and when the output is an input into another critical milestone. | Scope / Schedule | Medium | Functional Leads
One tracker creates an issue when trying to drive reporting for some or all tasks without the ability to filter for your audience. | When tracking minor actions, sensitive or critical milestones in the same tracker you need the ability to filter reporting for the different audiences (e.g. Team Lead vs. Steerco vs. Acquired Resources). | Reporting | Low | IMO
Roles & Responsibilities - I think we missed an opportunity to define how we plan, manage, execute and the expectations of the functional leads vs the IMO vs the Steerco. We had functional leads thrown at the deals mid-flight who didn't understand expectations and missed on deliverables (e.g. asset assessments) | Spend 15 min during kick-off to define the workstreams / leads objectives and the expectations | Scope / Schedule | High | IMO
Consistently set requests but failed to follow up with them; impact is that folks tune out requests. | Need better follow up when Next Steps require feedback or tasks / milestones are due. | Schedule | Medium | IMO
Feeling our way through a planning and tracking (e.g., Project Plans vs Milestone List, Action Items) | Need a defined process and tool set for planning and tracking the program. | Schedule / Reporting | High | IMO
Ownership - when you have multiple owners you have no owner. | Need to clear on ownership and who is driving a task / milestone vs stakeholders who own inputs to the deliverable. | Schedule | Medium | IMO
Change Management Plan (Comms, Training, etc.) | Traditionally during due diligence you recognize process changes and create a change management plan aligned to the project plan by function. The concern is that we are only focused on training, which is only one aspect of change management. | Change Management | Low | IMO
War Room email address for issues or questions has not been used; concern there are questions / issues that are not being addressed | Need to do a better job at communications to make sure users know about the email list | Change Management | Low | IMO
Metrics - no metrics to prove we are not impacting day-to-day business or improving process at the target or Acquirer. | Teams should propose 2-3 metrics by which they are regularly measured and can be applied / reported on at the target | Synergy | Low | IMO
Integration Due Diligence - no evidence of quality due diligence to use as a planning input | Need to see diligence docs as evidence the proper analysis is being done to build plans and execute | Scope / Schedule | High | IMO
© 100-Day Advisors MandAPlaybook.com

## Sheet2
Phase | Function | Impact Type | Impact Severity
Scoping | GDR Biz | Scope | High
Planning | IT | Schedule | Medium
Analysis / Design | CPE | Budget | Low
Development | Waterfall | Resources
Test | Adoption | Metrics
Release | Internal Comms
CM&C | RAIC
Disti
Services
Channels
CCW