## Synergy Tracker
Synergy Tracker
[8 empty] | Opportunity Type (mark one with X) |  |  |  | Opportunity Phase (mark one with X) |  |  | Annual Savings ($000s) | [5 empty] | Additional Details
Synergy Initiative # | Function - Business/Product Line - Sub-function | Workstream | Workstream Ref # | Description of Synergy Opportunity | Category | Date Original Input | Date Updated | Eliminate Redundancy | Revenue Increase | Service Level | Service Delivery Model | Phase 1: Opportunity Identified | Phase 2: Approved | Phase 3: Implemented | Salaries & Wages | Payroll-related Costs | Dues/ Subscritpions | Facilities Costs | Other Non-Labor | TOTAL | Position Title (Labor reductions only, list all headcount reductions on separate lines) | Date Estimated Implement | Date Actual Implement | Risk-Exposure L,M,H | Difficulty | Transfer? Y/N | Costs to achieve ($000s) (excluding severance) | Comments Discuss implications/considerations of implementing, key activities to be done to implement, potential risks to the company as a result of implementing, key milestones to achieve, difficulties or barriers to implementing
1 | Finance / Corporate | Financial Reporting | 1.1 | Consolidate external audit and consulting fees under single engagement | Labor/Non-Labor | 1/15/2026 | 2/1/2026 | X | [5 empty] | X | 180 | 27 |  |  | 10 | 217 | Sr. Finance Manager | 6/30/2026 |  | M | Medium | N | 45 | Consolidate Big 4 engagement; estimated 35% fee reduction on consulting scope
2 | Finance / Corporate | Financial Reporting | 1.3 | Eliminate duplicate financial reporting software licenses | Non-Labor | 1/15/2026 | 2/1/2026 | X | [5 empty] | X |  |  | 30 |  | 5 | 35 |  | 3/31/2026 | 3/31/2026 | L | Low | N | 8 | Consolidate to single reporting platform; contract renegotiated
3 | Finance / Corporate | Technical Accounting | 2.1 | Reduce technical accounting FTE through unified policy framework | Labor | 1/20/2026 | 2/5/2026 | X |  |  |  |  | X |  | 120 | 18 |  |  |  | 138 | Accounting Manager | 9/30/2026 |  | M | Medium | N | 22 | Unified GAAP policy eliminates duplicate research workload across legacy entities
4 | Finance / Corporate | Technical Accounting | 2.3 | Consolidate SAP Finance Master Data team post-ERP integration | Labor | 1/20/2026 | 2/10/2026 | X |  |  |  |  | X |  | 160 | 24 |  |  |  | 184 | SAP Finance Analyst | 9/30/2026 |  | M | High | N | 55 | Single SAP instance achieved; master data maintenance FTE reduced from 3 to 1.5
5 | Finance / Corporate | Company Accounting | 3.1 | Reduce corporate planning and decision support FTE | Labor | 1/25/2026 | 2/10/2026 | X |  |  |  |  | X |  | 140 | 21 |  |  |  | 161 | Financial Analyst II | 12/31/2026 |  | H | High | N | 30 | Consolidate FP&A and decision support into single COE; reduce headcount by 0.5 FTE
6 | Finance / Corporate | Company Accounting | 3.2 | Bank account rationalization — reduce from 18 to 9 accounts | Non-Labor | 1/25/2026 | 2/15/2026 | X | [5 empty] | X |  |  |  |  | 20 | 20 |  | 3/31/2026 | 3/31/2026 | L | Low | N | 10 | Bank fees and reconciliation workload reduced ~40%; two FTE redeployed
7 | Finance / Corporate | Company Accounting | 3.6 | Consolidate tax provision and statutory filings under single entity | Labor/Non-Labor | 1/25/2026 | 2/15/2026 | X |  |  |  |  | X |  | 95 | 14 |  |  | 15 | 124 | Tax Analyst | 6/30/2026 |  | M | High | N | 38 | Reduce from 4 to 2 statutory entities; external filing costs reduced
8 | HR / Benefits | Benefits | 4.1 | Consolidate pension plan actuarial and audit engagement | Non-Labor | 2/1/2026 | 2/20/2026 | X | [5 empty] | X |  |  |  |  | 55 | 55 |  | 6/30/2026 |  | M | Medium | N | 20 | Single actuary retained; plan audit consolidated — saves ~$55K annually
9 | HR / Benefits | Benefits | 4.2 | Renegotiate group insurance carrier under combined employee base | Non-Labor | 2/1/2026 | 2/20/2026 | X |  |  |  |  | X | [5 empty] | 45 | 45 |  | 9/30/2026 |  | M | Medium | N | 15 | Combined headcount increases negotiating leverage; est. 12% premium reduction
10 | HR / Benefits | Benefits | 4.5 | Harmonize AIP plan and eliminate legacy deferred comp programs | Labor/Non-Labor | 2/1/2026 | 2/20/2026 | X |  |  |  |  | X |  | 50 | 8 |  |  | 10 | 68 | Compensation Analyst | 12/31/2026 |  | H | High | N | 25 | Legacy deferred comp plans wound down; AIP aligned to single metric framework
11 | HR / Benefits | Benefits | 4.6 | Consolidate payroll processing to single system and vendor | Labor/Non-Labor | 2/5/2026 | 2/25/2026 | X |  |  |  |  | X |  | 110 | 17 |  |  | 25 | 152 | Payroll Specialist | 9/30/2026 |  | H | High | N | 40 | Migrate from 3 payroll platforms to 1; headcount reduced by 1.0 FTE
12 | HR / Benefits | Benefits | 4.7 | Consolidate HR and finance systems — reduce vendor count from 3 to 1 | Non-Labor | 2/5/2026 | 2/25/2026 |  |  |  | X |  | X |  |  |  | 45 |  | 30 | 75 |  | 12/31/2026 |  | M | Medium | N | 35 | Eliminate Workday + legacy HRIS overlap; consolidate to single SaaS platform
13 | IT / Infrastructure | IT Systems | 5.1 | Consolidate SAP Fixed Asset module; automate depreciation run | Non-Labor | 2/10/2026 | 3/1/2026 | X |  |  |  |  | X |  |  |  | 20 |  | 30 | 50 |  | 9/30/2026 |  | L | Medium | N | 28 | Single FA module replaces parallel instances; manual depreciation process eliminated
14 | IT / Infrastructure | IT Systems | 5.2 | Consolidate HR admin and general admin into shared services center | Labor | 2/10/2026 | 3/1/2026 |  |  |  | X |  | X |  | 130 | 20 |  |  |  | 150 | HR Generalist | 12/31/2026 |  | M | Medium | Y | 32 | Transition HR admin to SSO; 1.0 FTE transfer, 0.5 FTE reduction
15 | Finance / Corporate | Financial Reporting | 1.4 | Centralize ad hoc reporting; reduce embedded FTE in business units | Labor | 2/15/2026 | 3/5/2026 | X |  |  |  |  | X |  | 95 | 14 |  |  |  | 109 | Reporting Analyst | 9/30/2026 |  | M | Medium | Y | 20 | Consolidate 3 embedded reporting analysts to 1 central team FTE
16 | Finance / Corporate | Company Accounting | 3.3 | Rationalize lease accounting workload post-ASC 842 stabilization | Labor | 2/15/2026 | 3/5/2026 | X |  |  |  | X |  |  | 75 | 11 |  |  |  | 86 | Lease Accounting Analyst | 12/31/2026 |  | H | High | N | 18 | Initial lease population complete; ongoing maintenance requires 0.5 FTE less
17 | Finance / Corporate | Technical Accounting | 2.2 | Consolidate accounting policy SharePoint to single intranet site | Non-Labor | 2/20/2026 | 3/10/2026 | X | [5 empty] | X |  |  | 15 |  | 10 | 25 |  | 3/31/2026 | 3/31/2026 | L | Low | N | 5 | Decommission legacy SharePoint; single policy hub reduces maintenance FTE by 0.2
18 | Finance / Corporate | Financial Reporting | 1.5 | ERP consolidation reduces consolidation workload by 20% | Labor | 2/20/2026 | 3/10/2026 | X |  |  |  |  | X |  | 55 | 8 |  |  |  | 63 | Consolidations Analyst | 9/30/2026 |  | M | Medium | N | 22 | Single ERP eliminates inter-company eliminations across legacy entities
19 | Finance / Corporate | Financial Reporting | 1.7 | Reduce internal audit oversight FTE post-integration | Labor | 3/1/2026 | 3/15/2026 | X |  |  |  | X |  |  | 65 | 10 |  |  |  | 75 | Internal Audit Manager | 12/31/2026 |  | M | High | N | 15 | Combined control environment reduces scope; co-source model introduced
20 | HR / Benefits | Benefits | 4.3 | Consolidate stock compensation administration to single platform | Non-Labor | 3/1/2026 | 3/15/2026 | X |  |  |  |  | X |  |  |  | 20 |  | 15 | 35 |  | 9/30/2026 |  | L | Low | N | 12 | Equity platform consolidated; duplicate equity admin roles eliminated
21 | Finance / Corporate | Company Accounting | 3.4 | Consolidate third-party contracts under master services agreement | Non-Labor | 3/5/2026 | 3/20/2026 | X |  |  |  |  | X |  |  |  | 10 |  | 15 | 25 |  | 6/30/2026 |  | L | Low | N | 8 | Reduce vendor count from 12 to 5; MSA provides volume pricing
22 | IT / Infrastructure | IT Systems | 5.2 | Reduce embedded IT FTE in Finance through infrastructure consolidation | Labor | 3/5/2026 | 3/20/2026 |  |  |  | X | X |  |  | 145 | 22 |  |  |  | 167 | IT Business Partner | 12/31/2026 |  | H | High | Y | 28 | 2.0 FTE redeployed to central IT; 0.5 FTE eliminated post-restructure
23 | Finance / Corporate | Company Accounting | 3.5 | Streamline acquisition/divestiture support workload post-close | Labor | 3/10/2026 | 3/25/2026 | X |  |  |  | X |  |  | 85 | 13 |  |  |  | 98 | Corp Development Analyst | 12/31/2026 |  | H | High | N | 18 | Transition support work winds down 12 months post-close; FTE redeployed
24 | Finance / Corporate | Financial Reporting | 1.8 | Eliminate duplicate professional dues under unified entity | Non-Labor | 3/10/2026 | 3/25/2026 | X | [5 empty] | X |  |  | 12 |  |  | 12 |  | 3/31/2026 | 3/31/2026 | L | Low | N | 3 | Professional memberships consolidated; duplicate registrations cancelled
Total | [7 empty] | 1505 | 1505 | 1505 | 1505 | 1505 | 1505 | 1505 | 1505 | 227 | 152 | 0 | 285 | 2169
© 100-Day Advisors MandAPlaybook.com

## OH Synergies
M&A Overhead Synergy Estimates
|  | Year End Estimate | [7 empty] | Place X in box that represents the type of service provided | [8 empty] | Year End Estimate Including Estimated Synergies |  |  | VARIANCE Year to Last Year |  | COMMENTS ON VARIANCE
|  | FTE |  |  |  | Total Labor/Non-Labor Costs ($000s) |  |  |  | Location where work done | Required to be in Business |  |  | Discretionary |  |  | COMMENTS ON CURRENT WORK BREAKDOWN/COST STRUCTURE
Description of Direct Functional Services | Work Stream Ref # | AC | Support | Target | TOTAL | AC | Support | Target | TOTAL |  | Regulatory1 | Required - Done Internally | Regulatory or Required - Outsourced | Risk Mitigation2 | Non-Strategic | Strategic |  |  | FTE | Total Labor/Non-Labor Costs ($000s) |  | FTE | Total Labor/Non-Labor Costs ($000s)
Financial Reporting Summary | 1 |  |  |  | 0 | 975 | 110 | 745 | 1830 | [9 empty] | 7.7 | 842 |  | \ | -133
Consulting fees | 1.1 | 2 | 0.5 | 1.5 | 4 | 280 | 60 | 180 | 520 |  |  |  | X | [5 empty] | 1.8 | 230 |  | -2.2 | -50 | Reduced consulting spend post-integration; single audit firm retained
SEC & Governmental Reporting, including Annual Report and FACT Book | 1.2 | 1 | 0 | 1 | 2 | 120 | 0 | 120 | 240 |  | X | [7 empty] | 1 | 120
Software and printing services for preparation of third party financial reports | 1.3 | 0.5 | 0 | 0.3 | 0.8 | 45 | 0 | 30 | 75 | [6 empty] | X |  |  | 0.4 | 35 |  | -0.4 | -10 | Software licenses consolidated to single vendor
Internal Periodic Reporting, Ad Hoc Reporting & Queries (e.g. sustainability, investor conference prep) | 1.4 | 1.5 | 0.5 | 1 | 3 | 190 | 50 | 130 | 370 |  |  | X |  |  | X |  |  |  | 1.2 | 160 |  | -1.8 | -30 | Ad hoc reporting centralized; headcount reduced by 0.3 FTE
Consolidations | 1.5 | 1 | 0 | 0.8 | 1.8 | 110 | 0 | 90 | 200 |  |  | X | [6 empty] | 0.9 | 95 |  | -0.9 | -15 | Consolidation workload reduced with unified ERP
Work resulting from consulting firm and internal audits | 1.6 | 1 | 0 | 1 | 2 | 80 | 0 | 80 | 160 |  | X | [7 empty] | 1 | 80 |  | -1 | 0
Internal Audit Oversight | 1.7 | 1 | 0 | 0.8 | 1.8 | 95 | 0 | 75 | 170 |  |  | X | [6 empty] | 0.8 | 80 |  | -1 | -15 | Internal audit scope narrowed post-integration
Dues | 1.8 | 0.2 | 0 | 0.2 | 0.4 | 15 | 0 | 15 | 30 |  | X | [7 empty] | 0.2 | 12 |  | -0.2 | -3 | Professional dues consolidated under single entity
Accting Research tools, certification and GAAP training costs | 1.9 | 0.5 | 0 | 0.3 | 0.8 | 40 | 0 | 25 | 65 |  |  | X | [6 empty] | 0.4 | 30 |  | -0.4 | -10 | Certification costs reduced; shared training program implemented
Technical Accounting - Summary | 2 | 4.5 | 1 | 3.3 | 8.8 | 500 | 100 | 380 | 140 | [9 empty] | 2.1 |  |  | -6.7 | -500
Accounting and other inquiries from businesses and others (i.e. Tax Department) | 2.1 | 1.5 | 0.5 | 1 | 3 | 170 | 50 | 120 | 50 |  |  | X | [6 empty] | 1.2 | 140 |  | -1.8 | -30 | Inquiry volume down 20% with unified accounting policy
Other technical accounting activities, including training & education, corp policy SharePoint maintenance, documentation for technical topics | 2.2 | 1 | 0 | 0.8 | 1.8 | 110 | 0 | 90 | 40 |  |  |  |  | X |  |  |  |  | 0.9 | 95 |  | -0.9 | -15 | Policy documentation consolidated to single SharePoint site
Finance Support to all businesses: business finance oversight, Finance Master Data maintenance, SAP system care and sustainability, Catchlight accounting support | 2.3 | 2 | 0.5 | 1.5 | 4 | 220 | 50 | 170 | 50 |  |  | X | [6 empty] | 1.8 | 190 |  | -2.2 | -30 | SAP master data team reduced; single instance achieved
Company Level Accounting & Function Support - Summary | 3 | 9 |  |  | 9 |  |  |  | 575 | [9 empty] | 8.1 |  |  | -0.9 | 0 | Increase reflects a portion of an intern. May need to convert interns to permanent staff, or add headcount to reduce overtime.
Corporate function support (decision support, planning, capital asset management, corporate fixed assets, corporate allocations) | 3.1 | 2 | 0 | 1.5 | 3.5 | 260 | 0 | 200 | 300 |  |  | X | [6 empty] | 1.8 | 230 |  | -1.7 | -30 | Reduced decision support FTE; planning cycle consolidated
Treasury accounting (debt, investments, bank reconciliations for WY, WNR, WYL, and WRECO, weekly cash deposit for miscellaneous checks received in FW, cash tagging support) | 3.2 | 1.5 | 0 | 1.2 | 2.7 | 160 | 0 | 130 | 100 |  |  | X | [6 empty] | 1.3 | 140 |  | -1.4 | -20 | Bank accounts rationalized from 18 to 9; recon workload reduced
Company level accounting (leases, LIFO/profit elim, investments in equity, FX, insurance, environmental reserve, corporate records management, employees on international payroll, Period 13 rollup, accounting support to the SSO, SPE accounting, WY common stock and dividends, miscellaneous receivables, interco accounting and guidance) | 3.3 | 3 | 0.5 | 2.5 | 6 | 330 | 50 | 280 | 100 |  |  | X | [6 empty] | 2.8 | 300 |  | -3.2 | -30 | Lease accounting workload increases near-term; target achieved in Y2
3rd party contracts - | 3.4 | 0.5 | 0 | 0.3 | 0.8 | 55 | 0 | 35 | 10 |  |  | X | [6 empty] | 0.4 | 40 |  | -0.4 | -15 | Vendor contracts consolidated to master services agreement
Support for projects: acquisitions, divestitures, restructuring, general business changes, and the resulting ongoing maintenance of discontinued operations | 3.5 | 1 | 0.5 | 0.8 | 2.3 | 110 | 50 | 90 | 35 |  | X | X | [6 empty] | 0.9 | 100 |  | -1.4 | -10
Tax | 3.6 | 1 | 0 | 0.8 | 1.8 | 120 | 0 | 100 | 30 | [9 empty] | 0.9 | 105 |  | -0.9 | -15 | Tax provision consolidated; single filing entity
Benefits - Summary | 4 | 8.6 |  |  | 8.6 |  |  |  | 450 | [9 empty] | 7.7 |  |  | -0.9 | 0
Pension & postretirement, including pension plan audit, government reporting | 4.1 | 2 | 0 | 1.5 | 3.5 | 250 | 0 | 190 | 100 |  | X | [7 empty] | 1.8 | 220 |  | -1.7 | -30 | Pension plan audit consolidated to single actuary
Group insurance, including some postretirement | 4.2 | 1 | 0 | 0.8 | 1.8 | 110 | 0 | 90 | 30 |  |  | X | [6 empty] | 0.9 | 95 |  | -0.9 | -15 | Group insurance consolidated; carrier renegotiated
Stock comp | 4.3 | 0.5 | 0 | 0.5 | 1 | 60 | 0 | 60 | 20 |  |  | X | [6 empty] | 0.5 | 55 |  | -0.5 | -5
Third-party valuation services for stock based compensation awards | 4.4 | 0.3 | 0 | 0.3 | 0.6 | 45 | 0 | 45 | 40 |  |  |  | X | [5 empty] | 0.3 | 38 |  | -0.3 | -7 | Valuation vendor retained; fee reduced under combined awards
Other compensation-related accounting areas: AIP and RONA, Deferred comp / Board of Directors comp | 4.5 | 0.8 | 0 | 0.5 | 1.3 | 90 | 0 | 65 | 60 | [6 empty] | X |  |  | 0.6 | 70 |  | -0.7 | -20 | AIP plan harmonized; deferred comp consolidated
Other benefits accounting areas (Workers comp, 401(k), WCB, payroll, accruals, payroll taxes, vacation, wageworks, relocation, garnishments, United Way, PAC contributions). Includes payments, recons and ongoing entries. | 4.6 | 2.5 | 0.5 | 2 | 5 | 275 | 50 | 225 | 100 |  | X | X | [6 empty] | 2.2 | 240 |  | -2.8 | -35 | Payroll processing consolidated to single system; headcount -0.3
Other benefits activities, including Financial and HR systems, partner and vendor relationships | 4.7 | 1.5 | 0 | 1.2 | 2.7 | 165 | 0 | 135 | 100 |  |  | X |  | X |  |  |  |  | 1.4 | 145 |  | -1.3 | -20 | HR/finance system vendor reduced from 3 to 1
Other Group-Wide Items | 5 | 3 |  |  | 3 |  |  |  | 200 | [9 empty] | 2.7 |  |  | -0.3 | 0
Depreciation on SAP Fixed Asset system | 5.1 | 1 | 0 | 0.8 | 1.8 | 120 | 0 | 100 | 100 | [5 empty] | X |  |  |  | 0.9 | 105 |  | -0.9 | -15 | SAP FA module consolidated; depreciation run automated
HR, people development, general admin | 5.2 | 2 | 0.5 | 1.5 | 4 | 220 | 50 | 170 | 100 |  |  |  |  | X | X | X |  |  | 1.8 | 190 |  | -2.2 | -30 | HR generalist roles reduced; admin consolidated with shared services
Total Direct Function Costs |  | 25.1 | 1 | 3.3 | 29.4 | 1475 | 210 | 1125 | 3195 | [9 empty] | 28.3 | 842 |  | -1.1 | -633
Indirect Function Costs (Show one line item by business for embedded FTE and $ by business) Include application license costs associated with your function |  | 3 | 1 | 2.5 |  | 380 | 100 | 310 | [10 empty] | 2.8 | 340 |  | 2.8 | -40 | IT embedded FTE reduced with unified infrastructure
|  | 2 | 0.5 | 1.5 |  | 240 | 50 | 190 | [10 empty] | 1.8 | 210 |  | 1.8 | -30 | Finance embedded FTE in business units reduced post-integration
Total Indirect Function Costs |  | 5 | 1.5 | 4 | 0 | 620 | 150 | 500 | 0 | [8 empty] | 0 | 4.6 | 550 | 0 | 4.6 | -70
Total Direct & Indirect Function FTE And COSTS |  | 30.1 | 2.5 | 7.3 | 29.4 | 2095 | 360 | 1625 | 3195 | [8 empty] | 0 | 32.9 | 1392 | 0 | 3.5 | -703
Examples of Regulatory: SEC Financial Reporting, Audit, OSHA reporting, etc. | [9 empty] | 1. Break out and report ONLY the FTE and costs for services that are due purely to regulatory REQUIREMENTS. List each service grouping separately and explain in the comments what the regulation is the service is addressing
Examples of Risk Mitigation: Ethics Compliance, Employment Law | [9 empty] | 2. Break out and report ONLY the FTE and costs for services that are due purely to risk mitigation. List each service grouping separately and state in the comments what risk is being mitigated by providing this service.
Examples of Required to in Business: Payroll, AP, AR, Accounting, IT Infrastructure | [9 empty] | 3. Break out and report ONLY the FTE and costs for services that are required to be in business. Mark an X if the service is currently done internally or outsourced.
Examples of Discretionary Non-Strategic: Help Desk, IT Project Management | [9 empty] | 4. Break out and report ONLY the FTE and costs for services that are discretionary. Mark an X if the service is generic or mark strategic if it provides us a competitive advantage. In the comments state what the competitive advantage is.
Examples of Discretionary Strategic: Leadership Development
0
© 100-Day Advisors MandAPlaybook.com

## RIF
Reduction in Force Tracker
Synergy Initiative # | Function - Business/Product Line - Sub-function | Employee Name | Last Day Worked Estimated | Last Day Worked Actual
1 | Finance / Corporate – Financial Reporting | John A. Martinez | 9/30/2026
3 | Finance / Corporate – Technical Accounting | Sandra K. Owens | 9/30/2026
4 | Finance / Corporate – Technical Accounting | Brian T. Calloway | 9/30/2026
4 | Finance / Corporate – Technical Accounting | Rachel M. Huang | 12/31/2026
5 | Finance / Corporate – Company Accounting | David P. Simmons | 12/31/2026
7 | Finance / Corporate – Company Accounting | Lisa R. Fernandez | 6/30/2026
10 | HR / Benefits | Thomas W. Nguyen | 12/31/2026
11 | HR / Benefits | Karen J. Whitfield | 9/30/2026
14 | IT / Infrastructure – Shared Services | Michael D. Torres | 12/31/2026
15 | Finance / Corporate – Financial Reporting | Angela S. Brooks | 9/30/2026
16 | Finance / Corporate – Company Accounting | Steven L. Park | 12/31/2026
19 | Finance / Corporate – Financial Reporting | Cynthia R. Coleman | 12/31/2026
22 | IT / Infrastructure | James B. Keller | 12/31/2026
23 | Finance / Corporate – Company Accounting | Nicole A. Patterson | 12/31/2026
© 100-Day Advisors MandAPlaybook.com