## Slide 1
M&A DAY 1
COMMUNICATIONS PLAN

## Slide 2
COMMUNICATIONS PLAN
PRE-CLOSE COMMUNICATIONS MEETING
PRE-CLOSE COMMUNICATIONS MEETING AGENDA
DAY 1 KEY EVENTS
DAY1 TOWN HALL WEBCAST
WEEK 1 ONWARDS - GROUP FUNCTION ENGAGEMENT
SENIOR LEADERSHIP MEETING
KEY MESSAGES
ALL EMPLOYEES
MANUFACTURING – PLANT EMPLOYEES
CUSTOMERS
SUPPLIERS
HOMEPAGE TEMPLATE
02
CONTENT
© 100-Day Advisors MandAPlaybook.com

## Slide 3
COMMUNICATIONS PLAN
15 Days Before Close
Day 1
First 30 days
Communications Meeting
Press Release
CEO Welcome Day Message
Welcome Video on
Integration Portal
Employee Information Guide
Employees Communications Playbook (for managers)
Customer Communications Playbook (for customer-facing employees)
Supplier Communications Playbook (for employees with supplier responsibilities)
Welcome Week slide deck
Communication Meeting Materials
June 15
Participants:
Leaders
Topics:
NewCo transaction overview, implications
Day 1 communications plan
Resources available (playbooks and what to expect to receive for Day 1)
Post Meeting:
IMO checkpoint calls
As needed calls with WS to align on specific topics
Lock Down Materials:
Employees
Media
Customers
Suppliers
Day 1: CEO Welcome Message
Day 2 onwards: Group Functional Meetings
Day 1: Site Visits Employee Townhalls
Day 30 onwards: Integration Portal Updates / Weekly Newsletter
Day 1: Press Release in all markets
Day 1: Website + Social Media announcement
Day 1: Notification Letter
Day 2: Notification Letter
Post Day 1: On-going news and social media monitoring and response
Day 3-15: Visits to Key Customers
D3-15: Key Supplier engagement by procurement teams
Welcome Video
Integration Portal
Employee Information Guide
03
© 100-Day Advisors MandAPlaybook.com

## Slide 4
PRE-CLOSE COMMUNICATIONS MEETING
Purpose:
Preparing managers to carry out Day / Week 1 activities
Recommended Participants:
Vice Presidents and Senior Managers
Post Meeting:
Checkpoint calls with IMO on progress, updates, issues
Duration:
½ Day
04
© 100-Day Advisors MandAPlaybook.com

## Slide 5
Topics
Estimated Duration
Recommended Owner
NewCo Overview
  Scale, footprint, brands
  Benefits, strategy
  Values and culture
Transaction Overview
  Deal implications
  Financial / synergy commitments
Communications Plan Overview
  Leading up to Day 1
  Day 1
  Post Day 1
General Implications / Integration Plans
  Manufacturing (Safety)
  Legal
  Finance
  IT
  Others
30 min
30 min
30 min
30 min
IMO
Supported by: Legal, Corporate
IMO
Supported by: Legal
Corporate
Corporate / IMO / WS
Topics
Estimated Duration
Recommended Owner
HR Implications
  Day 1 organization and implications
  Employment, compensation, process and systems
  Employee Communications Playbook review
  What you will receive on Day 1: employee roster etc.
Sales/Customer Implications
  Brand and sales management post Day 1
  Customer scenarios: overlap / non-overlap customers
  Customer Communications Playbook review
  What you will receive on Day 1: customer listings, etc.
Supplier Implications
  Supplier management post Day 1
  Scenarios: overlap / non-overlap suppliers
  Supplier Communications Playbook review
1 Hour
1.5 Hour
30 Mint
HR
Supported by: Corporate
Sales
Supported by: Corporate
Procurement
Supported by: Corporate
05
PRE-CLOSE COMMUNICATIONS MEETING AGENDA
© 100-Day Advisors MandAPlaybook.com

## Slide 6
KEY EVENTS
15 Days Prior to Close:
10 Days Prior to Close:
05 Days Prior to Close:
Day 01:
Day 2 and 3:
Finalize all communications materials
Prepare Site Visits and material
Complete Integration Portal
Prepare Site Visit Logistics
Conduct Preparatory Meeting
Obtain clearance on closing
Email all leaders on finalized closing date and final communications materials
Prepare executives for press release distribution and media channels
6am: Press release crosses PR newswire (align with Boral ASX release)
6am: CEO Message distributed
6am: Invite sent for Site Visits
Website / Social Media banner released
Sales teams plan local customer, supplier, employee outreach
Site Visits – Town Halls with Employees
Customer and Supplier Letters sent
Customer and supplier outreach (engagement)
06
© 100-Day Advisors MandAPlaybook.com

## Slide 7
DAY 1 TOWN HALL WEBCAST
Objectives:
Welcome all employees onto the NewCo
Overview the new business (vision, scope, footprint, leadership)
Integration Overview and Guiding Principles
Employee Q&As
07
© 100-Day Advisors MandAPlaybook.com

## Slide 8
WEEK 1 ONWARDS - GROUP FUNCTION ENGAGEMENT
Function
Participants
Owner
Potential Topics
HR
HR leaders
Corporate HR
Establish contact and get to know the new functional organization
Integration Plans for HR
Guidance for HR leaders
Manufacturing
Manufacturing Leaders
Manufacturing at HQ
Establish contact and get to know the new functional organization
Integration Plans for Manufacturing
Safety, Operating Principles
Guidance for Manufacturing leaders
Finance
Finance leaders
Corporate Finance
Establish contact and get to know the new functional organization
Integration Plans for Finance
Guidance for Finance leaders
IT
IT leaders
Corporate IT
Establish contact and get to know the new functional organization
Integration Plans for IT
Guidance for IT leaders
Sales & Marketing
TBC
TBC
TBC
08
© 100-Day Advisors MandAPlaybook.com

## Slide 9
SENIOR LEADERSHIP MEETING
Objectives:
Align new leadership team on NewCo’s vision, mission, strategic plan
Align new culture – setting the tone for the new business
Team-building / networking
Mode:
1-3 day workshop
Participants:
HQ
Group Functional Leaders
Country GMs
Proposed Timing:
February / March 2020
09
© 100-Day Advisors MandAPlaybook.com

## Slide 10
KEY MESSAGES
Employees
Customers
Suppliers
NewCo overview
Day 1 organization structure
Create more value for customers together
For now, no changes to brands and products, sales and distribution, manufacturing operations
Elimination of some jobs (back office redundancies)
Common benefits
Continued commitment and enhanced capability to provide long term value to market
For now, no changes to brands, products, pricing, sales contacts, distribution process
For now, no changes to supply arrangements
KEY TASKS
Site Visits: Top Executives
Townhall (Webcast)
Customer letter from their sales account manager
Engage key accounts by sales account manager
Supplier letter from their current contract owner
Engage key vendors by contract owner
10
© 100-Day Advisors MandAPlaybook.com

## Slide 11
ALL EMPLOYEES
Communications Plan
Townhall (Webcast)
Collateral
Messages
NewCo overview
Day 1 Organization Structure
Stronger and better business together
For now, no changes to brands and products, sales and distribution, manufacturing operations
Employee impacts – no immediate changes (jobs, job locations, benefits)
Valued as a critical part to help the new company achieve its purpose, strategy and goals
Timing
Receive All-Employees Day 1 communications
CEO Welcome Message:
  Welcome Video
  Link to Integration Portal (to access Employee Guide and other resources)
Hosted by CEO:
  Welcome speeches
  Overview of NewCo (vision, scope, goals)
Engaged by their Country GMs
Local Country Townhalls / Meet and Greets
Engaged by their managers
11
Day 1
Day 2
Week 1-3
© 100-Day Advisors MandAPlaybook.com

## Slide 12
MANUFACTURING – PLANT EMPLOYEES
Communications Plan
[PMs] Join Global Townhall (Webcast)
Collateral
Timing
[PMs] Receive All-Employees Day 1 communications
CEO Welcome Message:
  Welcome Video
  Link to Integration Portal
Hosted by CEO:
  Welcome speeches
  Overview of NewCo (vision, scope, goals)
Plant managers begin to engage plant employees
Welcome Video and Webcast recording
Employee Communications Playbook (Guide, Speaking Points, FAQs)
Day 1
(relevant materials printed to notice boards)
Day 2
Play videos to employees, team huddles
12
NewCo overview
Day 1 Organization Structure
Safety as a key focus
No changes immediately to manufacturing processes / activity, distribution processes – business as usual
Continue plant manufacturing activities for quality products
Plant managers – engage and cascade communication to their plant employees
Messages
© 100-Day Advisors MandAPlaybook.com

## Slide 13
CUSTOMERS
Communications Plan
Key accounts engaged personally by sales account manager
Collateral
Timing
Customer letter from their sales account manager
Customer Letter
None (Sales Team will be equipped with speaking points to talk about the new co.)
Week 1
Week 1-2
13
Acquirer has acquired Acquired Company
Continued commitment and combined capabilities to add long-term
No changes to brands, products, pricing, sales contacts, distribution process immediately
Continue to partner with current sales persons to fulfill orders for respective brands
Messages
© 100-Day Advisors MandAPlaybook.com

## Slide 14
Communications Plan
Key Suppliers engaged personally by contract owner
Collateral
Timing
Supplier letter from their current contract owner
Supplier Letter
None (Refer Supplier Communications Playbook for Guide, Letters, Speaking Points, FAQs)
Week 1
Week 1-2
SUPPLIERS
NewCo entity details (name, registration)
14
Acquirer has acquired Acquired Company
Stronger and better business together
No changes to supply arrangements immediately – business as usual until we engage in further discussions
Continue to work with contract owners to fulfill supply arrangements
Messages
© 100-Day Advisors MandAPlaybook.com

## Slide 15
HOMEPAGE TEMPLATE
logo
Navigation Menu
Welcome, user@email
Welcome Video
CEO’s Message
Benefits
Day 1
FAQs
News & Announcements
Resources
Category 1
Category 2
Category 3
Category 4
Headline 1
Headline 2
Headline 3
Headline 4
Rolling FAQs Updated weekly
Employee Information Resources | News & Announcements | Employee Directory
Displays various categories of resources
List of News with thumbnail with Title & short description, links to Content Pages.
15

## Slide 16
contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting