## Slide 1
M&A INTEGRATION TRANSITION
TO REGULAR OPERATIONS

## Slide 2
AGENDA
Integration-Related and Regular Tasks
The Exit Criteria
Transition to Regular Processes
Closure Checklist
01
© 100-Day Advisors MandAPlaybook.com

## Slide 3: THE EXIT CRITERIA
The former effort is part of the HR workstream Exit Criteria; completion of the implementation is not
When a workstream no longer needs to operate under the supervision of the IMO when:
The remaining tasks of the workstreams will be addressed via regular day-to day processes
Example – System implementation
The selection and integration of a new payroll system is called for as part of integration and initiated as part of the HR workstream managed by the IMO
Once the implementation effort is underway, it transitioned to the IT PMO for completion
The remaining tasks of the workstream have no dependencies on other workstreams
02
© 100-Day Advisors MandAPlaybook.com

## Slide 4
CLOSURE CHECKLIST
Majority of activities are completed
Activities still underway, incomplete or not started are included in the line organization business/action plan
Closure will not hinder other workstreams achieving their acquisition targets Acquisition objectives/KPIs developed/reached or on target according to plan Team structure and responsibilities agreed upon
All risks identified with the workstream have been identified mitigating actions, with ownership, are in place
Handover to receiving line organization complete (with handshaking protocol) “Lessons learned” have been captured
Workstream documentation stored in Smartsheet
Short closure report complete (i.e., this presentation)
03
© 100-Day Advisors MandAPlaybook.com

## Slide 5: TRANSITION TO REGULAR PROCESSES
The workstream has completed its major milestones
The former effort is part of the HR workstream exit criteria; completion of the implementation is not
When a workstream no longer needs to operate under the supervision of the IMO when:
The remaining tasks of the workstream have no dependencies on other workstreams
Example – System implementation
The selection and integration of a new payroll system is called for as part of integration and initiated as part of the HR workstream managed by the IMO
Once the implementation effort is underway, it transitioned to the IT PMO for completion
04
© 100-Day Advisors MandAPlaybook.com

## Slide 6: INTEGRATION RELATED AND REGULAR TASKS
Part of regular operations is when new clients are onboarded
At close, Acquiree clients will become Acquirer clients and will undergo a one-time screening en masse as if they were new clients
The one-time effort is an integration matter, even though it mirrors an ongoing regular process
Many tasks occur once for integration purposes while also occurring during regular operations
Example
05
© 100-Day Advisors MandAPlaybook.com

## Slide 7
contact us
email
inquiries@MandAPlaybook.com
website
MandAPlaybook.com/consulting
06